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اللجنــة التنفيـذيــــة للصنــدوق المــتعــدد الأطـــراف
لتنفيـــذ بروتوكـول مونتريــال 
الاجتماع الخامس والتسعون
مونتريال، 4 - 8 ديسمبر/ كانون الاول 2024
البند 8(أ) من جدول الأعمال المؤقت [footnoteRef:1] [1:  UNEP/OzL.Pro/ExCom/95/1 ] 



تحديث عن حالة تنفيذ خطة الأعمال المجمعة للصندوق المتعدد الأطراف 
للفترة 2024-2026
مقدمة 
1. في اجتماعها الثالث والتسعين، أقرت اللجنة التنفيذية خطة الأعمال المجمعة للصندوق المتعدد الأطراف للفترة 2024-2026. واستجابة للمقرر 93/28، أدخلت الأمانة تعديلات على خطة الأعمال المجمعة للفترة 2024-2026، على النحو المبين في الجدول 1.
الجدول 1- تخصيص الموارد لخطة الأعمال المجمعة المعدلة للصندوق المتعدد الأطراف للفترة 2024-2026 (بالدولار الأمريكي)*
	الوصف 
	2024
	2025
	2026
	المجموع 

	أنشطة المواد الهيدروكلوروفلوروكربونية
	 
	 
	 
	 

	الخطط المعتمدة لإدارة إزالة المواد الهيدروكلوروفلوروكربونية  
	48,499,466
	50,384,491
	50,158,180
	149,042,137

	الخطط المعتمدة لإدارة إزالة إنتاج المواد الهيدروكلوروفلوروكربونية 
	23,232,000
	0
	0
	23,232,000

	المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية - الإعداد
	134,400
	44,300
	0
	178,700

	المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية 
	4,970,041
	6,870,087
	10,870,876
	22,711,004

	المرحلة الثالثة من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية - الإعداد
	522,900
	65,400
	0
	588,300

	المرحلة الثالثة من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية 
	15,849,471
	10,765,760
	23,015,282
	49,630,513

	المرحلة الرابعة من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية - الإعداد
	70,000
	0
	0
	70,000

	المرحلة الرابعة من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية
	0
	0
	3,691,000
	3,691,000

	التحقق من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية**
	588,600
	588,600
	588,600
	1,765,800

	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية – كفاءة استخدام الطاقة
	3,726,111
	3,305,040
	111,200
	7,142,351

	المجموع الفرعي لأنشطة المواد الهيدروكلوروفلوروكربونية
	97,592,989
	72,023,678
	88,435,138
	258,051,805

	أنشطة الهيدروفلوروكربون
	 
	 
	 
	 

	خطط تنفيذ تعديل كيغالي بشأن المواد الهيدروفلوروكربونية المعتمدة 
	0
	10,127,716
	6,590,654
	16,718,370

	المشروعات المعتمدة للتحكم في انبعاثات الهيدروفلوروكربون-23
	414,238
	626,900
	572,433
	1,613,571

	الهيدروفلوروكربون – الأنشطة التمكينية
	53,500
	160,500
	0
	214,000

	الهيدروفلوروكربون – المساعدة الفنية
	678,000
	0
	0
	678,000

	الهيدروفلوروكربون-23
	8,000,000
	0
	0
	8,000,000

	المرحلة الأولى من خطة تنفيذ تعديل كيغالي
	11,458,349
	27,565,521
	6,378,667
	45,402,537

	المرحلة الأولى من خطة تنفيذ تعديل كيغالي – إعداد الاستثمار
	32,100
	0
	0
	32,100

	المرحلة الأولى من خطة تنفيذ تعديل كيغالي – الاستثمار
	3,712,616
	0
	0
	3,712,616

	المرحلة الأولى من خطة تنفيذ تعديل كيغالي – الإعداد
	2,891,415
	1,167,771
	211,280
	4,270,466

	المجموع الفرعي لأنشطة المواد الهيدروفلوروكربونية
	27,240,219
	39,648,408
	13,753,034
	80,641,660

	الأنشطة الأخرى
	 
	 
	 
	 

	مشروع تجريبي لكفاءة استخدام الطاقة - إيضاحي
	1,870,000
	1,000,000
	0
	2,870,000

	مشروع تجريبي لكفاءة استخدام الطاقة - الاستثمار
	4,789,988
	248,600
	0
	5,038,588

	مشروع تجريبي لكفاءة استخدام الطاقة - الإعداد
	85,600
	0
	0
	85,600

	إعداد بنوك المواد المستنفدة للأوزون
	1,232,150
	310,300
	0
	1,542,450

	المجموع الفرعي لأنشطة المواد الهيدروفلوروكربونية
	7,977,738
	1,558,900
	0
	9,536,638

	الأنشطة القياسية
	 
	 
	 
	 

	التعزيز المؤسسي 
	22,071,008
	1,830,362
	21,294,756
	45,196,125

	برنامج المساعدة على الامتثال 
	11,765,667
	12,113,777
	12,310,330
	36,189,774

	الوحدة الأساسية
	6,611,529
	6,653,609
	6,095,985
	19,361,122

	تكاليف السكرتارية واللجنة التنفيذية والرصد والتقييم مطروحًا منها نظيرتها الكندية
	7,202,023
	6,816,624
	6,964,604
	20,983,251

	أمين الخزانة
	500,000
	500,000
	500,000
	1,500,000

	المجموع الفرعي للأنشطة القياسية 
	48,150,226
	27,914,372
	47,165,675
	123,230,273

	المجموع الكلي
	180,961,172
	141,145,358
	149,353,846
	471,460,376

	بحسب الوكالة
	 
	 
	 
	 

	أستراليا
	0
	615,610
	0
	615,610

	النمسا
	783,667
	0
	0
	783,667

	فرنسا
	671,075
	0
	0
	671,075

	ألمانيا
	7,500,449
	2,148,339
	5,834,901
	15,483,689

	اليوئنديبي
	44,305,827
	38,729,891
	40,741,817
	123,777,535

	اليونيب
	47,977,295
	27,975,506
	35,097,810
	111,050,611

	اليونيدو
	40,363,268
	49,551,567
	30,746,018
	120,660,853

	البنك الدولي
	31,068,968
	14,219,221
	28,880,096
	74,168,285

	التحقق من خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية **
	588,600
	588,600
	588,600
	1,765,800

	تكاليف السكرتارية واللجنة التنفيذية والرصد والتقييم مطروحًا منها نظيرتها الكندية
	7,202,023
	6,816,624
	6,964,604
	20,983,251

	أمين الخزانة
	500,000
	500,000
	500,000
	1,500,000


* تشمل تكاليف دعم الوكالة  حيثما ينطبق ذلك.
** وافقت اللجنة التنفيذية على تمويل إعداد تقارير التحقق لخطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية للبلدان ذات حجم الاستهلاك المنخفض على أساس سنوي.

حالة تنفيذ خطة الأعمال لعام 2024
يبلغ إجمالي قيم خطة الأعمال لعام 2024، 180,961,172 دولار أمريكي. ومن هذا المبلغ، تمت الموافقة على 61,332,446 دولار أمريكي في الاجتماع الرابع والتسعين. وبالإضافة إلى ذلك، سيتم النظر في الأنشطة البالغة 124,178,563 دولار أمريكي في الاجتماع الخامس والتسعين؛ وإذا تمت الموافقة على جميع مقترحات المشروعات المقدمة حسب الطلب، ستتجاوز ميزانية خطة الأعمال لعام 2024 بمبلغ 4,549,837 دولار أمريكيا على النحو المبين في الجدول 2. 
الجدول 2- خطة الأعمال المجمعة لعام 2024 والمشروعات الموصي بها للاجتماع الخامس والتسعين والرصيد (بالدولار الأمريكي)*
	بنود الميزانية
	القيمة الإجمالية في خطة الأعمال
	الموافقات في الاجتماع الرابع والتسعين
	الأنشطة الموصي بها للاجتماع الخامس والتسعين
	الرصيد 
(أعلى) / أقل

	الوكالات الثنائية
	8,955,191
	7,722,115
	4,501,291
	(3,268,215)

	برنامج الأمم المتحدة الإنمائي
	44,305,827
	16,932,440
	22,592,547
	4,780,840

	برنامج الأمم المتحدة للبيئة
	47,977,295
	12,910,251
	34,033,332
	1,033,712

	اليونيدو
	40,363,268
	23,196,140
	27,767,338
	(10,600,210)

	البنك الدولي
	31,068,968
	0
	27,582,032
	3,486,936

	التحقق من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية
	588,600
	571,500
	0
	17,100

	المجموع الفرعي (الوكالات)
	173,259,149
	61,332,446
	116,476,540
	(4,549,837)

	الأمانة / اللجنة التنفيذية/ الرصد والتقييم (باستثناء النظير الكندي)
	7,202,023
	0
	7,202,023
	0

	أمين الخزانة
	500,000
	0
	500,000
	0

	المجموع الفرعي (التكاليف القياسية)
	7,702,023
	0
	7,702,023
	0

	المجموع
	180,961,172
	61,332,446
	124,178,563
	(4,549,837)


* شاملًا تكاليف الوحدة الأساسية.

وتتجاوز قيمة مقترحات المشروعات الموصى بها إلى الاجتماع الخامس والثمانين البالغة 116,476,540 دولار أمريكي قيمتها في خطة الأعمال للفترة 2024 بمبلغ 25,156,871 دولار أمريكي وتشمل 15,899,209 دولار أمريكي المرتبط بمقترحات المشروعات غير المدرجة في خطة الأعمال لعام 2024.[footnoteRef:2] [2:  المرحلة الأولى من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لبوتان (اليوئنديبي واليونيب)؛ المرحلة الثانية من خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية لجزر كوك (اليونيب)، وكيريباتي (اليونيب)، وجزر مارشال (اليونيب) وميكرونيزيا (ولايات – الموحدة) (اليونيب)، وناورو (اليونيب)، ونيوي (اليونيب)، وبالاو (اليونيب)، والبلدان الجزرية في منطقة المحيط الهادئ (البلدان الجزرية في منطقة المحيط الهادئ) (أستراليا واليونيب)، ساموا (اليونيب)، جزر سليمان (اليونيب)، وتونغا (اليونيب)، وتوفالو (اليونيب)، وفانواتو (اليونيب)، والمرحلة الثالثة من خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية لشيلي )اليوئنديبي) والمكسيك (ألمانيا)؛ وإعداد مشروع واحد للمرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لدومينيكا (اليونيدو)؛ وثلاثة أنشطة لإعداد المشروع للمرحلة الثالثة من خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية لأنغولا (اليوئنديبي) وينغلاديش (اليوئنديبي واليونيب)؛ وإعداد مشروع للمرحلة الرابعة من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لنيجيريا (ألمانيا)؛ ومشروع استثماري لخطة تنفيذ تعديل كيغالي للأرجنتين (اليونيدو)؛ وإعداد مشروع لمشروع استثماري لخطة تنفيذ تعديل كيغالي لإندونيسيا (البنك الدولي)؛ وأربعة مشاريع إعداد المشروع للمرحلة الأولى من خطط تنفيذ تعديل كيغالي لجزر البهاما (اليونيب واليونيدو) وباربادوس (اليونيب) والصين (اليوئنديبي)؛ والمرحلة الأولى من خطط تنفيذ تعديل كيغالي لبنن (اليونيب واليونيدو)، وتشاد (اليونيب واليونيدو)، وغواتيمالا (اليونيب واليونيدو)، وموريشيوس (ألمانيا)، ومنطقة البلدان الجزرية في المحيط الهادئ (أستراليا واليونيب)، والسنغال (اليونيب واليونيدو)، وأوروغواي (اليوئنديبي واليونيدو)؛ و16 مشروعا لكفاءة استخدام الطاقة بموجب المقرر 89/6 لبوتان (اليونيب)، وجزر كوك (اليونيب)، وكيريباتي (اليونيب)، وجزر مارشال (اليونيب)، وميكرونيزيا (ولايات – الموحدة) (اليونيب)، وناورو (اليونيب)، ونيوي (اليونيب)، وبالاو (اليونيب)، ومنطقة البلدان الجزرية في المحيط الهادئ (أستراليا واليونيب)، وسانت فنسنت وجزر غرينادين (اليونيب)، وساموا (اليونيب)، وجزر سليمان (اليونيب)، وتونغا (اليونيب)، وتوفالو (اليونيب)، وفانواتو (اليونيب)؛ و28 نشاطا لإعداد لقوائم الجرد الوطنية لبنوك نفايات المواد الخاضعة للرقابة بموجب المقرر 91/66 لجزر البهاما (اليونيب)، وينغلاديش (اليونيدو)، وبوتان (اليونيب) وبروني دار السلام (اليونيب)، والكونغو (اليونيدو)، وجزر كوك (اليونيب)، وإسواتيني (اليونيب)، وفيجي (اليونيب)، وغامبيا (اليونيب)، وإندونيسيا (اليوئنديبي)، وكيريباتي (اليونيب)، ومدغشقر (اليونيدو)، ونيوي (اليونيب) وبالاو (اليونيب)، وساموا (اليونيب)، والسنغال (ألمانيا) وجزر سليمان (اليونيب)، وتايلند (البنك الدولي)، وتيمور – لشيتي (اليونيب) وتونغا (اليونيب)، وتوفالو (اليونيب) وأوغندا (اليونيب، وفانواتو (اليونيب).] 

وتبلغ قيمة الأنشطة ذات الصلة بالهيدروفلوروكربون الموصى بها إلى الاجتماع الخامس والتسعين 19,833,551 دولار أمريكي ومنها 8,720,978 دولار أمريكي مرتبطا بمقترحات المشروعات غير المدرجة في خطة الأعمال لعام 2024. ويسرد المرفق الأول بالوثيقة الحالية المشروعات ذات الصلة بالهيدروفلوروكربون المقدمة من الوكالات الثنائية والمنفذة إلى الاجتماع الخامس والتسعين.
وتبلغ قيمة المشروعات الموصى بها بموجب نافذة التمويل للمشروعات التجريبية لكفاءة استخدام الطاقة عملا بالمقرر 91/65 مبلغ 4,642,176 دولار أمريكي. ومع الأخذ في الاعتبار الموافقات في الاجتماعات الثاني والتسعين والثالث والتسعين والرابع والتسعين البالغة 5,976,489 دولار أمريكي، والقيم الموصى بها إلى الاجتماع الخامس والتسعين، يبلغ التمويل المتبقي المتاح بموجب نافذة التمويل هذه 9,381,335 دولار أمريكي. ويسرد المرفق الثاني بالوثيقة الحالية المشروعات التجريبية المقدمة من الوكالات الثنائية والمنفذة إلى الاجتماع الخامس والتسعين عملا بالمقرر 91/65.
وتبلغ قيمة المشروعات الموصى بها بموجب نافذة التمويل لكفاءة استخدام الطاقة عملا بالمقرر 94/60 مبلغ 1,170,247 دولار أمريكي ويبلغ التمويل المتبقي المتاح بموجب نافذة التمويل هذه 98,829,753 دولار أمريكي. ويسرد المرفق الثالث بالوثيقة الحالية المشروعات المقدمة من الوكالات الثنائية والمنفذة إلى الاجتماع الخامس والتسعين عملا بالمقرر 94/60.
وتبلغ قيمة المشروعات الموصى بها بموجب نافذة التمويل لإعداد قوائم الجرد الوطنية لبنوك نفايات المواد الخاضعة للرقابة عملا بالمقرر 91/66، 2,638,600 دولار أمريكي بما في ذلك 2,446,500 دولار أمريكي غير مدرجة في خطة الأعمال لعام 2024. ويسرد المرفق الرابع بالوثيقة الحالية أنشطة إعداد المشروعات المقدمة من الوكالات الثنائية والمنفذة إلى الاجتماع الخامس والتسعين عملا بالمقرر 91/66.
الالتزامات الآجلة
قيمة المبلغ الإجمالي للالتزامات الآجلة الحالية للاتفاقات المتعددة السنوات للفترة من 2024 إلى 2031 هي 336.66 مليون دولار أمريكي، بافتراض أنه ستتم الموافقة من حيث المبدأ على طلبات تمويل الاتفاقات المتعددة السنوات المقدمة إلى الاجتماع الخامس والتسعين، على النحو المبين في الجدول 3.
الجدول 3. الالتزامات الآجلة (2024-2031) (بآلاف الدولارات الأمريكية)
	الوصف
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	2031
	المجموع

	الموافق عليها من حيث المبدأ
	99,643
	50,780
	67,400
	22,538
	20,214
	8,176
	15,120
	57
	283,929

	المقدمة إلى الاجتماع الخامس والتسعين
	22,866
	0
	0
	24,773
	139
	2,367
	2,583
	0
	52,729

	المجموع
	122,510
	50,780
	67,400
	47,312
	20,353
	10,543
	17,703
	57
	336,657




التوصية
قد ترغب اللجنة التنفيذية في الإحاطة علما بما يلي:
(1) تحديث حالة تنفيذ خطة الأعمال المجمعة للصندوق المتعدد الأطراف على النحو الوارد في الوثيقة UNEP/OzL.Pro/ExCom/95/23؛ 
(2) تبلغ القيمة الإجمالية للأنشطة على النحو الموصى به إلى الاجتماع الخامس والتسعين 116,476,540 دولار أمريكي (تشمل 19,833,551 دولار أمريكي للأنشطة المتعلقة بالمواد الهيدروفلوروكربونية؛ و4,642,176 دولار أمريكي للمشروعات التجريبية لكفاءة استخدام الطاقة بموجب المقرر 94/60؛ و2,638,600 دولار أمريكي لإعداد قوائم الجرد الوطنية لبنوك نفايات المواد الخاضعة للرقابة عملا بالمقرر 91/66)، منها مبلغ 15,899,209 دولار أمريكي مرتبطا بمقترحات المشروعات غير المدرجة في خطة الأعمال لعام 2024.

UNEP/OzL.Pro/ExCom/95/23


UNEP/OzL.Pro/ExCom/95/23



إن وثائق ما قبل دورات اللجنة التنفيذية للصندوق المتعدد الأطراف لتنفيذ بروتوكول مونتريال 
قد تصدر دون إخلال بأي قرار تتخذه اللجنة التنفيذية بعد صدورها. 
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Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 95TH MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Argentina
	UNIDO
	INV
	KIP
	Investment project to phase out R‑410A in domestic air conditioner manufacturing sector in Argentina
	5,697,593
	398,832

	Bahamas (the)
	UNEP
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	91,000
	11,830

	Bahamas (the)
	UNIDO
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	39,000
	2,730

	Barbados
	UNEP
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	130,000
	16,900

	Benin
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	117,500
	15,275

	Benin
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	60,000
	7,800

	Chad
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	141,000
	18,330

	Chad
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	75,000
	9,750

	China
	UNDP
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	250,000
	17,500

	Colombia
	Germany
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	258,825
	33,647

	Colombia
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	1,066,225
	74,636

	Colombia
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (local installation and assembly subsector)
	341,100
	23,877

	Colombia
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (manufacturing sector)
	1,023,513
	71,646

	Colombia
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	124,148
	8,690

	Cook Islands (the)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	23,250
	3,023

	Costa Rica
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first trance)
	356,880
	45,029

	Costa Rica
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first trance) (PMU)
	14,088
	1,778

	Guatemala
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	10,000
	1,300

	Guatemala
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	251,019
	17,571

	Indonesia
	IBRD
	PRP
	KIP
	Preparation of a KIP investment project in the domestic and stand-alone commercial refrigerator manufacturing sector
	80,000
	5,600

	Kiribati
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	15,000
	1,950

	Lesotho
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	64,000
	8,320

	Lesotho
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	18,000
	2,340

	Marshall Islands (the)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	11,750
	1,527

	Mauritius
	Germany
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	103,000
	13,390

	Micronesia (Federated States of)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	63,500
	8,255

	Morocco
	UNIDO
	INV
	KIP
	Conversion of two production lines in one enterprise (MANAR) manufacturing domestic refrigeration equipment from HFC-134a to R-600a
	352,985
	24,709

	Nauru
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	10,500
	1,365

	Nigeria
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	1,902,050
	133,144

	Nigeria
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	130,800
	17,004

	Nigeria
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	705,510
	49,386

	Niue
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	9,250
	1,202

	Oman
	UNEP
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	160,000
	20,800

	Oman
	UNIDO
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	30,000
	2,100

	Palau
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	57,500
	7,475

	Rwanda
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	48,400
	6,292

	Rwanda
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	27,500
	3,575

	Samoa
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	66,000
	8,580

	Senegal
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	168,000
	21,840

	Senegal
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	127,500
	8,925

	Solomon Islands
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	74,125
	9,637

	Togo
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	117,500
	15,275

	Togo
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	70,000
	9,100

	Tonga
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	60,750
	7,898

	Türkiye
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	845,445
	59,181

	Türkiye
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	1,943,985
	136,079

	Tuvalu
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	12,250
	1,592

	Uruguay
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	126,927
	16,500

	Uruguay
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	49,860
	6,482

	Vanuatu
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	31,625
	4,112

	Zimbabwe
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	90,000
	11,700

	Zimbabwe
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	151,500
	19,695

	Region: ASP
	Australia
	INV
	KIP
	Regional Kigali HFC implementation plan for Pacific Island Countries (stage I, first tranche)
	295,000
	38,350

	Region: ASP
	UNEP
	TAS
	KIP
	Regional Kigali HFC implementation plan for Pacific Island Countries (stage I, first tranche)
	247,500
	32,174
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Annex II

PILOT PROJECTS FOR ENERGY EFFICIENCY (DECISION 91/65) 
SUBMITTED TO THE 95TH MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	China
	UNDP
	INV
	EEF
	Pilot project to enhance the energy efficiency of cooling technologies in data centres through the demonstration of single-phase immersion cooling system in a data centre (decision 91/65)
	1,790,800
	125,356

	Colombia
	UNDP
	TAS
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65)
	506,319
	35,442

	Costa Rica
	UNDP
	INV
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65)
	260,000
	18,200

	Honduras
	UNIDO
	INV
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65)
	278,068
	19,465

	Malaysia
	IBRD
	INV
	EEF
	Pilot project to enhance the energy efficiency of stand-alone commercial refrigeration equipment in Malaysia in the context of the HFC phase-down (investment and non-investment activities) (decisions 91/65)
	500,000
	35,000

	Montenegro
	UNIDO
	TAS
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65)
	120,000
	10,800

	Peru
	UNEP
	TAS
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65)
	115,000
	14,950

	Uganda
	United Kingdom of Great Britain and Northern Ireland
	INV
	EEF
	Demonstration of energy-efficient ultra‑low GWP technology in a supermarket (decision 91/65)
	435,200
	56,576

	Uruguay
	UNDP
	INV
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of technologies in the commercial refrigeration and residential AC sectors in the context of HFC phase-down (non-investment activities) (decision 91/65)
	300,000
	21,000
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Annex III

PROJECTS FOR ENERGY EFFICIENCY PURSUANT TO DECISION 94/60
SUBMITTED TO THE 95TH MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Egypt
	UNIDO
	PRP
	EEF
	Preparation of a pilot project on energy efficiency (decision 94/60)
	210,000
	14,700

	Malaysia
	IBRD
	INV
	EEF
	Pilot project to enhance the energy efficiency of stand-alone commercial refrigeration equipment in Malaysia in the context of the HFC phase-down (investment and non‑investment activities) (decisions 94/60)
	415,689
	29,098

	Nigeria
	UNIDO
	PRP
	EEF
	Preparation of a pilot project on energy efficiency (decision 94/60)
	78,000
	5,460

	Thailand
	IBRD
	PRP
	EEF
	Preparation of a project for enhancing energy efficiency in manufacturing of light commercial air-conditioning (AC) systems in the context of HFC phase-down (decision 94/60)
	150,000
	10,500

	Tunisia
	UNIDO
	PRP
	EEF
	Preparation of a pilot project on energy efficiency (decision 94/60)
	20,000
	1,400

	Türkiye
	UNIDO
	PRP
	EEF
	Preparation of a pilot project on energy efficiency (decision 94/60)
	220,000
	15,400
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Annex IV

PROJECT PREPARATION FOR NATIONAL INVENTORIES OF BANKS 
OF WASTE‑CONTROLLED SUBSTANCES (DECISION 91/66) 
SUBMITTED TO THE 95TH MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Bahamas (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Bangladesh
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Bhutan
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Brunei Darussalam
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Congo (the)
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Cook Islands (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Eswatini
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Fiji
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Gambia (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Indonesia
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	7,000

	Kiribati
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Madagascar
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Maldives
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Marshall Islands (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Micronesia (Federated States of)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Mongolia
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Nauru
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Nepal
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Niue
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Palau
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Samoa
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Senegal
	Germany
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Solomon Islands
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Sri Lanka
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Thailand
	IBRD
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	7,000

	Timor-Leste
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Tonga
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Tuvalu
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Uganda
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Vanuatu
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100
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