| EP |  | ### الأمم المتحدة |  |
| --- | --- | --- | --- |
| Distr. GENERAL UNEP/OzL.Pro/ExCom/96/4 7 May 2025 ARABIC ORIGINAL: ENGLISH | #### برنامج #### الأمم المتحدة #### للبيئة |  |  |

اللجنــة التنفيـذيــــة للصنــدوق المــتعــدد الأطـــراف

لتنفيـــذ بروتوكـول مونتريــال

الاجتماع السادس والتسعون

مونتريال، 26-30 مایو/أیار 2025

البند 4(ب) من جدول الأعمال المؤقت

# تقرير عن الأرصدة وتوافر الموارد

# مقدمة

# تعرض هذه الوثيقة موجزا للتعديلات المالية التي أشارت إليها الوكالات المنفذة والوكالات الثنائية على النحو الذي وافقت عليه الأمانة. وهي تتضمن بيانات إحصائية من جميع المشاريع التي احتفظت بأرصدتها لأكثر من 12 شهرا بعد إنجاز المشروع، على النحو المطلوب بموجب المقررين 28/7 و56/2(ج). وتتناول الوثيقة الأرصدة التي يتعين إعادتها مقابل المشاريع على سبيل المتابعة للمقررات ذات الصلة (المشار إليها باسم "مشاريع نُفّذت بموجب مقررات" في هذه الوثيقة) وتحويلات المشاريع. وهي تشير كذلك إلى مستوى الموارد النقدية المتاحة للجنة التنفيذية على النحو المسجل في وثيقة حالة المساهمات والمصروفات، على النحو المطلوب بموجب المقرر 41/92(ب)، وتقدم توصية في هذا الصدد. وترد المبالغ التي تحتفظ بها الوكالات المنفذة والوكالات الثنائية للمشاريع المنجَزة، وللمشاريع المنفَّذة بموجب مقررات في المرفقين الأول والثاني. ويعرض المرفق الثالث الأموال التي أعادتها الوكالات المنفذة من المشاريع المنجَزة والمشاريع الإضافية القائمة على المساهمات الطوعية.

# الأموال التي يتعين إعادتها إلى الاجتماع السادس والتسعين

# يبلغ مجموع الأموال التي يتعين على الوكالات المنفذة إعادتها 1,467,369 دولارا أمريكيا من المشاريع المنجَزة والمشاريع الإضافية القائمة على المساهمات الطوعية، على النحو المبيَّن في الجدول 1.

# الجدول 1. الأموال التي يتعين إعادتها من الوكالات المنفذة إلى الاجتماع السادس والتسعين (بالدولار الأميركي)

| الوكالة | تكلفة المشروع | تكلفة دعم الوكالة | التكلفة الإجمالية |
| --- | --- | --- | --- |
| اليوئنديبي | 307,094 | 24,914 | 332,008 |
| اليونيب* | 1,006,119 | 56,387 | 1,062,506 |
| اليونيدو** | 67,866 | 4,989 | 72,855 |
| المجموع | 1,381,079 | 86,290 | 1,467,369 |

* تشمل الأموال المعادة من اليونيب مبلغ 500,000 دولار أمريكي لمشروع سيُنقل إلى اليونيدو.

** تشمل الأموال المعادة من اليونيدو مبلغ 41,098 دولارا أمريكيا لمشروع سيُنقل إلى اليوئنديبي، على النحو المبيَّن في الجدول 4.

# الأموال المحتفَظ بها لدى الوكالات التنفيذية والوكالات الثنائية

# يبلغ مجموع الأموال المحتفَظ بها 3,127,741 دولارا أمريكيا (3,123,653 دولارا أمريكيا لدى الوكالات التنفيذية و4,088 دولارا أمريكيا لدى إحدى الوكالات الثنائية)، على النحو المبيَّن في الجدولين 2 و3.

الجدول 2. أرصدة المشاريع المنجَزة والمشاريع المنفَّذة بموجب مقررات التي تحتفظ بها الوكالات المنفذة (بما في ذلك تكاليف دعم الوكالة)

| سنة الإنجاز | اليوئنديبي |  | اليونيدو |  | المجموع |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | العدد | دولار أمريكي | العدد | دولار أمريكي | العدد | دولار أمريكي |
| المشاريع التي مضى على إنجازها أكثر من سنتين |  |  |  |  |  |  |
| 2021 | 0 | 0 | 1 | 33,422 | 1 | 33,422 |
| 2022 | 3 | 102,335 | 6 | 111,287 | 9 | 213,622 |
| من 1 يناير/كانون الثاني إلى 30 أبريل/نيسان 2023 | 0 | 0 | 0 | 0 | 0 | 0 |
| المجموع الفرعي | 3 | 102,335 | 7 | 144,709 | 10 | 247,044 |
| المشاريع التي مضى على إنجازها أقل من سنتين |  |  |  |  |  |  |
| من 1 مايو/أيار إلى 31 ديسمبر/كانون الأول 2023 | 27 | 1,652,542 | 11 | 1,222,643 | 38 | 2,875,185 |
| المجموع الفرعي | 27 | 1,652,542 | 11 | 1,222,643 | 38 | 2,875,185 |
| المجموع | 30 | 1,754,877 | 18 | 1,367,352 | 48 | 3,122,229 |
| المشاريع المنفَّذة بموجب مقررات |  |  |  |  |  |  |
|  | 0 | 0 | 1 | 1,424 | 1 | 1,424 |
| المجموع الكلي | 30 | 1,754,877 | 19 | 1,368,776 | 49 | 3,123,653 |

الجدول 3. رصيد أحد المشاريع المنجَزة الذي تحتفظ به إحدى الوكالات الثنائية

| الوكالة | رمز المشروع | سنة الإنجاز | رصيد الالتزامات (دولار أمريكي) |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | رصيد المشروع | رصيد تكلفة دعم الوكالة | المجموع |
| إسبانيا | MEX/PHA/81/TAS/190 | 2023 | 3,667 | 421 | 4,088 |

# نقل المشاريع

# طلبت حكومة جنوب أفريقيا تحويل أموال مشروع التعزيز المؤسسي (المرحلة الأولى) من اليونيب إلى اليونيدو على النحو المبيَّن أدناه:

## SOA/SEV/94/INS/18 - 500,000 دولار أمريكي ولا توجد تكاليف دعم للوكالة. وسوف يستلزم التحويل إلى اليونيدو تكاليف دعم للوكالة أعلى قدرها 35,000 دولار أمريكي.

# وطلبت حكومة شيلي تحويل الأموال المخصصة لخطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثالثة، الشريحة الأولى) من اليونيدو إلى اليوئنديبي، على النحو المبيَّن أدناه:

## CHI/PHA/88/INV/205 - 38,409 دولارات أمريكية، بالإضافة إلى تكاليف دعم الوكالة البالغة 2,689 دولارا أمريكيا.

# ويعرض الجدول 4 معلومات مُفصَّلة عن الأرصدة التي يتعين تحويلها. وقد ترغب اللجنة التنفيذية في الموافقة على هذا الطلب.

الجدول 4. أرصدة مشاريع جنوب أفريقيا و شيلي التي يتعين تحويلها

| عنوان المشروع | رقم المشروع | الإعادة |  |  | التحويل |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | إلى الصندوق المتعدد الأطراف |  |  | إلى الوكالة |  |  |
|  |  | من | الرصيد | تكاليف دعم الوكالة | من | الرصيد | تكاليف دعم الوكالة |
| مشروع التعزيز المؤسسي (المرحلة الأولى: 6/2024 - 5/2027) | SOA/SEV/94/INS/18 | اليونيب | 500,000 | - | اليونيدو | 500,000 | 35,000 |
| خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثالثة، الشريحة الأولى) | CHI/PHA/88/INV/205 | اليونيدو | 38,409 | 2,689 | اليوئنديبي | 38,409 | 2,689 |

توافر الموارد

# تمت الموافقة على ميزانية الصندوق المتعدد الأطراف بمبلغ 965 مليون دولار أمريكي لفترة الثلاث سنوات 2024-2026، على النحو الذي قررته الأطراف (المقرر 35/1). وتشير الوثيقة المتعلقة بحالة المساهمات والمصروفات إلى وجود رصيد متاح قدره 581,090,072 دولارا أمريكيا في 30 أبريل/نيسان 2025. ويبلغ إجمالي الرصيد الذي أعادته الوكالات المنفذة إلى الاجتماع السادس والتسعين 926,271 دولارا أمريكيا، باستثناء 500,000 دولار أمريكي أعادها اليونيب لتحويلها إلى اليونيدو، و41,098 دولارا أمريكيا أعادتها اليونيدو لتحويلها إلى اليوئنديبي. وبالتالي، فإن إجمالي مستوى الموارد المتاحة للموافقة عليها في الاجتماع السادس والتسعين هو 582,016,343 دولارا أمريكيا.

# تعليقات الأمانة

# ذكّرت الأمانة الوكالات المنفذة بأنه ينبغي إعادة أرصدة المشاريع المنجَزة منذ عام واحد أو أكثر، والمشاريع المنفذة بموجب مقررات ومشاريع المساهمات الطوعية الإضافية، إلى الصندوق المتعدد الأطراف في أقرب وقت ممكن.

# وبالنظر إلى أن إجمالي مستوى التمويل للمشاريع والأنشطة بالصيغة المقدَّم بها إلى الاجتماع السادس والتسعين يبلغ 53,386,363 دولارا أمريكيا، فإن هناك موارد كافية متاحة للموافقات في الاجتماع السادس والتسعين.

التوصية

# قد ترغب اللجنة التنفيذية في الآتي:

## (أ)	أن تحيط علما بما يلي:

  - التقرير المتعلق بالأرصدة وتوافر الموارد الوارد في الوثيقة UNEP/OzL.Pro/ExCom/96/4؛

  - أن صافي مستوى الأموال التي ستقوم الوكالات المنفذة بإعادتها في الاجتماع السادس والتسعين يبلغ 926,271 دولارا أمريكيا، ويتألف من مبلغ 307,094 دولارا أمريكيا بالإضافة إلى تكاليف دعم الوكالة البالغة 24,914 دولارا أمريكيا من اليوئنديبي؛ و506,119 دولارا أمريكيا بالإضافة إلى تكاليف دعم الوكالة البالغة 56,387 دولارا أمريكيا من اليونيب؛ و29,457 دولارا أمريكيا بالإضافة إلى تكاليف دعم الوكالة البالغة 2,300 دولار أمريكي من اليونيدو؛

  - أن اليوئنديبي يحتفظ بأرصدة قدرها 102,335 دولارا أمريكيا، بما في ذلك تكاليف دعم الوكالة، لثلاثة مشاريع أُنجزت قبل أكثر من عامين؛

  - أن اليونيدو تحتفظ بأرصدة قدرها 144,709 دولارات أمريكية، بما في ذلك تكاليف دعم الوكالة، لسبعة مشاريع أُنجزت قبل أكثر من عامين؛ و1,424 دولارا أمريكيا، بما في ذلك تكاليف دعم الوكالة، لمشروع واحد أُنجز "بموجب مقرر صادر عن اللجنة التنفيذية"؛

  - أن اليونيب سيعيد في الاجتماع السادس والتسعين الأرصدة من مشروع التعزيز المؤسسي (المرحلة الأولى) في جنوب أفريقيا (SOA/SEV/94/INS/18) البالغة 500,000 دولار أمريكي؛

  - أن اليونيدو ستعيد في الاجتماع السادس والتسعين الأرصدة من المرحلة الثالثة من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية في شيلي (الشريحة الأولى) (CHI/PHA/88/INV/205) البالغة 38,409 دولارات أمريكية، بالإضافة إلى تكاليف دعم الوكالة البالغة 2,689 دولارا أمريكيا؛

## (ب)	أن تطلب إلى اليوئنديبي واليونيدو ما يلي:

- المضي قدما في صرف أو إلغاء الأموال الملتزَم بها غير اللازمة للمشاريع المنجَزة، وإعادة الأرصدة المرتبطة بها في الاجتماع السابع والتسعين؛

- المضي قدما في صرف أو إلغاء الالتزامات الخاصة بالمشاريع التي أُنجزت قبل أكثر من عامين وإعادة الأرصدة في الاجتماع السابع والتسعين؛

## (ج)	أن تطلب كذلك إلى اليونيدو أن تمضي قدما في أن تصرف أو تعيد، خلال الاجتماع السابع والتسعين، أرصدة المشروع الذي أُنجز بموجب مقرر؛

## (د)	أن تطلب إلى أمين الخزانة ما يلي:

- أن يحول في الاجتماع السادس والتسعين الأموال التي أعادها اليونيب إلى اليونيدو لتنفيذ مشروع التعزيز المؤسسي في جنوب أفريقيا (المرحلة الأولى) (SOA/SEV/94/INS/18) المشار إليه في الفقرة الفرعية (أ)(5) أعلاه، والبالغة 500,000 دولار أمريكي، بالإضافة إلى تكاليف دعم الوكالة البالغة 35,000 دولار أمريكي؛

- أن يحول في الاجتماع السادس والتسعين الأموال التي أعادتها اليونيدو إلى اليوئنديبي لتنفيذ خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثالثة، الشريحة الأولى) (CHI/PHA/88/INV/205) المشار إليها في الفقرة الفرعية (أ)(6) أعلاه، والبالغة 38,409 دولارات أمريكية، بالإضافة إلى تكاليف دعم الوكالة البالغة 2,689 دولار أمريكي.

Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AND BILATERAL AGENCIES FOR COMPLETED PROJECTS

| Code | Project title | Date completed (Actual) | Approved funding plus adjustments as of 31 Dec 2023 (US $) | Funds disbursed as of 96th meeting (US $) | Balances committed as per 96th meeting (US $) | Balances not-committed as per 96th meeting (US $) | Support cost on balances committed and not committed as per 96th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| COL/SEV/88/INS/115 | Extension of institutional strengthening project (phase XIII: 12/2021-11/2023) | Dec-23 | 352,768 | 328,161 | 24,607 |  | 1,723 |  |  |  |
| COS/SEV/88/INS/64 | Extension of institutional strengthening project (phase XIV: 1/2022-12/2023) | Dec-23 | 179,857 | 170,446 | 9,411 |  | 659 |  |  |  |
| EGY/PHA/79/TAS/132 | HCFC phase-out management plan (stage II, first tranche) (project management and monitoring) | Dec-22 | 75,000 | 67,871 | 7,129 |  | 499 |  |  |  |
| EGY/PHA/84/INV/144 | HCFC phase-out management plan (stage II, second tranche) (extruded polystyrene foam sector) | Dec-23 | 1,761,750 | 1,577,664 | 184,086 |  | 12,886 |  |  |  |
| GHA/KIP/87/PRP/51 | Preparation of Kigali HFC implementation plan | Aug-23 | 130,000 | 87,053 | 42,947 |  | 3,006 |  |  |  |
| GHA/PHA/87/INV/50 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 459,820 | 452,430 | 7,390 |  | 517 |  |  |  |
| IDS/PHA/87/PRP/216 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | Dec-23 | 90,000 | 84,295 | 5,705 |  | 399 |  |  |  |
| IND/PHA/87/PRP/487 | Preparation of HCFC phase-out management plan (stage III) (refrigeration sector) | Aug-23 | 150,000 | 89,958 | 60,042 |  | 4,203 |  |  |  |
| IRA/PHA/90/INV/262 | HCFC phase-out management plan (stage II, fourth tranche) (PMU) | Dec-23 | 92,000 | 69,877 | 22,123 |  | 1,549 |  |  |  |
| IRA/PHA/92/INV/264 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | Dec-23 | 93,017 | 0 | 93,017 |  | 6,511 |  |  |  |
| IRA/PHA/92/INV/265 | HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration sector) | Dec-23 | 145,255 | 0 | 145,255 |  | 10,168 |  |  |  |
| IRA/SEV/86/INS/249 | Extension of the institutional strengthening project (phase XIII: 4/2021-3/2023) | May-23 | 222,094 | 178,036 | 44,058 |  | 3,084 |  |  |  |
| KAM/KIP/88/PRP/40 | Preparation of Kigali HFC implementation plan | Dec-23 | 35,000 | 25,013 | 9,987 |  | 699 |  |  |  |
| KYR/KIP/87/PRP/45 | Preparation of Kigali HFC implementation plan | Aug-23 | 91,000 | 74,690 | 16,310 |  | 1,142 |  |  |  |
| KYR/PHA/90/TAS/47 | Verification report on the implementation of stage II of the HCFC phase-out management plan | Jul-23 | 30,000 | 0 | 30,000 |  | 2,700 |  |  |  |
| LAO/PHA/86/INV/38 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 107,000 | 86,720 | 20,280 |  | 1,825 |  |  |  |
| LEB/SEV/86/INS/96 | Extension of the institutional strengthening project (phase XII: 4/2021-3/2023) | Dec-23 | 198,515 | 157,610 | 40,905 |  | 2,863 |  |  |  |
| MAL/PHA/84/INV/191 | HCFC phase-out management plan (stage II, second tranche) (polyurethane foam sector) | Dec-23 | 1,703,922 | 1,651,948 | 51,974 |  | 3,638 |  |  |  |
| MAL/PHA/84/TAS/186 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | Dec-23 | 627,053 | 174,875 | 452,178 |  | 31,653 |  |  |  |
| MAL/PHA/88/INV/193 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector and management and coordination) | Dec-23 | 154,900 | 39,789 | 115,111 |  | 8,058 |  |  |  |
| MAL/SEV/88/INS/192 | Extension of institutional strengthening project (phase XIV: 1/2022-12/2023) | Dec-23 | 357,760 | 349,613 | 8,147 |  | 570 |  |  |  |
| MEX/KIP/87/PRP/195 | Preparation of Kigali HFC implementation plan | Aug-23 | 85,000 | 76,433 | 8,567 |  | 600 |  |  |  |
| NIR/PHA/81/TAS/148 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Dec-22 | 1,077,113 | 1,063,456 | 13,657 |  | 956 |  |  |  |
| NIR/PHA/81/TAS/150 | HCFC phase-out management plan (stage II, first tranche) (project management and coordination) | Dec-22 | 165,000 | 90,146 | 74,854 |  | 5,240 |  |  |  |
| NIR/PHA/88/INV/162 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | Dec-23 | 977,407 | 962,333 | 15,074 |  | 1,055 |  |  |  |
| PAR/KIP/87/PRP/42 | Preparation of Kigali HFC implementation plan | Aug-23 | 170,000 | 159,958 | 10,042 |  | 703 |  |  |  |
| PER/KIP/87/PRP/59 | Preparation of Kigali HFC implementation plan | Sep-23 | 190,000 | 185,925 | 4,075 |  | 285 |  |  |  |
| PER/PHA/85/INV/57 | HCFC phase-out management plan (stage II, second tranche) | Jun-23 | 233,400 | 194,591 | 38,809 |  | 2,717 |  |  |  |
| SWA/KIP/87/PRP/33 | Preparation of Kigali HFC implementation plan | Aug-23 | 30,000 | 3,000 | 27,000 |  | 1,890 |  |  |  |
| TRI/PHA/86/INV/38 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 498,756 | 442,364 | 56,392 |  | 3,947 |  |  |  |
| TOTAL UNDP |  |  |  |  | 1,639,132 |  | 115,745 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| CMR/KIP/88/PRP/49 | Preparation of Kigali HFC implementation plan | Dec-23 | 190,000 | 188,249 | 1,751 |  | 123 | 1 | 97 |  |
| CPR/PHA/88/INV/607 | HCFC phase-out management plan (stage II, fourth tranche) (extruded polystyrene foam sector plan) | Dec-23 | 4,400,000 | 3,960,000 | 440,000 |  | 30,800 | 1 | 97 |  |
| GAB/PHA/79/INV/34 | HCFC phase-out management plan (stage I, third tranche) | Dec-22 | 119,900 | 60,409 | 59,491 |  | 5,354 | 1 | 97 |  |
| GUA/PHA/91/TAS/61 | Verification report on the implementation of stage II of the HCFC phase-out management plan | Dec-23 | 30,000 | 29,899 | 101 |  | 9 | 1 | 97 |  |
| IVC/PHA/84/INV/45 | HCFC phase-out management plan (stage I, third tranche) | Dec-22 | 460,000 | 449,046 | 10,954 |  | 767 | 1 | 97 |  |
| JOR/PHA/84/TAS/107 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector, project management and coordination) | Dec-23 | 294,122 | 90,153 | 203,969 |  | 14,277 | 1 | 97 |  |
| LIB/PHA/75/INV/36 | HCFC phase-out management plan (stage I, first tranche) (foam sector) | Dec-23 | 943,094 | 713,112 | 229,982 |  | 16,099 | 1 | 97 |  |
| LIB/SEV/85/INS/44 | Renewal of the institutional strengthening project (phase VI: 7/2020-6/2022) | Jun-23 | 174,164 | 166,234 | 7,930 |  | 555 | 1 | 97 |  |
| MOZ/PHA/66/INV/23 | HCFC phase-out management plan (stage I, first tranche) | Dec-22 | 75,000 | 72,133 | 2,867 |  | 258 | 1 | 97 |  |
| NER/PHA/84/INV/39 | HCFC phase-out management plan (stage I, second tranche) | Dec-22 | 90,000 | 76,492 | 13,508 |  | 946 | 1 | 97 |  |
| NER/PHA/88/INV/41 | HCFC phase-out management plan (stage I, third tranche) | Dec-22 | 20,000 | 19,002 | 998 |  | 70 | 1 | 97 |  |
| NIC/PHA/86/INV/40 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 100,092 | 98,549 | 1,543 |  | 108 | 1 | 97 |  |
| PHI/PHA/83/INV/104 | HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector) | Dec-23 | 537,856 | 346,679 | 191,177 |  | 13,382 | 1 | 97 |  |
| PHI/PHA/83/TAS/105 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Dec-23 | 273,894 | 234,651 | 39,243 |  | 2,747 | 1 | 97 |  |
| SEN/PHA/85/INV/41 | HCFC phase-out management plan (stage I, third tranche) | Dec-21 | 50,000 | 18,910 | 31,090 |  | 2,332 | 1 | 97 |  |
| SEN/PHA/85/PRP/43 | Preparation of a HCFC phase-out management plan (stage II) | Jun-22 | 20,000 | 4,977 | 15,023 |  | 1,052 | 1 | 97 |  |
| SOA/PHA/91/INV/16 | HCFC phase-out management plan (stage I, fifth tranche) (refrigeration servicing, custom training and monitoring) | Dec-23 | 178,760 | 157,305 | 21,455 |  | 1,502 | 1 | 97 |  |
| SOM/PHA/88/INV/16 | HCFC phase-out management plan (stage I, third tranche) | Jun-23 | 40,000 | 34,494 | 5,506 |  | 385 | 1 | 97 |  |
| TOTAL UNIDO |  |  |  |  | 1,276,587 |  | 90,765 |  |  |  |
| SPAIN |  |  |  |  |  |  |  |  |  |  |
| MEX/PHA/81/TAS/190 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) | Dec-23 | 1,070,000 | 1,066,333 | 3,667 |  | 421 | 1 | 97 |  |
| TOTAL SPAIN |  |  |  |  | 3,667 |  | 421 |  |  |  |

Annex II

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR BY-DECISION PROJECTS

| CODE | Project title | Approved funding plus adjustments as of 31 December 2023 (US $) | Funds disbursed as of 96th meeting (US $) | Balances committed as per 96th meeting (US $) | Balances not- committed as per 96th meeting (US $) | Support cost on balances committed and not-committed as per 96th meeting (US $) | Why any balances could not be returned? | When they could be returned? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNIDO |  |  |  |  |  |  |  |  |
| BRA/PHA/75/INV/311 | HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration and air-conditioning sector) | 1,472,175 | 1,470,844 | 1,331 |  | 93 | Project is ongoing until December 2025. Partial funding based on decision was completed at the 90th and 94th meetings. The project is not completed and should not be listed in the completed sheet | 98 |
| TOTAL UNIDO |  |  |  | 1,331 |  | 93 |  |  |

Annex III

DETAILS ON COMPLETED, BY-DECISIONS AND ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AND BILATERAL AGENCIES

| Code |  | Project title |  |  | Project costs returned (US $) | Agency support costs (US $) |  | Total (US $) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |
| ARG/SEV/82/INS/188 |  | Extension for institutional strengthening project (phase X: 1/2019-12/2020) |  |  | -120 | 0 |  | -120 |
| BRA/DES/72/DEM/305 |  | Pilot demonstration project on ODS waste management and disposal |  |  | -64 | 0 |  | -64 |
| BRA/PHA/88/PRP/330 |  | Preparation of HCFC phase-out management plan (stage III) (Overarching) |  |  | 621 | 43 |  | 664 |
| BZE/SEV/85/TAS/37 |  | Enabling activities for HFC phase-down |  |  | 5,424 | 380 |  | 5,804 |
| CHI/PHA/81/INV/197 |  | HCFC phase-out management plan (stage II, second tranche) (foam sector) |  |  | -42,459 | 0 |  | -42,459 |
| COL/PHA/84/TAS/108 |  | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector, project management and monitoring) |  |  | -6,182 | 0 |  | -6,182 |
| COL/PHA/85/PRP/109 |  | Preparation of a HCFC phase-out management plan (stage III) |  |  | 391 | 27 |  | 418 |
| HAI/SEV/84/TAS/23 |  | Enabling activities for HFC phase-down |  |  | 4,689 | 328 |  | 5,017 |
| PAN/PHA/83/PRP/49 |  | Preparation of a HCFC phase-out management plan (stage III) |  |  | 3,272 | 229 |  | 3,501 |
| SRL/SEV/86/INS/57 |  | Extension of the institutional strengthening project (phase XIII: 1/2021-12/2022) |  |  | 1,762 | 123 |  | 1,885 |
| TRI/SEV/88/INS/41 |  | Extension of the institutional strengthening project (phase XI: 12/2021-12/2023) |  |  | 1,819 | 127 |  | 1,946 |
| URU/PHA/77/INV/67 |  | HCFC phase-out management plan (stage II, first tranche) (foam sector) |  |  | 37,789 | 2,645 |  | 40,434 |
| URU/PHA/82/INV/72 |  | HCFC phase-out management plan (stage II, second tranche) (foam sector) |  |  | 300,153 | 21,011 |  | 321,164 |
| Total completed projects |  |  |  |  | 307,095 | 24,914 |  | 332,008 |
| TOTAL UNDP |  |  |  |  | 307,095 | 24,914 |  | 332,008 |
| UNEP |  |  |  |  |  |  |  |  |
| ASP/DES/95/PRP/72 |  | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) |  |  | 0 | 2,800 |  | 2,800 |
| BAR/PHA/86/TAS/30 |  | Verification report on the implementation of stage I of the HCFC phase-out management plan |  |  | 9,950 | 1,294 |  | 11,244 |
| CHI/PHA/81/TAS/195 |  | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) |  |  | 10,016 | 1,302 |  | 11,318 |
| COL/PHA/84/TAS/107 |  | HCFC phase-out management plan (stage II, third tranche) (technical assistance in policies formulation and implementation) |  |  | (13,243) | (1,722) |  | (14,965) |
| CPR/PHA/77/TAS/581 |  | HCFC phase-out management plan (stage II, first tranche) (refrigeration and air-conditioning servicing sector plan and enabling component) |  |  | 695 | 77 |  | 772 |
| EQG/PHA/90/TAS/19 |  | HCFC phase-out management plan (stage I, fifth tranche) |  |  | 87 | 11 |  | 98 |
| GAM/KIP/90/PRP/45 |  | Preparation of a Kigali HFC implementation plan |  |  | 9,750 | 1,268 |  | 11,018 |
| GLO/SEV/91/TAS/361 |  | Compliance Assistance Programme: 2023 budget |  |  | 46,792 | 3,743 |  | 50,535 |
| GUA/PHA/86/TAS/58 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 5,491 | 714 |  | 6,205 |
| KAM/KIP/88/PRP/41 |  | Preparation of Kigali HFC implementation plan |  |  | 10,867 | 1,413 |  | 12,280 |
| KAM/PHA/83/TAS/35 |  | HCFC phase-out management plan (fourth tranche) |  |  | 1,324 | 172 |  | 1,496 |
| MOL/SEV/87/INS/44 |  | Extension of the institutional strengthening project (phase XI: 7/2021-6/2023) |  |  | 6,030 | 0 |  | 6,030 |
| MOZ/KIP/90/PRP/37 |  | Preparation of a Kigali HFC implementation plan |  |  | 9,700 | 1,261 |  | 10,961 |
| NIC/DES/93/PRP/52 |  | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) |  |  | 35,000 | 4,550 |  | 39,550 |
| NIC/EEF/92/TAS/50 |  | HCFC phase-out management plan (stage II, second tranche) (energy efficiency - related activities under decision 89/6) |  |  | 51,000 | 6,630 |  | 57,630 |
| NIC/EEF/93/DEM/54 |  | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65) |  |  | 30,000 | 3,900 |  | 33,900 |
| NIC/KIP/93/TAS/55 |  | Kigali HFC implementation plan (stage I, first tranche) |  |  | 25,000 | 3,250 |  | 28,250 |
| NIC/PHA/94/TAS/58 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 30,000 | 3,900 |  | 33,900 |
| NIC/SEV/92/INS/51 |  | Renewal of institutional strengthening project (phase XI: 7/2023-6/2026) |  |  | 50,000 | 0 |  | 50,000 |
| PER/SEV/80/INS/56 |  | Renewal of institutional strengthening project (phase V: 1/2018-12/2019) |  |  | 18,209 | 0 |  | 18,209 |
| PRC/PHA/76/TAS/30 |  | HCFC phase-out management plan (stage I, third tranche) |  |  | 24,850 | 3,231 |  | 28,081 |
| RWA/PHA/86/TAS/34 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 18,581 | 2,416 |  | 20,997 |
| SAU/PHA/86/PRP/36 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 36,625 | 4,761 |  | 41,386 |
| SSD/SEV/76/INS/03 |  | Institutional strengthening project (phase I: 5/2016-4/2018) |  |  | 563 | 0 |  | 563 |
| SWA/PHA/86/TAS/29 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 20,000 | 2,600 |  | 22,600 |
| TKM/KIP/87/PRP/18 |  | Preparation of Kigali HFC implementation plan |  |  | 1,480 | 192 |  | 1,672 |
| TLS/PHA/80/TAS/16 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 299 | 39 |  | 338 |
| UGA/PHA/86/TAS/29 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 17,052 | 2,217 |  | 19,269 |
| ZAM/PHA/86/TAS/40 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 20,000 | 2,600 |  | 22,600 |
| ZIM/PHA/86/TAS/61 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 30,000 | 3,769 |  | 33,769 |
| SOA/SEV/94/INS/18 |  | Institutional strengthening project (phase I: 6/2024-5/2027) |  |  | 500,000 | 0 |  | 500,000 |
| Total completed projects |  |  |  |  | 1,006,119 | 56,387 |  | 1,062,506 |
| TOTAL UNEP |  |  |  |  | 1,006,119 | 56,387 |  | 1,062,506 |
| UNIDO |  |  |  |  |  |  |  |  |
| ALG/SEV/84/TAS/83 |  | Enabling activities for HFC phase-down |  |  | 5,201 | 364 |  | 5,565 |
| BKF/PHA/84/PRP/41 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 793 | 55 |  | 848 |
| CHI/PHA/88/INV/205 |  | HCFC phase-out management plan (stage III, first tranche) |  |  | 38,409 | 2,689 |  | 41,098 |
| GUI/PHA/86/PRP/37 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 209 | 15 |  | 224 |
| JOR/PHA/77/INV/101 |  | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) |  |  | 645 | 45 |  | 690 |
| LEB/REF/88/PRP/99 |  | Project preparation for HFC-related project in the manufacturing sector at Lematic Industries to convert the production of residential air-conditioning from R-410A to R-290 |  |  | 760 | 53 |  | 813 |
| MDN/SEV/88/INS/48 |  | Extension of the institutional strengthening project (phase VII: 12/2021-11/2023) |  |  | 444 | 31 |  | 475 |
| MEX/PHA/73/INV/174 |  | HCFC phase-out management plan (stage II, first tranche) (cleaning agent phase-out in refrigeration servicing sector) |  |  | 987 | 69 |  | 1,056 |
| MEX/PHA/81/INV/189 |  | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) |  |  | 61 | 4 |  | 65 |
| MOZ/PHA/83/INV/31 |  | HCFC phase-out management plan (stage I, third and fourth tranches) |  |  | 10,139 | 912 |  | 11,051 |
| SYR/REF/62/INV/103 |  | Phase-out of HCFC-22 and HCFC-141b from the manufacture of unitary air-conditioning equipment and rigid polyurethane insulation panels at Al Hafez Group |  |  | 4,437 | 333 |  | 4,769 |
| TKM/PHA/86/INV/17 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 133 | 9 |  | 142 |
| TKM/SEV/86/INS/16 |  | Extension of the institutional strengthening project (phase V: 1/2021-12/2022) |  |  | 6 | 0 |  | 6 |
| ZAM/PHA/77/INV/33 |  | HCFC phase-out management plan (stage I, third tranche) |  |  | 664 | 60 |  | 724 |
| Total completed projects |  |  |  |  | 62,887 | 4,640 |  | 67,527 |
| ARG/REF/81/INV/01+ |  | Conversion project for replacement of HFC-134a with isobutane (R-600a)/propane (R-290)-based refrigerant in the manufacture of domestic and commercial refrigeration equipment at Briket, Bambi and Mabe-Kronen |  |  | 2,700 | 189 |  | 2,890 |
| VEN/SEV/81/TAS/01+ |  | Enabling activities for HFC phase-down |  |  | 2,279 | 160 |  | 2,439 |
| Total “additional voluntary contributions” projects |  |  |  |  | 4,980 | 349 |  | 5,328 |
| TOTAL UNIDO |  |  |  |  | 67,866 | 4,989 |  | 72,855 |

UNEP/OzL.Pro/ExCom/96/1

تستند البيانات المعروضة إلى نموذج الإبلاغ الذي أُعِدَّ عملا بالمقرر 31/2.

UNEP/OzL.Pro/ExCom/96/3

انظر الخطاب المؤرخ 4 مارس/آذار 2025 المُرسَل من وزارة الغابات والثروة السمكية والبيئة في جنوب أفريقيا.

المقرر 95/34(أ)(2) والمرفق التاسع عشر بالوثيقة UNEP/OzL.Pro/ExCom/95/94

1: Outstanding obligations to be paid, funds will be returned with next balance list. 2: Project is ongoing based on revised decision from the 95th Executive Committee meeting. 3: Project is ongoing until December 2025. Partial funding based on decision was completed at the 90th and 94th meeting. The project is not completed and should not be listed in the Completed sheet.