| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/91/27 10 November 2022 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-first Meeting

Montreal, 5-9 December 2022

Item 8(d)(v) of the provisional agenda

THE WORLD BANK Business plan for 2023–2025

# Introduction

# This document presents the World Bank business plan for 2023–2025 and includes the planned activities for the reduction of controlled substances under the Montreal Protocol during the period 2023-2025. The narrative of the World Bank’s business plan for 2023–2025 is attached to the present document.

# This document consists of the following sections:

- Planned activities during the period 2023–2025

- Secretariat’s comments

- Proposed adjustments by the Secretariat

- Performance indicators

- Recommendation

I.	Planned activities during the period 2023–2025

# Table 1 sets out, by year, the value of activities included in the World Bank’s business plan.

Table 1. Resource allocation in the World Bank business plan for 2023–2025 (US $)* – as submitted

| Description | 2023 | 2024 | 2025 | Total (2023–2025) | Total after 2025 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 7,614,689 | 24,488,763 | 5,350,000 | 37,453,452 | 4,494,000 |
| HPMP preparation – stage III | 160,500 | 0 | 0 | 160,500 | 0 |
| HPMP stage III | 0 | 1,070,000 | 2,140,000 | 3,210,000 | 2,140,000 |
| HCFC activities subtotal | 7,775,189 | 25,558,763 | 7,490,000 | 40,823,952 | 6,634,000 |
| HFC activities |  |  |  |  |  |
| Kigali HFC implementation plan (KIP) preparation | 470,800 | 0 | 0 | 470,800 | 0 |
| KIPs | 3,210,000 | 3,210,000 | 0 | 6,420,000 | 42,800,000 |
| HFC activities subtotal | 3,680,800 | 3,210,000 | 0 | 6,890,800 | 42,800,000 |
| Standard activities |  |  |  |  |  |
| Core unit | 1,747,145 | 1,759,375 | 1,771,691 | 5,278,211 | 0 |
| Institutional strengthening (IS) | 676,584 | 0 | 676,584 | 1,353,168 | 0 |
| Standard activities subtotal | 2,423,729 | 1,759,375 | 2,448,275 | 6,631,379 | 0 |
| Total | 13,879,718 | 30,528,138 | 9,938,275 | 54,346,131 | 49,434,000 |

* Including agency support costs where applicable.

# II.	Secretariat’s comments

II.1	HCFC activities

# Stage III of HPMPs

# A total of US $5.35 million is planned for stage III of HPMPs for one country (Viet Nam), including US $3.21 million for 2023–2025 while US $2.14 million is for the period after 2025. Inclusion of stage III of HPMPs in the business plan including project preparation is allowed for countries for which stage II of the HPMP had been approved and which had a reduction target beyond 2024 (decision 88/34(d)).

II.2	HFC-related activities

# KIP project preparation

# A total of US $470,800 is included for KIP project preparation activities in the 2023-2025 business plan for two countries (Indonesia and Thailand). These two countries have not yet ratified the Kigali Amendment but have submitted the required letter from their respective Government indicating their intent to make best efforts to ratify the Kigali Amendment.

KIPs

# Decision 84/46(g) allowed inclusion of KIPs in the business plan only for countries that had ratified the Kigali Amendment. A total of US $49.22 million is included for KIPs for four countries (Indonesia, Malaysia, Thailand and Viet Nam). Two of these countries (Indonesia and Thailand) have not yet ratified the Kigali Amendment.

# II.3	Core unit costs

# The core unit costs are expected to increase at an annual rate of 0.7 per cent as agreed.

III.	Proposed adjustments by the Secretariat

# The adjustments to the World Bank business plan for 2023–2025 were based on relevant decisions of the Executive Committee. In reviewing the revised business plan of the World Bank for 2023–2025, the Secretariat noted that the following adjustments were not included:

Table 2. Adjustments to the World Bank business plan for 2023–2025 (US $)* – as proposed by the Secretariat

| Adjustment | 2023–2025 | After 2025 |
| --- | --- | --- |
| PRP for KIPs pursuant to decision 87/50 | (74,968) | 0 |
| KIPs pursuant to decision 84/46(g) | (3,210,000) | (21,400,000) |

* Including agency support costs where applicable.

# Table 3 presents the results of the Secretariat’s proposed adjustments to the World Bank business plan for 2023–2025, which are also addressed in the context of the consolidated business plan of the Multilateral Fund for 2023–2025.

Table 3. Resource allocation in the World Bank’s adjusted business plan for 2023–2025 (US $)*

| Description | 2023 | 2024 | 2025 | Total (2023–2025) | Total after 2025 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HPMPs | 7,614,689 | 24,488,763 | 5,350,000 | 37,453,452 | 4,494,000 |
| HPMP preparation – stage III | 160,500 | 0 | 0 | 160,500 | 0 |
| HPMP stage III | 0 | 1,070,000 | 2,140,000 | 3,210,000 | 2,140,000 |
| HCFC activities subtotal | 7,775,189 | 25,558,763 | 7,490,000 | 40,823,952 | 6,634,000 |
| HFC activities |  |  |  |  |  |
| KIP preparation | 395,832 | 0 | 0 | 395,832 | 0 |
| KIPs | 3,210,000 | 0 | 0 | 3,210,000 | 21,400,000 |
| HFC activities subtotal | 3,605,832 | 0 | 0 | 3,605,832 | 21,400,000 |
| Standard activities |  |  |  |  |  |
| Core unit | 1,747,145 | 1,759,375 | 1,771,691 | 5,278,211 | 0 |
| IS | 676,584 | 0 | 676,584 | 1,353,168 | 0 |
| Standard activities subtotal | 2,423,729 | 1,759,375 | 2,448,275 | 6,631,379 | 0 |
| Total | 13,804,750 | 27,318,138 | 9,938,275 | 51,061,163 | 28,034,000 |

* Including agency support costs where applicable.

IV.	Performance indicators

# The World Bank submitted performance indicators pursuant to decision 71/28 in its business plan narrative. The Secretariat informed the World Bank of the targets shown in table 4.

Table 4. Performance indicators for the World Bank for 2023

| Type of indicator | Short title | Calculation | 2023 target |
| --- | --- | --- | --- |
| Planning-- Approval | Tranches approved | Number of tranches approved vs. those planned* | 4 |
| Planning-- Approval | Projects/activities approved | Number of projects/activities approved vs. those planned (including project preparation activities) | 6 |
| Implementation | Funds disbursed | Based on estimated disbursement in progress report | US $8,701,634 |
| Implementation | ODS phase-out | ODS phase-out for the tranche when the next tranche is approved vs. those planned per business plans* | 814.6 ODP tonnes |
| Implementation | Project completion for activities | Project completion vs. planned in progress reports for all activities (excluding project preparation) | 5 |
| Administrative | Speed of financial completion | The extent to which projects are financially completed 12 months after project completion | 90% |
| Administrative | Timely submission of project completion reports | Timely submission of project completion reports vs. those agreed | 4 |
| Administrative | Timely submission of progress reports | Timely submission of progress reports and business plans and responses unless otherwise agreed | On time |

* The target of an agency would be reduced if it could not submit a tranche owing to another lead or cooperating agency, if agreed by that agency.

V.	Recommendation

# The Executive Committee may wish:

## To note the World Bank business plan for 2023–2025, contained in document UNEP/OzL.Pro/ExCom/91/27; and

## To approve the performance indicators for the World Bank as set out in table 4 of document UNEP/OzL.Pro/ExCom/91/27.

UNEP/OzL.Pro/ExCom/91/1

A draft business plan for 2023–2025 of the World Bank was discussed at the Inter-agency coordination meeting (IACM) held in Montreal from 20 to 22 September 2022. The business plan contained in this document has addressed the issues raised at the meeting.

Funding for the preparation of national implementation plans to meet initial reduction obligations for the phase-down of HFCs could be provided, at the earliest, five years prior to those obligations, after a country had ratified the Kigali Amendment and on the basis of guidelines to be approved in the future (decision 79/46(b)(iii)). In addition, HFC phase-down preparation activities could be included in the business plan for countries that had not ratified the Kigali Amendment but had submitted a letter indicating their Government’s intent to make best efforts to ratify the Kigali Amendment (decision 84/46(f)). The guidelines for the preparation of KIPs were approved at the 87th meeting (decision 87/50).

The World Bank’s 2023 core unit costs will be considered at the 91st meeting (UNEP/OzL.Pro/ExCom/91/59).

UNEP/OzL.Pro/ExCom/91/22