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اللجنــة التنفيـذيــــة للصنــدوق المــتعــدد الأطـــراف
لتنفيـــذ بروتوكـول مونتريــال 
الاجتماع الثامن والتسعون
مونتريال، 22-26 يونيو/حزيران 2026
البند 4(ب) من جدول الأعمال المؤقت[footnoteRef:2] [2: UNEP/OzL.Pro/ExCom/98/1 ] 



تقرير عن الأرصدة وتوافر الموارد


مقدمة
1. [bookmark: _Hlk197628347]تعرض هذه الوثيقة موجزا للتعديلات المالية التي أشارت إليها الوكالات المنفذة والوكالات الثنائية على النحو الذي وافقت عليه الأمانة. وهي تتضمن بيانات إحصائية[footnoteRef:3] من جميع المشاريع التي احتفظت بأرصدتها لأكثر من 12 شهرا بعد إنجاز المشروع، على النحو المطلوب بموجب المقررين 28/7 و56/2(ج). وتتناول الوثيقة الأرصدة التي يتعين إعادتها مقابل المشاريع على سبيل المتابعة للمقررات ذات الصلة (المشار إليها باسم "مشاريع نُفّذت بموجب مقررات" في هذه الوثيقة). وهي تشير كذلك إلى مستوى الموارد النقدية المتاحة للجنة التنفيذية على النحو المسجل في وثيقة حالة المساهمات والمصروفات،[footnoteRef:4] على النحو المطلوب بموجب المقرر 41/92(ب)، وتقدم توصية في هذا الصدد. وترد المبالغ التي تحتفظ بها الوكالات المنفذة للمشاريع المنجَزة ومشاريع المساهمات الطوعية الإضافية في المرفقين الأول والثاني على التوالي. ويعرض المرفق الثالث الأموال التي أعادتها الوكالات المنفذة من المشاريع المنجَزة ومشاريع المساهمات الطوعية الإضافية والمشاريع المنفَّذة بموجب مقررات. [3:  تستند البيانات المعروضة إلى نموذج الإبلاغ الذي أُعِدَّ عملا بالمقرر 31/2.]  [4:  UNEP/OzL.Pro/ExCom/98/3 ] 

الأموال التي يتعين إعادتها إلى الاجتماع الثامن والتسعين
2. [bookmark: _Hlk197587959]يبلغ مجموع الأموال التي يتعين على الوكالات المنفذة إعادتها 1,417,152 دولارا أمريكيا من المشاريع المنجَزة ومشاريع المساهمات الطوعية الإضافية والمشاريع المنفَّذة بموجب مقررات، على النحو المبيَّن في الجدول 1.
الجدول 1. الأموال التي يتعين إعادتها من الوكالات المنفذة إلى الاجتماع الثامن والتسعين (بالدولار الأمريكي)
	الوكالة
	تكلفة المشروع
	تكلفة دعم الوكالة
	التكلفة الإجمالية

	اليوئنديبي
	105,125
	7,918
	113,043

	اليونيب
	594,160
	42,303
	636,463

	اليونيدو
	620,860
	46,786
	667,646

	المجموع
	1,320,145
	97,007
	1,417,152


الأموال التي تحتفظ بها الوكالات المنفذة 
3. يبلغ مجموع الأموال التي تحتفظ بها الوكالات المنفذة 5,125,184 دولارا أمريكيا، على النحو المبيَّن في الجدول 2.
الجدول 2. أرصدة المشاريع المنجَزة ومشاريع المساهمات الطوعية الإضافية التي تحتفظ بها الوكالات المنفذة (بما في ذلك تكاليف دعم الوكالة)
	سنة الإنجاز
	اليوئنديبي
	اليونيدو
	المجموع

	 
	العدد
	دولار أمريكي
	العدد
	دولار أمريكي
	العدد
	دولار أمريكي

	المشاريع التي مضى على إنجازها أكثر من سنتين

	2021
	0
	0
	1
	-367
	1
	-367

	[bookmark: RANGE!A6]2022
	2
	56,723
	5
	99,526
	7
	156,249

	2023
	7
	629,753
	5
	468,332
	12
	1,098,085

	من 1 يناير/كانون الثاني إلى 30 أبريل/نيسان 2024
	0
	0
	0
	0
	0
	0

	المجموع الفرعي
	9
	       686,476 
	11
	       567,491 
	20
	 1,253,967 

	المشاريع التي مضى على إنجازها أقل من سنتين

	من 1 مايو/أيار إلى 
31 ديسمبر/كانون الأول 2024
	21
	3,381,616
	12
	398,199
	33
	3,779,815

	المجموع الفرعي
	21
	    3,381,616 
	12
	     398,199 
	33
	 3,779,815 

	المجموع
	30
	     4,068,092 
	23
	     965,690 
	53
	 5,033,782 

	مشاريع المساهمات الطوعية الإضافية

	 
	0
	0
	1
	       91,402 
	1
	91,402

	المجموع الكلي
	30
	    4,068,092 
	24
	  1,057,092 
	54
	 5,125,184 




توافر الموارد
4. تمت الموافقة على ميزانية الصندوق المتعدد الأطراف بمبلغ 965 مليون دولار أمريكي لفترة الثلاث سنوات 2024-2026، على النحو الذي قررته الأطراف (المقرر 35/1). وتشير الوثيقة المتعلقة بحالة المساهمات والمصروفات إلى وجود رصيد متاح قدره 652,281,816 دولارا أمريكيا في 15 مايو/أيار 2026. ويبلغ إجمالي الرصيد الذي أعادته الوكالات المنفذة إلى الاجتماع الثامن والتسعين 1,417,152 دولارا أمريكيا .وبالتالي، فإن إجمالي مستوى الموارد المتاحة للموافقة عليها في الاجتماع الثامن والتسعين هو 653,698,968 دولارا أمريكيا.
تعليقات الأمانة
5. ذكّرت الأمانة الوكالات المنفذة بأنه ينبغي إعادة أرصدة المشاريع المنجَزة قبل عام واحد أو بعده، وكذلك المشاريع المنفذة بموجب مقررات ومشاريع المساهمات الطوعية الإضافية، إلى الصندوق المتعدد الأطراف في أقرب وقت ممكن.
6. وبالنظر إلى أن إجمالي مستوى التمويل للمشاريع والأنشطة بصيغته المقدَّمة إلى الاجتماع الثامن والتسعين يبلغ 155,293,564 دولارا أمريكيا،[footnoteRef:5] فإن هناك موارد كافية متاحة للموافقات في الاجتماع الثامن والتسعين. [5:  اعتبارا من 4 مايو/أيار 2026] 

التوصية
7. قد ترغب اللجنة التنفيذية فيما يلي:
(أ)	أن تحيط علما بما يلي: 
(1) التقرير المتعلق بالأرصدة وتوافر الموارد الوارد في الوثيقة UNEP/OzL.Pro/ExCom/98/4؛
(2) [bookmark: _Hlk197606110][bookmark: _Hlk197620565]أن صافي مستوى الأموال التي ستقوم الوكالات المنفذة بإعادتها في الاجتماع الثامن والتسعين يبلغ 1,417,152 دولارا أمريكيا، ويتألف من مبلغ 105,125 دولارا أمريكيا بالإضافة إلى تكاليف دعم الوكالة البالغة 7,918 دولارا أمريكيا من اليوئنديبي؛ و594,160 دولارا أمريكيا، بالإضافة إلى تكاليف دعم الوكالة البالغة 42,303 دولارا أمريكيا من اليونيب؛ و620,860 دولارا أمريكيا، بالإضافة إلى تكاليف دعم الوكالة البالغة 46,786 دولارا أمريكيا من اليونيدو؛
(3) أن اليوئنديبي احتفظ بأرصدة قدرها 686,476 دولارا أمريكيا، بما في ذلك تكاليف دعم الوكالة، لتسعة مشاريع أُنجزت على مدى عامين سابقين؛
(4) أن اليونيدو احتفظت بأرصدة قدرها 567,491 دولارا أمريكيا، بما في ذلك تكاليف دعم الوكالة، لأحد عشر مشروعا أُنجزت على مدى عامين سابقين؛ و91,402 دولارا أمريكيا، بما في ذلك تكاليف دعم مشروع واحد تم تمويله من المساهمات الطوعية الإضافية؛
[bookmark: _Hlk197620390](ب)	أن تطلب إلى اليوئنديبي واليونيدو ما يلي:
(1) المضي قدما في صرف أو إلغاء الأموال الملتزَم بها غير اللازمة للمشاريع المنجَزة، وإعادة الأرصدة المرتبطة بها في الاجتماع التاسع والتسعين؛
(2) المضي قدما في صرف أو إلغاء الالتزامات الخاصة بالمشاريع التي أُنجزت على مدى عامين سابقين، وإعادة الأرصدة في الاجتماع التاسع والتسعين؛
(ب)	أن تطلب إلى اليونيدو المضي قدما في أن تصرف أو تعيد، خلال الاجتماع التاسع والتسعين، أرصدة المشروع المموَّل من المساهمات الطوعية الإضافية؛
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إن وثائق ما قبل دورات اللجنة التنفيذية للصندوق المتعدد الأطراف لتنفيذ بروتوكول مونتريال 
قد تصدر دون إخلال بأي قرار تتخذه اللجنة التنفيذية بعد صدورها.
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Annex I
COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR COMPLETED PROJECTS

	Code
	Project Title
	Date Completed (Actual)
	Approved funding plus adjustments as of 
31 December 2024 
(US $)
	Funds disbursed as of
 98th meeting 
(US $)
	 Balances committed as per 98th meeting 
(US $)
	 Balances not-committed as per 98th meeting 
(US $)
	 Support cost on balances committed and not committed as per 
98th meeting (US $)
	Why any balances could not be returned?
	When they could be returned?
	Project subject to decision

	UNDP
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	BGD/PHA/90/INV/59
	HCFC phase-out management plan (stage II, second tranche) (air-conditioning sector)
	Dec-24
	1,967,866
	1,678,655
	289,211
	0
	20,245
	 
	 
	 

	BZE/PHA/87/INV/40
	HCFC phase-out management plan (stage II, first tranche)
	Dec-24
	73,854
	41,316
	32,538
	0
	2,928
	 
	 
	 

	COS/KIP/87/PRP/63
	Preparation of Kigali HFC implementation plan
	Dec-24
	170,000
	163,390
	6,610
	0
	463
	 
	 
	 

	CUB/KIP/87/PRP/65
	Preparation of Kigali HFC implementation plan
	Aug-24
	170,000
	154,279
	15,721
	0
	1,100
	 
	 
	 

	DOM/KIP/87/PRP/73
	Preparation of Kigali HFC implementation plan
	Aug-24
	190,000
	174,370
	15,630
	0
	1,094
	 
	 
	 

	EGY/PHA/79/TAS/132
	HCFC phase-out management plan (stage II, first tranche) (project management and monitoring)
	Dec-22
	75,000
	39,629
	35,371
	0
	2,476
	 
	 
	 

	EGY/PHA/84/INV/144
	HCFC phase-out management plan (stage II, second tranche) (extruded polystyrene foam sector)
	Dec-23
	1,761,750
	1,627,929
	133,821
	0
	9,368
	 
	 
	 

	ELS/PHA/87/INV/43
	HCFC phase-out management plan (stage II, first tranche)
	Dec-24
	169,000
	66,702
	102,298
	0
	7,161
	 
	 
	 

	GHA/KIP/87/PRP/51
	Preparation of Kigali HFC implementation plan
	Aug-23
	130,000
	126,468
	3,532
	0
	247
	 
	 
	 

	GRN/KIP/88/PRP/28
	Preparation of Kigali HFC implementation plan
	Dec-24
	40,000
	14,163
	25,837
	0
	1,809
	 
	 
	 

	HAI/SEV/90/INS/25
	Extension of the institutional strengthening project (phase V: 7/2022-6/2024)
	Dec-24
	128,000
	119,478
	8,522
	0
	597
	 
	 
	 

	IDS/PHA/81/INV/213
	HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector)
	Dec-24
	753,500
	158,983
	594,517
	0
	41,616
	 
	 
	 

	IDS/PHA/87/PRP/216
	Preparation of HCFC phase-out management plan (stage III) (Overarching)
	Dec-23
	90,000
	87,245
	2,755
	0
	193
	 
	 
	 

	IDS/PHA/88/INV/217
	HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector)
	Dec-24
	627,086
	0
	627,086
	0
	43,896
	 
	 
	 

	IDS/PHA/92/INV/220
	HCFC phase-out management plan (stage II, fourth tranche)
	Dec-24
	433,300
	0
	433,300
	0
	30,331
	 
	 
	 

	IND/PHA/86/TAS/482
	HCFC phase-out management plan (stage II, third tranche) (project management and monitoring)
	Dec-24
	800,000
	0
	800,000
	0
	56,000
	 
	 
	 

	IRA/PHA/86/INV/243
	HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration sector)
	Dec-24
	576,090
	551,597
	24,493
	0
	1,714
	 
	 
	 

	IRA/PHA/90/INV/262
	HCFC phase-out management plan (stage II, fourth tranche) (PMU)
	Dec-23
	92,000
	69,877
	22,123
	0
	1,549
	 
	 
	 

	IRA/PHA/92/INV/264
	HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector)
	Dec-23
	93,017
	0
	93,017
	0
	6,511
	 
	 
	 

	IRA/PHA/92/INV/265
	HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration sector)
	Dec-23
	145,255
	0
	145,255
	0
	10,168
	 
	 
	 

	MDV/KIP/87/PRP/36
	Preparation of Kigali HFC implementation plan
	Dec-24
	35,000
	22,026
	12,974
	0
	908
	 
	 
	 

	NIR/KIP/87/PRP/156
	Preparation of Kigali HFC implementation plan
	Dec-24
	137,000
	124,331
	12,669
	0
	887
	 
	 
	 

	NIR/PHA/81/TAS/150
	HCFC phase-out management plan (stage II, first tranche) (project management and coordination)
	Dec-22
	165,000
	147,359
	17,641
	0
	1,235
	 
	 
	 

	NIR/PHA/88/INV/163
	HCFC phase-out management plan (stage II, second tranche) (project management and coordination)
	Dec-24
	75,000
	41,581
	33,419
	0
	2,339
	 
	 
	 

	SRL/SEV/91/INS/61
	Extension of the institutional strengthening project (phase XIV: 1/2023-12/2024)
	Dec-24
	236,796
	234,222
	2,574
	0
	180
	 
	 
	 

	TRI/KIP/87/PRP/40
	Preparation of Kigali HFC implementation plan
	Dec-24
	190,000
	145,057
	44,943
	0
	3,146
	 
	 
	 

	TRI/PHA/86/INV/38
	HCFC phase-out management plan (stage II, first tranche)
	Dec-23
	498,756
	310,706
	188,050
	0
	13,164
	 
	 
	 

	URU/KIP/87/PRP/77
	Preparation of Kigali HFC implementation plan
	Dec-24
	190,000
	160,103
	29,897
	0
	2,093
	 
	 
	 

	URU/PHA/86/INV/76
	HCFC phase-out management plan (stage III, first tranche)
	Dec-24
	350,601
	313,973
	36,628
	0
	2,564
	 
	 
	 

	ZIM/KIP/91/PRP/66
	Preparation of a Kigali HFC implementation plan
	Dec-24
	51,000
	40,086
	10,914
	0
	764
	 
	 
	 

	Total UNDP
	 
	 
	10,414,871
	6,613,525
	3,801,346
	0
	266,746
	 
	 
	 

	UNIDO
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	BOL/PHA/87/INV/50
	HCFC phase-out management plan (stage II, first tranche)
	Aug-24
	141,009
	128,910
	12,099
	0
	847
	 
	 
	 

	BRA/PHA/82/INV/320
	HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration and air-conditioning sector)
	Dec-24
	2,647,057
	1,613,586
	289,368
	0
	20,256
	 
	 
	 

	CMR/KIP/88/PRP/49
	Preparation of Kigali HFC implementation plan
	Dec-23
	190,000
	188,394
	1,606
	0
	112
	 
	 
	 

	CPR/PHA/88/INV/607
	HCFC phase-out management plan (stage II, fourth tranche) (extruded polystyrene foam sector plan)
	Dec-23
	4,400,000
	4,405,665
	-5,665
	0
	-397
	 
	 
	 

	GAB/PHA/79/INV/34
	HCFC phase-out management plan (stage I, third tranche)
	Dec-22
	119,900
	60,409
	59,491
	0
	5,354
	 
	 
	 

	GAM/KIP/90/PRP/44
	Preparation of a Kigali HFC implementation plan
	Dec-24
	39,000
	36,622
	2,378
	0
	166
	 
	 
	 

	IVC/PHA/84/PRP/47
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-24
	20,000
	16,024
	3,976
	0
	278
	 
	 
	 

	JOR/PHA/84/TAS/107
	HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector, project management and coordination)
	Dec-23
	294,122
	90,153
	203,969
	0
	14,277
	 
	 
	 

	LIB/PHA/75/INV/36
	HCFC phase-out management plan (stage I, first tranche) (foam sector)
	Dec-23
	1,690,627
	713,112
	229,982
	0
	16,099
	 
	 
	 

	LIB/SEV/85/INS/44
	Renewal of the institutional strengthening project (phase VI: 7/2020-6/2022)
	Jun-23
	174,164
	166,361
	7,803
	0
	546
	 
	 
	 

	MEX/PHA/90/INV/200
	HCFC phase-out management plan (stage II, fourth tranche) (cleaning agent phase-out in refrigeration servicing sector and project implementation and monitoring)
	Dec-24
	1,612,350
	1,612,260
	90
	0
	6
	 
	 
	 

	MEX/PHA/92/INV/206
	HCFC phase-out management plan (stage II, fifth tranche)
	Dec-24
	450,600
	448,181
	2,419
	0
	169
	 
	 
	 

	MOZ/PHA/66/INV/23
	HCFC phase-out management plan (stage I, first tranche)
	Dec-22
	75,000
	72,133
	2,867
	0
	258
	 
	 
	 

	NER/PHA/84/INV/39
	HCFC phase-out management plan (stage I, second tranche)
	Dec-22
	90,000
	76,492
	13,508
	0
	946
	 
	 
	 

	NER/PHA/88/INV/41
	HCFC phase-out management plan (stage I, third tranche)
	Dec-22
	20,000
	19,002
	998
	0
	70
	 
	 
	 

	SAU/REF/86/PRP/35
	Preparation of a HCFC phase-out management plan (stage II) (air-conditioning)
	Dec-24
	150,000
	141,442
	8,558
	0
	599
	 
	 
	 

	SEN/PHA/85/INV/41
	HCFC phase-out management plan (stage I, third tranche)
	Dec-21
	50,000
	50,341
	-341
	0
	-26
	 
	 
	 

	SEN/PHA/85/PRP/43
	Preparation of a HCFC phase-out management plan (stage II)
	Jun-22
	20,000
	5,015
	14,985
	0
	1,049
	 
	 
	 

	SIL/KIP/88/PRP/43
	Preparation of Kigali HFC implementation plan
	Dec-24
	39,000
	39,014
	-14
	0
	-1
	 
	 
	 

	SIL/PHA/87/INV/40
	HCFC phase-out management plan (stage II, first tranche)
	Dec-24
	117,000
	92,734
	24,266
	0
	2,184
	 
	 
	 

	SOM/PHA/88/PRP/17
	Preparation of HCFC phase-out management plan (stage II) (Overarching)
	Dec-24
	60,000
	57,244
	2,756
	0
	193
	 
	 
	 

	TUR/KIP/90/PRP/113
	Preparation of a Kigali HFC implementation plan
	Dec-24
	120,000
	108,720
	11,280
	0
	790
	 
	 
	 

	VEN/PHA/91/INV/137
	HCFC phase-out management plan (stage II, second tranche) (servicing sector)
	Dec-24
	261,444
	246,924
	14,520
	0
	1,016
	 
	 
	 

	Total UNIDO 
	 
	 
	12,781,273
	10,388,738
	900,899
	0
	64,791
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Annex II
COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS
	CODE
	Project title
	Approved funding plus adjustments as of 
31 December 2025 (US $) 
	Funds disbursed as of 
98th meeting (US $)
	Balances committed as per 
98th meeting (US $)
	Balances not- committed as per 
98th meeting (US $)
	Support cost on balances committed and not-committed as per 
98th meeting
(US $) 
	Why any balances could not be returned?
	When they could be returned?

	UNIDO

	ARG/SEV/81/TAS/02+ 
	Enabling activities for HFC phase-down
	250,000

	164,578

	85,422
	
	5,980
	
	

	TOTAL UNIDO
	
	
	
	85,422
	
	5,980
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Annex III
DETAILS ON COMPLETED, ADDITIONAL VOLUNTARY CONTRIBUTIONS AND BY‑DECISIONS PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES

	Code
	Project title
	Project costs returned 
(US $)
	Agency support costs returned 
(US $)
	Total
(US $) 

	UNDP
	 
	 
	 
	 

	COL/KIP/87/PRP/110
	Preparation of Kigali HFC implementation plan
	75
	5
	80

	COL/PHA/88/INV/111
	HCFC phase-out management plan (stage II, fourth tranche)
	2,712
	190
	2,902

	COL/SEV/88/INS/115
	Extension of institutional strengthening project (phase XIII: 12/2021-11/2023)
	802
	56
	858

	COS/PHA/91/TAS/66
	Verification report on the implementation of stage II of the HCFC phase-out management plan
	3,841
	346
	4,187

	GHA/SEV/91/INS/54
	Extension of the institutional strengthening project (phase XV: 1/2023-12/2024)
	4
	0
	4

	HAI/PHA/91/PRP/26
	Preparation of HCFC phase-out management plan (stage II) (Overarching)
	7,233
	506
	7,739

	IDS/SEV/90/INS/219
	Extension of institutional strengthening project (phase XIII: 7/2022-6/2024)
	2
	0
	2

	IND/KIP/92/PRP/505
	Preparation of a KIP investment project in the refrigeration manufacturing sector for Mech Air Industries
	28,499
	1,995
	30,494

	KAM/KIP/88/PRP/40
	Preparation of Kigali HFC implementation plan
	10,027
	702
	10,729

	LAO/KIP/87/PRP/39
	Preparation of Kigali HFC implementation plan
	297
	21
	318

	LAO/PHA/86/INV/38
	HCFC phase-out management plan (stage II, first tranche)
	254
	23
	277

	LEB/KIP/87/PRP/98
	Preparation of Kigali HFC implementation plan
	3,886
	272
	4,158

	LEB/SEV/86/INS/96
	Extension of the institutional strengthening project (phase XII: 4/2021-3/2023)
	2,233
	156
	2,389

	MAL/PHA/87/PRP/189
	Preparation of HCFC phase-out management plan (stage III) (Overarching)
	3,946
	276
	4,222

	MEX/FOA/90/PRP/198
	Preparation for HFC investment projects in the foam sector
	3,935
	275
	4,210

	MEX/KIP/87/PRP/195
	Preparation of Kigali HFC implementation plan
	3,883
	272
	4,155

	MEX/REF/92/INV/204
	Conversion of the manufacturing of commercial refrigerators from HFC-134a to propane (R-290) at the enterprise Friocima
	23,922
	2,153
	26,075

	PAK/SEV/87/INS/108
	Extension of the institutional strengthening project (phase XI: 7/2021-6/2023)
	1,257
	88
	1,345

	PAN/KIP/87/PRP/53
	Preparation of Kigali HFC implementation plan
	82
	6
	88

	PAR/KIP/87/PRP/42
	Preparation of Kigali HFC implementation plan
	-65
	-5
	-70

	SRL/KIP/87/PRP/59
	Preparation of Kigali HFC implementation plan
	-154
	-11
	-165

	SWA/KIP/87/PRP/33
	Preparation of Kigali HFC implementation plan
	284
	20
	304

	Total completed projects
	96,955
	7,346
	104,301

	FIJ/SEV/80/TAS/01+
	Enabling activities for HFC phase-down
	8,170
	572
	8,742

	Total “additional voluntary contributions” projects
	8,170
	572
	8,742

	Total UNDP 
	 
	105,125
	7,918
	113,043

	UNEP
	 
	 
	 
	 

	CKI/SEV/88/INS/18
	Extension of the institutional strengthening project (phase VIII: 7/2022-6/2024)
	5,000
	0
	5,000

	ELS/PHA/87/TAS/42
	HCFC phase-out management plan (stage II, first tranche)
	1,419
	184
	1,603

	GLO/SEV/93/TAS/368
	Compliance Assistance Programme: 2024 budget
	468,485
	37,479
	505,964

	GUA/SEV/88/INS/60
	Renewal of the institutional strengthening project (phase IX: 12/2021-11-2023)
	13,315
	0
	13,315

	IND/PHA/86/TAS/483
	HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector plan)
	7,246
	878
	8,124

	KYR/SEV/91/INS/48
	Extension of the institutional strengthening project (phase XI: 1/2023-12/2024)
	4,602
	0
	4,602

	NIC/PHA/92/TAS/47
	HCFC phase-out management plan (stage II, second tranche)
	26,312
	3,421
	29,733

	NIC/SEV/92/INS/51
	Renewal of institutional strengthening project (phase XI: 7/2023-6/2026)
	65,161
	0
	65,161

	PAK/PHA/88/TAS/109
	HCFC phase-out management plan (stage II, third tranche)
	2,539
	330
	2,869

	SEN/KIP/87/PRP/44
	Preparation of Kigali HFC implementation plan
	81
	11
	92

	Total completed projects
	594,160
	42,303
	636,463

	Total UNEP 
	 
	594,160
	42,303
	636,463

	UNIDO
	 
	 
	 
	 

	BAH/PHA/93/INV/46
	HCFC phase-out management plan (stage II, second tranche)
	108
	8
	116

	BRA/PHA/75/INV/311
	HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration and air-conditioning sector)
	1,699
	119
	1,818

	BRA/PHA/88/INV/327
	HCFC phase-out management plan (stage II, fifth tranche) (commercial refrigeration and air-conditioning sector)
	23,994
	1,680
	25,674

	CPR/PHA/75/INV/564
	HCFC phase-out management plan (stage I, fifth tranche) (room air-conditioner manufacturing sector plan) 
	-5,665
	-5,385
	-11,050

	GUA/KIP/94/PRP/69
	Preparation of a Kigali HFC implementation plan (stage I)
	216
	15
	231

	HON/KIP/90/PRP/55
	Preparation of a Kigali HFC implementation plan
	34
	2
	36

	JOR/PHA/92/PRP/115
	Preparation of HCFC phase-out management plan (stage III) (Overarching)
	15
	1
	16

	MEX/PHA/92/INV/205
	Destruction of emissions of HFC-23 generated in the production of HCFC-22 in Quimobasicos (second tranche)
	32
	2
	34

	MOR/KIP/92/PRP/79
	Preparation of a KIP investment project in the refrigeration manufacturing sector for MANAR
	471
	33
	504

	NIC/PHA/86/INV/40
	HCFC phase-out management plan (stage II, first tranche)
	1,505
	105
	1,610

	PAK/PHA/76/INV/94
	HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector)
	16,483
	1,154
	17,637

	PAK/PHA/83/INV/102
	HCFC phase-out management plan (stage II, second tranche) (polyurethane foam sector)
	43,813
	3,067
	46,880

	PAK/PHA/83/TAS/100
	HCFC phase-out management plan (stage II, second tranche) (project management unit)
	34,237
	2,397
	36,634

	PAK/PHA/90/INV/110
	HCFC phase-out management plan (stage II, fourth tranche) (domestic air-conditioner manufacturing sector)
	1,882
	131
	2,013

	PHI/PHA/83/INV/104
	HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector)
	188,014
	13,160
	201,174

	PHI/PHA/83/TAS/105
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector)
	38,932
	2,726
	41,658

	PRC/KIP/91/PRP/38
	Preparation of a Kigali HFC implementation plan
	1,196
	84
	1,280

	RWA/KIP/88/PRP/38
	Preparation of Kigali HFC implementation plan
	6,238
	440
	6,678

	SOA/PHA/91/INV/16
	HCFC phase-out management plan (stage I, fifth tranche) (refrigeration servicing, custom training and monitoring)
	21,481
	1,503
	22,984

	Total completed projects
	374,685
	21,242
	395,927

	IRQ/PHA/74/INV/23
	HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector)
	8,064
	605
	8,669

	NIC/EEF/92/TAS/49
	HCFC phase-out management plan (stage II, second tranche) (energy efficiency - related activities under decision 89/6)
	23,618
	1,653
	25,271

	NIC/KIP/93/INV/57
	Kigali HFC implementation plan (stage I, first tranche)
	137,870
	17,923
	155,793

	NIC/PHA/92/INV/48
	HCFC phase-out management plan (stage II, second tranche)
	56,623
	3,963
	60,586

	PAK/PHA/90/INV/111
	HCFC phase-out management plan (stage III, first tranche) (foam sector)
	20,000
	1,400
	21,400

	Total "by-decision" projects
	246,175
	25,544
	271,719

	Total UNIDO  
	620,860
	46,786
	667,646
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