| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/93/29 11 November 2023 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-third Meeting

Montreal, 15-19 December 2023

Item 8(d)(iv) of the provisional agenda

UNIDO BUSINESS PLAN FOR 2024–2026

# Introduction

# This document presents UNIDO business plan for 2024–2026 and includes the planned activities for the reduction of controlled substances under the Montreal Protocol during the period 2024–2026. The narrative of UNIDO’s business plan for 2024–2026 is attached to the present document.

# This document consists of the following sections:

- Planned activities during the period 2024–2026

- Secretariat’s comments

- Proposed adjustments by the Secretariat

- Performance indicators

- Recommendation

I.	Planned activities during the period 2024–2026

# Table 1 sets out, by year, the value of activities included in UNIDO’s business plan.

Table 1. Resource allocation in the UNIDO business plan for 2024–2026 (US $)* – as submitted

| Description | 2024 | 2025 | 2026 | Total (2024–2026) | Total after 2026 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 13,127,189 | 20,614,411 | 14,595,331 | 48,336,931 | 26,746,533 |
| HPMP project preparation (PRP) – stage II | 32,100 | 16,050 | 0 | 48,150 | 0 |
| HPMP stage II | 3,165,108 | 6,108,855 | 6,375,852 | 15,649,815 | 50,870,043 |
| HPMP PRP – stage III | 347,750 | 42,800 | 0 | 390,550 | 0 |
| HPMP stage III | 3,736,863 | 5,851,810 | 3,568,569 | 13,157,243 | 32,437,102 |
| HPMP – energy efficiency | 1,076,420 | 417,300 | 32,100 | 1,525,820 | 0 |
| HCFC activities subtotal | 21,485,431 | 33,051,226 | 24,571,852 | 79,108,509 | 110,053,677 |
| HFC activities |  |  |  |  |  |
| Approved Kigali HFC implementation plans (KIPs) | 0 | 0 | 434,420 | 434,420 | 481,500 |
| Approved HFC-23 emission control | 414,238 | 626,900 | 572,433 | 1,613,571 | 2,123,880 |
| KIP stage I – PRP | 1,001,220 | 527,953 | 60,990 | 1,590,163 | 0 |
| KIP stage I | 2,687,077 | 8,872,260 | 8,738,855 | 20,298,192 | 25,639,684 |
| KIP stage I – investment PRP | 32,100 | 0 | 0 | 32,100 |  |
| KIP stage I – investment | 749,000 | 0 | 0 | 749,000 | 0 |
| HFC activities subtotal | 4,883,635 | 10,027,113 | 9,806,698 | 24,717,446 | 28,245,064 |
| Other activities |  |  |  |  |  |
| Pilot project for energy efficiency – investment | 1,562,200 | 0 | 0 | 1,562,200 | 0 |
| National inventories of banks of waste-controlled substances – PRP | 454,750 | 0 | 0 | 454,750 | 0 |
| Technical assistance – gender mainstreaming | 2,501,660 | 0 | 0 | 2,501,660 | 0 |
| Other activities subtotal | 4,518,610 | 0 | 0 | 4,518,610 | 0 |
| Standard activities |  |  |  |  |  |
| Institutional strengthening (IS) | 2,746,395 | 1,650,362 | 2,523,806 | 6,920,563 | 0 |
| Core unit | 2,079,213 | 2,093,768 | 2,108,424 | 6,281,405 | 0 |
| Standard activities subtotal | 4,825,608 | 3,744,129 | 4,632,231 | 13,201,968 | 0 |
| Total | 35,713,284 | 46,822,468 | 39,010,780 | 121,546,532 | 138,298,741 |

* Including agency support costs where applicable.

# II.	Secretariat’s comments

II.1	HCFC activities

# Stage II of HPMPs

# The total level of funding for stage II of HPMPs for nine low-volume-consuming (LVC) countries to meet the 100 per cent reduction of the HCFC baseline amounts to US $1.84 million (including US $756,495 for 2024–2026 and US $1.08 million for the period after 2026).

# The total level of funding for stage II of HPMPs for seven non-LVC countries amounts to US $64.68 million (including US $14.89 million for 2024–2026 and US $49.79 million for the period after 2026).

# A total of US $48,150 is included in the business plan for the preparation of stage II of the HPMPs for three countries for 2024–2026.

# Stage III of HPMPs

# A total of US $45.59 million is planned for stage III of HPMPs for 17 countries (including US $13.16 million for 2024-2026 and US $32.44 million for the period after 2026).

# A total of US $390,550 is included in the business plan for the preparation of stage III of the HPMPs for ten countries for 2024–2026.

# Energy efficiency for LVC countries

# Decision 89/6 allowed bilateral and implementing agencies, when submitting existing and future stages of HPMPs for LVC countries, to include the funding associated with the need for the introduction of alternatives to HCFCs with low- or zero-global-warming potential (GWP) and for maintaining energy efficiency in the refrigeration servicing sector.

# A total of US $1.53 million is included in the business plan for energy efficiency activities for 29 LVC countries for 2024–2026.

II.2	HFC-related activities

# KIP project preparation

# A total of US $1.59 million is included in the business plan for the preparation of stage I of the KIPs for 16 countries in 2024–2026. In addition, UNIDO also included one preparation activity for one KIP investment project for one country amounting to US $32,100 in 2024.

# Fifteen of the 16 countries for which KIP project preparation activities have been included have not yet ratified the Kigali Amendment but have submitted the required letter from their respective Government indicating their intent to make best efforts to ratify the Kigali Amendment in line with decision 84/46(f).

# Stage I of KIPs

# A total of US $45.94 million is included in the business plan for stage I of the KIPs for 50 countries (including US $20.3 million for 2024–2026 and US $25.64 million for the period after 2026). In addition, UNIDO also included KIP investment projects for two countries (Lebanon and Morocco) amounting to US $749,000 in 2024. All these countries have ratified the Kigali Amendment.

II.3	Other activities

Pilot projects for energy efficiency (decision 91/65)

# A total of US $1.56 million is included in the business plan under the funding window for pilot projects for energy efficiency (decision 91/65) in 2024 for four countries (Armenia, the Gambia, Jordan, and Mauritania).

Project preparation for national inventories of banks of waste-controlled substances (decision 91/66)

# A total of US $454,750 is included in the business plan for the preparation of national inventories of banks of waste-controlled substances (decision 91/66) in 2024 for five countries (Bosnia and Herzegovina, Jordan, Libya, Mauritania, and South Africa).

Gender mainstreaming technical assistance project

# UNIDO’s business plan included one global technical assistance project, “Increasing gender equality and economic empowerment of women in the refrigeration and air-conditioning (RAC) sectors (WEERAC)”, amounting to US $2.5 million in 2024. The objective of this proposal is to systematise and improve the delivery of actions targeted to gender mainstreaming in the UNIDO portfolio, by analysing the gaps in knowledge and addressing the needs of national ozone units (NOUs), energy and environment counterparts and RAC sector beneficiaries. At present, there is no funding window for such technical assistance projects. Further, implementation of the operational gender mainstreaming policy and its associated relevant decisions should be included in each Article 5 country’s national plans to phase out controlled substances. The issue is presented in the Consolidated business plan of the Multilateral Fund for 2024–2026.

# II.4	Core unit costs

# The core unit costs are expected to increase at an annual rate of 0.7 per cent as agreed.

III.	Proposed adjustments by the Secretariat

# The adjustments to the UNIDO business plan for 2024–2026 were based on relevant decisions of the Executive Committee. In reviewing the revised UNIDO business plan for 2024–2026, the Secretariat noted that the following adjustments were not included:

Table 2. Adjustments to the UNIDO business plan for 2024–2026 (US $)* – as proposed by the Secretariat

| Adjustment | 2024–2026 | After 2026 |
| --- | --- | --- |
| HPMP values to reflect the actual amounts approved under the Agreements including tranches of HPMPs that have been submitted to the 93rd meeting | (1,121,199) | (18,511,470) |
| PRP for stage II of HPMPs pursuant to decision 71/42 | (10,700) | 0 |
| Stage II of HPMPs in non-LVC countries with the refrigeration manufacturing sector based on a maximum cost-effectiveness of US $8.40/kg | (357,683) | (2,692,047) |
| HPMP values to reflect draft Agreements submitted to the 93rd meeting | (623,686) | (356,373) |
| Energy efficiency for LVC countries that have been submitted to the 93rd meeting | (250,380) | 0 |
| KIP stage I values to reflect the draft Agreements submitted to the 93rd meeting | 36,628 | (39,240) |
| KIP stage I servicing sector pursuant to decision 92/37 | (1,297,697) | (3,027,960) |
| Technical assistance (global project on gender mainstreaming) | (2,501,660) | 0 |

* Including agency support costs where applicable.

# Table 3 presents the results of the Secretariat’s proposed adjustments to the UNIDO business plan for 2024–2026, which are also addressed in the context of the consolidated business plan of the Multilateral Fund for 2024–2026.

# Table 3. Resource allocation in UNIDO’s adjusted business plan for 2024–2026 (US $)*

| Description | 2024 | 2025 | 2026 | Total (2024–2026) | Total after 2026 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HPMPs | 12,691,432 | 19,928,969 | 14,595,331 | 47,215,732 | 8,235,063 |
| HPMP PRP – stage II | 21,400 | 16,050 | 0 | 37,450 | 0 |
| HPMP stage II | 3,165,108 | 5,751,172 | 6,375,852 | 15,292,132 | 48,177,996 |
| HPMP PRP – stage III | 347,750 | 42,800 | 0 | 390,550 | 0 |
| HPMP stage III | 3,736,863 | 5,851,810 | 2,944,883 | 12,533,557 | 32,080,728 |
| HPMP – energy efficiency | 858,140 | 385,200 | 32,100 | 1,275,440 | 0 |
| HCFC activities subtotal | 20,820,694 | 31,976,001 | 23,948,166 | 76,744,861 | 88,493,788 |
| HFC activities |  |  |  |  |  |
| Approved KIPs | 0 | 0 | 434,420 | 434,420 | 481,500 |
| Approved HFC-23 emission control | 414,238 | 626,900 | 572,433 | 1,613,571 | 2,123,880 |
| KIP stage I – PRP | 1,001,220 | 527,953 | 60,990 | 1,590,163 | 0 |
| KIP stage I | 2,684,533 | 7,577,107 | 8,775,483 | 19,037,123 | 22,572,484 |
| KIP stage I – investment PRP | 32,100 | 0 | 0 | 32,100 | 0 |
| KIP stage I - investment | 749,000 | 0 | 0 | 749,000 | 0 |
| HFC activities subtotal | 4,881,091 | 8,731,960 | 9,843,326 | 23,456,377 | 25,177,864 |
| Other activities |  |  |  |  |  |
| Pilot project for energy efficiency – investment | 1,562,200 | 0 | 0 | 1,562,200 | 0 |
| National inventories of banks of waste-controlled substances – PRP | 454,750 | 0 | 0 | 454,750 | 0 |
| Technical assistance – gender mainstreaming | 0 | 0 | 0 | 0 | 0 |
| Other activities subtotal | 2,016,950 | 0 | 0 | 2,016,950 | 0 |
| Standard activities |  |  |  |  |  |
| IS | 2,746,395 | 1,650,362 | 2,523,806 | 6,920,563 | 0 |
| Core unit | 2,079,213 | 2,093,768 | 2,108,424 | 6,281,405 | 0 |
| Standard activities subtotal | 4,825,608 | 3,744,129 | 4,632,231 | 13,201,968 | 0 |
| Total | 32,544,343 | 44,452,091 | 38,423,722 | 115,420,155 | 113,671,652 |

*Including agency support costs where applicable.

IV.	Performance indicators

# UNIDO submitted performance indicators pursuant to decision 71/28 in its business plan narrative. The Secretariat informed UNIDO of the targets shown in table 4.

Table 4. Performance indicators for UNIDO for 2024

| Type of indicator | Short title | Calculation | 2024 target |
| --- | --- | --- | --- |
| Planning-Approval | Tranches approved | Number of tranches approved vs. those planned* | 62 |
| Planning-Approval | Projects/activities approved | Number of projects/activities approved vs. those planned (including project preparation activities) | 56 |
| Implementation | Funds disbursed | Based on estimated disbursement in progress report | US $27,456,835 |
| Implementation | ODS phase-out | ODS phase-out for the tranche when the next tranche is approved vs. those planned per business plans* | 258.1 ODP tonnes |
| Implementation | Project completion for activities | Project completion vs. planned in progress reports for all activities (excluding project preparation) | 69 |
| Administrative | Speed of financial completion | The extent to which projects are financially completed 12 months after project completion | 12 months after operational completion |
| Administrative | Timely submission of project completion reports | Timely submission of project completion reports vs. those agreed | On time (4) |
| Administrative | Timely submission of progress reports | Timely submission of progress reports and business plans and responses unless otherwise agreed | On time |

- * The targets of an agency would be reduced “if it could not submit a tranche owing to another cooperating agency or lead agency” or “if the HPMP submitted for consideration by the Executive Committee was not approved as a result of factors beyond the control of the NOU and the agency”.

V.	Recommendation

# The Executive Committee may wish:

## To note the UNIDO business plan for 2024–2026, contained in document UNEP/OzL.Pro/ExCom/93/29; and

## To approve the performance indicators for UNIDO as set out in table 4 of document UNEP/OzL.Pro/ExCom/93/29.

UNEP/OzL.Pro/ExCom/93/1

A draft business plan for 2024–2026 of UNIDO was discussed at the Inter-agency coordination meeting (IACM) held in Montreal from 3 to 5 October 2023. The business plan contained in this document has addressed the issues raised at the meeting.

UNEP/OzL.Pro/ExCom/93/25

UNIDO’s 2024 core unit costs will be considered at the 93rd meeting (UNEP/OzL.Pro/ExCom/93/95).

As agreed at the Inter-agency coordination meeting.

UNEP/OzL.Pro/ExCom/93/25