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اللجنــة التنفيـذيــــة للصنــدوق المــتعــدد الأطـــراف
لتنفيـــذ بروتوكـول مونتريــال 
الاجتمــــــاع الخامس والتسعــــون 
[bookmark: _Hlk128756171]مونتريال، 4 - 8 ديسمبر/كانون الأول 2023
البندان 9 (ج) و(د) من جدول الأعمال المؤقت[footnoteRef:2] [2:  الوثيقة UNEP/ OzL.Pro /ExCom/95/1] 


 
تعديلات برنامج عمل برنامج الأمم المتحدة الإنمائي لعام 2024



تعليقات وتوصيات أمانة الصندوق
1. يطلب برنامج الأمم المتحدة الإنمائي (اليوئنديبي) موافقة من اللجنة التنفيذية على مبلغ قدره 2,622,345 دولارا أمريكيا، بالإضافة إلى تكاليف دعم الوكالة وقدرها 183,564 دولارا أمريكيا لتعديلات برنامج عمله لعام 2024 المدرجة في الجدول 1. ومرفق الطلب بهذه الوثيقة.
الجدول 1: تعديلات برنامج عمل برنامج الأمم المتحدة الإنمائي (اليوئنديبي) لعام 2024
	البلد
	النشاط/ المشروع
	المبلغ المطلوب (بالدولار الأمريكي)
	المبلغ الموصي به (بالدولار الأمريكي)

	القسم ألف: الأنشطة الموصي لها بالموافقة الشمولية

	ألف1: تجديد مشروعات التعزيز المؤسسي

	غانا
	تجديد مشروع التعزيز المؤسسي (المرحلة السادسة عشرة)
	368,559
	368,559

	هايتي
	تجديد مشروع التعزيز المؤسسي (المرحلة السادسة)
	264,960
	264,960

	إيران (الجمهورية الإسلامية)
	تجديد مشروع التعزيز المؤسسي (المرحلة الخامسة عشرة)
	459,735
	459,735

	نيجيريا
	تجديد مشروع التعزيز المؤسسي (المرحلة الثالثة عشرة)
	688,896
	688,896

	سريلانكا
	تجديد مشروع التعزيز المؤسسي (المرحلة الخامسة عشرة)
	355,195
	355,195

	المجموع الفرعي لألف 1 
	2,137,345
	2,137,345

	تكاليف دعم الوكالة
	149,614
	149,614

	المجموع لألف 1
	2,286,959
	2,286,959

	ألف 2: إعداد المشروعات لخطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية

	أنغولا
	إعداد خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثالثة)
	40,000
	40,000

	بنغلاديش أ
	إعداد خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثالثة)
	45,000
	45,000

	نيجيريا ب
	إعداد خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الرابعة)
	50,000
	50,000

	المجموع الفرعي لألف 2
	135,000
	135,000

	تكاليف دعم الوكالة
	9,450
	9,450

	المجموع لألف 2
	144,450
	144,450

	ألف 3: إعداد قوائم الجرد الوطنية لبنك المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها وخطط لجمع ونقل والتخلص من هذه المواد[footnoteRef:3] [3:  يشار إليه هنا بإعداد قائمة جرد وطنية لبنوك المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها ووضع الخطة.
] 


	أندونيسيا
	إعداد قائمة جرد وطنية لبنوك المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها وخطة
	100,000
	100,000

	المجموع الفرعي لألف 4
	100,000
	100,000

	تكاليف دعم الوكالة
	7,000
	7,000

	المجموع لألف 4
	107,000
	107,000

	القسم باء: الأنشطة الموصي لها بالنظر فيها بصفة فردية

	باء 1: إعداد المشروعات لخطة تنفيذ تعديل كيغالي للمواد الهيدروفلوروكربونية

	الصين
	إعداد مشروع توضيحي في تصنيع الضواغط لقطاع صناعات تكييف الهواء المتنقل 
	250,000
	*

	المجموع الفرعي لباء 1
	30.000
	*

	تكاليف دعم الوكالة لباء 1
	2,100
	*

	المجموع لباء 1
	32,100
	*

	الإجمالي لألف 1 وألف 2 وألف 3 وباء 1 
	2,622,345
	2,372,345

	تكاليف دعم الوكالة لألف 1 وألف 2 وألف 3 وباء 1 
	183,564
	166,064

	المجموع الكلي
	2,805,909
	2,508,409


أ اليونيب بصفته الوكالة المنفذة المتعاونة
ب حكومة ألمانيا بصفتها وكالة ثنائية متعاونة
* وكالة ثنائية
* موصى بالنظر فيها بصفة فردية
القسم ألف: الأنشطة الموصي لها بالموافقة الشمولية
ألف1: تجديد مشروعات التعزيز المؤسسي
وصف المشروع
قدم برنامج الأمم المتحدة الإنمائي طلبات لتجديد مشروعات التعزيز المؤسسي للبلدان المذكورة في القسم ألف 1 من الجدول 1. ويرد وصف هذه المشروعات في المرفق الأول بهذه الوثيقة.
تعليقات الأمانة
استعرضت الأمانة طلبات تجديد مشروعات التعزيز المؤسسي الخمسة نيابة عن الحكومات المعنية في ضوء المبادئ التوجيهية[footnoteRef:4] والقرارات ذات الصلة فيما يتعلق بالأهلية ومستويات التمويل. وتم فحص الطلبات في ضوء خطط العمل الأصلية للمرحلة السابقة، وبيانات البرنامج القطري والمادة 7، وأحدث تقرير عن تنفيذ خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية، والتقرير المرحلي للوكالة، وأي مقررات ذات صلة صادرة عن اجتماعات الأطراف. ولوحظ أن جميع البلدان الخمسة قد قدمت بيانات برامجها القطرية لعام 2023 وبيانات المادة 7، وتمتثل لأهداف الرقابة بموجب بروتوكول مونتريال وأن الاستهلاك السنوي المبلغ عنه للمواد الهيدروكلوروفلوروكربونية لا يتجاوز الحد الأقصى السنوي للاستهلاك المسموح به المذكور في اتفاقاتها لخطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية المبرمة مع اللجنة التنفيذية. علاوة على ذلك، تضمنت جميع الطلبات المقدمة تقييماً لمؤشرات الأداء ومخاطر المشروع والاستدامة وتحقيق أهداف التعزيز المؤسسي، وفقاً للمقرر 91/63 (ب). [4:  المقرر 91/63: (ب) أن توافق على النموذج المنقح للتقارير النهائية وطلبات لتمديد تمويل التعزيز المؤسسي ومؤشرات الأداء المقابلة؛ و(ج) مطالبة بلدان المادة 5، من خلال الوكالات الثنائية والوكالات المنفذة، باستخدام النموذج المنقح المذكور في الفقرة الفرعية (ب) أعلاه لجميع طلبات تجديد التعزيز المؤسسي اعتبارًا من أول اجتماع للجنة التنفيذية في عام 2023.] 

توصية الأمانة
توصي الأمانة بالموافقة الشمولية على طلبات تجديد التعزيز المؤسسي لغانا وهايتي وجمهورية إيران الإسلامية ونيجيريا وسري لانكا عند مستويات التمويل المبينة في القسم ألف 1 من الجدول 1 من هذه الوثيقة. وقد ترغب اللجنة التنفيذية في أن تعرب للحكومات المذكورة أعلاه عن التعليقات الواردة في المرفق الثاني بهذه الوثيقة.
ألف 2: إعداد المشروعات لخطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية
وصف المشروع
قدم برنامج الأمم المتحدة الإنمائي (اليوئنديبي) طلبات لإعداد المرحلة الثالثة من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لبلدين من بلدان المادة 5، لبلد واحد بصفته الوكالة المنفذة المعينة، وللبلد الآخر، بصفته الوكالة الرئيسية مع برنامج الأمم المتحدة للبيئة بصفته الوكالة المتعاونة؛ وطلب واحد لإعداد المرحلة الرابعة من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية مع حكومة ألمانيا بصفتها الوكالة المتعاونة، على النحو المبين في القسم ألف 2 من الجدول 1.
وأدرج اليونيب، بصفته الوكالة المتعاونة مع بنغلاديش، طلبا للحصول على 15,000 دولار أمريكي، بالإضافة إلى تكاليف دعم الوكالة البالغة 1,950 دولار أمريكي في تعديلات برنامج عمله[footnoteRef:5] لعام 2024، في حين قدمت حكومة ألمانيا، بصفتها وكالة ثنائية متعاونة مع نيجيريا، طلبا للحصول على 20,000 دولار أمريكي، بالإضافة إلى تكاليف دعم الوكالة البالغة 2,600 دولار أمريكي في إطار التعاون الثنائي.[footnoteRef:6] [5:  الوثيقة UNEP/OzL.Pro/ExCom/95/36.]  [6: الوثيقة UNEP/OzL.Pro/ExCom/95/32.] 

وقدمت الوكالة المعينة/المنفذة الرئيسية وصفا للأنشطة لدعم طلب إعداد المشروع للمرحلة الثالثة من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية في أنغولا وبنغلاديش وللمرحلة الرابعة من الخطة في نيجيريا، الذي شمل: مبرر للتمويل المطلوب لإعداد المشروع؛ وتقرير مرحلي عن تنفيذ المراحل السابقة من خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية على التوالي؛ وقائمة بالأنشطة التي سيتم تنفيذها أثناء إعداد المشروع، والميزانيات المقابلة لها، باستخدام نموذج طلبات إعداد المشروعات لخطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية.
تعليقات الأمانة
[bookmark: _Hlk182901891]أثناء استعراض هذه الطلبات، أخذت الأمانة في الاعتبار المبادئ التوجيهية لتمويل إعداد خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية لبلدان المادة 5 الواردة في المقرر 71/42، والتقدم المحرز في المراحل السابقة من خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية بما في ذلك حالة تنفيذ الشرائح حتى وقت إعداد هذه الوثيقة؛ والمقرر 84/46 (هـ).[footnoteRef:7] وأشارت الأمانة إلى أن التمويل المطلوب يتوافق مع المقرر 71/42. [7:  لا يُسمح بإدراج المرحلة الثالثة من خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية إلا للبلدان التي لديها مرحلة ثانية معتمدة من خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية مع أهداف خفض أقل من أهداف الامتثال لعام2025 .] 

[bookmark: _Hlk182902037]وأشارت الأمانة إلى أن كلا المرحلتين الثانية والثالثة من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية في نيجيريا جارية وأن كلا المرحلتين ستكتملان في 31 ديسمبر/كانون الأول 2026.[footnoteRef:8] وعلاوة على ذلك، أشارت الأمانة إلى أن طلبات الإعداد الثلاثة تتوافق مع القرار 82/45 الذي يسمح بتقديم طلبات إعداد المشروع للمرحلة اللاحقة من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية قبل عامين من تاريخ انتهاء المرحلة السابقة من الخطة. [8:  مُددت المرحلة الثانية وفقا للمقرر 93/36(أ)(أربعة عشرة) واعتُمدت المرحلة الثالثة في المقرر 91/46.] 

وأشارت الأمانة كذلك إلى أن البلدان الثلاثة قدمت بياناتها لعام 2023 بموجب المادة 7[footnoteRef:9] وبيانات برنامجها القطري، وأن البلدان ممتثلة لأهداف الرقابة بموجب بروتوكول مونتريال، وأن استهلاكها السنوي المبلغ عنه من المواد الهيدروكلوروفلوروكربونية لا يتجاوز الحد الأقصى السنوي المسموح به للاستهلاك المنصوص عليه في اتفاقاتها لخطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية المبرمة مع اللجنة التنفيذية. [9:  أكدت الأمانة أن حكومة أنغولا قدمت بيانات المادة 7 المتعلقة بالمواد الهيدروكلوروفلوروكربونية لعام 2023، على الرغم من أنها لم تُنشر حتى 15 نوفمبر/تشرين الثاني 2024 على الموقع الشبكي لأمانة الأوزون.] 

[bookmark: _Hlk182902596]وأكد برنامج الأمم المتحدة الإنمائي (اليوئنديبي) أن المرحلة الثالثة من خطتي إدارة إزالة المواد الهيدروكلوروفلوروكربونية في أنغولا وبنغلاديش والمرحلة الرابعة من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية في نيجيريا ستؤدي إلى التخلص التدريجي من 100% من خط الأساس للمواد الهيدروكلوروفلوروكربونية في تلك البلدان بحلول 1 يناير/كانون الثاني 2030.
توصيات الأمانة
توصي الأمانة بالموافقة الشمولية على إعداد المشروع للمرحلة الثالثة من خطتي إدارة إزالة المواد الهيدروكلوروفلوروكربونية في أنغولا وبنغلاديش وللمرحلة الرابعة من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية في نيجيريا بمستوى التمويل المبين في القسم ألف 2 من الجدول 1.
ألف 3: إعداد قائمة جرد وطنية لبنوك المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها وخطة لجمع ونقل والتخلص من هذه المواد
وصف المشروع
قدم برنامج الأمم المتحدة الإنمائي، بصفته الوكالة المنفذة المعينة، طلبا لإعداد قائمة جرد وطنية لبنوك المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها ووضع خطة في بلد واحد، على النحو المبين في القسم ألف 3 من الجدول 1.
تعليقات الأمانة
أثناء استعراض هذا الطلب، أخذت الأمانة في الاعتبار معايير إعداد خطة وطنية وقائمة جرد لبنوك المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها الواردة في المقرر 91/66؛ والأنشطة المقترحة لإعداد المشروع وارتباطها بالخطة الوطنية للبلد للإزالة/التخفيض التدريجي (أي خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية أو خطة تنفيذ تعديل كيغالي للمواد الهيدروفلوروكربونية قيد الإعداد). وأشارت الأمانة إلى أن طلب التمويل يتوافق مع المقرر 91/66.
وقدم برنامج الأمم المتحدة الإنمائي، بصفته الوكالة المنفذة المعينة، وصفا للأنشطة اللازمة لإعداد قائمة جرد وطنية لبنوك المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها ووضع خطة في إندونيسيا، باستخدام نموذج التقديم المناسب لمقترح المشروع.
وتضمنت الأنشطة الواردة في طلب التمويل لإندونيسيا إعداد قائمة الجرد الوطنية وخطة العمل والتقرير النهائي؛ والتقييمات التنظيمية لتحديد احتياجات الرقابة لبنوك المواد غير المرغوب فيها من المواد المستنفدة للأوزون والمواد الهيدروفلوروكربونية؛ والمشاورات مع أصحاب المصلحة المعنيين؛ وجمع وتحليل البيانات عن كميات مواد التبريد غير المستخدمة أو غير المرغوب فيها من أنواع ومصادر المعدات المحددة والتحقق منها؛ وتحديد نموذج مستدام للتكلفة والتمويل اللازم للتنفيذ؛ واعتبارات تعميم مراعاة المنظور الجنساني.
توصية الأمانة
توصي الأمانة بالموافقة الشمولية على إعداد قائمة جرد وطنية لبنوك المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها ووضع خطة لجمع ونقل والتخلص من هذه المواد في إندونيسيا بمستوى التمويل المبين في القسم ألف 3 من الجدول 1.
القسم ب: الأنشطة الموصي بالنظر فيها بصفة فردية
باء 1: إعداد المشروع لخطة لتنفيذ تعديل كيغالي للمواد الهيدروفلوروكربونية
وصف المشروع
بصفته الوكالة المعينة، قدم برنامج الأمم المتحدة الإنمائي، خلال الاجتماع الرابع والتسعين، طلبا لإعداد المرحلة الأولى من خطة تنفيذ تعديل كيغالي للمواد الهيدروفلوروكربونية في الصين، بمبلغ 250,000 دولار أميركي، بالإضافة إلى تكاليف دعم الوكالة البالغة 17,500 دولار أميركي. وعقب مناقشات ثنائية بين الأعضاء، وافقت اللجنة التنفيذية على إرجاء النظر في مشروع إعداد المرحلة الأولى من خطة تنفيذ تعديل كيغالي للمواد الهيدروفلوروكربونية في الصين[footnoteRef:10] إلى الاجتماع الخامس والتسعين. ووفقا لذلك، أُدرج طلب التمويل المقدم خلال الاجتماع الرابع والتسعين في هذه الوثيقة، على النحو المبين في القسم باء1 من الجدول 1. [10:  الفقرة 121 من الوثيقة UNEP/OzL.Pro/ExCom/94/67.] 

تعليقات الأمانة (استُخلصت تعليقات الأمانة العامة وتوصياتها من برنامج عمل البرنامج الإنمائي لعام 2024 (UNEP/OzL.Pro/ExCom/94/18) حيث لم ترد أي معلومات جديدة)
[bookmark: _Hlk182905472]أثناء استعراض الطلب، أخذت الأمانة في الاعتبار المبادئ التوجيهية لإعداد خطط تنفيذ تعديل كيغالي على النحو الوارد في المقرر 87/50، والأنشطة المقترحة لإعداد المشروعات وارتباطها بالأنشطة التمكينية، وغيرها من المشروعات المتعلقة بالمواد الهيدروفلوروكربونية في البلد.
[bookmark: _Hlk182926547]ووصف برنامج الأمم المتحدة الإنمائي، بصفته الوكالة المنفذة المعينة، الأنشطة المطلوبة لإعداد الاستراتيجية الشاملة لخطة تنفيذ تعديل كيغالي في الصين باستخدام نموذج طلبات إعداد المشروعات للخطة. وتضمن التقرير بيانات عن استهلاك المواد الهيدروفلوروكربونية ومركبات المواد الهيدروفلوروكربونية لعام 2022. وشملت أنشطة إعداد المشروع تحليلا تاريخيا لإنتاج واستيراد وتصدير المواد الهيدروفلوروكربونية واستخدامها؛ ودراسة استقصائية وتحليل قطاعيين؛ والبحوث المتعلقة بالتكنولوجيات البديلة للمواد الهيدروفلوروكربونية على المستوى الوطني والدولي؛ وتقييم للتكنولوجيات البديلة؛ والبحوث التنظيمية والمتعلقة بالسياسات؛ ووضع استراتيجية شاملة للخفض التدريجي للمواد الهيدروفلوروكربونية وتصديق أصحاب المصلحة. وأشارت الأمانة إلى أن حكومة الصين قبلت تعديل كيغالي[footnoteRef:11] وقدمت خطاب تأييد يشير إلى نيتها اتخاذ إجراء بشأن الخفض التدريجي للمواد الهيدروفلوروكربونية. وأشارت الأمانة كذلك إلى أنه نظرا لأن خط الأساس للمواد الهيدروفلوروكربونية لديها تتجاوز 2,000 طن من قدرات استنفاد الأوزون،[footnoteRef:12] فإن مستوى التمويل يعتمد على كل حالة على حدة وفقا للمقرر 87/50(ج). [11:  تاريخ قبول تعديل كيغالي: 17 يونيو/حزيران 2021.]  [12:  خط الأساس للمواد الهيدروفلوروكربونية في الصين هو 57,818.7 طنا من قدرة استنفاد الأوزون.] 

وردا على طلب التوضيح (في ذلك الوقت)، أشار برنامج الأمم المتحدة الإنمائي، نيابة عن حكومة الصين، إلى أولوية البلاد في البدء باستعراض دقيق للنهج الشاملة للقطاعات والقطاعات الفرعية، واعتزام الحكومة، بحصولها على معلومات أكثر تفصيلا، تقديم إعداد المشروع لخطط قطاع التصنيع إلى الاجتماع الخامس والتسعين.
توصية الأمانة
قد ترغب اللجنة التنفيذية في النظر في الموافقة على إعداد المشروع أو على استراتيجية شاملة للمرحلة الأولى من خطة تنفيذ تعديل كيغالي للمواد الهيدروفلوروكربونية في الصين بمبلغ قدره 250,000 دولار أمريكي، بالإضافة إلى تكاليف دعم الوكالة وقدرها 17,500 دولار أمريكي لبرنامج الأمم المتحدة الإنمائي.
UNEP/OzL.Pro/ExCom/95/35


UNEP/OzL.Pro/ExCom/95/35



إن وثائق ما قبل دورات اللجنة التنفيذية للصندوق المتعدد الأطراف لتنفيذ بروتوكول مونتريال 
قد تصدر دون إخلال بأي قرار تتخذه اللجنة التنفيذية بعد صدورها. 
4
5
Annex I

INSTITUTIONAL STRENGTHENING PROJECT PROPOSALS[footnoteRef:13] [13:  Data as at December 2022 are based on document UNEP/OzL.Pro/ExCom/93/16.
] 


Ghana: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNDP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Oct-92
	207,016

	Phase II:
	Oct-96
	120,910

	Phase III:
	Nov-98
	112,181

	Phase IV:
	Dec-00
	120,910

	Phase V:
	Nov-02
	156,211

	Phase VI:
	Jul-04
	149,241

	Phase VII:
	Nov-06
	149,457

	Phase VIII:
	Nov-08
	149,408

	Phase IX:
	Dec-10
	147,742

	Phase X:
	Jul-12
	148,837

	Phase XI:
	May-14
	130,116

	Phase XII:
	May-16
	186,878

	Phase XIII:
	Dec-18
	189,862

	Phase XIV:
	Dec-20
	190,324

	Phase XV:
	Dec-22
	262,906

	Total:
	2,421,999

	Amount requested for renewal (phase XVI) (US $):
	368,559

	Amount recommended for approval for phase XVI (US $): 
	368,559

	Agency support costs (US $):
	25,799

	Total cost of institutional strengthening phase XVI to the Multilateral Fund (US $):
	394,359

	Date of approval of country programme:
	1992

	Date of approval of HCFC phase-out management plan:
	2010

	Date of approval of Kigali HFC implementation plan:
	2023

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a) Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b) Annex C, Group I (HCFCs) (average 2009-2010)
	57.3

	(c) Annex E, (methyl bromide) (average 1995-1998)
	0.0

	(d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	1,805,702

	Latest reported ODS consumption (2023) (ODP tonnes) as per Article 7:
	

	(a) Annex B, Group III (methyl chloroform)
	0.00

	(b) Annex C, Group I (HCFCs)
	14.81

	(c) Annex E, (methyl bromide)
	0.00

	Total:
	14.81

	(d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7
	715,052

	Year of reported country programme implementation data:
	2023

	Amount approved for projects (as at May 2024) (US $):
	7,542,346

	Amount disbursed (as at December 2023) (US $):
	6,285,338

	ODS to be phased out (as at May 2024) (ODP tonnes):
	787.9

	ODS phased out (as at December 2023) (ODP tonnes):
	455.3


1. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a) Investment projects:
	2,670,729

	(b) Institutional strengthening:
	2,421,999

	(c) Project preparation, technical assistance, training and other non-investment projects:
	2,449,618

	 Total:
	7,542,346

	(d) HFC activities funded from additional voluntary contributions
	150,000



Progress report
2. During phase XV of the institutional strengthening (IS) project, Ghana undertook a number of important initiatives. Amongst other activities, the national ozone unit (NOU): ensured the operation of the quota system and import controls; trained customs officers; collected data, checked and reported the required information on a timely basis; ensured consultation with key stakeholders at the national level, particularly through a steering committee and industry associations; supervised and monitored project implementation, particularly as related to the refrigeration and air-conditioning (RAC) servicing sector; raised awareness at the national level, through seminars and Ozone Day activities, including efforts to increase the participation of females in the refrigeration and cooling sector through career guidance counsellors; and participated in regional and international meetings related to the Montreal Protocol. Regulation L.I. 1812 was amended to include additional provisions for the control of HFCs and HFC-based equipment. In order to promote hydrocarbon safety and discourage retrofitting with hydrocarbons, warning stickers were developed, printed and distributed to be displayed on the compressors of converted units. Ghana continued implementation of the HCFC phase-out management plan (HPMP) and has initiated work on stage I of the Kigali HFC implementation plan (KIP). 
Plan of action
3.  Over the next three years of phase XVI, Ghana intends to continue with activities and initiatives to facilitate the fulfilment of its Montreal Protocol commitments, focusing efforts to sustain HCFC reductions and implementing activities agreed under stage II of the HPMP to achieve the 67.5 per cent reduction in HCFCs by 2025, and the first stage of its KIP to fulfil its commitments regarding HFC consumption. Specifically, the plan of action will focus on strengthening the regulatory environment for the safe use of hydrocarbons and management of controlled substances and their alternatives; ensuring continued import controls and implementation of the licensing system including for the control of HFC imports; monitoring dealers and warehouses; controlling brands of refrigerants to ensure availability of genuine refrigerants; cooperating with neighbouring countries to combat illegal trade; continuing networking and stakeholder engagement; monitoring of ongoing projects and ensuring sustainability of completed ones; and pursuing awareness‑raising to keep Montreal Protocol on the public agenda to generate collective responsibility among all stakeholders. Furthermore, Ghana will ensure successful implementation of stage II of the HPMP and stage I of the KIP.
Sustainability and risk assessment
4. The involvement of major national and local stakeholders in the project planning and implementation ensures the sustainability of the project interventions. Lack of adequate collaboration with stakeholders would result in delays in project implementation which is considered as a major risk to the project. The collaboration and cooperation that exists among stakeholders serves as a mitigation measure to manage the risk, especially through the leadership provided by the national steering committee.
Haiti: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNDP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-02
	50,000

	Phase I (years 2 and 3):
	Jul-04
	100,000

	Phase II:
	Nov-06
	100,000

	Phase III:
	Nov-09 & Apr-10
	70,863

	
	Jul-10
	17,064*

	Phase IV:
	Nov-15
	54,329

	Phase V:
	Jun-22
	136,960

	Total:
	529,216

	Amount requested for renewal (phase VI) (US $):
	264,960

	Amount recommended for approval for phase VI (US $): 
	264,960

	Agency support costs (US $):
	18,547

	Total cost of institutional strengthening phase VI to the Multilateral Fund (US $):
	283,507

	Date of approval of country programme:
	2000

	Date of approval of HCFC phase-out management plan:
	2012

	Date of approval of Kigali HFC implementation plan:
	n/a

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a) Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.20

	(b) Annex C, Group I (HCFCs) (average 2009-2010)
	3.63

	(c) Annex E, (methyl bromide) (average 1995-1998)
	0.00

	(d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	149,322

	Latest reported ODS consumption (2023) (ODP tonnes) as per Article 7:
	

	(a) Annex B, Group III (methyl chloroform)
	0.00

	(b) Annex C, Group I (HCFCs)
	0.74

	(c) Annex E, (methyl bromide)
	0.00

	Total:
	0.74

	(d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7
	83,633

	Year of reported country programme implementation data:
	2023

	Amount approved for projects (as at May 2024) (US $):
	1,682,111

	Amount disbursed (as at December 2023) (US $):
	1,461,016

	ODS to be phased out (as at May 2024) (ODP tonnes):
	147.8

	ODS phased out (as at December 2023) (ODP tonnes):
	147.8


*Additional emergency assistance for institutional strengthening approved at the 61st meeting
5. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a) Investment projects:
	267,751

	(b) Institutional strengthening:
	529,216

	(c) Project preparation, technical assistance, training and other non-investment projects:
	885,145

	 Total:
	1,682,111

	(d) HFC activities funded from additional voluntary contributions
	0


Progress report
6. During phase V of the IS project, the political instability in the country affected the progress of Montreal Protocol related activities. However, the IS project assisted the country to remain in compliance with the Montreal Protocol and carry out tasks that included: meetings with ministries and institutions to promote ratification of the Kigali Amendment; online meetings with staff of the HPMP project; facilitating the visit of a UNDP consultant who met with the NOU staff regarding the preparation of stage II of the HPMP and efforts to ratify the Kigali Amendment; training refrigeration technicians in the informal sector on good refrigeration practices including safe handling of hydrocarbons; training customs officers including practical sessions on refrigerant identification; commemoration of International Ozone Day; and reporting of ODS consumption data to both the Fund and Ozone Secretariats. Following the departure of the assistant national ozone officer a new assistant was recruited in September 2024. 
Plan of action
7. Phase VI of the IS project will allow the NOU to continue activities to ensure that Haiti maintains the 35 percent reduction in HCFCs achieved in 2020, and to achieve the 67.5 percent reduction target by 2025. Activities planned include the continued application of national legislation and steps to ensure the availability of the necessary personnel and administrative arrangements to support the implementation of the Montreal Protocol in Haiti. During phase VI, the NOU will continue to collect and report ODS consumption data to the Ozone and Fund Secretariats in a timely manner; build the capacity of customs officials; strengthen the capacity of technicians to enable the transition to energy‑efficient low‑GWP alternatives; and support the national refrigeration association. The NOU will also focus on developing a public awareness and education campaign appropriate to the country’s special circumstances, as well as strengthening relationships with national stakeholders. Challenges to be addressed include the ratification of the Kigali Amendment, the development of the licensing and quota system for HFCs, and initiating activities to implement the HFC phase-down. The NOU intends to seek a more active presence in the regional network and meetings of the Montreal Protocol.
Sustainability and risk assessment
8. During implementation of phase V of the IS project, efforts have been made to ensure training of customs officials and RAC technicians to ensure awareness‑raising to assure sustainability of knowledge and skills. However, the complex political and social situation that has prevailed in Haiti increased the risk of not fulfilling the activities planned under the project. In particular there was a lack of stakeholder participation due to the aforementioned challenges. Nevertheless, UNDP continues to work closely with the NOU to continue their efforts to successfully implement the Montreal Protocol in Haiti.


Iran (Islamic Republic of:) Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNDP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Oct-92
	226,226

	Phase II:
	Nov-97
	150,821

	Phase III:
	Dec-00
	150,793

	Phase IV:
	Nov-02
	194,478

	Phase V:
	Dec-04 & Nov-05
	185,039

	Phase VI:
	Nov-06 & Nov-07
	186,361

	Phase VII:
	Nov-08
	186,091

	Phase VIII:
	Jul-10
	186,524

	Phase IX:
	Jul-12
	185,657

	Phase X:
	May-14
	185,585

	Phase XI:
	Dec-16
	237,641

	Phase XII:
	Dec-18
	237,134

	Phase XIII:
	Dec-20
	237,641

	Phase XIV:
	Dec-22
	327,945

	 Total:
	2,877,936

	Amount requested for renewal (phase XV) (US $):
	459,735

	Amount recommended for approval for phase XV (US $): 
	459,735

	Agency support costs (US $):
	32,181

	Total cost of institutional strengthening phase XV to the Multilateral Fund (US $):
	491,916

	Date of approval of country programme:
	1993

	Date of approval of HCFC phase-out management plan:
	2011

	Date of approval of Kigali HFC implementation plan:
	n/a

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
(a) Annex B, Group III (methyl chloroform) (average 1998-2000)
(b) Annex C, Group I (HCFCs) (average 2009-2010)
(c) Annex E, (methyl bromide) (average 1995-1998)
(d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	

	
	8.7

	
	380.5

	
	26.7

	
	Not available

	Latest reported ODS consumption (2023) (ODP tonnes) as per Article 7:
	0.00

	(a) Annex B, Group III (methyl chloroform)
	

	(b) Annex C, Group I (HCFCs)
	93.66

	(c) Annex E (methyl bromide)
 Total:
(d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7
	0.00

	
	93.66

	
	Not available

	Year of reported country programme implementation data:
	2023

	Amount approved for projects (as at May 2024) (US $):
	90,975,558

	Amount disbursed (as at December 2023) (US $):
	77,956,693

	ODS to be phased out (as at May 2024) (ODP tonnes):
	7461.2

	ODS phased out (as at December 2023) (ODP tonnes):
	7095



9. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a) Investment projects:
	82,600,037

	(b) Institutional strengthening:
	2,877,936

	(c) Project preparation, technical assistance, training and other non-investment projects:
	5,497,586

	 Total:
	90,975,558

	(d) HFC activities funded from additional voluntary contributions
	0



Progress report
10. The Islamic Republic of Iran, under phase XIV of the IS project, has successfully sustained ODS phase‑out through effective enforcement of regulation, monitoring and collaboration with key stakeholders. The NOU implemented various activities for awareness and training of stakeholders and submitted Article 7 and country programme data. The NOU supported implementation of the activities under stage II of the HPMP and the initiation of activities under stage III of the HPMP. The NOU also led discussions with the aim of making progress towards ratification of the Kigali Amendment. 
Plan of action
11. Under phase XV, the Islamic Republic of Iran plans to continue its efforts to fulfil its obligations under the Montreal Protocol and eliminate ODS consumption according to the agreed schedule. The country will continue implementation of ODS phase-out activities through enforcement of policies, strategies, control measures, technical assistance, and monitoring mechanisms to sustain the compliance with the provisions of the Montreal Protocol. The IS project supports the Ozone Layer Protection Unit to cooperate nationally with the established network of Ozone Cells in provinces to implement ODS policy and control measures and carry out other awareness-raising and training activities. Consideration of the Kigali Amendment by the Parliament will be facilitated through the next phase of the IS project.
Sustainability and risk assessment
12. Phase XV of the IS project will be implemented following UNDP’s National Implementation Modality which gives the Government of the Islamic Republic of Iran complete ownership of project results. The UNDP country office and Bangkok Regional Hub will provide technical and implementation support to the Government and UNDP will co-chair the country’s project steering committee The Government, through the NOU, will continue to be the project implementing partner, co‑chairing the project steering committee and having full accountability over the project intended results and outputs. Risks are identified using the UNDP Enterprise Risk Management categories and relevant risk tools may be applied for each component. Project risks can be identified during project implementation by the NOU (as implementing partner) and can be updated at any time through the project steering committee. Hence, initially, the project is categorised as moderate risk as the project concern of areas where UNDP strikes a balance between the potential upside benefits and downside risks of a decision and explores new solutions and options for delivery. In the context of the Islamic Republic of Iran, the geopolitical and macro-economic circumstances including currency fluctuation, inflation, and economic downturn could affect the implementation speed of NOU activities. Similarly, these macro factors could also affect the progress of government regulatory activities. These risks will continue to be managed through effective coordination mechanism amongst various agencies, supported and linked to the Project Board.


Nigeria: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNDP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-93
	339,000

	Phase II:
	Jul-01
	225,038

	Phase III:
	Jul-03
	279,392

	Phase IV:
	Apr-06
	279,290

	Phase V:
	Apr-08
	275,451

	Phase VI:
	Dec-10
	277,341

	Phase VII:
	Dec-12
	278,200

	Phase VIII:
	Nov-14
	272,242

	Phase IX:
	May-16
	356,096

	Phase X:
	Dec-18
	356,096

	Phase XI:
	Dec-20
	356,096

	Phase XII:
	Dec-22
	491,412

	 Total:
	3,785,655

	Amount requested for renewal (phase XIII) (US $):
	688,896

	Amount recommended for approval for phase XIII (US $): 
	688,896

	Agency support costs (US $):
	48,223

	Total cost of institutional strengthening phase XIII to the Multilateral Fund (US $):
	737,119

	Date of approval of country programme:
	1997

	Date of approval of HCFC phase-out management plan:
	2010

	Date of approval of Kigali HFC implementation plan:
	n/a

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a) Annex B, Group III (methyl chloroform) (average 1998-2000)
	32.9

	(b) Annex C, Group I (HCFCs) (average 2009-2010)
	344.88

	(c) Annex E, (methyl bromide) (average 1995-1998)
	2.9

	(d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	15,187,779

	Latest reported ODS consumption (2023) (ODP tonnes) as per Article 7:
	

	(a) Annex B, Group III (methyl chloroform)
	0

	(b) Annex C, Group I (HCFCs)
	103.66

	(c) Annex E (methyl bromide)
	0

	Total:
	103.66

	(d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7
	22,809,651

	Year of reported country programme implementation data:
	2023

	Amount approved for projects (as at May 2024) (US $):
	55,615,152

	Amount disbursed (as at December 2023) (US $):
	43,951,902

	ODS to be phased out (as at May 2024) (ODP tonnes):
	6310.5

	ODS phased out (as at December 2023) (ODP tonnes):
	6235.6



13. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a) Investment projects:
	46,362,548

	(b) Institutional strengthening:
	3,785,655

	(c) Project preparation, technical assistance, training and other non-investment projects:
	5,466,949

	 Total:
	55,615,152

	(d) HFC activities funded from additional voluntary contributions
	250,000



Progress report
14. Nigeria has successfully implemented phase XII of the IS project. The NOU ensured implementation and enforcement of the licensing and quota system for all Montreal Protocol controlled substances; facilitated timely data collection and reporting of consumption; supported implementation of HCFC phase‑out and HFC phase‑down activities; and also strengthened coordination between national agencies and stakeholders to support the objectives of the Montreal Protocol. Additionally, Nigeria contributed to regional and global knowledge building on Montreal Protocol activities; promoted awareness among multiple stakeholder groups on the subject of ozone protection; and facilitated the integration of the Multilateral Fund gender policy into its Montreal Protocol activities. The country successfully completed preparatory activities for the submission of stage I of the Kigali HFC implementation plan.
Plan of action
15. Through the implementation of phase XIII, the NOU of Nigeria aims to further strengthen coordination with relevant stakeholder groups to facilitate a common understanding of Montreal Protocol activities at the national level. The country aims to explore opportunities for the utilization of digital tools to enhance data collection, management and reporting to the Multilateral Fund and Ozone Secretariats. Furthermore, the country aims to explore increased collaboration with other countries in the region through joint activities and participation in regional and global programmes to facilitate knowledge sharing and cooperation. Therefore, over the next three years, Nigeria’s action plan will continue with activities and initiatives designed to facilitate the fulfilment of the country’s commitments to the Montreal Protocol including its Kigali Amendment, strengthen the HCFC and HFC import quota/licensing systems, promote awareness on the Montreal Protocol activities and encourage the adoption of ODS alternatives. The NOU will prioritize gender mainstreaming in the implementation of all activities. Nigeria shall also in the next three years prioritise the successful initiation of stage I of the country’s KIP.
Sustainability and risk assessment
16. The safety issues associated with ozone-friendly and low-GWP alternatives to HCFCs in the servicing sector such as flammability, toxicity and high pressure need to be well explained to technicians and end users to avoid fatal accidents during use.


Sri Lanka: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNDP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-94
	174,788

	Phase II:
	Nov-97
	116,526

	Phase III:
	Nov-99
	116,526

	Phase IV:
	Jul-02
	148,457

	Phase V:
	Jul-04
	144,095

	Phase VI:
	Nov-06
	142,718

	Phase VII:
	Jul-08
	128,658

	Phase VIII:
	Jul-10
	143,620

	Phase IX:
	Jul-12
	142,263

	Phase X:
	May-14
	143,440

	Phase XI:
	May-16
	183,603

	Phase XII:
	Dec-18
	183,497

	Phase XIII:
	Dec-20
	183,603

	Phase XIV:
	Dec-22
	253,372

	 Total:
	2,205,166

	Amount requested for renewal (phase XV) (US $):
	355,195

	Amount recommended for approval for phase XV (US $): 
	355,195

	Agency support costs (US $):
	24,864

	Total cost of institutional strengthening phase XV to the Multilateral Fund (US $):
	380,059

	Date of approval of country programme:
	1994

	Date of approval of HCFC phase-out management plan:
	2010

	Date of approval of Kigali HFC implementation plan:
	n/a

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a) Annex B, Group III (methyl chloroform) (average 1998-2000)
	3.0

	(b) Annex C, Group I (HCFCs) (average 2009-2010)
	13.9

	(c) Annex E (methyl bromide) (average 1995-1998)
	4.1

	(d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	1,170,234

	Latest reported ODS consumption (2023) (ODP tonnes) as per Article 7:
	

	(a) Annex B, Group III (methyl chloroform)
	0.00

	(b) Annex C, Group I (HCFCs)
	8.58

	(c) Annex E (methyl bromide)
	0.00

	 Total:
	8.58

	(d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7
	1,156,405

	Year of reported country programme implementation data:
	2023

	Amount approved for projects (as at May 2024) (US $):
	8,531,388

	Amount disbursed (as at December 2023) (US $):
	6,173,378

	ODS to be phased out (as at May 2024) (ODP tonnes):
	108

	ODS phased out (as at December 2023) (ODP tonnes):
	99.3



17. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a) Investment projects:
	1,822,167

	(b) Institutional strengthening:
	2,205,166

	(c) Project preparation, technical assistance, training and other non-investment projects:
	4,504,054

	 Total:
	8,531,388

	(d) HFC activities funded from additional voluntary contributions
	150,000



Progress report
18. During phase XIV of the IS project, Sri Lanka continued implementation of activities to ensure sustainability of ODS phase-out to ensure the country’s compliance with the Montreal Protocol obligations and expanded the quota and licensing systems to include HFCs in compliance with the Kigali Amendment. Nine NOU staff received training on the operationalization of the HFC quota system. The NOU also implemented a number of gender-sensitive/gender-responsive activities for the awareness and training of stakeholders including encouraging young women to train for the RAC sector. The NOU worked with other national agencies and stakeholders to ensure monitoring of ODS phase-out, coordinate the implementation of stage II of the HPMP, and the preparation of the project proposal for the KIP. IS activities allowed for coordinated efforts and complementary actions to support the enforcement of sector bans for methyl bromide and HCFC-141b, and assisted the monitoring of the national compliance targets and national policies to ensure coordinated actions under stage II of the HPMP. 
Plan of action
19. Under phase XV, Sri Lanka will continue its efforts to fulfil its obligations under the Montreal Protocol and its Kigali Amendment and include activities to continue implementation of stage II of the HPMP and start the implementation of stage I of the KIP. The activities of the IS project will include: coordination mechanisms to allow complementary work between the HPMP implementation team, which is under the IS project as Sri Lanka is a low-volume-consuming (LVC) country in terms of the HPMP, and the future project management unit (PMU) for stage I of the KIP as Sri Lanka is classified as a non-LVC country under the Kigali Amendment; continued management, monitoring and enforcement of measures on controlled substances to ensure sustainability of the ODS phase-out and HFC phase-down; monitoring the implementation of the HPMP, and strengthening institutional engagement to support the achievement of compliance targets; continue implementation and enforcement of the Montreal Protocol’s related legal framework; continued the awareness outreach activities for involvement of all stakeholders in sustaining ODS phase-out and HFC phase-down.
Sustainability and risk assessment
20. Phase XV of the IS project will continue to be implemented following UNDP’s National Implementation Modality which allows the Government of Sri Lanka total ownership of project results. In terms of implementation risks, the UNDP country office will provide support to the Government by providing the Enterprise Resources Planning (ERP) System, the financial rules and regulations for the project’s execution, and information technology tools required to deliver the project tasks. UNDP will apply its financial and procurement rules and regulations which are expected to address any risks related to delays in project execution. UNDP will co-chair the project steering committee together with the Government of Sri Lanka, through its NOU, as the project implementing partner. Sri Lanka has full accountability over the project intended results and outputs. Risks are identified using UNDP’s risk matrix and relevant risk screening tools where and when applicable. Based on UNDP’s categorization system, Sri Lanka’s IS project is assessed as low risk.
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المرفق الثاني
مسودة الآراء التي أعربت عنها اللجنة التنفيذية بشأن تجديد
مشروعات التعزيز المؤسسي المقدمة إلى الاجتماع الخامس والتسعين
غانا
1. [bookmark: _Hlk182909645]استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي في غانا (المرحلة السادسة عشرة) ولاحظت مع التقدير أن غانا قدمت بيانات المادة7 وبيانات البرنامج القطري لعامي 2022 و2023 إلى كل من أمانة الأوزون وأمانة الصندوق على التوالي، مشيرة إلى أن البلد حقق أهدافه لخفض المواد الهيدروكلوروفلوروكربونية لكلا العامين. ولاحظت اللجنة كذلك التقدم الذي أحرزته غانا في التخلص التدريجي من استهلاك المواد المستنفدة للأوزون أثناء فترة المشروع من خلال فرض ضوابط استيراد المواد المستنفدة للأوزون من خلال نظام التراخيص والحصص، ونشر الوعي، وتوفير التدريب لموظفي الجمارك وفنيي التبريد، مع اتخاذ إجراءات للرفع من مستوى مشاركة النساء في قطاعي التجميد والتبريد. واعترفت اللجنة بالجهود التي تبذلها حكومة غانا للحد من استهلاك المواد الهيدروكلوروفلوروكربونية والمواد الهيدروفلوروكربونية، ولذلك تأمل أن تواصل حكومة غانا، خلال السنوات الثلاث القادمة، تنفيذ خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية، وخطة تنفيذ تعديل كيغالي ومشروع التعزيز المؤسسي بنجاح من أجل تحقيق التخفيض المطلوب بنسبة 67.5 في المئة في استهلاك المواد الهيدروكلوروفلوروكربونية بحلول1 يناير/ كانون الثاني 2025، والحفاظ على تجميد استهلاك المواد الهيدروفلوروكربونية الذي تحقق في 1 يناير/كانون الثاني 2024، والعمل على تحقيق الهدف المتمثل تخفيض الاستهلاك بنسبة 10 في المائة بحلول 1 يناير/كانون الثاني 2029.
هايتي
استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي في هايتي (المرحلة السادسة) ولاحظت مع التقدير أن هايتي أبلغت كلا من أمانة الأوزون وأمانة الصندوق على التوالي، ببيانات المادة 7 والبرنامج القطري لعامي 2022 و2023، مشيرة إلى أن البلاد ممتثلة لجدول التخلص التدريجي بموجب بروتوكول مونتريال. وأشارت اللجنة كذلك إلى إن هايتي تتخلص فعليا من استهلاك المواد المستنفدة للأوزون، على الرغم من الظروف الصعبة في البلاد، من خلال تنفيذ أنظمة الترخيص والحصص، فضلا عن اعتماد البدائل ذات القدرة المنخفضة على إحداث الاحترار العالمي، وأن البلاد تسير على الطريق الصحيح لتحقيق أهداف التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية. وأقرت اللجنة بالجهود التي تبذلها حكومة هايتي للحد من استهلاك المواد الهيدروكلوروفلوروكربونية ولإحراز تقدم نحو التصديق على تعديل كيغالي، ولذلك فهي تأمل أن تواصل حكومة هايتي خلال السنوات الثلاث المقبلة تنفيذ خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية ومشروع التعزيز المؤسسي بنجاح من أجل تحقيق التخفيض المطلوب بنسبة 67.5 في المئة في استهلاك المواد الهيدروكلوروفلوروكربونية بحلول1 يناير/ كانون الثاني 2025 والتصديق على تعديل كيغالي.
إيران (جمهورية - الإسلامية)
[bookmark: _Hlk182910769]استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي في جمهورية إيران الإسلامية (المرحلة الرابعة عشرة) وأشارت مع التقدير إلى أن حكومة جمهورية إيران الإسلامية أبلغت كلا من أمانة الأوزون وأمانة الصندوق على التوالي، ببيانات المادة 7 والبرنامج القطري لعامي 2022 و2023، مشيرة إلى أن البلاد ممتثلة لبروتوكول مونتريال وحققت أهداف التخفيض وفقا لاتفاق البلد مع اللجنة التنفيذية لكلا العامين. وأشارت اللجنة إلى الإنفاذ المتواصل لتدابير الرقابة لحفاظ على التخلص التدريجي من المواد المستنفدة للأوزون، بما في ذلك تحديث القواعد واللوائح وإدخال تحسينات على نظام التراخيص والحصص للمواد الهيدروكلوروفلوروكربونية. وأقرت اللجنة التنفيذية بالجهود التي تبذلها حكومة جمهورية إيران الإسلامية لتنفيذ المرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية، وإعداد المرحلة الثالثة منها، ولإحراز تقدم نحو التصديق على تعديل كيغالي، ولذلك فهي تأمل أن تواصل حكومة جمهورية إيران الإسلامية خلال السنوات الثلاث المقبلة تنفيذ أنشطة الصندوق المتعدد الأطراف على مستوى السياسات والمشاريع لتمكينها من الامتثال لتدابير الرقابة التالية الواردة في بروتوكول مونتريال وتقديم صك التصديق على تعديل كيغالي.
نيجيريا
[bookmark: _Hlk182911914]استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي في نيجيريا )المرحلة الثالثة عشرة) وأشارت مع التقدير إلى أن نيجيريا أبلغت عن بيانات المادة7 وبيانات البرنامج القطري لعامي 2022 و2023 إلى أمانتي الأوزون والصندوق، على التوالي، مشيرة إلى أن البلد حقق أهدافه المتمثلة في خفض المواد الهيدروكلوروفلوروكربونية بموجب بروتوكول مونتريال والاتفاق المبرم بين البلد واللجنة التنفيذية. وأشارت اللجنة أن وحدة الأوزون الوطنية في نيجيريا سهلت العمل مع أصحاب المصلحة الرئيسيين على زيادة التعاون والوعي الوطنيين بالتزامات البلاد بموجب بروتوكول مونتريال وتعزيز جمع بيانات المواد الخاضعة للرقابة والإبلاغ عنها. وأقرت اللجنة بجهود حكومة نيجيريا للحد من استهلاك  المواد الهيدروكلوروفلوروكربونية والمواد الهيدروفلوروكربونية، وبالتالي فهي تأمل أن تواصل حكومة نيجيريا بنجاح، خلال السنوات الثلاث المقبلة، تنفيذ المرحلة الثالثة من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية ومشروع التعزيز المؤسسي وأن تبدأ في تنفيذ المرحلة الأولى من خطة التنفيذ للمواد الهيدروكلوروفلوروكربونية بموجب تعديل كيغالي، لتحقيق ومواصلة الامتثال لتدابير الرقابة الواردة في بروتوكول مونتريال.
سري لانكا
استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي في سري لانكا (المرحلة الخامسة عشرة) وأشارت مع التقدير أن سري لانكا أبلغت أمانتي الأوزون والصندوق على التوالي ببيانات المادة 7 والبرنامج القطري لعامي 2022 و2023، مشيرة إلى أن البلد ممتثل لبروتوكول مونتريال، وأنه حقق أهدافه المتمثلة في خفض المواد الهيدروكلوروفلوروكربونية وفقا للاتفاق المبرم بين البلد واللجنة التنفيذية، وأنه واصل التخلص التدريجي من المواد الأخرى المستنفدة للأوزون. وأشارت اللجنة إلى أن حكومة سري لانكا قد اتخذت إجراءات لتعميم مراعاة المنظور الجنساني بما يتماشى مع سياسة الصندوق المتعدد الأطراف بشأن تعميم المنظور الجنساني وإنشاء آليات تنسيق تسمح بمواءمة العمل بين الفرق والوحدات المختلفة التي تنفذ خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية، ومشروع التعزيز المؤسسي، وخطة التنفيذ للمواد الهيدروفلوروكربونية بموجب تعديل كيغالي في المستقبل. وأقرت اللجنة بالجهود التي تبذلها حكومة سري لانكا للحد من استهلاك  المواد الهيدروكلوروفلوروكربونية والمواد الهيدروفلوروكربونية، ولذلك فهي تأمل أن تواصل حكومة سري لانكا بنجاح، خلال السنوات الثلاث المقبلة، تنفيذ أنشطة الصندوق المتعدد الأطراف على مستوى السياسات والمشاريع لتمكينها من الامتثال لتدابير الرقابة التالية الواردة في بروتوكول مونتريال.
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