| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/91/14 9 November 2022 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-first Meeting

Montreal, 5-9 December 2022

Item 7(a)(iii) of the provisional agenda

PROGRESS REPORT OF UNDP AS AT 31 DECEMBER 2021

Introduction

# This document presents the progress report of UNDP as at 31 December 2021.

# The progress report of UNDP includes the status of implementation of projects, including 18 HFC-related projects that have been funded under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment.

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2021, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs which are measured in CO2-eq tonnes.

# This document consists of the following sections:

## I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2021 and cumulative since 1991 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs). It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee.

## II.	Projects approved for Annex F substances (HFCs) under the additional voluntary contributions for fast-start support for HFC phase-down.

III.	Recommendation.

I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund

I.1	Progress in implementation of projects for 2021 and cumulative since 1991

# As of 31 December 2021, the Executive Committee had approved US $1.004 billion in projects for UNDP, consisting of US $883.61 million for the implementation of investment and non-investment projects and US $121.27 million for agency support costs, as shown in table 1.

# Table 1. Approved funding by sector for UNDP as at 31 December 2021

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 26,054,837 |
| Destruction | 3,606,279 |
| Foam | 173,140,713 |
| Halon | 4,996,973 |
| HFC phase-down plan | 3,183,000 |
| Fumigants | 20,081,241 |
| Phase-out plan | 378,675,934 |
| Process agent | 1,286,923 |
| Production | 1,056,000 |
| Refrigeration | 139,598,314 |
| Several | 67,812,809 |
| Solvents | 63,699,997 |
| Sterilant | 417,628 |
| Sub-total | 883,610,648 |
| Agency support costs | 121,270,538 |
| Total | 1,004,881,186 |

# In 2021, 66 new projects and activities were approved. This level of funding is expected to result in the phase-out of 69,419 ODP tonnes and 240,094 CO2-eq tonnes of consumption of controlled substances. Annex I shows the status of project implementation per country in 2021.

# Table 2 shows the status of project implementation including fund disbursement per project type as at 31 December 2021.  Annex II presents analytical information per year since 1991.

Table 2. Status of project implementation by type as at 31 December 2021

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 22 | 22 | 100 | 1,628,797 | 1,628,797 | 0 | 100 |
| Demonstration | 42 | 41 | 98 | 21,719,011 | 21,599,917 | 119,094 | 99 |
| Institutional strengthening (IS) | 265 | 241 | 91 | 57,444,952 | 52,351,763 | 5,093,189 | 91 |
| Investment | 1,331 | 1,264 | 95 | 725,664,632 | 679,155,019 | 46,509,613 | 94 |
| Project preparation | 574 | 536 | 93 | 26,231,244 | 22,156,807 | 4,074,437 | 84 |
| Technical assistance | 329 | 309 | 94 | 49,331,523 | 42,396,630 | 6,934,893 | 86 |
| Training | 28 | 28 | 100 | 1,590,489 | 1,590,489 | 0 | 100 |
| Total | 2,591 | 2,441 | 94 | 883,610,648 | 820,879,422 | 62,731,226 | 93 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

# Implementation of projects and activities by UNDP for 2021 and cumulative since 1991 up to 31 December 2021 is summarized as follows:

## Phase-out: In 2021, 923.6 ODP tonnes and 15,873 CO2-eq tonnes of consumption of controlled substances were phased out and an additional 359.6 ODP tonnes of consumption of controlled substances were approved for phase-out. Since 1991, 68,821 ODP tonnes and 240,094 CO2-eq tonnes of consumption of controlled substances had been phased out, of an expected total of 69,419 ODP tonnes and 240,094 CO2-eq tonnes from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2021, US $24.66 million was disbursed and US $22.52 million was planned for disbursement based on the 2020 progress report, representing a rate of disbursement of 109 per cent of that planned. Cumulatively, US $820.88 million had been disbursed out of the total US $883.61 million approved for disbursement (excluding agency support costs), representing a rate of disbursement of 93 per cent. In 2021, US $24.65 million was approved for implementation;

## Cost-effectiveness (in ODP): Since 1991, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $11.15/kg. The average cost-effectiveness of investment projects per ODP tonne was US $10.05/kg for completed projects and US $66.17/kg for ongoing projects;

## Number of projects completed: In 2021, 62 projects were completed. Since 1991, 2,441 projects of the 2,591 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 94 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2021 were completed on average 37 months after their approval. Since 1991, the average time for completion of investment projects has been 34 months after their approval. First disbursements under these projects occurred, on average, 13 months after they had been approved;

## Speed of delivery – non-investment projects: Projects that were completed in 2021 were completed on average 33 months after their approval. Since 1991, the average time for completion of non-investment projects has been 39 months after their approval. First disbursements under these projects occurred, on average, 13 months after they had been approved;

## Project preparation: Of the 574 project preparation activities approved by the end of 2021, 536 have been completed, leaving 38 ongoing activities. In 2021, 14 projects preparation activity has been completed;

## Implementation delays: A total of 150 projects were under implementation at the end of 2021, experiencing, on average, a delay of seven months. Twenty of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2021, 47 MYAs for HCFC phase-out management plans (HPMPs) were under implementation. Since 1991, 156 MYAs have been approved and 109 MYAs have been completed, representing a completion rate of 70 per cent.

# Table 3 summarized progress made by UNDP since 1991.

## Table 3: Progress made by UNDP since 1991

| Phase out achieved |  | Disbursement (US $) | Average CE (US$/kg) | Number of projects |  | Speed of delivery for completion (months) |  | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes | CO2-eq tonnes |  |  | Approved | Completed | Investment | Non- investment |  | Approved | Completed |
| 68,821 | 240,094 | 820,879,422 | 11.15 | 2,591 | 2,441 | 34 | 39 | 7 | 156 | 109 |

HFC-related projects

# As of 31 December 2021, the Executive Committee had approved 36 HFC-related projects (including three investment projects, 25 preparation projects and eight enabling activities) under regular contributions amounting to US $6,318,767 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 5 to 9.

Table 4. HFC-related projects approved under regular contributions

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 3 | 2 | 67 | 2,491,767 | 2,159,576 | 332,191 | 87 |
| Project preparation | 25 | 0 | 0 | 3,183,000 | 0 | 3,183,000 | 0 |
| Technical assistance - Enabling activities | 8 | 4 | 50 | 644,000 | 423,586 | 220,414 | 66 |
| Total | 36 | 6 | 17 | 6,318,767 | 2,583,162 | 3,735,605 | 41 |

* Excludes agency support costs.

** 167.8 mt (240,094 CO2-eq tonnes) was approved and phased out for investment projects.

# As of the end of 2021, of the 36 projects, two investment projects and four enabling activities have been completed, leaving 30 ongoing. Extension of the completion dates of the four ongoing projects for enabling activities had been approved; these activities are at various stages of implementation.

# The remaining ongoing investment project, for which the extension of the completion date was approved at the 87th meeting, is expected to be completed in 2023.

# Of the total cumulative funding approved of US $6,318,767 (excluding agency support costs), US $2,583,162 had been disbursed, representing a disbursement rate of 41 per cent.

I.2	Issues identified in project implementation in 2021

# Further to the review process in 2021, several issues were discussed and satisfactorily addressed, except for issues on 20 projects classified as projects with implementation delays (including 19 projects related to components of MYAs that are subject to procedures for project cancellation, in line with decision 84/45(c); and one HFC investment project). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 92nd meeting.

# In addition, issues have been identified in one IS and two MYA projects. These issues are also presented in Annex III. For each of these projects, a brief description on the status of implementation and the outstanding issues are presented and a recommendation is proposed for consideration by the Executive Committee.

# Details of progress in implementation of projects associated with the HPMPs for China (overarching strategy and solvents sector plan), India, Nigeria (stage III), and South Sudan and reports on projects with specific reporting requirements associated with the HPMPs for Brazil, Colombia, Trinidad and Tobago, and Uruguay, have been submitted to the 91st meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. The issues relating to the HPMPs for Guyana, Mali and Nigeria (stage II), tranches of which were due at the 91st meeting but were not submitted, are addressed in the document on tranche submission delays.

# Of the 88 ongoing projects, excluding IS and project preparation, 21 projects have revised planned dates of completion since the 2020 progress report.  In line with decision 82/11(c)(ii), the Secretariat noted that renewal of the IS project for China had not been submitted for the last two years.

II.	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down

# As of 31 December 2021, the Executive Committee had approved 18 HFC-related projects under the additional voluntary contributions amounting to US $6,010,703 (excluding agency support costs). A summary of the status of these projects is presented in table 5.

# Table 5. Status of approved HFC-related projects as of the end of 2021

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 2 | 2 | 100 | 4,406,610 | 4,402,590 | 4,020 | 100 |
| Project preparation | 5 | 5 | 100 | 83,511 | 83,511 | 0 | 100 |
| Technical assistance - Enabling activities | 11 | 10 | 91 | 1,520,582 | 1,450,187 | 70,395 | 95 |
| Total | 18 | 17 | 94 | 6,010,703 | 5,936,288 | 74,415 | 99 |

* Excludes agency support costs.

** 480.6 mt (587,301 CO2-eq tonnes) was approved and phased out for investment projects.

# As of the end of 2021, of the 18 projects approved, 17 projects had been completed (two investment projects, five enabling activities and ten preparation activities). The remaining ongoing project for enabling activities, for which the completion date was extended, is expected to be completed in 2022.

# Of the total cumulative funding approved of US $6,010,703, US $5,936,288 had been disbursed, representing a disbursement rate of 99 per cent.

III.	Recommendation

# The Executive Committee may wish:

## To note the progress report of UNDP as at 31 December 2021 contained in document UNEP/OzL.Pro/ExCom/91/14; and

## To approve the recommendations related to ongoing projects with specific issues contained in Annex III to the present document.

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNDP

PER COUNTRY FOR 2021

# Table 1 of Annex I presents the status of project implementation by country for 2021 in achieved phased out, planned and achieved disbursements and project completion.

Table 1. Status of project implementation by UNDP for 2021

| Country | Phased out in 2021 (ODP tonnes) | Phased out in 2021 (CO2-eq tonnes) | Estimated funds disbursed in 2021 (US$) | Funds disbursed in 2021 (US$) | Percentage of funds disbursed over estimation in 2021 | Percentage of planned projects completed in 2021* |
| --- | --- | --- | --- | --- | --- | --- |
| Angola | 5.2 |  | 44,727 | 19,150 | 43 | 100 |
| Argentina | 0 |  | 105,091 | 119,931 | 114 |  |
| Armenia | 0 |  | 6,921 | 20,622 | 298 | 100 |
| Bangladesh | 0 |  | 695,591 | 540,551 | 78 | 0 |
| Belize | 0 |  | 26,500 | 17,953 | 68 | 100 |
| Brazil | 53.6 |  | 3,093,879 | 938,968 | 30 |  |
| Brunei Darussalam | 0 |  | 10,924 | 8,212 | 75 | 0 |
| Cambodia | 0 |  | 22,735 | 40,000 | 176 |  |
| Chile | 0 |  | 186,001 | 156,501 | 84 | 100 |
| China | 332.2 |  | 1,106,389 | 2,766,364 | 250 | 100 |
| Colombia | 63.4 |  | 843,183 | 1,721,706 | 204 |  |
| Costa Rica | 0 |  | 126,541 | 155,021 | 123 |  |
| Cuba | 0 |  | 231,234 | 144,689 | 63 | 100 |
| Democratic Republic of the Congo (the) | 2.2 |  | 17,143 | 2,931 | 17 |  |
| Dominican Republic (the) | 0 |  | 299,125 | 206,124 | 69 | 100 |
| Egypt | 33.6 |  | 1,182,997 | 733,659 | 62 | 0 |
| El Salvador | 0 |  | 65,312 | 106,384 | 163 | 100 |
| Eswatini | 0 |  | 25,000 | 0 | 0 | 100 |
| Fiji | 0 |  | 48,926 | 54,779 | 112 | 50 |
| Georgia | 2.1 |  | 98,440 | 154,634 | 157 | 100 |
| Ghana | 8 |  | 133,642 | 208,244 | 156 | 100 |
| Guyana | 0 |  | 53,979 | 931 | 2 |  |
| Haiti | 0.2 |  | 29,608 | 73,966 | 250 | 100 |
| India | 346.6 |  | 6,607,388 | 11,854,587 | 179 | 100 |
| Indonesia | 10.2 |  | 1,061,531 | 570,044 | 54 | 0 |
| Iran (Islamic Republic of) | 2.8 |  | 1,467,253 | 783,977 | 53 | 100 |
| Jamaica | 0 |  | 86,775 | 66,035 | 76 | 100 |
| Kyrgyzstan | 0 |  | 81,597 | 147,561 | 181 | 100 |
| Lao People's Democratic Republic (the) | 0 |  | 32,100 | 0 | 0 |  |
| Lebanon | 1.9 |  | 309,221 | 485,572 | 157 | 100 |
| Malaysia | 9 |  | 891,540 | 470,118 | 53 | 100 |
| Maldives | 0 |  | 1,070 | 1,528 | 143 |  |
| Mali | 0 |  | 19,875 | 0 | 0 | 0 |
| Mauritania | 0 |  | 31,500 | 0 | 0 | 0 |
| Mexico | 0 |  | 1,149,829 | 200,227 | 17 |  |
| Mozambique | 0 |  | 10,000 | 0 | 0 | 0 |
| Nepal | 0 |  | 31,399 | 0 | 0 | 0 |
| Nigeria | 30.4 |  | 797,834 | 672,685 | 84 | 0 |
| Pakistan | 0 |  | 34,011 | 114,474 | 337 | 100 |
| Panama | 5.7 |  | 293,709 | 362,214 | 123 | 100 |
| Paraguay | 0 |  | 19,478 | 18,177 | 93 | 100 |
| Peru | 0 |  | 80,525 | 52,512 | 65 |  |
| Republic of Moldova (the) | 0 |  | 36,349 | 40,988 | 113 | 67 |
| Sri Lanka | 5.4 |  | 165,972 | 74,299 | 45 | 100 |
| Timor-Leste | 0 |  | 10,500 | 0 | 0 | 0 |
| Trinidad and Tobago | 0 |  | 244,291 | 181,805 | 74 | 100 |
| Uruguay | 0 |  | 366,533 | 304,780 | 83 | 40 |
| Venezuela (Bolivarian Republic of) | 0 |  | 99,201 | 59,577 | 60 |  |
| Zimbabwe | 11.1** | 15,873** | 140,083 | 3,432 | 2 |  |
| Grand total | 923.6 | 15,873 | 22,523,452 | 24,655,912 | 109 | 70 |

* For projects that were planned to be completed in 2021.

** 11.1 mt (15,873 CO2-eq tonnes) phased out in 2021 for HFC-related projects.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNDP

PER YEAR AS AT 31 DECEMBER 2021

# Table 1 of Annex II presents an overview of the status of project implementation by year. All projects and activities approved between 1991 and 2013 and in 2015, have now been completed.

Table 1. Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1991 | 15 | 15 | 100 | 1,149,032 | 1,149,032 | 0 | 100 |
| 1992 | 67 | 67 | 100 | 8,619,002 | 8,619,002 | 0 | 100 |
| 1993 | 57 | 57 | 100 | 13,204,712 | 13,204,712 | 0 | 100 |
| 1994 | 148 | 148 | 100 | 49,481,581 | 49,481,581 | 0 | 100 |
| 1995 | 117 | 117 | 100 | 29,599,446 | 29,599,446 | 0 | 100 |
| 1996 | 83 | 83 | 100 | 27,838,805 | 27,838,805 | 0 | 100 |
| 1997 | 188 | 188 | 100 | 44,056,257 | 44,056,257 | 0 | 100 |
| 1998 | 172 | 172 | 100 | 31,305,010 | 31,305,010 | 0 | 100 |
| 1999 | 204 | 204 | 100 | 35,896,884 | 35,896,884 | 0 | 100 |
| 2000 | 149 | 149 | 100 | 31,268,361 | 31,268,361 | 0 | 100 |
| 2001 | 179 | 179 | 100 | 35,292,271 | 35,292,271 | 0 | 100 |
| 2002 | 117 | 117 | 100 | 44,316,422 | 44,316,422 | 0 | 100 |
| 2003 | 64 | 64 | 100 | 36,336,530 | 36,336,530 | 0 | 100 |
| 2004 | 69 | 69 | 100 | 24,802,714 | 24,802,714 | 0 | 100 |
| 2005 | 53 | 53 | 100 | 29,124,833 | 29,124,833 | 0 | 100 |
| 2006 | 62 | 62 | 100 | 15,753,459 | 15,753,459 | 0 | 100 |
| 2007 | 54 | 54 | 100 | 12,142,486 | 12,142,486 | 0 | 100 |
| 2008 | 84 | 84 | 100 | 22,873,866 | 22,873,866 | 0 | 100 |
| 2009 | 92 | 92 | 100 | 13,217,903 | 13,217,903 | 0 | 100 |
| 2010 | 43 | 43 | 100 | 19,567,970 | 19,567,970 | 0 | 100 |
| 2011 | 63 | 63 | 100 | 57,415,931 | 57,415,931 | 0 | 100 |
| 2012 | 29 | 29 | 100 | 33,889,850 | 33,817,257 | 72,593 | 100 |
| 2013 | 43 | 43 | 100 | 34,432,909 | 33,958,972 | 473,937 | 99 |
| 2014 | 67 | 66 | 99 | 22,561,208 | 22,442,114 | 119,094 | 99 |
| 2015 | 75 | 75 | 100 | 31,409,354 | 30,229,223 | 1,180,131 | 96 |
| 2016 | 52 | 49 | 94 | 41,918,720 | 39,804,442 | 2,114,278 | 95 |
| 2017 | 27 | 22 | 81 | 30,616,637 | 30,129,464 | 487,173 | 98 |
| 2018 | 60 | 44 | 73 | 40,274,462 | 27,837,785 | 12,436,677 | 69 |
| 2019 | 41 | 22 | 54 | 10,391,357 | 4,474,052 | 5,917,305 | 43 |
| 2020 | 51 | 11 | 22 | 30,206,633 | 14,760,078 | 15,446,555 | 49 |
| 2021 | 66 | 0 | 0 | 24,646,043 | 162,560 | 24,483,483 | 1 |
| Total | 2,591 | 2,441 | 94 | 883,610,648 | 820,879,422 | 62,731,226 | 93 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

Annex III

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR UNDP

| Country/project code | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- |
| BGD/PHA/81/INV/51 | HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector) | 20 | 12 months delays | To request UNDP to report to the 92nd meeting on this project with implementation delays |
| BGD/PHA/81/TAS/49 | HCFC phase-out management plan (stage II, first tranche) (project management unit) | 26 | 12 months delays | To request UNDP to report to the 92nd meeting on this project with implementation delays |
| BRA/PHA/82/INV/323 | HCFC phase-out management plan (stage II, third tranche) (foam sector) | 46 | 12 months delays | To request UNDP to report to the 92nd meeting on this project with implementation delays |
| BRA/PHA/82/TAS/322 | HCFC phase-out management plan (stage II, third tranche) (regulatory actions and project monitoring) | 30 | 12 months delays | To request UNDP to report to the 92nd meeting on this project with implementation delays |
| BRA/SEV/86/INS/324 | Extension of institutional strengthening project (phase IX: 1/2021-12/2022) | 0 | Delays in project document signature | To request UNDP to provide a status report to the 92nd meeting on status of signature of project document |
| CHI/PHA/81/INV/197 | HCFC phase-out management plan (stage II, second tranche) (foam sector) | 73 | 12 months delays | To request UNDP to report to the 92nd meeting on this project with implementation delays |
| COS/PHA/84/INV/60 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | 0 | 18 months delays | To request UNDP to report to the 92nd meeting on this project with implementation delays |
| CPR/PHA/80/INV/587 | HCFC phase-out management plan (stage II, second tranche) (industrial and commercial refrigeration and air-conditioning sector plan) | 100 | 12 months delays | To request UNDP to report to the 92nd meeting on this project with implementation delays |
| EGY/PHA/79/TAS/132 | HCFC phase-out management plan (stage II, first tranche) (project management and monitoring) | 13 | 12 months delays | To request UNDP to report to the 92nd meeting on this project with implementation delays |
| EGY/PHA/84/TAS/143 | HCFC phase-out management plan (stage II, second tranche) (project management and monitoring) | 0 | 18 months delays | To request UNDP to report to the 92nd meeting on this project with implementation delays |
| GUY/PHA/83/INV/32 | HCFC phase-out management plan (stage II, second tranche) | 0 | 18 months delays | To request UNDP to report to the 92nd meeting on this project with implementation delays |
| IDS/PHA/76/INV/211 | HCFC phase-out management plan (stage II, first tranche) (fire fighting sector) | 0 | 12 and 18 months delays | To request UNDP to report to the 92nd meeting on this project with implementation delays |
| IDS/PHA/76/TAS/210 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 54 | 12 months delays | To request UNDP to report to the 92nd meeting on this project with implementation delays |
| IDS/PHA/81/INV/213 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 0 | 12 and 18 months delays | To request UNDP to report to the 92nd meeting on this project with implementation delays |
| KAM/PHA/83/INV/36 | HCFC phase-out management plan (fourth tranche) | 76 | 12 months delays | To request UNDP to report to the 92nd meeting on this project with implementation delays |
| MAL/PHA/77/TAS/183 | HCFC phase-out management plan (stage II, first tranche) (management and coordination) | 16 | 12 months delays | To request UNDP to report to the 92nd meeting on this project with implementation delays |
| MAL/PHA/84/TAS/186 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 0 | 18 months delays | To request UNDP to report to the 92nd meeting on this project with implementation delays |
| MAL/PHA/84/TAS/187 | HCFC phase-out management plan (stage II, second tranche) (management and coordination) | 0 | 18 months delays | To request UNDP to report to the 92nd meeting on this project with implementation delays |
| NEP/PHA/86/INV/41 | HCFC phase-out management plan (stage II, first tranche) | 0 | Project implementation affected due to changes in administrative procedures in the Government | To request UNDP to provide a status report to the 92nd meeting on implementation progress |
| NEP/PHA/86/INV/44 | HCFC phase-out management plan (stage I, third tranche) | 0 | Project implementation affected due to changes in administrative procedures in the Government | To request UNDP to provide a status report to the 92nd meeting on implementation progress |
| TLS/PHA/80/INV/15 | HCFC phase-out management plan (stage II, first tranche) | 36 | 12 months delays | To request UNDP to report to the 92nd meeting on this project with implementation delays |
| URU/PHA/85/INV/75 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector and implementation and monitoring) | 51 | 12 months delays | To request UNDP to report to the 92nd meeting on this project with implementation delays |
| ZIM/REF/82/INV/55 | Conversion from HFC-134a to isobutane in the manufacture of domestic refrigerators at Capri (SME Harare) | 0 | 18 months delays | To request UNDP to report to the 92nd meeting on this project with implementation delays |

UNEP/OzL.Pro/ExCom/91/1

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database that is available upon request.

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 91st meeting.

Ongoing projects are all projects that were under implementation as at 31 December 2021. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

In line with decision 84/12(b), a detailed progress report providing an overview of the objectives, status of implementation, key findings and lessons learned, the amounts of HFC phased out where applicable, the level of funds approved and disbursed and potential challenges in completing the projects and activities, is presented in the consolidated progress report (UNEP/OzL.Pro/ExCom/91/12).

Phase-out of ODS is expressed in ODP tonnes and of HFCs in CO2-eq tonnes.

From the 11.1 mt phased out in 2021 for HFC-related projects.

Including 167.8 mt of HFC investment projects. Cost-effectiveness in CO2-eq is not included due to the limited number of projects approved.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61).

UNEP/OzL.Pro/ExCom/91/38

UNEP/OzL.Pro/ExCom/91/42

UNEP/OzL.Pro/ExCom/91/49

UNEP/OzL.Pro/ExCom/91/52

UNEP/OzL.Pro/ExCom/91/18

UNEP/OzL.Pro/ExCom/91/21

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.