| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/93/34 7 December 2023 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-third Meeting

Montreal, 15-19 December 2023

Item 9(d) of the provisional agenda

projects recommended for individual consideration

# This document provides summary information on projects and activities submitted to the 93rd meeting that are recommended for individual consideration. Table 1 presents a list of these requests.

Table 1: Requests recommended for individual consideration

| Projects and activities | No. of countries | No. of funding requests | Amount recommended (US $) | Amount in principle (US $) |
| --- | --- | --- | --- | --- |
| Stage II/III of HPMPs | 6 | 14 | 7,300,366 | 17,907,720 |
| Tranches of approved HPMPs | 1 | 5 | 21,479,467 |  |
| Stage I of KIPs | 23 | 54 | 20,372,787 | 51,905,576 |
| HFC-related investment projects | 1 | 3 | 1,250,593 |  |
| Preparation for KIPs and/or investment-related activities | 2 | 2 | 267,500 |  |
| Additional activities to maintain energy efficiency in the servicing sector (decision 89/6) | 1* | 1 | 135,265.00 |  |
| Preparation for a pilot project on energy efficiency | 1 and a global | 2 | 117,700 |  |
| Pilot project on energy efficiency | 11 | 13 | 7,169,581 |  |
| Compliance Assistance Programme (2024 budget) |  | 1 | 11,265,696 |  |
| Core unit costs (2024) |  | 3 | 5,969,740 |  |
| Total |  | 98 | 75,328,695 |  |

* Activities for the country (Mozambique) have been submitted as part of a new stage of its HPMP to this meeting.

Note: Funding amounts include agency support costs.

# Tables 2-5 provide more information on the above-listed projects and activities recommended for individual consideration, including non-investment preparatory activities presented in the work programmes of implementing agencies and in the bilateral cooperation document; and tranche requests under stage II of the HCFC phase-out management plan (HPMP), requests for new stages II and III of HPMPs, requests for stage I of Kigali HFC implementation plans (KIPs) including HFC investment projects submitted as part of the KIPs, and pilot projects related to energy efficiency submitted in line with decision 91/65, as presented in the respective country project proposals.

Table 2: Non- investment activities – preparatory projects

| Country /Region | Project title | IAs | Doc. # | Issue |
| --- | --- | --- | --- | --- |
| Global | Preparation of a pilot project to demonstrate the use of digital monitoring and management tools to enhance energy efficiency and reduce emission of greenhouse gases in the space cooling and cold chain sectors in Colombia, Lebanon, Panama, Sri Lanka, and Trinidad and Tobago | UNDP | 93/35 | Guidance sought from the Executive Committee as the proposal represents a new prospective approach for considering energy efficiency in the context of the Montreal Protocol |
| India | Preparation of a demonstration project for the manufacture of compressors in the mobile air-conditioning manufacturing sector | UNDP | 93/35 | Guidance sought from the Executive Committee on demonstration projects submitted as part of KIPs other than end-user projects submitted in line with decision 92/36 |
| Thailand | Preparation of a KIP (stage I) | World Bank | 93/38 | The country has not ratified the Kigali Amendment |
| Viet Nam | Preparation of a pilot project to maintain and/or enhance energy efficiency in the air-conditioning (AC) sector | World Bank | 93/38 | Guidance sought from the Executive Committee as the project is not submitted in the context of HFC phase-down |

Table 3: HPMP stage and tranche requests

| Country | Stage / Tranche # | Implementing agencies | Doc. # | Para. # | Issue |
| --- | --- | --- | --- | --- | --- |
| Requests for stage II or III of the HPMP |  |  |  |  |  |
| Guinea | Stage II | UNEP/UNIDO | 93/58 |  | All technical and cost issues resolved |
| Lebanon | Stage III | UNDP | 93/64 |  | All technical and cost issues resolved |
| Mozambique | Stage II | UNEP/UNDP | 93/73 |  | All technical and cost issues resolved |
| Philippines (the) | Stage III | UNIDO | 93/82 |  | All technical and cost issues resolved |
| Suriname | Stage II | UNEP/UNIDO | 93/88 |  | All technical and cost issues resolved |
| Viet Nam | Stage III | World Bank | 93/93 | 1-40 | All technical and cost issues resolved |
| Tranche requests under stage II of the HPMP |  |  |  |  |  |
| China – XPS* | Sixth tranche | UNIDO/ Germany | 93/47 | 27-45 | All technical and cost issues resolved |
| China – PU* | Fourth tranche | World Bank | 93/47 | 46-70 | All technical and cost issues resolved |
| China – ICR* | Fifth tranche | UNDP | 93/47 | 71-91 | All technical and cost issues resolved |
| China – Solvent | Sixth tranche | UNDP | 93/47 | 92-113 | All technical and cost issues resolved |
| China – Servicing* | Sixth tranche | UNEP/ Germany/Japan | 93/47 | 114-134 | All technical and cost issues resolved |

*XPS = extruded polystyrene foam sector; PU = polyurethane foam sector; ICR = industrial and commercial refrigeration and air-conditioning sector; Servicing = refrigeration and air-conditioning servicing sector and the national enabling programme

Table 4: KIP stage I requests

| Country | Implementing agencies | Doc. # | Para. # | Issue |  |
| --- | --- | --- | --- | --- | --- |
| KIPs that may not require a presentation by the Secretariat |  |  |  |  |  |
| Albania | UNIDO/UNEP | 93/39 | 18-65 | All technical and cost issues resolved |  |
| Bolivia (Plurinational State of) | UNIDO/UNEP | 93/43 | 29-87 | All technical and cost issues resolved |  |
| Cambodia | UNEP/UNDP | 93/45 |  | All technical and cost issues resolved |  |
| Congo (the) | UNIDO/UNEP | 93/49 |  | All technical and cost issues resolved |  |
| Grenada | UNEP/UNDP | 93/56 | 19-63 | All technical and cost issues resolved |  |
| Kyrgyzstan | UNDP/UNEP | 93/63 | 1-48 | All technical and cost issues resolved |  |
| Malawi | UNEP/UNIDO | 93/67 |  | All technical and cost issues resolved |  |
| Nicaragua | UNIDO | 93/75 | 1-61 | All technical and cost issues resolved |  |
| Niger (the) | UNIDO/UNEP | 93/76 |  | All technical and cost issues resolved |  |
| North Macedonia | UNIDO | 93/78 | 18-79 | All technical and cost issues resolved |  |
| Trinidad and Tobago | UNDP | 93/89 | 20-80 | All technical and cost issues resolved |  |
| Turkmenistan | UNIDO | 93/91 | 1-52 | All technical and cost issues resolved |  |
| KIPs that require a presentation by the Secretariat |  |  |  |  |  |
| Chile | UNDP/UNEP | 93/46 |  | Funding requested for more than 10 per cent reduction from the baseline |  |
| Cuba | UNDP | 93/50 |  | Inclusion of investment projects in the absence of cost guidelines |  |
| Dominican Republic | UNDP/UNEP/ UNIDO | 93/51 |  | Cost calculation for the servicing sector |  |
| Ecuador | UNIDO | 93/52 | 33-98 | Cost calculation for the servicing sector |  |
| Ghana | UNDP/UNEP | 93/55 |  | Low share of HFC consumption in the baseline |  |
| Jordan | UNIDO | 93/62 |  | Inclusion of investment projects in the absence of cost guidelines |  |
| Malaysia | World Bank | 93/68 |  | Inclusion of investment projects in the absence of cost guidelines |  |
| Mexico | UNIDO/UNDP/ UNEP | 93/70 | 1-117 | Inclusion of investment projects in the absence of cost guidelines; cost calculation for the servicing sector |  |
| Panama | UNDP | 93/80 |  | Cost calculation for the servicing sector |  |
| Peru | UNDP | 93/81 |  | Cost calculation for the servicing sector |  |
| Viet Nam | World Bank/UNEP | 93/93 | 41-110 | Inclusion of investment projects in the absence of cost guidelines |  |
| HFC investment projects in India (to be included in stage I of the KIP) (UNDP) |  |  |  |  |  |
| Project title |  |  | Doc. # | Para. # | Issue |
| Conversion from R-407C and R-410A to HFC-32 in the manufacturing of light commercial packaged and ducted AC units at Voltas, Ltd. |  |  | 93/60 | 1-25 | All technical and cost issues resolved |
| Demonstration/conversion from R-404A and R-407C to CO2 trans-critical heat pump technology in the food processing and cold storage refrigeration equipment manufacturing at Mech Air Industries |  |  | 93/60 | 26-46 | Limited impact and sustainability of conversion |
| Conversion of the manufacturing of commercial refrigeration appliances at Rockwell Industries, Ltd. from HFC-134a to propane |  |  | 93/60 | 47-71 | All technical and cost issues resolved - The Secretariat will present this investment project together with the request for technical assistance to enhance the energy efficiency of converted equipment 93/60, para. 72-84 and included in table 5 |

Table 5: Pilot projects related to energy efficiency in the servicing sector (decision 91/65)

| Country | Project title |  |  |  | IA |  | Doc. # | Para. # |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Non-investment projects |  |  |  |  |  |  |  |  |
| Bolivia (Plurinational State of) | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down through provision of equipment and training to 30 trainers on the use of CO2-based technology in medium- and low-temperature applications; and a demonstration project for detecting and preventing leakages in HFC-based commercial refrigeration systems and reinforcing good practices in equipment installation, commissioning, operation, and maintenance in the commercial refrigeration sector |  |  |  | UNIDO |  | 93/43 | 88-102 |
| Ecuador | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down through promoting the coordination between the NOU and energy-efficiency and climate authorities; support to the servicing sector; and support for the introduction or improvement of MEPS and labelling systems, with emphasis on the commercial and industrial RAC systems |  |  |  | UNIDO |  | 93/52 | 99-114 |
| Egypt | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down through upgrading and strengthening three testing laboratories and implementing MEPS and equipment labelling |  |  |  | UNIDO |  | 93/53 |  |
| Kyrgyzstan | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down through the development of MEPS and labelling for RAC equipment up to 3 kW |  |  |  | UNEP |  | 93/63 | 49-66 |
| Mexico | Energy-efficiency strategy for the Kigali HFC implementation plan: Institutional coordination with energy-efficiency authorities, strengthening of MEPS for equipment using alternatives to HFCs, and support provided to the servicing and local assembly sectors |  |  |  | UNIDO |  | 93/70 | 118-138 |
| Nicaragua | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down through provision of equipment and training to 45 trainers on the use of CO2-based technology in medium- and low temperature applications; and a demonstration project for detecting and preventing leakages in HFC-based commercial refrigeration systems and reinforcing good practices in equipment installation, commissioning, operation, and maintenance in the commercial refrigeration sector |  |  |  | UNIDO |  | 93/75 | 62-79 |
| Nigeria | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down through establishing labelling standards for refrigeration appliances, survey of the market, review and updates to MEPS, upgrading a laboratory testing facility and training staff in verification testing, developing a green procurement policy, training for customs officers, and raising awareness |  |  |  | UNIDO |  | 93/77 | 29-53 |
| South Africa | Energy-efficiency strategy for the Kigali HFC implementation plan: Replacement of chillers in public buildings and collection of data to assist in the development of relevant MEPS |  |  |  | UNIDO |  | 93/87 |  |
| Turkmenistan | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down through support for inter-institutional coordination; and the introduction of MEPS, labelling systems, and a National Plan for Energy Efficiency in the RACHP sector |  |  |  | UNIDO |  | 93/91 | 53-72 |
| Investment projects |  |  |  |  |  |  |  |  |
| China | Demonstration project of replacing HFC-134a with R-744 in the field of electric vehicles |  |  |  | UNIDO |  | 93/47 | 135-176 |
| India | Conversion of the manufacturing of commercial refrigeration appliances at Rockwell Industries, Ltd. from HFC-134a to propane: Technical assistance to enhance the energy efficiency of converted equipment |  |  |  | UNDP |  | 93/60 | 72-84 |
| India | Design and development of a pilot-scale energy-efficient rotary compressor and a microchannel heat exchanger compatible with R-290 technology at Godrej & Boyce Mfg., Ltd. in the manufacturing of room air conditioners |  |  |  | Germany |  | 93/60 | 85-117 |

UNEP/OzL.Pro/ExCom/93/1