| 联 合 国 |  | EP |
| --- | --- | --- |
|  | ### 联 合 国 ### 环 境 规 划 署 | Distr. GENERAL UNEP/OzL.Pro/ExCom/92/11 9 May 2023 CHINESE ORIGINAL: ENGLISH |

执行蒙特利尔议定书

多边基金执行委员会

第九十二次会议

2023年5月29日至6月2日，蒙特利尔

临时议程第8(a)项

多边基金2023-2025年综合业务计划最新执行情况

- 导言

# 本文件包含下列部分：

## 第一部分：	2023-2025年业务计划的最新执行情况

## 第二部分：	2021-2023三年期的资源分配情况

第三部分：	建议

## 第一部分：2023-2025年业务计划的最新执行情况

# 在第九十一次会议上，执行委员会核准了多边基金2023-2025年综合业务计划。根据第91/31号决定，秘书处调整了2023-2025年综合业务计划，如表1所示。

表1.多边基金调整后的2023-2025年综合业务计划资源分配情况（美元）*

| 说明 | 2023年 | 2024年 | 2025年 | 共计 |
| --- | --- | --- | --- | --- |
| 氟氯烃活动 |  |  |  |  |
| 核准的氟氯烃淘汰管理计划 | 60,280,861 | 56,111,450 | 43,084,350 | 159,476,661 |
| 氟氯烃淘汰管理计划项目编制 – 第二阶段 | 200,480 | 77,600 | 0 | 278,080 |
| 氟氯烃淘汰管理计划第二阶段 | 2,937,082 | 5,199,804 | 3,462,199 | 11,599,085 |
| 氟氯烃淘汰管理计划第二阶段 – 投资 | 0 | 248,532 | 0 | 248,532 |
| 氟氯烃淘汰管理计划项目编制 – 第三阶段 | 290,100 | 92,750 | 0 | 382,850 |
| 氟氯烃淘汰管理计划第三阶段 | 14,794,713 | 10,344,520 | 20,526,731 | 45,665,964 |
| 氟氯烃淘汰管理计划项目编制 – 第四阶段 | 90,000 | 0 | 0 | 90,000 |
| 氟氯烃淘汰管理计划第四阶段 | 0 | 0 | 2,093,000 | 2,093,000 |
| 氟氯烃淘汰管理计划 – 能效 | 3,258,494 | 2,672,980 | 3,379,420 | 9,310,894 |
| 氟氯烃淘汰管理计划核查** | 588,600 | 588,600 | 588,600 | 1,765,800 |
| 氟氯烃活动小计 | 82,440,330 | 75,336,236 | 73,134,299 | 230,910,865 |
| 氢氟碳化物活动 |  |  |  |  |
| 氢氟碳化物逐步减少的扶持活动 | 53,500 | 160,500 | 0 | 214,000 |
| 基加利氢氟碳化物实施计划 – 项目编制 | 3,945,431 | 2,567,011 | 144,560 | 6,657,002 |
| 基加利氢氟碳化物实施计划 | 27,299,967 | 21,437,607 | 245,413 | 48,982,987 |
| 基加利氢氟碳化物实施计划项目编制 – 投资 | 129,000 | 0 | 0 | 129,000 |
| 基加利氢氟碳化物实施计划 – 投资 | 321,000 | 8,963,616 | 0 | 9,284,616 |
| HFC-23排放控制项目编制 | 43,000 | 0 | 0 | 43,000 |
| HFC-23排放控制 | 0 | 8,000,000 | 0 | 8,000,000 |
| 氢氟碳化物 – 技术援助 | 0 | 678,000 | 0 | 678,000 |
| 氢氟碳化物活动小计 | 31,791,898 | 41,806,734 | 389,973 | 73,988,605 |
| 能效试点项目 |  |  |  |  |
| 能效试点项目 | 20,000,000 | 0 | 0 | 20,000,000 |
| 能效试点项目小计 | 20,000,000 | 0 | 0 | 20,000,000 |
| 标准活动 |  |  |  |  |
| 体制强化 | 27,860,444 | 16,639,896 | 0 | 44,500,341 |
| 履约援助方案 | 11,445,002 | 11,788,350 | 12,142,003 | 35,375,355 |
| 核心单位 | 5,969,740 | 6,011,529 | 6,053,610 | 18,034,878 |
| 秘书处、执行委员会以及监测和评价费用减去加拿大对应费用 | 7,237,326 | 7,202,023 | 6,816,624 | 21,255,973 |
| 财务主任 | 500,000 | 500,000 | 500,000 | 1,500,000 |
| 标准活动小计 | 53,012,512 | 42,141,798 | 25,512,237 | 120,666,547 |
| 总计 | 187,244,740 | 159,284,767 | 99,036,509 | 445,566,017 |
| 澳大利亚 | 0 | 0 | 152,497 | 152,497 |
| 奥地利 | 783,667 | 0 | 0 | 783,667 |
| 法国 | 671,075 | 0 | 0 | 671,075 |
| 德国 | 1,349,869 | 3,705,721 | 1,028,250 | 6,083,840 |
| 日本 | 67,800 | 0 | 0 | 67,800 |
| 开发计划署 | 62,425,117 | 54,216,500 | 29,064,016 | 145,705,634 |
| 环境规划署 | 40,325,066 | 36,674,895 | 22,071,085 | 99,071,046 |
| 工发组织 | 38,767,526 | 29,078,890 | 29,553,746 | 97,400,162 |
| 世界银行 | 14,528,694 | 27,318,138 | 9,261,691 | 51,108,523 |
| 氟氯烃淘汰管理计划核查** | 588,600 | 588,600 | 588,600 | 1,765,800 |
| 能效试点项目 | 20,000,000 | 0 | 0 | 20,000,000 |
| 秘书处、执行委员会以及监测和评价费用减去加拿大对应费用 | 7,237,326 | 7,202,023 | 6,816,624 | 21,255,973 |
| 财务主任 | 500,000 | 500,000 | 500,000 | 1,500,000 |

* 包括适用的机构支助费用。

**低消费量国家编制氟氯烃淘汰管理计划核查报告的供资由执行委员会每年核准。

I.1	2023年业务计划执行情况

# 表2列出了各机构向第九十二次会议提交的文件（截至2023年5月9日），以及2023年业务计划中的项目资金余额。

表2. 2023年综合业务计划，向第九十二次会议提交的项目建议，以及结余（美元）*

| 预算项目 | 业务计划的资金总额 | 向第九十二次会议建议的活动 | 余额 （高于）/低于 |
| --- | --- | --- | --- |
| 双边机构 | 2,872,411 | 687,988 | 2,184,423 |
| 开发计划署 | 62,425,117 | 11,901,104 | 50,524,013 |
| 环境规划署 | 40,325,066 | 6,702,361 | 33,622,705 |
| 工发组织 | 38,767,526 | 8,573,725 | 30,193,802 |
| 世界银行 | 14,528,694 | 2,681,988 | 11,846,706 |
| 氟氯烃淘汰管理计划核查 | 588,600 | 573,900 | 14,700 |
| 能效试点项目 | 20,000,000 | 33,900 | 19,966,100 |
| 小计（机构） | 179,507,414 | 31,154,966 | 148,352,448 |
| 秘书处/执行委员会/监测和评价（不包括加拿大对应费用） | 7,237,326 | 0 | 7,237,326 |
| 财务主任 | 500,000 | 0 | 500,000 |
| 小计（标准费用） | 7,737,326 | 0 | 7,737,326 |
| 共计 | 187,244,740 | 31,154,966 | 156,089,774 |

* 包括核心单位费用。

# 向第九十二次会议建议的项目提案金额为31,154,966美元，比2023年业务计划中的金额高1,508,497美元，包括与未列入2023年业务计划的项目提案有关的1,544,028美元。

# 提交给第九十二次会议的氢氟碳化物相关活动金额为 3,822,128 美元，其中 751,182 美元与未列入 2023 年业务计划的项目提案有关。本文件附件一列出了双边和执行机构向第九十二次会议提交的氢氟碳化物相关项目。

# I.2	预先承付款项

# 如表3所示，假设提交给第九十二次会议的多年期协定的供资申请原则上得到核准，则2023年至2031年期间多年期协定的现有预先承付款项总额为247.81亿美元。

表3. 预先承付款项（2023–2031年）（千美元）

| 说明 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 共计 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 原则上核准 | 60,788 | 56,111 | 43,084 | 42,503 | 10,189 | 1,429 | 4,733 | 6,410 | 57 | 225,305 |
| 提交第九十二次会议 | 6,871 | 0 | 6,257 | 2,346 | 0 | 4,741 | 0 | 2,291 | 0 | 22,506 |
| 共计 | 67,659 | 56,111 | 49,342 | 44,850 | 10,189 | 6,170 | 4,733 | 8,701 | 57 | 247,811 |

# 第二部分：2021-2023三年期的资源分配情况

# 《蒙特利尔议定书》缔约方为2021-2023年三年期核准的资源金额为540,000,000美元。考虑到2021年和2022年的核准额以及2023年业务计划的187,244,740美元，2023年底的可用资源为141,594,808美元。此外，缔约方第五次特别会议还注意到，2018-2020年三年期间应向多边基金提供的2.46亿美元的剩余资金将在2023年之后用于支持《蒙特利尔议定书》的执行（第Ex.V/1号决定）。因此，2024-2026年三年期的可用资源总额为387,594,808美元。

表4. 2021-2023三年期的资源分配情况（美元）

| 说明 | 金额（美元） |
| --- | --- |
| 2021–2023年三年期总预算 | 540,000,000 |
| 2021年核准额包括秘书处/执行委员会/监测和评价/财务主任 | (104,132,796) |
| 2022年核准额包括秘书处/执行委员会/监测和评价/财务主任 | (107,027,656) |
| 2023年业务计划 | (179,507,414) |
| 2023年秘书处/执行委员会/监测和评价/财务主任 | (7,737,326) |
| 2023年底可用资源 | 141,594,808 |
| 将在2023年后使用的2018–2020三年期结转金额 | 246,000,000 |
| 2024–2026三年期可用资源总额 | 387,594,808 |

# 第三部分：建议

# 谨建议执行委员会注意到：

## UNEP/OzL.Pro/ExCom/92/11 号文件所载多边基金 2023-2025 年综合业务计划的最新执行情况；以及

## 向第九十二次会议申请的活动总金额为31,154,966美元（包括用于氢氟碳化物相关活动的3,822,128美元），其中1,544,028美元与未列入2023年业务计划的项目提案有关。

Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 92ND MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Burundi | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan | 119,000 | 15,470 |
| Burundi | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan | 51,000 | 3,570 |
| Cameroon | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 355,500 | 24,885 |
| Costa Rica | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 1,571,267 | 109,989 |
| Guatemala | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan | 51,000 | 6,630 |
| Guatemala | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan | 119,000 | 8,330 |
| India | Germany | PRP | KIP | Preparation for a pilot project to maintain and/or enhance energy efficiency | 30,000 | 3,900 |
| India | UNDP | PRP | KIP | Preparation of a KIP investment project in the air conditioner (AC) manufacturing sector for Voltas Limited | 30,000 | 2,100 |
| India | UNDP | PRP | KIP | Preparation of a KIP investment project in the refrigeration manufacturing sector for Mech Air Industries | 30,000 | 2,100 |
| India | UNDP | PRP | KIP | Preparation of a KIP investment project in the refrigeration manufacturing sector for Rockwell Industries | 30,000 | 2,100 |
| Indonesia | IBRD | PRP | KIP | Preparation of a Kigali HFC implementation plan | 220,000 | 15,400 |
| Mexico | UNDP | INV | REF | Conversion of the manufacturing of commercial refrigerators from HFC-134a to propane (R-290) at the enterprise Friocima | 143,850 | 12,947 |
| Mexico | UNIDO | INV | PHA | Destruction of emissions of HFC-23 generated in the production of HCFC-22 in Quimobasicos (second tranche) | 387,561 | 27,129 |
| Morocco | UNIDO | PRP | KIP | Preparation of a KIP investment project in the refrigeration manufacturing sector for MANAR | 30,000 | 2,100 |
| Venezuela (Bolivarian Republic of) | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan | 220,000 | 15,400 |
| Viet Nam | IBRD | PRP | KIP | Preparation of a KIP investment project in the commercial refrigeration sector for Sanaky | 30,000 | 2,100 |
| Viet Nam | IBRD | PRP | KIP | Preparation of a KIP investment project in the domestic refrigeration sector for Aqua Electrical Appliances, Darling Electronics, and Hoa Phat Refrigeration Engineering | 80,000 | 5,600 |
| Viet Nam | IBRD | PRP | KIP | Preparation of a KIP investment project in the industrial refrigeration sector for Quang Thang Refrigeration | 30,000 | 2,100 |
| Viet Nam | IBRD | PRP | KIP | Preparation of a KIP investment project in the mobile air-conditioning sector for Thaco Auto | 30,000 | 2,100 |

UNEP/OzL.Pro/ExCom/92/1号文件

印度尼西亚（澳大利亚）和乌拉圭（工发组织）的氟氯烃淘汰管理计划第三阶段；摩洛哥（工发组织）和越南（四个项目）（世界银行）的五个投资项目的基加利氢氟碳化物实施计划编制；墨西哥（开发计划署）的一个氢氟碳化物投资项目；布基纳法索（德国）根据第89/6号决定的一个能效项目；以及喀麦隆（工发组织）的基加利氢氟碳化物实施计划第一阶段。