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多边基金2023-2025年综合业务计划最新执行情况 


导言

本文件包含下列部分：
第一部分：	2023-2025年业务计划的最新执行情况

第二部分：	2021-2023三年期的资源分配情况

第三部分：	建议

第一部分：2023-2025年业务计划的最新执行情况

在第九十一次会议上，执行委员会核准了多边基金2023-2025年综合业务计划。根据第91/31号决定，秘书处调整了2023-2025年综合业务计划，如表1所示。


表1.多边基金调整后的2023-2025年综合业务计划资源分配情况（美元）*
	说明
	2023年
	2024年
	2025年
	共计

	氟氯烃活动
	 
	 
	 
	 

	核准的氟氯烃淘汰管理计划
	60,280,861
	56,111,450
	43,084,350
	159,476,661

	氟氯烃淘汰管理计划项目编制 – 第二阶段
	200,480
	77,600
	0
	278,080

	氟氯烃淘汰管理计划第二阶段
	2,937,082
	5,199,804
	3,462,199
	11,599,085

	氟氯烃淘汰管理计划第二阶段 – 投资
	0
	248,532
	0
	248,532

	氟氯烃淘汰管理计划项目编制 – 第三阶段
	290,100
	92,750
	0
	382,850

	氟氯烃淘汰管理计划第三阶段
	14,794,713
	10,344,520
	20,526,731
	45,665,964

	氟氯烃淘汰管理计划项目编制 – 第四阶段
	90,000
	0
	0
	90,000

	氟氯烃淘汰管理计划第四阶段
	0
	0
	2,093,000
	2,093,000

	氟氯烃淘汰管理计划 – 能效
	3,258,494
	2,672,980
	3,379,420
	9,310,894

	氟氯烃淘汰管理计划核查**
	588,600
	588,600
	588,600
	1,765,800

	氟氯烃活动小计
	82,440,330
	75,336,236
	73,134,299
	230,910,865

	氢氟碳化物活动
	 
	 
	 
	 

	氢氟碳化物逐步减少的扶持活动
	53,500
	160,500
	0
	214,000

	基加利氢氟碳化物实施计划 – 项目编制
	3,945,431
	2,567,011
	144,560
	6,657,002

	基加利氢氟碳化物实施计划
	27,299,967
	21,437,607
	245,413
	48,982,987

	基加利氢氟碳化物实施计划项目编制 – 投资
	129,000
	0
	0
	129,000

	基加利氢氟碳化物实施计划 – 投资
	321,000
	8,963,616
	0
	9,284,616

	HFC-23排放控制项目编制
	43,000
	0
	0
	43,000

	HFC-23排放控制
	0
	8,000,000
	0
	8,000,000

	氢氟碳化物 – 技术援助
	0
	678,000
	0
	678,000

	氢氟碳化物活动小计
	31,791,898
	41,806,734
	389,973
	73,988,605

	能效试点项目
	 
	 
	 
	 

	能效试点项目
	20,000,000
	0
	0
	20,000,000

	能效试点项目小计
	20,000,000
	0
	0
	20,000,000

	标准活动
	 
	 
	 
	 

	体制强化
	27,860,444
	16,639,896
	0
	44,500,341

	履约援助方案
	11,445,002
	11,788,350
	12,142,003
	35,375,355

	核心单位
	5,969,740
	6,011,529
	6,053,610
	18,034,878

	秘书处、执行委员会以及监测和评价费用减去加拿大对应费用
	7,237,326
	7,202,023
	6,816,624
	21,255,973

	财务主任
	500,000
	500,000
	500,000
	1,500,000

	标准活动小计
	53,012,512
	42,141,798
	25,512,237
	120,666,547

	总计
	187,244,740
	159,284,767
	99,036,509
	445,566,017

	澳大利亚
	0
	0
	152,497
	152,497

	奥地利
	783,667
	0
	0
	783,667

	法国
	671,075
	0
	0
	671,075

	德国
	1,349,869
	3,705,721
	1,028,250
	6,083,840

	日本
	67,800
	0
	0
	67,800

	开发计划署
	62,425,117
	54,216,500
	29,064,016
	145,705,634

	环境规划署
	40,325,066
	36,674,895
	22,071,085
	99,071,046

	工发组织
	38,767,526
	29,078,890
	29,553,746
	97,400,162

	世界银行
	14,528,694
	27,318,138
	9,261,691
	51,108,523

	氟氯烃淘汰管理计划核查**
	588,600
	588,600
	588,600
	1,765,800

	能效试点项目
	20,000,000
	0
	0
	20,000,000

	秘书处、执行委员会以及监测和评价费用减去加拿大对应费用
	7,237,326
	7,202,023
	6,816,624
	21,255,973

	财务主任
	500,000
	500,000
	500,000
	1,500,000


* 包括适用的机构支助费用。
**低消费量国家编制氟氯烃淘汰管理计划核查报告的供资由执行委员会每年核准。

I.1	2023年业务计划执行情况

表2列出了各机构向第九十二次会议提交的文件（截至2023年5月9日），以及2023年业务计划中的项目资金余额。
表2. 2023年综合业务计划，向第九十二次会议提交的项目建议，以及结余（美元）*
	预算项目
	业务计划的资金总额
	向第九十二次会议建议的活动
	余额
（高于）/低于

	双边机构
	2,872,411
	687,988
	2,184,423

	开发计划署
	62,425,117
	11,901,104
	50,524,013

	环境规划署
	40,325,066
	6,702,361
	33,622,705

	工发组织
	38,767,526
	8,573,725
	30,193,802

	世界银行
	14,528,694
	2,681,988
	11,846,706

	氟氯烃淘汰管理计划核查
	588,600
	573,900
	14,700

	能效试点项目
	20,000,000
	33,900
	19,966,100

	小计（机构）
	179,507,414
	31,154,966
	148,352,448

	秘书处/执行委员会/监测和评价（不包括加拿大对应费用）
	7,237,326
	0
	7,237,326

	财务主任
	500,000
	0
	500,000

	小计（标准费用）
	7,737,326
	0
	7,737,326

	共计
	187,244,740
	[bookmark: _Hlk134542832]31,154,966
	156,089,774


* 包括核心单位费用。

向第九十二次会议建议的项目提案金额为31,154,966美元，比2023年业务计划中的金额高1,508,497美元，包括与未列入2023年业务计划的项目提案有关的1,544,028美元[footnoteRef:2]。  [2: 印度尼西亚（澳大利亚）和乌拉圭（工发组织）的氟氯烃淘汰管理计划第三阶段；摩洛哥（工发组织）和越南（四个项目）（世界银行）的五个投资项目的基加利氢氟碳化物实施计划编制；墨西哥（开发计划署）的一个氢氟碳化物投资项目；布基纳法索（德国）根据第89/6号决定的一个能效项目；以及喀麦隆（工发组织）的基加利氢氟碳化物实施计划第一阶段。 ] 

提交给第九十二次会议的氢氟碳化物相关活动金额为 3,822,128 美元，其中 751,182 美元与未列入 2023 年业务计划的项目提案有关。本文件附件一列出了双边和执行机构向第九十二次会议提交的氢氟碳化物相关项目。 
I.2	预先承付款项
如表3所示，假设提交给第九十二次会议的多年期协定的供资申请原则上得到核准，则2023年至2031年期间多年期协定的现有预先承付款项总额为247.81亿美元。
表3. 预先承付款项（2023–2031年）（千美元）
	说明
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	2031
	共计

	原则上核准
	60,788
	56,111
	43,084
	42,503
	10,189
	1,429
	4,733
	6,410
	57
	225,305

	提交第九十二次会议
	6,871
	0
	6,257
	2,346
	0
	4,741
	0
	2,291
	0
	22,506

	共计
	67,659
	56,111
	49,342
	44,850
	10,189
	6,170
	4,733
	8,701
	57
	247,811


第二部分：2021-2023三年期的资源分配情况

《蒙特利尔议定书》缔约方为2021-2023年三年期核准的资源金额为540,000,000美元。考虑到2021年和2022年的核准额以及2023年业务计划的187,244,740美元，2023年底的可用资源为141,594,808美元。此外，缔约方第五次特别会议还注意到，2018-2020年三年期间应向多边基金提供的2.46亿美元的剩余资金将在2023年之后用于支持《蒙特利尔议定书》的执行（第Ex.V/1号决定）。因此，2024-2026年三年期的可用资源总额为387,594,808美元。
表4. 2021-2023三年期的资源分配情况（美元）
	说明
	金额（美元）

	2021–2023年三年期总预算
	540,000,000

	2021年核准额包括秘书处/执行委员会/监测和评价/财务主任
	(104,132,796)

	2022年核准额包括秘书处/执行委员会/监测和评价/财务主任
	(107,027,656)

	2023年业务计划
	(179,507,414)

	2023年秘书处/执行委员会/监测和评价/财务主任
	(7,737,326)

	2023年底可用资源
	141,594,808

	将在2023年后使用的2018–2020三年期结转金额 
	246,000,000

	2024–2026三年期可用资源总额
	387,594,808



第三部分：建议 

谨建议执行委员会注意到：
UNEP/OzL.Pro/ExCom/92/11 号文件所载多边基金 2023-2025 年综合业务计划的最新执行情况；以及
向第九十二次会议申请的活动总金额为31,154,966美元（包括用于氢氟碳化物相关活动的3,822,128美元），其中1,544,028美元与未列入2023年业务计划的项目提案有关。
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执行蒙特利尔议定书多边基金执行委员会的会前文件不妨碍文件印发后执行委员会可能作出的任何决定。
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Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 92ND MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Burundi
	UNEP
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan
	119,000
	15,470

	Burundi
	UNIDO
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan
	51,000
	3,570

	Cameroon
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	355,500
	24,885

	Costa Rica
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	1,571,267
	109,989

	Guatemala
	UNEP
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan
	51,000
	6,630

	Guatemala
	UNIDO
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan
	119,000
	8,330

	India
	Germany
	PRP
	KIP
	Preparation for a pilot project to maintain and/or enhance energy efficiency
	30,000
	3,900

	India
	UNDP
	PRP
	KIP
	Preparation of a KIP investment project in the air conditioner (AC) manufacturing sector for Voltas Limited
	30,000
	2,100

	India
	UNDP
	PRP
	KIP
	Preparation of a KIP investment project in the refrigeration manufacturing sector for Mech Air Industries
	30,000
	2,100

	India
	UNDP
	PRP
	KIP
	Preparation of a KIP investment project in the refrigeration manufacturing sector for Rockwell Industries
	30,000
	2,100

	Indonesia
	IBRD
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan
	220,000
	15,400

	Mexico
	UNDP
	INV
	REF
	Conversion of the manufacturing of commercial refrigerators from HFC-134a to propane (R-290) at the enterprise Friocima
	143,850
	12,947

	Mexico
	UNIDO
	INV
	PHA
	Destruction of emissions of HFC‑23 generated in the production of HCFC-22 in Quimobasicos (second tranche)
	387,561
	27,129

	Morocco
	UNIDO
	PRP
	KIP
	Preparation of a KIP investment project in the refrigeration manufacturing sector for MANAR
	30,000
	2,100

	Venezuela (Bolivarian Republic of)
	UNIDO
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan
	220,000
	15,400

	Viet Nam
	IBRD
	PRP
	KIP
	Preparation of a KIP investment project in the commercial refrigeration sector for Sanaky
	30,000
	2,100

	Viet Nam
	IBRD
	PRP
	KIP
	Preparation of a KIP investment project in the domestic refrigeration sector for Aqua Electrical Appliances, Darling Electronics, and Hoa Phat Refrigeration Engineering
	80,000
	5,600

	Viet Nam
	IBRD
	PRP
	KIP
	Preparation of a KIP investment project in the industrial refrigeration sector for Quang Thang Refrigeration
	30,000
	2,100

	Viet Nam
	IBRD
	PRP
	KIP
	Preparation of a KIP investment project in the mobile air‑conditioning sector for Thaco Auto
	30,000
	2,100
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