| ### NACIONES UNIDAS |  | EP |
| --- | --- | --- |
|  | Programa de las Naciones Unidas para el Medio Ambiente | Distr. GENERAL UNEP/OzL.Pro/ExCom/97/4 6 de noviembre de 2025 ESPAÑOL ORIGINAL: INGLÉS |

COMITÉ EJECUTIVO DEL
FONDO MULTILATERAL PARA LA
APLICACIÓN DEL PROTOCOLO DE MONTREAL
Nonagésima séptima reunión

Montreal, 1-5 de diciembre de 2025

Punto 4 b) del orden del día provisional

# INFORME SOBRE SALDOS Y DISPONIBILIDAD DE RECURSOS

# Introducción

# El presente documento resume los ajustes financieros indicados por los organismos bilaterales y de ejecución, según lo acordado por la Secretaría. Incluye datos estadísticos de todos los proyectos con saldos que se han retenido durante más de 12 meses después de la terminación del proyecto, de conformidad con lo estipulado en las decisiones 28/7 y 56/2 c). Se ocupa de los saldos que habrán de devolverse de los proyectos como seguimiento a las decisiones pertinentes (mencionados como proyectos “por decisión” en el presente documento) y de proyectos transferidos. Indica también el nivel de recursos de que dispone el Comité Ejecutivo en efectivo según lo registrado en el documento sobre la situación de las contribuciones y los desembolsos, como se estipula en la decisión 41/92 b), y presenta una recomendación. Las cantidades que obran en poder de los organismos de ejecución para los proyectos terminados y proyectos de contribuciones voluntarias adicionales se incluyen en el anexo I y el anexo II, respectivamente. En el anexo III se presentan los fondos reintegrados por los organismos bilaterales y de ejecución de proyectos terminados y por decisión.

# Fondos a reintegrar a la 97ª reunión

# Los fondos totales que han de devolver los organismos bilaterales y de ejecución ascienden a USD 5.264.171 (es decir, USD 5.197.904 por parte de los organismos de ejecución y USD 66.267 por parte de los organismos bilaterales) provenientes de proyectos terminados y por decisión, tal y como se indica en los cuadros 1 y 2.

# Cuadro 1. Fondos que han de reintegrar los organismos de ejecución a la 97ª reunión (USD)

| Organismo | Costo del proyecto | Gastos de apoyo | Costo total |
| --- | --- | --- | --- |
| PNUD | 2.829.839 | 195.450 | 3.025.289 |
| PNUMA* | 1.452.490 | 132.618 | 1.585.108 |
| ONUDI | 282.284 | 21.088 | 303.372 |
| Banco Mundial* | 255.995 | 28.140 | 284.135 |
| Total | 4.820.608 | 377.296 | 5.197.904 |

*Incluye los fondos reintegrados por el PNUMA, por un total de USD 124.300, junto con los gastos de apoyo, por valor de USD 16.159, y el reintegro del Banco Mundial, por valor de USD 77.483, más los gastos de apoyo, por valor de USD 5.424.  El total de las sumas que se transferirán a la ONUDI se indica en el cuadro 4.

| Organismo | Costo del proyecto | Gastos de apoyo | Total |
| --- | --- | --- | --- |
| Alemania | 58.643 | 7.624 | 66.267 |

Cuadro 2. Fondos que ha de reintegrar un organismo bilateral a la 97ª reunión (USD)

# Fondos en poder de los organismos de ejecución

# El total de fondos en poder de los organismos de ejecución asciende a USD 6.994.293, tal y como se muestra en el cuadro 3.

Cuadro 3. Saldos de proyectos terminados y proyectos financiados con contribuciones voluntarias adicionales en poder de los organismos de ejecución (incluidos gastos de apoyo)

| Año de terminación | PNUD |  | ONUDI |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Cantidad | USD | Cantidad | USD | Cantidad | USD |
| Proyectos terminados hace más de dos años |  |  |  |  |  |  |
| 2021 | 0 | 0 | 1 | 33.422 | 1 | 33.422 |
| 2022 | 5 | 198.729 | 3 | 84.045 | 8 | 282.774 |
| Del 1 de ene. Al 31 oct. 2023 | 5 | 106.656 | 1 | 8.485 | 6 | 115.141 |
| Subtotal | 10 | 305.385 | 5 | 125.952 | 15 | 431.337 |
| Proyectos terminados hace menos de dos años |  |  |  |  |  |  |
| Del 1 de nov. al 31 de dic. 2023 | 12 | 822.651 | 8 | 1.199.261 | 20 | 2.021.912 |
| 2024 | 36 | 3.701.642 | 28 | 830.660 | 64 | 4.532.302 |
| Subtotal | 48 | 4.524.293 | 36 | 2.029.921 | 84 | 6.554.214 |
| Total | 58 | 4.829.678 | 41 | 2.155.873 | 99 | 6.985.551 |
| Proyecto financiado con contribuciones voluntarias adicionales |  |  |  |  |  |  |
|  | 1 | 8.742 |  |  | 1 | 8.742 |
| Total general | 59 | 4.838.420 | 41 | 2.155.873 | 100 | 6.994.293 |

# Transferencia de proyectos

# El Gobierno de Armenia ha solicitado la transferencia de fondos del PNUMA a la ONUDI para el plan de gestión para la eliminación de HCFC (PGEH) (etapa III, primer tramo) y el plan de aplicación de la Enmienda de Kigali relativa a los HFC (PAK) (etapa I, primer tramo).

# El Gobierno de Guatemala ha solicitado la transferencia de fondos del PNUMA a la ONUDI para la renovación del proyecto de fortalecimiento institucional (etapa X: 6/2024-5/2027).

# Además, el Gobierno de Jordania ha solicitado la transferencia del Banco Mundial a la ONUDI de los saldos restantes de los fondos para la prórroga del proyecto de fortalecimiento institucional (etapa XIII: 1/2019-12/2020).

# En el cuadro 4 figura información detallada sobre los saldos que se han de transferir. El Comité Ejecutivo podrá considerar oportuno aprobar dichas solicitudes.

Cuadro 4. Saldos de proyectos a transferir para proyectos en Armenia, Guatemala y Jordania

| Título del proyecto | N.º de proyecto | Reintegro |  |  | Transferencia |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Al Fondo Multilateral |  |  | Al organismo |  |  |
|  |  | De | Saldo | GAP | A | Saldo | GAP |
| Plan de aplicación de la Enmienda de Kigali relativa a los HFC (etapa I, primer tramo) | ARM/KIP/94/TAS/32 | PNUMA | 66.000 | 8.580 | ONUDI | 66.000 | 8.580 |
| Plan de gestión para la eliminación de HCFC (etapa III, primer tramo) | ARM/PHA/96/TAS/34 | PNUMA | 58.300 | 7.579 | ONUDI | 58.300 | 4.081 |
| Renovación del proyecto de fortalecimiento institucional (etapa X: 6/2024-5-2027) | GUA/SEV/94/INS/68 | PNUMA | 330.670 | 0 | ONUDI | 330.670 | 23.147 |
| Prórroga del proyecto de fortalecimiento institucional (etapa XIII: 1/2019-12/2020) | JOR/SEV/82/INS/105 | Banco Mundial | 77.483 | 5.424 | ONUDI | 77.483 | 5.424 |
| TOTAL |  |  | 532.453 | 21.583 |  | 532.453 | 41.232 |

Disponibilidad de recursos

# Para el trienio 2024-2026, las Partes del Fondo Multilateral aprobaron un presupuesto de USD 965.000.000 (decisión XXXV/1). A fecha 21 de octubre de 2025, el documento Situación de las contribuciones y los desembolsos muestra que el saldo disponible asciende a USD 642.928.645. El saldo total que los organismos bilaterales y de ejecución reintegran a la 97ª reunión asciende a la suma de USD 4.974.538, excluyendo USD 223.366 que se transferirán a la ONUDI. En consecuencia, el nivel total de recursos disponibles para aprobación en la 97ª reunión asciende a la suma de USD 647.903.183.

# Observaciones de la Secretaría

# La Secretaría recordó a los organismos de ejecución que los saldos de los proyectos terminados hace un año o más, así como los proyectos “por decisión” y los proyectos financiados con contribuciones voluntarias adicionales deberían reintegrarse sin demora al Fondo Multilateral.

# Teniendo en cuenta que el nivel total de financiación para los proyectos y actividades presentados tras su revisión en la 97ª reunión asciende a USD 108.014.129, se dispone de recursos suficientes para las aprobaciones en la 97ª reunión.

Recomendación

# El Comité Ejecutivo podrá estimar oportuno:

## a)	Tomar nota de lo siguiente:

### El informe sobre saldos y disponibilidad de recursos que figura en el documento UNEP/OzL.Pro/ExCom/97/4;

### Que el volumen neto de fondos que los organismos de ejecución reintegran a la 97ª reunión asciende a un total de USD 4.974.538, de los cuales USD 2.829.839, más gastos de apoyo de USD 195.450 que reintegra el PNUD; USD 1.328.190, más gastos de apoyo de USD 116.459 que reintegra el PNUMA; USD 282.284, más gastos de apoyo de USD 21.088 que reintegra la ONUDI, y USD 178.512, más gastos de apoyo de USD 22.716 que reintegra el Banco Mundial;

### Que el PNUD mantenía a su haber saldos de USD 305.385, incluidos gastos de apoyo, por concepto de diez proyectos terminados hace más de dos años, y de USD 8.742, incluidos gastos de apoyo, por concepto de un «proyecto financiado con cargo a las contribuciones voluntarias adicionales»;

### Que la ONUDI mantenía a su haber saldos de USD 125.952, incluidos gastos de apoyo, por concepto de cinco proyectos terminados hace más de dos años;

### Que el PNUMA reintegra a la 97ª reunión los saldos de los proyectos para Armenia por un importe de USD 124.300, más gastos de apoyo por valor de USD 16.159, que consisten en:

### USD 58.300, más gastos de apoyo de USD 7.579, correspondientes al plan de gestión para la eliminación de HCFC (etapa III, primer tramo) (ARM/PHA/96/TAS/34);

### USD 66.000, más gastos de apoyo de USD 8.580, correspondientes  al plan de aplicación de la Enmienda de Kigali relativa a los HFC (etapa I, primer tramo) (ARM/KIP/94/TAS/32);

### Que el Banco Mundial reintegra a la 97ª reunión el saldo de la prórroga del proyecto de fortalecimiento institucional (etapa XIII: 1/2019-12/2020) por un importe de USD 77.483, más gastos de apoyo por valor de USD 5.424;

### Que el Gobierno de Alemania reintegra USD 66.267, incluidos gastos de apoyo para dos proyectos terminados;

## b)	Solicitar al PNUD y a la ONUDI:

### Proceder al desembolso o cancelación de los fondos comprometidos que no se precisaron para proyectos terminados y reintegrar los saldos respectivos a la 98ª reunión;

### Proceder al desembolso o cancelación de los fondos comprometidos para proyectos terminados hace más de dos años y reintegrar los saldos respectivos a la 98ª reunión;

## c)	Solicitar al PNUD que proceda al desembolso o reintegro a la 98ª reunión de los saldos  del proyecto financiado por contribuciones voluntarias adicionales;

## d)	Solicitar a la Tesorería:

### Descontar de las futuras aprobaciones del PNUMA en la 97ª reunión, un total de USD 330.670 que se habían asignado para la renovación del proyecto de fortalecimiento institucional (etapa X: 6/2024-5-2027) (GUA/SEV/94/INS/68);

### En la 97ª reunión, transferir a la ONUDI los fondos reintegrados o descontados para los proyectos mencionados en los incisos a) v), a) vi) y d) i) para su ejecución, por un importe de USD 532.453, más gastos de apoyo por valor de USD 41.232, que consisten en:

### USD 58.300, más gastos de apoyo de USD 4.081, para el plan de gestión para la eliminación de HCFC en Armenia (etapa III, primer tramo) (ARM/PHA/96/TAS/34);

### USD 66.000, más gastos de apoyo de USD 8.580, para el plan de aplicación de la Enmienda de Kigali relativa a los HFC (etapa I, primer tramo) (ARM/KIP/94/TAS/32);

### USD 330.670, más gastos de apoyo de USD 23.147 para la renovación del proyecto de fortalecimiento institucional (etapa X: 6/2024-5-2027) (GUA/SEV/94/INS/68); y

### USD 77.483, más gastos de apoyo de USD 5.424 para la prórroga del proyecto de fortalecimiento institucional (etapa XIII: 1/2019-12/2020) (JOR/SEV/82/INS/105).

AnnexI

COMMITTEDANDNOT-COMMITTEDBALANCESHELDBYIMPLEMENTINGANDBILATERALAGENCIESFORCOMPLETEDPROJECTS

| Code | Projecttitle | Datecompleted(Actual) | Approvedfundingplusadjustmentsasof 31Dec2024 (US$) | Fundsdisbursedasof 97thmeeting(US$) | Balancescommittedasper 97thmeeting(US$) | Balancesnot-committedasper 97thmeeting(US$) | Supportcostonbalancescommittedandnotcommittedasper 97thmeeting(US$) | Whyanybalancescouldnotbereturned? | Whentheycouldbereturned? | Projectsubjecttodecision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| ANG/PHA/79/INV/19 | HCFC phase-out management plan (stage II, first tranche) | Aug-22 | 450,000 | 403,483 | 46,517 |  | 3,256 |  |  |  |
| BGD/PHA/90/INV/59 | HCFC phase-out management plan (stage II, second tranche) (air-conditioning sector) | Dec-24 | 1,967,866 | 1,678,655 | 289,211 |  | 20,245 |  |  |  |
| BZE/PHA/87/INV/40 | HCFC phase-out management plan (stage II, first tranche) | Dec-24 | 73,854 | 41,316 | 32,538 |  | 2,928 |  |  |  |
| COL/SEV/88/INS/115 | Extension of institutional strengthening project (phase XIII: 12/2021-11/2023) | Dec-23 | 352,768 | 340,514 | 12,254 |  | 858 |  |  |  |
| COS/KIP/87/PRP/63 | Preparation of Kigali HFC implementation plan | Dec-24 | 170,000 | 163,390 | 6,610 |  | 463 |  |  |  |
| COS/PHA/91/TAS/66 | Verification report on the implementation of stage II of the HCFC phase-out management plan | Dec-24 | 30,000 | 26,159 | 3,841 |  | 346 |  |  |  |
| CUB/KIP/87/PRP/65 | Preparation of Kigali HFC implementation plan | Aug-24 | 170,000 | 154,279 | 15,721 |  | 1,100 |  |  |  |
| DOM/KIP/87/PRP/73 | Preparation of Kigali HFC implementation plan | Aug-24 | 190,000 | 174,370 | 15,630 |  | 1,094 |  |  |  |
| EGY/PHA/79/TAS/132 | HCFC phase-out management plan (stage II, first tranche) (project management and monitoring) | Dec-22 | 75,000 | 39,629 | 35,371 |  | 2,476 |  |  |  |
| EGY/PHA/84/INV/144 | HCFC phase-out management plan (stage II, second tranche) (extruded polystyrene foam sector) | Dec-23 | 1,761,750 | 1,611,791 | 149,959 |  | 10,497 |  |  |  |
| ELS/PHA/87/INV/43 | HCFC phase-out management plan (stage II, first tranche) | Dec-24 | 169,000 | 66,702 | 102,298 |  | 7,161 |  |  |  |
| GHA/KIP/87/PRP/51 | Preparation of Kigali HFC implementation plan | Aug-23 | 130,000 | 100,875 | 29,125 |  | 2,039 |  |  |  |
| GHA/PHA/87/INV/50 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 459,820 | 451,580 | 8,240 |  | 577 |  |  |  |
| GRN/KIP/88/PRP/28 | Preparation of Kigali HFC implementation plan | Dec-24 | 40,000 | 14,163 | 25,837 |  | 1,809 |  |  |  |
| HAI/PHA/91/PRP/26 | Preparation of HCFC phase-out management plan (stage II) (Overarching) | Dec-24 | 30,000 | 22,767 | 7,233 |  | 506 |  |  |  |
| HAI/SEV/90/INS/25 | Extension of the institutional strengthening project (phase V: 7/2022-6/2024) | Dec-24 | 128,000 | 112,274 | 15,726 |  | 1,101 |  |  |  |
| IDS/PHA/81/INV/213 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | Dec-24 | 753,500 | 158,983 | 594,517 |  | 41,616 |  |  |  |
| IDS/PHA/87/PRP/216 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | Dec-23 | 90,000 | 85,929 | 4,071 |  | 285 |  |  |  |
| IDS/PHA/88/INV/217 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) | Dec-24 | 627,086 | 0 | 627,086 |  | 43,896 |  |  |  |
| IDS/PHA/92/INV/220 | HCFC phase-out management plan (stage II, fourth tranche) | Dec-24 | 433,300 | 0 | 433,300 |  | 30,331 |  |  |  |
| IND/KIP/92/PRP/505 | Preparation of a KIP investment project in the refrigeration manufacturing sector for Mech Air Industries | Dec-24 | 30,000 | 1,501 | 28,499 |  | 1,995 |  |  |  |
| IND/PHA/86/TAS/482 | HCFC phase-out management plan (stage II, third tranche) (project management and monitoring) | Dec-24 | 800,000 | 0 | 800,000 |  | 56,000 |  |  |  |
| IRA/PHA/86/INV/243 | HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration sector) | Dec-24 | 576,090 | 551,597 | 24,493 |  | 1,714 |  |  |  |
| IRA/PHA/90/INV/262 | HCFC phase-out management plan (stage II, fourth tranche) (PMU) | Dec-23 | 92,000 | 69,877 | 22,123 |  | 1,549 |  |  |  |
| IRA/PHA/92/INV/264 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | Dec-23 | 93,017 | 0 | 93,017 |  | 6,511 |  |  |  |
| IRA/PHA/92/INV/265 | HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration sector) | Dec-23 | 145,255 | 0 | 145,255 |  | 10,168 |  |  |  |
| IRA/SEV/86/INS/249 | Extension of the institutional strengthening project (phase XIII: 4/2021-3/2023) | May-23 | 222,094 | 178,036 | 44,058 |  | 3,084 |  |  |  |
| KAM/KIP/88/PRP/40 | Preparation of Kigali HFC implementation plan | Dec-23 | 35,000 | 24,973 | 10,027 |  | 702 |  |  |  |
| KAM/PHA/83/INV/36 | HCFC phase-out management plan (fourth tranche) | Dec-24 | 150,000 | 144,216 | 5,784 |  | 434 |  |  |  |
| LAO/KIP/87/PRP/39 | Preparation of Kigali HFC implementation plan | Dec-24 | 35,000 | 34,703 | 297 |  | 21 |  |  |  |
| LAO/PHA/86/INV/38 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 107,000 | 88,847 | 18,153 |  | 1,634 |  |  |  |
| LEB/KIP/87/PRP/98 | Preparation of Kigali HFC implementation plan | Aug-24 | 190,000 | 186,114 | 3,886 |  | 272 |  |  |  |
| LEB/PHA/86/INV/97 | HCFC phase-out management plan (stage II, third tranche) (air-conditioning sector) | Dec-24 | 170,000 | 160,866 | 9,134 |  | 639 |  |  |  |
| LEB/SEV/86/INS/96 | Extension of the institutional strengthening project (phase XII: 4/2021-3/2023) | Dec-23 | 198,515 | 196,282 | 2,233 |  | 156 |  |  |  |
| MAL/PHA/87/PRP/189 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | Dec-24 | 90,000 | 77,729 | 12,271 |  | 859 |  |  |  |
| MAL/PHA/88/INV/193 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector and management and coordination) | Dec-23 | 154,900 | 39,789 | 115,111 |  | 8,058 |  |  |  |
| MDV/KIP/87/PRP/36 | Preparation of Kigali HFC implementation plan | Dec-24 | 35,000 | 22,026 | 12,974 |  | 908 |  |  |  |
| MEX/FOA/90/PRP/198 | Preparation for HFC investment projects in the foam sector | Dec-24 | 80,000 | 76,065 | 3,935 |  | 275 |  |  |  |
| MEX/KIP/87/PRP/195 | Preparation of Kigali HFC implementation plan | Aug-23 | 85,000 | 76,433 | 8,567 |  | 600 |  |  |  |
| MEX/REF/92/INV/204 | Conversion of the manufacturing of commercial refrigerators from HFC-134a to propane (R-290) at the enterprise Friocima | Dec-24 | 136,500 | 112,605 | 23,895 |  | 2,151 |  |  |  |
| NEP/PHA/86/INV/41 | HCFC phase-out management plan (stage II, first tranche) | Dec-24 | 90,000 | 73,239 | 16,761 |  | 1,508 |  |  |  |
| NIR/KIP/87/PRP/156 | Preparation of Kigali HFC implementation plan | Dec-24 | 137,000 | 121,589 | 15,411 |  | 1,079 |  |  |  |
| NIR/PHA/81/INV/147 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | Dec-24 | 1,357,887 | 1,288,947 | 68,940 |  | 4,826 |  |  |  |
| NIR/PHA/81/TAS/148 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Dec-22 | 1,077,113 | 1,063,456 | 13,657 |  | 956 |  |  |  |
| NIR/PHA/81/TAS/150 | HCFC phase-out management plan (stage II, first tranche) (project management and coordination) | Dec-22 | 165,000 | 90,146 | 74,854 |  | 5,240 |  |  |  |
| NIR/PHA/88/INV/163 | HCFC phase-out management plan (stage II, second tranche) (project management and coordination) | Dec-24 | 75,000 | 41,581 | 33,419 |  | 2,339 |  |  |  |
| PAK/SEV/87/INS/108 | Extension of the institutional strengthening project (phase XI: 7/2021-6/2023) | Jun-23 | 287,318 | 285,993 | 1,325 |  | 93 |  |  |  |
| PAN/KIP/87/PRP/53 | Preparation of Kigali HFC implementation plan | Jul-24 | 190,000 | 176,061 | 13,939 |  | 976 |  |  |  |
| SRL/SEV/91/INS/61 | Extension of the institutional strengthening project (phase XIV: 1/2023-12/2024) | Dec-24 | 236,796 | 234,222 | 2,574 |  | 180 |  |  |  |
| SWA/KIP/87/PRP/33 | Preparation of Kigali HFC implementation plan | Aug-23 | 30,000 | 13,397 | 16,603 |  | 1,162 |  |  |  |
| SWA/PHA/86/INV/31 | HCFC phase-out management plan (stage II, first tranche) | Dec-24 | 50,000 | 49,044 | 956 |  | 86 |  |  |  |
| TLS/PHA/88/INV/24 | HCFC phase-out management plan (stage II, second tranche) | Dec-24 | 41,500 | 36,020 | 5,480 |  | 493 |  |  |  |
| TRI/KIP/87/PRP/40 | Preparation of Kigali HFC implementation plan | Dec-24 | 190,000 | 145,057 | 44,943 |  | 3,146 |  |  |  |
| TRI/PHA/86/INV/38 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 498,756 | 310,706 | 188,050 |  | 13,164 |  |  |  |
| URU/KIP/87/PRP/77 | Preparation of Kigali HFC implementation plan | Dec-24 | 190,000 | 80,724 | 109,276 |  | 7,649 |  |  |  |
| URU/PHA/86/INV/76 | HCFC phase-out management plan (stage III, first tranche) | Dec-24 | 350,601 | 328,657 | 21,944 |  | 1,536 |  |  |  |
| ZIM/KIP/91/PRP/66 | Preparation of a Kigali HFC implementation plan | Dec-24 | 51,000 | 21,468 | 29,532 |  | 2,067 |  |  |  |
| ZIM/PHA/86/INV/60 | HCFC phase-out management plan (stage II, first tranche) | Dec-22 | 100,000 | 84,671 | 15,329 |  | 1,073 |  |  |  |
| TOTALUNDP |  |  |  |  | 4,511,791 |  | 317,887 |  |  |  |
| UNIDO |
| BAH/PHA/93/INV/46 | HCFC phase-out management plan (stage II, second tranche) | Dec-24 | 54,000 | 50,300 | 3,700 |  | 259 | 1 | 98 |  |
| BOL/PHA/87/INV/50 | HCFC phase-out management plan (stage II, first tranche) | Aug-24 | 141,009 | 128,506 | 12,503 |  | 875 | 1 | 98 |  |
| BRA/PHA/75/INV/311 | HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration and air-conditioning sector) | Dec-24 | 1,472,175 | 1,470,636 | 1,539 |  | 108 | 1 | 98 |  |
| BRA/PHA/75/TAS/308 | HCFC phase-out management plan (stage II, first tranche) (project monitoring) | Dec-24 | 276,000 | 275,415 | 585 |  | 41 | 1 | 98 |  |
| BRA/PHA/82/INV/320 | HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration and air-conditioning sector) | Dec-24 | 1,902,953 | 1,589,233 | 313,720 |  | 21,961 | 1 | 98 |  |
| BRA/PHA/88/INV/327 | HCFC phase-out management plan (stage II, fifth tranche) (commercial refrigeration and air-conditioning sector) | Dec-24 | 116,000 | 92,339 | 23,661 |  | 1,656 | 1 | 98 |  |
| CMR/KIP/88/PRP/49 | Preparation of Kigali HFC implementation plan | Dec-23 | 190,000 | 188,249 | 1,751 |  | 123 | 1 | 98 |  |
| CPR/PHA/88/INV/607 | HCFC phase-out management plan (stage II, fourth tranche) (extruded polystyrene foam sector plan) | Dec-23 | 4,400,000 | 3,965,665 | 434,335 |  | 30,403 | 1 | 98 |  |
| GAB/PHA/79/INV/34 | HCFC phase-out management plan (stage I, third tranche) | Dec-22 | 119,900 | 60,409 | 59,491 |  | 5,354 | 1 | 98 |  |
| GAM/KIP/90/PRP/44 | Preparation of a Kigali HFC implementation plan | Dec-24 | 39,000 | 38,520 | 480 |  | 34 | 1 | 98 |  |
| GUA/KIP/94/PRP/69 | Preparation of a Kigali HFC implementation plan (stage I) | Dec-24 | 119,000 | 91,515 | 27,485 |  | 1,924 | 1 | 98 |  |
| HON/KIP/90/PRP/55 | Preparation of a Kigali HFC implementation plan | Dec-24 | 170,000 | 164,642 | 5,358 |  | 375 | 1 | 98 |  |
| IVC/PHA/84/PRP/47 | Preparation of a HCFC phase-out management plan (stage II) | Dec-24 | 20,000 | 16,024 | 3,976 |  | 278 | 1 | 98 |  |
| JOR/PHA/84/TAS/107 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector, project management and coordination) | Dec-23 | 294,122 | 90,153 | 203,969 |  | 14,277 | 1 | 98 |  |
| JOR/PHA/92/PRP/115 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | Dec-24 | 35,000 | 34,988 | 12 |  | 1 | 1 | 98 |  |
| LIB/PHA/75/INV/36 | HCFC phase-out management plan (stage I, first tranche) (foam sector) | Dec-23 | 943,094 | 713,112 | 229,982 |  | 16,099 | n.a. | n.a. |  |
| LIB/SEV/85/INS/44 | Renewal of the institutional strengthening project (phase VI: 7/2020-6/2022) | Jun-23 | 174,164 | 166,234 | 7,930 |  | 555 | 1 | 98 |  |
| MEX/PHA/90/INV/200 | HCFC phase-out management plan (stage II, fourth tranche) (cleaning agent phase-out in refrigeration servicing sector and project implementation and monitoring) | Dec-24 | 1,612,350 | 1,567,895 | 44,455 |  | 3,112 | 1 | 98 |  |
| MEX/PHA/91/PRP/202 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | Dec-24 | 90,000 | 78,290 | 11,710 |  | 820 | 1 | 98 |  |
| MEX/PHA/92/INV/205 | Destruction of emissions of HFC-23 generated in the production of HCFC-22 in Quimobasicos (second tranche) | Jun-24 | 387,561 | 387,529 | 32 |  | 2 | 1 | 98 |  |
| MEX/PHA/92/INV/206 | HCFC phase-out management plan (stage II, fifth tranche) | Dec-24 | 450,600 | 284,533 | 166,067 |  | 11,625 | 1 | 98 |  |
| MOR/KIP/92/PRP/79 | Preparation of a KIP investment project in the refrigeration manufacturing sector for MANAR | Dec-24 | 30,000 | 29,564 | 436 |  | 31 | 1 | 98 |  |
| MOZ/PHA/66/INV/23 | HCFC phase-out management plan (stage I, first tranche) | Dec-22 | 75,000 | 72,133 | 2,867 |  | 258 | 1 | 98 |  |
| NIC/PHA/86/INV/40 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 100,092 | 98,549 | 1,543 |  | 108 | 1 | 98 |  |
| PAK/PHA/76/INV/94 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | Dec-24 | 2,160,200 | 2,142,457 | 17,743 |  | 1,242 | 1 | 98 |  |
| PAK/PHA/83/INV/102 | HCFC phase-out management plan (stage II, second tranche) (polyurethane foam sector) | Dec-24 | 570,352 | 522,507 | 47,845 |  | 3,349 | 1 | 98 |  |
| PAK/PHA/83/TAS/100 | HCFC phase-out management plan (stage II, second tranche) (project management unit) | Dec-24 | 294,500 | 257,155 | 37,345 |  | 2,614 | 1 | 98 |  |
| PAK/PHA/90/INV/110 | HCFC phase-out management plan (stage II, fourth tranche) (domestic air-conditioner manufacturing sector) | Dec-24 | 161,340 | 159,458 | 1,882 |  | 132 | 1 | 98 |  |
| PHI/PHA/83/INV/104 | HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector) | Dec-23 | 537,856 | 348,037 | 189,819 |  | 13,286 | 1 | 98 |  |
| PHI/PHA/83/TAS/105 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Dec-23 | 273,894 | 235,967 | 37,927 |  | 2,655 | 1 | 98 |  |
| PRC/KIP/91/PRP/38 | Preparation of a Kigali HFC implementation plan | Dec-24 | 119,000 | 117,466 | 1,534 |  | 107 | 1 | 98 |  |
| RWA/KIP/88/PRP/38 | Preparation of Kigali HFC implementation plan | Dec-24 | 39,000 | 32,525 | 6,475 |  | 453 | 1 | 98 |  |
| SAU/REF/86/PRP/35 | Preparation of a HCFC phase-out management plan (stage II) (air-conditioning) | Dec-24 | 150,000 | 141,443 | 8,558 |  | 599 | 1 | 98 |  |
| SEN/PHA/85/INV/41 | HCFC phase-out management plan (stage I, third tranche) | Dec-21 | 50,000 | 18,910 | 31,090 |  | 2,332 | 1 | 98 |  |
| SEN/PHA/85/PRP/43 | Preparation of a HCFC phase-out management plan (stage II) | Jun-22 | 20,000 | 4,977 | 15,023 |  | 1,052 | 1 | 98 |  |
| SIL/KIP/88/PRP/43 | Preparation of Kigali HFC implementation plan | Dec-24 | 39,000 | 39,048 | -48 |  | -3 | 1 | 98 |  |
| SIL/PHA/87/INV/40 | HCFC phase-out management plan (stage II, first tranche) | Dec-24 | 117,000 | 92,734 | 24,266 |  | 2,184 | 1 | 98 |  |
| SOA/PHA/91/INV/16 | HCFC phase-out management plan (stage I, fifth tranche) (refrigeration servicing, custom training and monitoring) | Dec-23 | 178,760 | 157,279 | 21,481 |  | 1,504 | 1 | 98 |  |
| SOM/PHA/88/PRP/17 | Preparation of HCFC phase-out management plan (stage II) (Overarching) | Dec-24 | 60,000 | 57,183 | 2,817 |  | 197 | 1 | 98 |  |
| TUR/KIP/90/PRP/113 | Preparation of a Kigali HFC implementation plan | Dec-24 | 120,000 | 108,742 | 11,258 |  | 788 | 1 | 98 |  |
| VEN/PHA/91/INV/137 | HCFC phase-out management plan (stage II, second tranche) (servicing sector) | Dec-24 | 261,444 | 260,972 | 472 |  | 33 | 1 | 98 |  |
| TOTAL UNIDO |  |  |  |  | 2,013,071 |  | 142,802 | 1 | 98 |  |

Annex II

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS

| CODE | Project title | Approved funding plus adjustments as of 31 December 2024 (US $) | Funds disbursed as of 97thmeeting (US $) | Balances committed as per 97thmeeting (US $) | Balances not- committed as per 97thmeeting (US $) | Support cost on balances committed and not-committed as per 97th meeting (US $) | Why any balances could not be returned? | When they could be returned? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |
| FIJ/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 147,699 | 139,529 | 8,170 |  | 572 |  |  |
| TOTAL UNDP |  |  |  | 8,170 |  | 572 |  |  |

AnnexIII

DETAILSONCOMPLETED ANDBY-DECISIONSPROJECTSWITHRETURNEDBALANCESFROMIMPLEMENTINGANDBILATERALAGENCIES

| Code |  | Projecttitle |  |  | Projectcostsreturned (US$) | Agencysupportcosts(US$) |  | Total(US$) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |
| ARG/SEV/82/INS/188 |  | Extension for institutional strengthening project (phase X: 1/2019-12/2020) |  |  |  | -8 |  | -8 |
| BRA/DES/72/DEM/305 |  | Pilot demonstration project on ODS waste management and disposal |  |  |  | -4 |  | -4 |
| BRA/PHA/82/INV/323 |  | HCFC phase-out management plan (stage II, third tranche) (foam sector) |  |  | 530,731 | 37,151 |  | 567,882 |
| BRA/PHA/88/INV/326 |  | HCFC phase-out management plan (stage II, fifth tranche) (foam sector) |  |  | 1,194,264 | 83,598 |  | 1,277,862 |
| CHI/KIP/88/PRP/207 |  | Preparation of Kigali HFC implementation plan |  |  | 3,412 | 239 |  | 3,651 |
| CHI/PHA/81/INV/197 |  | HCFC phase-out management plan (stage II, second tranche) (foam sector) |  |  |  | -2,972 |  | -2,972 |
| CHI/PHA/85/INV/201 |  | HCFC phase-out management plan (stage II, third tranche) (foam sector) |  |  | 42,181 | 2,952 |  | 45,133 |
| COL/KIP/87/PRP/110 |  | Preparation of Kigali HFC implementation plan |  |  | 1,988 | 139 |  | 2,127 |
| COL/PHA/84/TAS/108 |  | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector, project management and monitoring) |  |  |  | -433 |  | -433 |
| COS/SEV/88/INS/64 |  | Extension of institutional strengthening project (phase XIV: 1/2022-12/2023) |  |  | 1,425 | 100 |  | 1,525 |
| CUB/SEV/90/INS/67 |  | Extension of institutional strengthening project (phase XII: 7/2022-6/2024) |  |  | 2,580 | 181 |  | 2,761 |
| GEO/PHA/91/TAS/45 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 7,352 | 662 |  | 8,013 |
| GHA/SEV/91/INS/54 |  | Extension of the institutional strengthening project (phase XV: 1/2023-12/2024) |  |  | 1,826 | 128 |  | 1,954 |
| IDS/SEV/90/INS/219 |  | Extension of institutional strengthening project (phase XIII: 7/2022-6/2024) |  |  | 5,812 | 407 |  | 6,219 |
| IND/PHA/86/INV/480 |  | HCFC phase-out management plan (stage II, third tranche) (polyurethane foam sector plan) |  |  | 641,013 | 44,871 |  | 685,884 |
| IND/PHA/87/PRP/487 |  | Preparation of HCFC phase-out management plan (stage III) (refrigeration sector) |  |  | 12,030 | 842 |  | 12,872 |
| JAM/PHA/91/TAS/45 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 1,586 | 143 |  | 1,729 |
| KYR/KIP/87/PRP/45 |  | Preparation of Kigali HFC implementation plan |  |  | 16,310 | 1,142 |  | 17,452 |
| KYR/PHA/90/TAS/47 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 30,000 | 2,700 |  | 32,700 |
| MAL/PHA/84/TAS/186 |  | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) |  |  | 261,610 | 18,313 |  | 279,923 |
| MAL/PHA/84/TAS/187 |  | HCFC phase-out management plan (stage II, second tranche) (management and coordination) |  |  | 30,800 | 2,156 |  | 32,956 |
| MAL/SEV/88/INS/192 |  | Extension of institutional strengthening project (phase XIV: 1/2022-12/2023) |  |  | 3,218 | 225 |  | 3,443 |
| MEX/REF/90/PRP/199 |  | Preparation for replacement of HFC-134a with HC-290 refrigerant in the manufacturing of commercial refrigerators at Friocima |  |  | 1,088 | 76 |  | 1,164 |
| MOL/PHA/88/INV/45 |  | HCFC phase-out management plan (stage III, first tranche) |  |  | 18,010 | 1,261 |  | 19,271 |
| NIR/SEV/86/INS/155 |  | Extension of the institutional strengthening project (phase XI: 12/2020-11/2022) |  |  | 589 | 41 |  | 630 |
| PAR/KIP/87/PRP/42 |  | Preparation of Kigali HFC implementation plan |  |  | 2,803 | 196 |  | 2,999 |
| PER/KIP/87/PRP/59 |  | Preparation of Kigali HFC implementation plan |  |  | 4,075 | 285 |  | 4,360 |
| SRL/KIP/87/PRP/59 |  | Preparation of Kigali HFC implementation plan |  |  | 872 | 61 |  | 933 |
| TRI/SEV/88/INS/41 |  | Extension of the institutional strengthening project (phase XI: 12/2021-12/2023) |  |  | -313 | -22 |  | -335 |
| TUR/KIP/90/PRP/112 |  | Preparation of a Kigali HFC implementation plan |  |  | 12,540 | 878 |  | 13,417 |
| VEN/SEV/82/INS/136 |  | Renewal of institutional strengthening project (phase XIV: 1/2019-12/2020) |  |  | 2,038 | 143 |  | 2,181 |
| Total completed projects |  |  |  |  | 2,829,839 | 195,450 |  | 3,025,289 |
| TOTAL UNDP |  |  |  |  | 2,829,839 | 195,450 |  | 3,025,289 |
| UNEP |  |  |  |  |  |  |  |  |
| ALB/SEV/88/INS/45 |  | Renewal of institutional strengthening project (phase X: 7/2022-6/2024) |  |  | 58 | 0 |  | 58 |
| ARM/KIP/87/PRP/27 |  | Preparation of Kigali HFC implementation plan |  |  | 1,311 | 170 |  | 1,481 |
| ARM/KIP/94/TAS/32 |  | Kigali HFC implementation plan (stage I, first tranche) |  |  | 66,000 | 5,247 |  | 71,247 |
| ARM/PHA/96/TAS/34 |  | HCFC phase-out management plan (stage III, first tranche) |  |  | 58,300 | 7,579 |  | 65,879 |
| BAH/PHA/93/TAS/45 |  | HCFC phase-out management plan (stage II, second tranche) |  |  | 1,324 | 172 |  | 1,496 |
| BEN/KIP/90/PRP/43 |  | Preparation of a Kigali HFC implementation plan |  |  | 26,111 | 3,394 |  | 29,505 |
| BHU/PHA/92/TAS/32 |  | Verification report on the implementation of the HCFC phase-out management plan |  |  | 7,077 | 920 |  | 7,997 |
| BKF/PHA/84/PRP/42 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 20,000 | 2,600 |  | 22,600 |
| CHD/KIP/90/PRP/39 |  | Preparation of a Kigali HFC implementation plan |  |  | 11,590 | 1,507 |  | 13,097 |
| CHD/PHA/90/TAS/41 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 2,186 | 275 |  | 2,461 |
| COI/PHA/91/TAS/34 |  | Verification report on the implementation of stage I of the HCFC phase-out management plan |  |  | 205 | 27 |  | 232 |
| DMI/PHA/62/TAS/19 |  | HCFC phase-out management plan (stage I, first tranche) |  |  | 4,450 | 579 |  | 5,029 |
| DMI/PHA/86/TAS/26 |  | Verification report on the implementation of stage I of the HCFC phase-out management plan |  |  | 875 | 114 |  | 989 |
| GBS/PHA/81/PRP/24 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 7,535 | 980 |  | 8,515 |
| GLO/SEV/93/TAS/368 |  | Compliance Assistance Programme: 2024 budget |  |  | 920,524 | 73,642 |  | 994,166 |
| GRN/KIP/88/PRP/29 |  | Preparation of Kigali HFC implementation plan |  |  | 6,429 | 836 |  | 7,265 |
| GUA/PHA/86/TAS/58 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | -3,535 | -460 |  | -3,995 |
| IND/PHA/82/TAS/476 |  | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector plan) |  |  | 532 | 64 |  | 596 |
| IND/PHA/86/TAS/483 |  | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector plan) |  |  | 4,989 | 604 |  | 5,593 |
| IRA/PHA/87/PRP/255 |  | Preparation of HCFC phase-out management plan (stage III) (Overarching) |  |  | 163 | 21 |  | 184 |
| IRQ/PHA/87/TAS/30 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 5,177 | 598 |  | 5,775 |
| KIR/PHA/85/TAS/16 |  | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) |  |  | 8,279 | 1,076 |  | 9,355 |
| KIR/SEV/87/INS/18 |  | Renewal of institutional strengthening project (phase VIII: 1/2022-12/2023) |  |  | 18,587 | 0 |  | 18,587 |
| LAO/KIP/87/PRP/40 |  | Preparation of Kigali HFC implementation plan |  |  | 1,058 | 138 |  | 1,196 |
| LAO/PHA/88/TAS/41 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 17,789 | 2,313 |  | 20,102 |
| LAO/SEV/91/INS/42 |  | Renewal of the institutional strengthening project (phase XI: 1/2023-12/2024) |  |  | 14 | 0 |  | 14 |
| MOL/PHA/88/TAS/46 |  | HCFC phase-out management plan (stage III, first tranche) |  |  | 5,725 | 744 |  | 6,469 |
| MON/PHA/88/TAS/34 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 1,552 | 202 |  | 1,754 |
| NEP/PHA/88/TAS/45 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 5,643 | 734 |  | 6,377 |
| NIC/KIP/93/TAS/55 |  | Kigali HFC implementation plan (stage I, first tranche) |  |  | 15,000 | 1,950 |  | 16,950 |
| PAK/PHA/83/TAS/101 |  | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) |  |  | 390 | 51 |  | 441 |
| PAK/PHA/88/TAS/109 |  | HCFC phase-out management plan (stage II, third tranche) |  |  | 2,596 | 337 |  | 2,933 |
| PAR/PHA/87/TAS/41 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 25 | 3 |  | 28 |
| PAR/PHA/91/TAS/45 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 6,518 | 847 |  | 7,365 |
| PAR/SEV/88/INS/44 |  | Extension of institutional strengthening project (phase X: 12/2021-11/2023) |  |  | 3,382 | 0 |  | 3,382 |
| PER/SEV/80/INS/56 |  | Renewal of institutional strengthening project (phase V: 1/2018-12/2019) |  |  | -4,138 | 0 |  | -4,138 |
| PRC/KIP/91/PRP/37 |  | Preparation of a Kigali HFC implementation plan |  |  | 31,137 | 4,048 |  | 35,185 |
| PRC/PHA/81/PRP/33 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 20 | 3 |  | 23 |
| QAT/PHA/88/TAS/27 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 4,600 | 598 |  | 5,198 |
| RWA/PHA/91/TAS/39 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 10 | 1 |  | 11 |
| SAM/PHA/92/TAS/28 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 17,279 | 2,246 |  | 19,525 |
| SEN/KIP/87/PRP/44 |  | Preparation of Kigali HFC implementation plan |  |  | 22,395 | 2,911 |  | 25,306 |
| SEY/KIP/90/PRP/28 |  | Preparation of a Kigali HFC implementation plan |  |  | 9,800 | 1,274 |  | 11,074 |
| SOI/PHA/92/TAS/20 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 15,737 | 2,046 |  | 17,783 |
| STL/KIP/91/PRP/36 |  | Preparation of a Kigali HFC implementation plan |  |  | 31,106 | 4,044 |  | 35,150 |
| SUR/PHA/92/TAS/33 |  | HCFC phase-out management plan (stage I, fourth tranche) |  |  | 13,500 | 1,755 |  | 15,255 |
| SUR/SEV/77/INS/25 |  | Extension of the institutional strengthening project (phase VI: 12/2016-11/2018) |  |  | 18,773 | 0 |  | 18,773 |
| TLS/SEV/88/INS/22 |  | Extension of institutional strengthening (phase VI: 7/2022-6/2024) |  |  | 14,955 | 0 |  | 14,955 |
| TOG/KIP/90/PRP/39 |  | Preparation of a Kigali HFC implementation plan |  |  | 19,256 | 2,503 |  | 21,759 |
| TON/PHA/92/TAS/20 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 17,133 | 2,227 |  | 19,360 |
| TTR/PHA/92/TAS/20 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 12,759 | 1,659 |  | 14,418 |
| UGA/PHA/91/TAS/34 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 205 | 27 |  | 232 |
| ZIM/KIP/91/PRP/65 |  | Preparation of a Kigali HFC implementation plan |  |  | 105 | 14 |  | 119 |
| Total completed projects |  |  |  |  | 1,452,490 | 132,618 |  | 1,585,108 |
| TOTAL UNEP |  |  |  |  | 1,452,490 | 132,618 |  | 1,585,108 |
| UNIDO |  |  |  |  |  |  |  |  |
| ALB/KIP/87/PRP/43 |  | Preparation of Kigali HFC implementation plan |  |  | 2,378 | 167 |  | 2,545 |
| BAH/PHA/88/INV/43 |  | HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration foam and spray foam sector - umbrella project) |  |  | 148 | 10 |  | 158 |
| BEN/KIP/90/PRP/42 |  | Preparation of a Kigali HFC implementation plan |  |  | 1,633 | 114 |  | 1,747 |
| ECU/REF/91/INV/81 |  | Conversion of the manufacturing of domestic and commercial refrigerators from HFC-134a to isobutane (R-600a) and propane (R-290) at Induglob |  |  | 213 | 15 |  | 228 |
| EGY/PHA/84/INV/141 |  | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector and project management unit) |  |  | 2,880 | 202 |  | 3,082 |
| EGY/PHA/88/INV/150 |  | HCFC phase-out management plan (stage II, third tranche) (enabling activities in the refrigeration and air-conditioning sector) |  |  | 1,231 | 86 |  | 1,317 |
| GAB/PHA/84/PRP/38 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 1,818 | 127 |  | 1,945 |
| GUA/PHA/91/TAS/61 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 111 | 10 |  | 121 |
| IVC/PHA/84/INV/45 |  | HCFC phase-out management plan (stage I, third tranche) |  |  | 11,628 | 814 |  | 12,442 |
| JOR/PHA/88/PRP/111 |  | Preparation of HCFC phase-out management plan (stage III) (Overarching) |  |  | 573 | 40 |  | 613 |
| LES/KIP/88/PRP/28 |  | Preparation of a Kigali HFC implementation plan |  |  | 1,291 | 90 |  | 1,381 |
| MOG/KIP/87/PRP/17 |  | Preparation of Kigali HFC implementation plan |  |  | 1,602 | 112 |  | 1,714 |
| NIR/KIP/87/PRP/158 |  | Preparation of Kigali HFC implementation plan |  |  | 3,190 | 223 |  | 3,413 |
| PAK/PHA/83/INV/99 |  | HCFC phase-out management plan (stage II, second tranche) (domestic air-conditioning sector) |  |  | 267 | 20 |  | 287 |
| SEN/KIP/87/PRP/45 |  | Preparation of Kigali HFC implementation plan |  |  | 3,879 | 272 |  | 4,151 |
| SOM/PHA/88/INV/16 |  | HCFC phase-out management plan (stage I, third tranche) |  |  | 5,506 | 385 |  | 5,891 |
| SUR/PHA/92/INV/32 |  | HCFC phase-out management plan (stage I, fourth tranche) |  |  | 1,064 | 96 |  | 1,160 |
| TKM/SEV/90/INS/20 |  | Extension of the institutional strengthening project (phase VI: 1/2023-12/2024) |  |  | 6 | 0 |  | 6 |
| TOG/KIP/90/PRP/38 |  | Preparation of a Kigali HFC implementation plan |  |  | 1,012 | 88 |  | 1,100 |
| TUN/KIP/88/PRP/80 |  | Preparation of Kigali HFC implementation plan |  |  | 4,694 | 329 |  | 5,023 |
| TUN/PHA/84/INV/75 |  | HCFC phase-out management plan (stage II, first tranche) (foam sector) |  |  | 879 | 61 |  | 940 |
| TUN/SEV/84/INS/77 |  | Extension of institutional strengthening project (phase IX: 1/2020-12/2021) |  |  | 455 | 31 |  | 486 |
| YUG/SEV/84/INS/53 |  | Extension of institutional strengthening project (phase VII: 12/2019-11/2021) |  |  | 10,559 | 739 |  | 11,298 |
| ZAM/PHA/86/INV/41 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 339 | 31 |  | 370 |
| Total completed projects |  |  |  |  | 57,356 | 4,062 |  | 61,418 |
| JOR/REF/81/INV/103 |  | Conversion of large commercial unitary roof top air-conditioning units of up to 400kW manufacturing facility from HFC (R134a, R407c, R410a) to propane R290 as refrigerant at Petra Engineering Industries Co. |  |  | 113,044 | 7,913 |  | 120,957 |
| NIC/EEF/93/DEM/56 |  | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) |  |  | 64,039 | 5,764 |  | 69,803 |
| NIC/DES/93/PRP/53 |  | Preparation of national inventory of banks of waste controlled substances and development of a national plan for management of these substances |  |  | 47,844 | 3,349 |  | 51,193 |
| Total “by-decision” projects |  |  |  |  | 224,928 | 17,026 |  | 241,954 |
| TOTAL UNIDO |  |  |  |  | 282,284 | 21,088 |  | 303,372 |
| WORLD BANK |  |  |  |  |  |  |  |  |
| GLO/SEV/93/TAS/366 |  | Core unit budget (2024) |  |  | 0 | 10,220 |  | 10,220 |
| JOR/PHA/91/INV/113 |  | HCFC phase-out management plan (stage II, third tranche) |  |  | 178,512 | 12,496 |  | 191,008 |
| JOR/SEV/82/INS/105 |  | Extension of institutional strengthening project (phase XIII: 1/2019-12/2020) |  |  | 77,483 | 5,424 |  | 82,907 |
| TOTAL WORLD BANK |  |  |  |  | 255,995 | 28,140 |  | 284,135 |
| GERMANY |  |  |  |  |  |  |  |  |
| EGY/PHA/84/INV/142 |  | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) |  |  | 28,643 | 3,724 |  | 32,367 |
| KEN/EEF/93/PRP/68 |  | Preparation for a pilot project on energy efficiency (decision 91/65) |  |  | 30,000 | 3,900 |  | 33,900 |
| TOTAL GERMANY |  |  |  |  | 58,643 | 7,624 |  | 66,267 |

UNEP/OzL.Pro/ExCom/97/1

Los datos presentados se basan en el formato de presentación de informes que se ha elaborado en respuesta a la decisión 31/2.

UNEP/OzL.Pro/ExCom/97/3

Outstanding obligations to be paid, funds will be returned with the next balance list.