| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/95/27 10 November 2024 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-fifth Meeting

Montreal, 4-8 December 2024

Item 8(d)(ii) of the provisional agenda

UNDP BUSINESS PLAN FOR 2025–2027

# Introduction

# This document presents UNDP business plan for 2025–2027 and includes the planned activities for the reduction of controlled substances and other activities under the Montreal Protocol during the period 2025–2027. The narrative of UNDP’s business plan for 2025–2027 is attached to the present document.

# This document consists of the following sections:

- Planned activities during the period 2025–2027

- Secretariat’s comments

- Proposed adjustments by the Secretariat

- Performance indicators

- Recommendation

I.	Planned activities during the period 2025–2027

# Table 1 sets out, by year, the value of activities included in UNDP’s business plan.

Table 1. Resource allocation in the UNDP business plan for 2025–2027 (US $)* – as submitted

| Description | 2025 | 2026 | 2027 | Total (2025–2027) | Total after 2027 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 17,142,461 | 20,420,783 | 10,570,777 | 48,134,021 | 16,251,370 |
| HPMP stage II | 563,840 | 55,000 | 87,200 | 706,040 | 222,560 |
| HPMP stage III | 609,542 | 996,000 | 899,662 | 2,505,204 | 1,287,000 |
| HPMP stage IV | 0 | 3,691,000 | 5,537,000 | 9,228,000 | 0 |
| HPMP – energy efficiency (decision 89/6) | 200,909 | 0 | 76,000 | 276,909 | 0 |
| HCFC activities subtotal | 18,516,752 | 25,162,783 | 17,170,639 | 60,850,174 | 17,760,930 |
| HFC activities |  |  |  |  |  |
| Approved Kigali HFC implementation plans (KIPs) | 2,196,994 | 2,423,439 | 1,791,841 | 6,412,274 | 750,372 |
| KIP stage I – project preparation (PRP) | 401,730 | 0 | 0 | 401,730 | 0 |
| KIP stage I | 7,034,456 | 15,807,879 | 23,041,355 | 45,883,689 | 14,717,259 |
| HFC investment – PRP | 85,600 | 0 | 0 | 85,600 | 0 |
| HFC investment | 0 | 96,000 | 0 | 96,000 | 0 |
| HFC demonstration | 650,000 | 0 | 0 | 650,000 | 0 |
| HFC-23 investment | 0 | 8,000,000 | 0 | 8,000,000 | 0 |
| HFC activities subtotal | 10,368,780 | 26,327,318 | 24,833,196 | 61,529,293 | 15,467,631 |
| Other activities |  |  |  |  |  |
| Pilot project for energy efficiency – demonstration (decision 91/65) | 5,370,000 | 0 | 0 | 5,370,000 | 0 |
| National inventories of banks of waste-controlled substances – PRP (decision 91/66) | 192,000 | 0 | 0 | 192,000 | 0 |
| Other activities subtotal | 5,562,000 | 0 | 0 | 5,562,000 | 0 |
| Standard activities |  |  |  |  |  |
| Institutional strengthening (IS) | 368,559 | 9,048,789 | 4,095,018 | 13,512,366 | 0 |
| Core unit | 2,388,150 | 2,203,467 | 2,218,892 | 6,810,510 | 0 |
| Standard activities subtotal | 2,756,710 | 11,252,256 | 6,313,910 | 20,322,876 | 0 |
| Total | 37,204,242 | 62,742,357 | 48,317,744 | 148,264,343 | 33,228,561 |

* Including agency support costs where applicable.

# II.	Secretariat’s comments

II.1	HCFC activities

# Stage II of HPMPs

# A total of US $928,600 is planned for stage II of the HPMPs for four low-volume-consuming (LVC) countries to meet 100 per cent reduction of the HCFC baseline (including US $706,040 for 2025-2027 and US $222,560 for the period after 2027).

# Stage III of HPMPs

# A total of US $3.79 million is planned for stage III of the HPMPs for five countries (including US $2.51 million for 2025–2027 and US $1.29 million for the period after 2027).

# Stage IV of HPMPs

# A total of US $9.23 million is planned for stage IV of the HPMP for one country for 2025–2027. Project preparation for this activity was submitted to the 95th meeting.

# Energy efficiency for LVC countries (decision 89/6)

# A total of US $276,909 is included in the business plan for energy efficiency activities for four LVC countries for 2025–2027.

II.2	HFC-related activities

# KIP project preparation

# A total of US $401,730 is included in the business plan for KIP project preparation activities for four countries in 2025.

# Three of the four countries for which KIP project preparation activities have been included have not yet ratified the Kigali Amendment but have submitted the required letter from their respective Government indicating their intent to make best efforts to ratify the Kigali Amendment in line with decision 84/46(f).

# Stage I of KIPs

# A total of US $60.6 million is included in the business plan for stage I of KIPs for 23 countries (including US $45.88 million for 2025–2027 and US $14.72 million for the period after 2027). All these countries have ratified the Kigali Amendment.

# HFC investment and project preparation

# UNDP’s business plan included an HFC investment project for one country amounting to US $96,000 in 2026. The project preparation for this activity amounting to US $85,600 is included in the 2025 business plan. This country has ratified the Kigali Amendment.

# HFC demonstration

# UNDP’s business plan included an HFC demonstration project for one country amounting to US $650,000 in 2025. The project preparation for this project was approved at the 93rd meeting.

# HFC-23 investment

# UNDP’s business plan included an investment project for HFC-23 emissions control for one country amounting to US $8 million in 2026. This country has ratified the Kigali Amendment.

II.3	Other activities

Pilot projects for energy efficiency (decision 91/65)

# A total of US $5.37 million is included in the business plan under the funding window for pilot projects for energy efficiency for 2025 for seven countries and one global project on demonstrating digital monitoring and management tools to enhance energy efficiency and reduce emission of greenhouse gases in the space cooling and cold chain sectors in Colombia, Lebanon, and Trinidad and Tobago. The project preparation for the global project was approved at the 94th meeting.

# Project preparation for national inventories of banks of waste-controlled substances (decision 91/66)

# A total of US $192,000 is included in the business plan for the preparation of national inventories of banks of waste-controlled substances for 2025 for two countries.

# II.4	Core unit costs

# The core unit costs are expected to increase at an annual rate of 0.7 per cent as agreed, and include additional core unit funding in the amount of US $200,000 in 2025 for 2026, pursuant to decision 93/95(b).

III.	Proposed adjustments by the Secretariat

# The adjustments to the UNDP business plan for 2025–2027 were based on relevant decisions of the Executive Committee. In reviewing the revised UNDP business plan for 2025–2027, the Secretariat noted that the following adjustments were not included:

Table 2. Adjustments to the UNDP business plan for 2025–2027 (US $)* – as proposed by the Secretariat

| Adjustment | 2025–2027 | After 2027 |
| --- | --- | --- |
| MYA values to reflect the actual amounts approved under the Agreements that have been submitted to the 95th meeting | 43,600 | 0 |
| Energy efficiency for LVC countries pursuant to decision 89/6 or submitted to the 95th meeting | (76,063) | 0 |
| Servicing sector for stage I of KIPs pursuant to decision 92/37 | (1,364) | 0 |
| Preparation for national inventories of banks of waste-controlled substances submitted to the 95th meeting | (96,000) | 0 |

* Including agency support costs where applicable.

# Table 3 presents the results of the Secretariat’s proposed adjustments to the UNDP business plan for 2025–2027, which are also addressed in the context of the consolidated business plan of the Multilateral Fund for 2025–2027.

Table 3. Resource allocation in UNDP’s adjusted business plan for 2025–2027 (US $)*

| Description | 2025 | 2026 | 2027 | Total (2025–2027) | Total after 2027 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HPMPs | 17,186,061 | 20,420,783 | 10,570,777 | 48,177,621 | 16,251,370 |
| HPMP stage II | 563,840 | 55,000 | 87,200 | 706,040 | 222,560 |
| HPMP stage III | 609,542 | 996,000 | 899,662 | 2,505,204 | 1,287,000 |
| HPMP stage IV | 0 | 3,691,000 | 5,537,000 | 9,228,000 | 0 |
| HPMP – energy efficiency (decision 89/6) | 124,846 | 0 | 76,000 | 200,846 | 0 |
| HCFC activities subtotal | 18,484,289 | 25,162,783 | 17,170,639 | 60,817,711 | 17,760,930 |
| HFC activities |  |  |  |  |  |
| Approved KIPs | 2,196,994 | 2,423,439 | 1,791,841 | 6,412,274 | 750,372 |
| KIP stage I – PRP | 401,730 | 0 | 0 | 401,730 | 0 |
| KIP stage I | 7,034,049 | 15,807,879 | 23,040,398 | 45,882,325 | 14,717,259 |
| HFC investment – PRP | 85,600 | 0 | 0 | 85,600 | 0 |
| HFC investment | 0 | 96,000 | 0 | 96,000 | 0 |
| HFC demonstration | 650,000 | 0 | 0 | 650,000 | 0 |
| HFC-23 investment | 0 | 8,000,000 | 0 | 8,000,000 | 0 |
| HFC activities subtotal | 10,368,373 | 26,327,318 | 24,832,239 | 61,527,929 | 15,467,631 |
| Other activities |  |  |  |  |  |
| Pilot project for energy efficiency – demonstration (decision 91/65) | 5,370,000 | 0 | 0 | 5,370,000 | 0 |
| National inventories of banks of waste-controlled substances – PRP (decision 91/66) | 96,000 | 0 | 0 | 96,000 | 0 |
| Other activities subtotal | 5,466,000 | 0 | 0 | 5,466,000 | 0 |
| Standard activities |  |  |  |  |  |
| IS | 368,559 | 9,048,789 | 4,095,018 | 13,512,366 | 0 |
| Core unit | 2,388,150 | 2,203,467 | 2,218,892 | 6,810,510 | 0 |
| Standard activities subtotal | 2,756,710 | 11,252,256 | 6,313,910 | 20,322,876 | 0 |
| Total | 37,075,372 | 62,742,357 | 48,316,787 | 148,134,517 | 33,228,561 |

* Including agency support costs where applicable.

IV.	Performance indicators

# UNDP submitted performance indicators pursuant to decision 93/8(d) in its business plan narrative. The Secretariat informed UNDP of the targets shown in table 4.

Table 4. Performance indicators for UNDP for 2025

| Type of indicator | Short title | Calculation | 2025 target |
| --- | --- | --- | --- |
| Planning-Approval | Tranches approved | Number of tranches approved vs. those planned* | 33 |
| Planning-Approval | Individual projects/ activities approved | Number of projects/activities approved vs. those planned (including project preparation activities) | 19 |
| Implementation | Funds disbursed | Based on estimated disbursement in progress reports | 19,663,303 |
| Implementation | ODS phase-out for HCFC-related projects | ODS phase-out for HCFC-related projects in ODP tonnes vs. those planned per progress reports | 942.9 ODP tonnes |
| Implementation | HFC phase-down for HFC-related projects | HFC phase-down for HFC-related projects in CO2-eq tonnes vs. those planned per progress reports | 462,857 CO2-eq tonnes |
| Implementation | Project operational completion | Project operational completion vs. planned in progress reports for all activities (excluding project preparation)** | 36 |
| Implementation | Gender mainstreaming | Operational policy on gender mainstreaming applied to all approved projects | 100% |
| Administrative | Speed of financial completion | The extent to which projects are financially completed within 12 months after project operational completion | 12 months after operational completion |
| Administrative | Timely submission of project completion reports | Timely submission of project completion reports based on the progress report | 0 |
| Administrative | Timely submission of progress reports and business plans | Timely submission of progress reports and business plans and responses unless otherwise agreed | On time |

- * The targets of an agency will be reduced if it cannot submit a tranche owing to another cooperating agency or lead agency or if the HCFC phase-out management plan or Kigali HFC implementation plan submitted for consideration by the Executive Committee is not approved as a result of factors beyond the control of the national ozone unit and agency.

- ** The targets of an agency will be reduced if an extension of the completion date has been approved by the Executive Committee.

# V.	Recommendation

# The Executive Committee may wish:

## To note the UNDP business plan for 2025–2027 contained in document UNEP/OzL.Pro/ExCom/95/27; and

## To approve the performance indicators for UNDP set out in table 4 of document UNEP/OzL.Pro/ExCom/95/27.

UNEP/OzL.Pro/ExCom/95/1

Decision 89/6 allowed bilateral and implementing agencies, when submitting existing and future stages of HPMPs for LVC countries, to include the funding associated with the need for the introduction of alternatives to HCFCs with low- or zero-global-warming potential and for maintaining energy efficiency in the refrigeration servicing sector.

The Executive Committee established a funding window and criteria for pilot projects to maintain and/or enhance energy efficiency of replacement technologies and equipment in the context of HFC phase-down.

The Executive Committee established a funding window and criteria for the preparations of national inventories of banks of used or unwanted controlled substances and a plan for the collection, transport, and disposal of such substances.

UNDP’s 2025 core unit costs will be considered at the 95th meeting (UNEP/OzL.Pro/ExCom/95/84).

The Executive Committee approved an increase in the core unit funding for UNDP by US $200,000, for each year of the triennium 2024–2026, for the strengthening of its capacity to provide technical and policy support to Article 5 countries, on the understanding that the increase only applied to the triennium 2024–2026.

UNEP/OzL.Pro/ExCom/95/25