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EVALUATION OF THE PERFORMANCE OF THE IMPLEMENTING AGENCIES 
AGAINST THEIR 2018 BUSINESS PLANS[footnoteRef:1] [1:  Also includes qualitative assessment of bilateral agencies.] 



Introduction

This document presents:
(a) The quantitative evaluations of the performance of the implementing agencies with respect to the performance targets set in the 2018 business plans and progress and financial reports submitted to the 84th meeting[footnoteRef:2]; [2:  Based on the performance indicators adopted in decision 41/93, as modified by decisions 47/51 and 71/28, and the targets that were adopted for the 2018 business plans in Annexes VIII – XI to the report of the 80th meeting (UNEP/OzL.Pro/ExCom/80/59).] 

(b) A trend analysis for each of the eight performance indicators; 
(c) The qualitative assessment of the performance of bilateral and implementing agencies based on input received from national ozone unit (NOU) officers; and
(d) Secretariat’s comments and recommendation. 
This document also includes the following three annexes: 
Annex I: 	Investment project performance by agency
Annex II: 	Non-investment project performance by agency
Annex III: 	Qualitative assessment of the implementing agencies by the national ozone units for 2018
UNEP/OzL.Pro/ExCom/84/10


UNEP/OzL.Pro/ExCom/84/10



Pre-session documents of the Executive Committee of the Multilateral Fund for the Implementation of the Montreal Protocol are without prejudice to any decision that the Executive Committee might take following issuance of the document.

2
5
Analysis of quantitative performance indicators 
Table 1 presents the approved targets, measures of progress towards achieving each target, and the number of targets achieved.
Table 1: 2018 performance indicator targets and achievement 
	Item


	UNDP
	UNEP
	UNIDO
	World Bank

	
	Target
	Agency achievement
	Secretariat assessment
	Met target
	Target
	Agency achievement
	Secretariat assessment
	Met target
	Target
	Agency achievement
	Secretariat assessment
	Met target
	Target
	Agency achievement
	Secretariat assessment
	Met    target

	Tranches approved*
	24
	20
	20
	No
	50
	29
	29
	No
	38
	22
	22
	No
	7
	4
	4
	No

	Projects/activities approved
	39
	34
	34
	No
	179
	145
	145
	No
	48
	52
	52
	Yes
	6
	5
	5
	No

	Funds disbursed (million US $)
	31.3 
	40.67 
	41.43 
	Yes
	14.91 
	17.76

	17.83 
	Yes
	23.57 
	25.75 
	25.88 
	Yes
	13.74 
	9.08 
	9.33
	No

	ODS phase-out*
	747.2
	716.2
	716.2
	No
	141.5
	122.1
	122.1
	No
	694.8
	472
	491.1
	No
	109.1
	98.1
	74.87
	No

	Project completion for activities
	41
	46
	46
	Yes
	130
	108
	108
	No
	57
	45
	47
	No
	17
	17
	17
	Yes

	Speed of financial completion
	70% 
(70)
	66
	66
	No
	14 months
	14 months
	14 months
	Yes
	12 months after operational completion
	12 months
	11.4 months
	Yes
	90%
	100%
	100%
	Yes

	Timely submission of project completion reports
	On time (3)
	On time (11)
	On time (11)
	Yes
	On time (20)
	Not on time
	Not on time (9)
	No
	On time
	On time
	On time
	Yes
	On time (18)
	Not on time
	Not on time (2)
	No

	Timely submission of progress reports
	On time
	On time
	On time
	Yes
	On time
	On time
	On time
	Yes
	On time
	On time
	On time
	Yes
	On time
	On time
	On time
	Yes

	Number of targets achieved
	
	
	
	4/8
	
	
	
	3/8
	
	
	
	5/8
	
	
	
	3/8
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* The targets of an agency would be reduced “if it could not submit a tranche owing to another cooperating agency or lead agency” or “if HPMP submitted for consideration by the Executive Committee was not approved as a result of factors beyond the control of the NOU and agency”. 
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Weighted assessment of performance
Table 2 presents the outcome of the 2018 weighted assessment by performance indicator based on the Secretariat’s methodology. 
Table 2: Weighted assessment of implementing agencies performance in 2018
	Item
	Weighting
	UNDP
	UNEP
	UNIDO
	World Bank

	
	
	% of target achieved
	Points
	% of target achieved
	Points
	% of target achieved
	Points
	% of target achieved
	Points

	Tranches approved
	10
	83
	8
	58
	6
	58
	6
	57
	6

	Projects/activities approved
	10
	87
	9
	81
	8
	108
	10
	83
	8

	Funds disbursed
	15
	132
	15
	120
	15
	110
	15
	68
	10

	ODS phase-out
	25
	96
	24
	86
	22
	71
	18
	69
	17

	Project completion for activities
	20
	112
	20
	83
	17
	82
	16
	100
	20

	Speed of financial completion
	10
	94
	9
	100
	10
	105
	10
	100
	10

	Timely submission of project completion reports
	5
	100
	5
	45
	2
	100
	5
	11
	1

	Timely submission of progress reports
	5
	100
	5
	100
	5
	100
	5
	100
	5

	2018 Assessment
	100
	 
	95
	 
	85
	 
	85
	 
	77



Analysis of other quantitative performance indicators
In line with decision 41/93,[footnoteRef:3] Annexes I and II present the historical analyses for investment[footnoteRef:4] and non-investment[footnoteRef:5] projects, respectively.  [3:  The Secretariat was requested to continue monitoring the investment and non‑investment performance indicators on the basis of trend analysis in future evaluations of the performance of implementing agencies.]  [4:  Investment projects include multi-year agreements (MYAs) that are so-designated by project code.]  [5:  Only the “funds disbursed”, “speed of first disbursement” and “speed of project completion” indicators are applicable to non-investment projects.] 

These annexes show that agencies have had various levels of success in different years. For investment projects, the target for ODS phased out was achieved by UNDP in 2018 while UNIDO and the World Bank did not achieve this target for that year. The target for the amount of funds disbursed was only achieved by UNDP and UNIDO while the World Bank met 62 per cent. UNDP and UNIDO reached their targets for project completion reports, and the World Bank met 11 per cent of its target. The speed of delivery and first disbursement for 2018 are similar to previous years reflecting the historical performance for all implementing agencies. The achievement of the target of “value of projects approved” increased for the World Bank, remained at similar level for UNDP and decreased for UNIDO. The target for “ODS to be phased out” has not been achieved for all implementing agencies in 2018. The indicators “cost‑effectiveness” and “cost of project preparation” are inconclusive with respect to any trend due to the differences in ODP of CFCs and HCFCs and the approval of MYAs instead of individual projects.
For non-investment projects, the target for the amount of funds disbursed was achieved by all implementing agencies, except UNEP. The speed of delivery and first disbursement for 2018 are similar to previous years for all implementing agencies.
Analysis of qualitative performance indicators 
A total of 118[footnoteRef:6] questionnaires received from the NOUs of 71 Article 5 countries to assess the qualitative performance of the bilateral and implementing agencies were processed.  [6:  France (1), Germany (7), UNDP (24), UNEP (52), UNIDO (32) and the World Bank (2).] 

Table 3 presents a summary of the overall ratings provided by the NOUs for the three main categories. It should be noted that several countries did not provide overall ratings for one or more of the categories, although they did send responses to individual questions that have been included in Annex III to the present document. Most of the overall ratings were satisfactory or above. 
Table 3: Overall ratings for qualitative performance of bilateral and implementing agencies by category
	Category
	Highly satisfactory
	Satisfactory
	Less satisfactory
	Unsatisfactory

	Impact
	55
	22
	3
	1

	Organization and cooperation
	40
	18
	1
	1

	Technical assistance/training
	46
	25
	2
	1



In addition to the three main categories, the NOUs provide ratings divided into several sub‑categories, and questions by sub-category (Annex III). There were 200 less than satisfactory ratings from the sub‑categories. 
SECRETARIAT’S COMMENTS AND RECOMMENDATIONS
COMMENTS
The implementing agencies have been informed of the results of the quantitative assessment of their performance for 2018, showing that all of them achieved 77 per cent or more of their targets.
The Secretariat noted, with appreciation, that 71 NOUs (as compared to 40 in 2018) submitted qualitative assessments. The Secretariat sent the assessments received from NOUs to the respective bilateral and implementing agencies for their comments, with an emphasis on the less than satisfactory ratings. Bilateral and implementing agencies provided comments and, where applicable, reported on the results of their dialogues with the respective NOUs. 
Dialogues between NOUs and bilateral and implementing agencies have been completed for all countries that identified issues in their qualitative assessments (i.e., ratings of “less satisfactory” or “unsatisfactory”). All agencies concerned reported that a way forward was agreed with the respective NOUs, and in a majority of cases, bilateral and implementing agencies have been able to resolve the issues identified in regards to the less than satisfactory ratings. 
The Executive Committee may wish to note, with appreciation, the efforts undertaken by bilateral and implementing agencies to have open and constructive discussions with the respective NOUs about the areas in which their services were perceived to be less than satisfactory, and the satisfactory outcome of their consultations with the NOUs concerned.
RECOMMENDATION
The Executive Committee may wish:
To note: 
The evaluation of the performance of implementing agencies against their 2018 business plans, as contained in document UNEP/OzL.Pro/ExCom/84/10; 
That all implementing agencies had a quantitative assessment of their performance for 2018 of at least 77 on a scale of 100;
That the trend analysis indicated that performance of implementing agencies had not improved in some indicators in 2018 in relation to 2017; 
With appreciation, the efforts undertaken by bilateral and implementing agencies to have open and constructive discussions with the respective national ozone units (NOUs) about the areas in which their services were perceived to be less than satisfactory, and the satisfactory outcome of their consultations with the NOUs concerned; and
[bookmark: _GoBack]Noting, with appreciation, that 71 out of the 144 countries submitted their assessments of the qualitative performance of the bilateral and implementing agencies assisting their governments, as compared to 40 in 2018, to encourage NOUs to submit, on a yearly basis and in a timely manner, such assessments.
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Annex I
INVESTMENT PROJECT PERFORMANCE BY AGENCY
(1996-2018)

	UNDP
	1996
	1997
	1998
	1999
	2000
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017
	2018

	ODS phased out
	24%
	93%
	100%
	76%
	41%
	99%
	92%
	100%
	79%
	91%
	85%
	100%
	86%
	100%
	N/A
	0%
	94%
	100%
	100%
	100%
	0%
	34%
	100%

	Funds disbursed
	59%
	100%
	95%
	90%
	100%
	95%
	77%
	64%
	100%
	96%
	66%
	76%
	98%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	97%
	97%
	100%

	Project completion reports
	
	
	
	38%
	93%
	86%
	87%
	100%
	97%
	79%
	30%
	82%
	74%
	100%
	54%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%

	Distribution among countries
	
	
	
	65%
	61%
	63%
	58%
	38%
	72%
	44%
	75%
	64%
	66%
	83%
	51%
	79%
	94%
	81%
	68%
	85%
	90%
	60%
	88%

	Value of projects approved
	100%
	100%
	
	100%
	80%
	100%
	99%
	65%
	73%
	82%
	83%
	77%
	100%
	100%
	38%
	87%
	100%
	87%
	89%
	91%
	100%
	80%
	79%

	ODS to be phased out
	74%
	100%
	
	100%
	92%
	96%
	77%
	44%
	89%
	70%
	100%
	100%
	100%
	100%
	100%
	92%
	61%
	100%
	29%
	83%
	84%
	84%
	96%

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Cost of project preparation 
(% of approvals)
	
	4.4%
	3%
	2.7%
	2.7%
	1.1%
	2.5%
	1.6%
	3.6%
	1.4%
	0.5%
	3.6%
	1.5%
	14.7%
	14.4%
	3.0%
	2.8%
	1.8%
	0.2%
	4.3%
	2.3%
	2.71%
	0.99%

	Cost-effectiveness ($/kg)
	
	6.1
	6.3
	9.14
	6.74
	8.3
	10.35
	7.1
	6.27
	8.24
	4.99
	5.76
	5.61
	6.09
	59.84
	146.85
	92.53
	56.92
	249.68
	70.89
	108.35
	184.95
	38.00

	Speed of first disbursement (months)
	
	13
	13
	12
	13
	12.84
	12.8
	12.8
	12.91
	12.9
	13.0
	13.1
	13.2
	13.4
	13.6 
	13.7
	13.7
	13.7
	13.7
	13.7
	13.6
	13.5
	13.6

	Speed of completion (months)
	24
	29
	29.5
	32
	33
	33.6
	32.7
	32.4
	32.41
	32.9
	33.6
	33.9
	33.8
	33.9
	34.2 
	34.6
	34.9 
	34.9
	35.2
	35.1
	34.4
	35.6
	35.7 

	Net emissions due to delays (ODP tonnes)
	
	
	
	8,995
	11,350
	11,727
	9,023
	6,466
	3,607
	4,538
	6,619
	2,674
	1,312
	92
	113
	101
	520
	538
	248
	238
	-881
	416.3
	499.6

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	UNIDO
	1996
	1997
	1998
	1999
	2000
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017
	2018

	ODS phased out
	73%
	80%
	100%
	57%
	70%
	100%
	100%
	88%
	100%
	99%
	100%
	100%
	84%
	86%
	100%
	100%
	0%
	27%
	42%
	100%
	100%
	100%
	50%

	Funds disbursed
	81%
	88%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	91%
	100%
	94%
	100%
	100%
	100%
	97%
	100%
	100%
	100%
	100%

	Project completion reports
	
	
	
	83%
	66%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	84%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%

	Distribution among countries
	
	
	
	83%
	74%
	89%
	73%
	78%
	67%
	79%
	69%
	75%
	82%
	61%
	81%
	83%
	100%
	72%
	67%
	100%
	76%
	54%
	64%

	Value of projects approved
	99%
	99%
	
	100%
	93%
	99%
	97%
	68%
	82%
	100%
	100%
	92%
	100%
	59%
	78%
	100%
	79%
	88%
	64%
	93%
	71%
	73%
	57%

	ODS to be phased out
	42%
	85%
	
	100%
	72%
	100%
	100%
	37%
	89%
	100%
	47%
	91%
	100%
	100%
	100%
	36%
	81%
	21%
	36%
	100%
	82%
	61%
	71%

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Cost of project preparation (% of approvals)
	
	2.2%
	4.2%
	2.7%
	3.8%
	2.7%
	3.3%
	3.6%
	2%
	0.9%
	1.8%
	2.1%
	1.3%
	11.9%
	5.7%
	2.7%
	3.9%
	1.1%
	1.3%
	1.8%
	3.6%
	2.6%
	0.4%

	Cost-effectiveness ($/kg)
	
	6.11
	6.27
	7.78
	6.71
	5.67
	7.28
	9.79
	3.58
	3.10
	7.13
	6.51
	9.34
	3.26
	22.58
	187.59
	35.34
	186.02
	79.01
	56.02
	65.50
	53.61
	22.83

	Speed of first disbursement (months)
	
	10
	9
	8
	9
	9.29
	9.16
	9.2
	9.06
	8.97
	9.0
	8.9
	8.7
	8.7
	8.7 
	8.4
	8.6
	8.5
	8.6
	9.0
	8.9
	9.0
	9.2

	Speed of completion (months)
	20
	24
	28
	26
	29
	29.85
	30.89
	31.7
	32.35
	32.98
	33.2
	33.5
	33.4
	33.7
	34.1 
	35.0
	35.9
	36.8
	38.3
	39.5
	40.2
	40.9
	41.1

	Net emissions due to delays (ODP tonnes)
	
	
	
	4,667
	5,899
	5,727
	5,960
	3,503
	13,035
	1,481
	3,864
	4,470
	3,431
	6,970
	8,918
	14,583
	17,144
	8,805
	9,939
	13,389
	6,906
	8,054.8
	7,971.7

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	World Bank
	1996
	1997
	1998
	1999
	2000
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017
	2018

	ODS phased out
	32%
	94%
	100%
	100%
	100%
	100%
	100%
	84%
	100%
	69%
	31%
	84%
	47%
	100%
	100%
	100%
	20%
	98%
	100%
	100%
	100%
	100%
	51%

	Funds disbursed
	64%
	77%
	88%
	97%
	100%
	74%
	100%
	100%
	73%
	100%
	100%
	100%
	100%
	73%
	64%
	43%
	15%
	100%
	100%
	100%
	78%
	96%
	62%

	Project completion reports
	
	
	
	61%
	98%
	74%
	100%
	84%
	84%
	100%
	84%
	74%
	69%
	25%
	20%
	85%
	10%
	100%
	24%
	24%
	8%
	33%
	11%

	Distribution among countries
	
	
	
	75%
	79%
	67%
	79%
	65%
	71%
	93%
	79%
	92%
	77%
	67%
	50%
	57%
	100%
	67%
	50%
	33%
	100%
	50%
	60%

	Value of projects approved
	94%
	87%
	
	100%
	75%
	92%
	100%
	82%
	94%
	83%
	87%
	83%
	93%
	98%
	3%
	93%
	29%
	93%
	72%
	100%
	39%
	29%
	95%

	ODS to be phased out
	34%
	100%
	
	100%
	83%
	72%
	91%
	65%
	59%
	100%
	66%
	93%
	35%
	100%
	89%
	11%
	7%
	25%
	11%
	100%
	50%
	74%
	69%

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Cost of project preparation (% of approvals)
	
	2.9%
	2.7%
	2.9%
	5.5%
	1.3%
	0.4%
	0.6%
	0.2%
	0.4%
	0.4%
	0.02%
	0.6%
	2.2%
	74.8%
	1.5%
	5.6%
	0.2%
	0.6%
	0.4%
	4.0%
	18.64%
	1.04%

	Cost-effectiveness ($/kg)
	
	3.6
	1.9
	2.83
	2.96
	3.85
	4.57
	6.12
	3.74
	1.04
	3.33
	3.29
	9.36
	1.43
	1.12
	545.23
	69.01
	118.26
	214.04
	19.84
	48.54
	52.66
	618.83

	Speed of first disbursement (months)
	
	26
	26
	25
	25
	25.33
	26.28
	26
	26.02
	25.7
	25.3
	25.0
	24.8
	24.8
	24.6 
	24.6
	24.7
	24.6
	24.6
	24.6
	24.6 
	24.5
	24.4 

	Speed of completion (months)
	37
	34
	40
	37
	39
	40.09
	41.35
	41
	40.88
	40.7
	40.3
	40.2
	39.8
	39.8
	40.2 
	40.2
	40.2
	40.3
	40.8
	40.8
	40.8
	41.0
	40.1 

	Net emissions due to delays (ODP tonnes)
	
	
	
	7,352
	16,608
	21,539
	22,324
	18,021
	8,338
	4,843
	5,674
	2,316
	1,303
	182
	1,680
	801
	901
	901
	1,002
	275
	455
	249.9
	788.4
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Annex II

NON-INVESTMENT PROJECT PERFORMANCE BY AGENCY
(1997-2018)

	UNDP
	1997
	1998
	1999
	2000
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017
	2018

	Funds disbursed
	100%
	98%
	100%
	100%
	93%
	61%
	100%
	100%
	100%
	92%
	100%
	100%
	100%
	100%
	100%
	84%
	88%
	100%
	47%
	82%
	100%
	100%

	Speed until first disbursement (months)
	12
	6
	11
	11.29
	12
	11.4
	11
	11.44
	11.5
	11.8
	11.7
	11.7
	11.8
	12.2
	11.8
	11.9
	11.9
	11.8
	12.0
	11.9
	11.8
	11.7

	Speed until project completion (months)
	31
	24
	33
	34.16
	36
	34.7
	35
	35.36
	35.4
	36.6
	37.3
	37.1
	37.3
	37.7
	37.1
	37.4
	37.2
	36.7
	36.3
	36.0
	36.8
	36.2

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	UNEP
	1997
	1998
	1999
	2000
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017
	2018

	Funds disbursed
	49%
	100%
	100%
	100%
	93%
	93%
	99%
	54%
	54%
	51%
	49%
	64%
	69%
	60%
	63%
	55%
	47%
	61%
	44%
	91%
	100%
	81%

	Speed until first disbursement (months)
	5
	3
	5
	6.33
	6.87
	7.3
	7.6
	8.49
	8.4
	8.4
	8.7
	9.0
	9.0
	9.5 
	9.6
	9.8
	9.8
	9.9
	10.1
	10.5
	10.5
	10.9

	Speed until project completion (months)
	20
	15
	25
	27.9
	29.66
	30.4
	31
	31.8
	32.4
	32.9
	33.2
	33.6
	32.9
	33.9 
	34.3
	34.4
	34.7
	35.3
	35.3
	36.1
	36.7
	36.7

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	UNIDO
	1997
	1998
	1999
	2000
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017
	2018

	Funds disbursed
	80%
	100%
	49%
	100%
	48%
	89%
	100%
	100%
	90%
	80%
	89%
	69%
	100%
	84%
	95%
	100%
	62%
	82%
	82%
	75%
	100%
	100%

	Speed until first disbursement (months)
	7
	6.5
	6
	8
	9.15
	9.85
	9.4
	9.34
	8.9
	9.8
	10.2
	10.6
	10.4
	10.4 
	10.3
	10.3
	10.2
	10.1
	10.0
	10.1
	10.4
	10.3

	Speed until project completion (months)
	24
	11
	29
	31
	33.66
	33.84
	33.7
	33.89
	31.9
	33.1
	33.0
	32.9
	32.0
	31.9 
	31.4
	32.8
	32.8
	33.7
	32.7
	33.4
	33.5
	32.7

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	World Bank
	1997
	1998
	1999
	2000
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017
	2018

	Funds disbursed
	100%
	49%
	35%
	27%
	12%
	38%
	100%
	79%
	100%
	57%
	59%
	59%
	19%
	47%
	75%
	59%
	49%
	42%
	100%
	88%
	100%
	100%

	Speed until first disbursement (months)
	16
	17
	5
	12
	11.95
	12.05
	13.7
	14.58
	13.6
	14.6
	14.3
	14.4
	14.4
	14.9 
	14.6
	15.1
	14.7
	14.0
	14.1
	14.8 
	16.8
	16.8 

	Speed until project completion (months)
	28
	32
	26
	30
	29.24
	28.85
	30
	30.39
	31
	31.5
	31.1
	30.7
	30.7
	30.3 
	30.1
	30.3
	30.2
	30.0
	29.8
	29.8
	29.2
	29.3 
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Annex III
QUALITATIVE ASSESSMENT OF THE IMPLEMENTING AGENCIES 
BY THE NATIONAL OZONE UNITS FOR 2018

	Category
	Sub-category
	Questions
	Values
	France
	Germany
	UNDP
	UNEP
	UNIDO
	World Bank

	IMPACT
	General
	Has cooperation with the implementing agency substantially contributed and added value to your work or organization in managing compliance in your country?
	Highly satisfactory
	1
	6
	14
	39
	22
	2

	
	
	
	Satisfactory
	 
	 
	7
	13
	7
	 

	
	
	
	Less satisfactory
	 
	1
	3
	 
	2
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	1
	 

	
	
	IMPACT (Overall Rating)
	Highly satisfactory
	1
	6
	12
	25
	11
	 

	
	
	
	Satisfactory
	 
	 
	5
	9
	8
	 

	
	
	
	Less satisfactory
	 
	 
	2
	 
	1
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	1
	 

	
	
	In the design and implementation of the project, has the implementing agency been striving to achieve sustainable results?
	Highly satisfactory
	1
	6
	15
	36
	18
	1

	
	
	
	Satisfactory
	 
	1
	7
	16
	11
	1

	
	
	
	Less satisfactory
	 
	 
	1
	 
	3
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 
	 

	ORGANIZATION AND COOPERATION
	General
	Did cooperation with the staff of the implementing agency take place in an atmosphere of mutual understanding?
	Highly satisfactory
	 
	4
	16
	42
	20
	1

	
	
	
	Satisfactory
	1
	3
	7
	10
	8
	1

	
	
	
	Less satisfactory
	 
	 
	1
	1
	4
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 
	 

	
	
	Did the implementing agency clearly explain its work plan and division of tasks?
	Highly satisfactory
	 
	4
	11
	36
	12
	1

	
	
	
	Satisfactory
	1
	2
	10
	16
	12
	1

	
	
	
	Less satisfactory
	 
	1
	1
	 
	6
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	1
	 

	
	
	Did the implementing agency sufficiently control and monitor the delivery of consultant services?
	Highly satisfactory
	 
	5
	10
	29
	14
	1

	
	
	
	Satisfactory
	1
	1
	11
	17
	12
	1

	
	
	
	Less satisfactory
	 
	 
	1
	1
	5
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	1
	 

	
	
	Did the responsible staff of the implementing agency communicate sufficiently and help to avoid misunderstanding?
	Highly satisfactory
	1
	3
	13
	42
	17
	2

	
	
	
	Satisfactory
	 
	3
	9
	10
	10
	 

	
	
	
	Less satisfactory
	 
	 
	2
	1
	3
	 

	
	
	
	Unsatisfactory
	 
	1
	 
	 
	2
	 

	
	
	Has the use of funds been directed effectively to reach the targets and was it agreed between the national ozone unit and the implementing agency?
	Highly satisfactory
	 
	5
	13
	42
	17
	2

	
	
	
	Satisfactory
	1
	2
	7
	9
	9
	 

	
	
	
	Less satisfactory
	 
	 
	1
	 
	5
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 
	 

	
	
	If there was a lead agency for a multi-agency project, did it coordinate the activities of the other implementing agencies satisfactorily?
	Highly satisfactory
	 
	1
	8
	22
	9
	 

	
	
	
	Satisfactory
	 
	 
	7
	16
	8
	1

	
	
	
	Less satisfactory
	 
	 
	 
	2
	3
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	1
	 

	
	
	ORGANIZATION AND COOPERATION (Overall Rating)
	Highly satisfactory
	 
	3
	8
	20
	9
	 

	
	
	
	Satisfactory
	1
	1
	4
	6
	6
	 

	
	
	
	Less satisfactory
	 
	 
	 
	1
	 
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	1
	 

	
	
	Was active involvement of the national ozone unit ensured in project Development?
	Highly satisfactory
	 
	5
	16
	38
	18
	1

	
	
	
	Satisfactory
	1
	2
	6
	13
	11
	1

	
	
	
	Less satisfactory
	 
	 
	1
	1
	3
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 
	 

	
	
	Was active involvement of the national ozone unit ensured in project Identification?
	Highly satisfactory
	 
	5
	15
	41
	18
	1

	
	
	
	Satisfactory
	1
	1
	5
	11
	10
	1

	
	
	
	Less satisfactory
	 
	1
	1
	 
	4
	 

	
	
	
	Unsatisfactory
	 
	 
	1
	 
	 
	 

	
	
	Was active involvement of the national ozone unit ensured in project Implementation?
	Highly satisfactory
	1
	6
	17
	40
	19
	1

	
	
	
	Satisfactory
	 
	1
	5
	12
	8
	1

	
	
	
	Less satisfactory
	 
	 
	1
	1
	4
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	1
	 

	
	
	Were the required services of the implementing agency delivered in time?
	Highly satisfactory
	1
	6
	9
	30
	11
	1

	
	
	
	Satisfactory
	 
	1
	10
	20
	14
	1

	
	
	
	Less satisfactory
	 
	 
	4
	2
	5
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	2
	 

	TECHNICAL ASSISTANCE/TRAINING
	General
	Did project partners receive sufficient technical advice and/or assistance in their decision-making on technology?
	Highly satisfactory
	1
	5
	12
	30
	15
	2

	
	
	
	Satisfactory
	 
	1
	8
	16
	11
	 

	
	
	
	Less satisfactory
	 
	1
	2
	 
	4
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 
	 

	
	
	Did the agency give sufficient consideration to training aspects within funding limits?
	Highly satisfactory
	1
	6
	11
	39
	14
	1

	
	
	
	Satisfactory
	 
	 
	8
	12
	13
	1

	
	
	
	Less satisfactory
	 
	 
	2
	 
	4
	 

	
	
	
	Unsatisfactory
	 
	1
	 
	 
	 
	 

	
	
	Do you feel that you have received sufficient support in building capacities for the national implementation of the project (within the funding limitations)?
	Highly satisfactory
	 
	5
	10
	37
	17
	2

	
	
	
	Satisfactory
	1
	2
	10
	15
	10
	 

	
	
	
	Less satisfactory
	 
	 
	 
	 
	4
	 

	
	
	
	Unsatisfactory
	 
	 
	2
	 
	1
	 

	
	
	Has the acquisition of services and equipment been successfully administered, contracted and its delivery monitored?
	Highly satisfactory
	 
	5
	12
	26
	16
	 

	
	
	
	Satisfactory
	1
	2
	5
	14
	9
	1

	
	
	
	Less satisfactory
	 
	 
	2
	 
	3
	 

	
	
	
	Unsatisfactory
	 
	 
	2
	 
	1
	 

	
	
	In case of need, was trouble-shooting by the agency quick and in direct response to your needs?
	Highly satisfactory
	 
	5
	12
	33
	11
	2

	
	
	
	Satisfactory
	1
	1
	6
	13
	13
	 

	
	
	
	Less satisfactory
	 
	1
	4
	 
	3
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	2
	 

	
	
	TECHNICAL ASSISTANCE/TRAINING (Overall Rating)
	Highly satisfactory
	 
	4
	10
	20
	11
	1

	
	
	
	Satisfactory
	1
	1
	5
	12
	6
	 

	
	
	
	Less satisfactory
	 
	 
	 
	 
	2
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	1
	 

	
	
	Was the selection and competence of consultants provided by the agency satisfactory?
	Highly satisfactory
	 
	4
	11
	32
	19
	1

	
	
	
	Satisfactory
	1
	1
	8
	13
	8
	 

	
	
	
	Less satisfactory
	 
	 
	1
	 
	4
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	1
	 

	
	
	Were project partners and stakeholders encouraged by the implementing agency to participate positively in decision-making and design of activities?
	Highly satisfactory
	1
	5
	12
	34
	19
	2

	
	
	
	Satisfactory
	 
	1
	7
	12
	7
	 

	
	
	
	Less satisfactory
	 
	1
	3
	 
	5
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	 

	
	Investment projects
	Has the agency been effective and met the expectations of stakeholders in providing technical advice, training and commissioning?
	Highly satisfactory
	1
	4
	11
	24
	12
	1

	
	
	
	Satisfactory
	 
	2
	8
	9
	11
	1

	
	
	
	Less satisfactory
	 
	 
	 
	 
	3
	 

	
	
	
	Unsatisfactory
	 
	 
	1
	 
	2
	 

	
	
	Has the agency been responsive in addressing any technical difficulties that may have been encountered subsequent to the provision of non-ODS technology?
	Highly satisfactory
	1
	3
	11
	22
	13
	2

	
	
	
	Satisfactory
	 
	3
	7
	8
	7
	 

	
	
	
	Less satisfactory
	 
	 
	1
	 
	2
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	3
	 

	
	National phase-out plans
	Has support for the distribution of equipment been adequate?
	Highly satisfactory
	1
	5
	10
	22
	13
	 

	
	
	
	Satisfactory
	 
	2
	7
	14
	10
	1

	
	
	
	Less satisfactory
	 
	 
	 
	1
	4
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	1
	 

	
	
	Has support to identify policy issues related to implementation been adequate?
	Highly satisfactory
	 
	2
	10
	31
	16
	1

	
	
	
	Satisfactory
	1
	2
	6
	17
	10
	1

	
	
	
	Less satisfactory
	 
	 
	2
	 
	5
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 
	 

	
	
	Has technical advice on equipment specifications been adequate?
	Highly satisfactory
	 
	4
	11
	26
	15
	1

	
	
	
	Satisfactory
	1
	3
	7
	10
	9
	1

	
	
	
	Less satisfactory
	 
	 
	1
	 
	5
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	1
	 

	
	
	Has the technical advice or training that was provided been effective?
	Highly satisfactory
	 
	5
	9
	37
	15
	2

	
	
	
	Satisfactory
	1
	2
	8
	9
	11
	 

	
	
	
	Less satisfactory
	 
	 
	1
	 
	3
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	1
	 

	
	
	Were proposed implementation strategies adequate?
	Highly satisfactory
	 
	5
	12
	30
	19
	2

	
	
	
	Satisfactory
	1
	1
	8
	15
	9
	 

	
	
	
	Less satisfactory
	 
	1
	 
	 
	2
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 
	 

	
	Regulatory assistance projects
	Were the regulations that were proposed by the agency Adapted to local circumstances?
	Highly satisfactory
	 
	2
	8
	27
	8
	1

	
	
	
	Satisfactory
	1
	2
	5
	18
	16
	1

	
	
	
	Less satisfactory
	 
	 
	1
	 
	2
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 
	 

	
	
	Were the regulations that were proposed by the agency Applicable?
	Highly satisfactory
	 
	2
	9
	29
	9
	1

	
	
	
	Satisfactory
	1
	2
	4
	16
	15
	1

	
	
	
	Less satisfactory
	 
	 
	1
	 
	2
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 
	 

	
	
	Were the regulations that were proposed by the agency Enforceable?
	Highly satisfactory
	 
	2
	8
	25
	7
	1

	
	
	
	Satisfactory
	1
	1
	4
	17
	14
	1

	
	
	
	Less satisfactory
	 
	 
	2
	 
	3
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 
	 

	
	Training projects
	Was the quality of the training provided satisfactory?
	Highly satisfactory
	 
	4
	11
	34
	16
	2

	
	
	
	Satisfactory
	1
	1
	10
	15
	9
	 

	
	
	
	Less satisfactory
	 
	 
	 
	 
	1
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 
	 

	
	
	Was the training designed so that those trained would be likely to use the skills taught?
	Highly satisfactory
	 
	4
	12
	36
	17
	2

	
	
	
	Satisfactory
	1
	1
	9
	15
	8
	 

	
	
	
	Less satisfactory
	 
	1
	 
	 
	1
	 

	
	
	
	Unsatisfactory
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