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ЗАМЕЧАНИЯ И РЕКОМЕНДАЦИИ СЕКРЕТАРИАТА ФОНДА
ЮНЕП просит Исполнительный комитет утвердить финансирование в размере 5 129 119 долларов США плюс эксплуатационные расходы учреждения в размере 150 800 долларов США для выполнения программы работы на 2026 год, сведенной воедино в таблице 1. Представленные на рассмотрение материалы прилагаются к настоящему документу.
Таблица 1: Программа работы ЮНЕП на 2026 год 
	Страна
	Мероприятие/проект
	Запрашивае-мая сумма (долл. США)
	Рекомендуемая сумма 
(долл. США)

	РАЗДЕЛ A. МЕРОПРИЯТИЯ, РЕКОМЕНДУЕМЫЕ ДЛЯ ОБЩЕГО УТВЕРЖДЕНИЯ

	[bookmark: _Hlk197603786]A1. Продление проектов по укреплению организационной инфраструктуры

	Камбоджа
	Продление проекта по укреплению организационной инфраструктуры (фаза XIII)
	298 522
	298 522

	Эритрея
	Продление проекта по укреплению организационной инфраструктуры (фаза VII)
	180 000
	180 000

	Эсватини
	Продление проекта по укреплению организационной инфраструктуры (фаза IX)
	180 000
	180 000

	Гамбия
	Продление проекта по укреплению организационной инфраструктуры (фаза XIII)
	180 000
	180 000

	Гренада
	Продление проекта по укреплению организационной инфраструктуры (фаза VIII)
	180 000
	180 000

	Кения
	Продление проекта по укреплению организационной инфраструктуры (фаза XIV)
	401 857
	401 857

	Либерия
	Продление проекта по укреплению организационной инфраструктуры (фаза XI)
	225 780
	225 780

	Монголия
	Продление проекта по укреплению организационной инфраструктуры (фаза XIV)
	180 000
	180 000

	Ниуэ
	Продление проекта по укреплению организационной инфраструктуры (фаза X)
	100 000
	100 000

	Палау
	Продление проекта по укреплению организационной инфраструктуры (фаза XI)
	180 000
	180 000

	Республика Молдова
	Продление проекта по укреплению организационной инфраструктуры (фаза XIII)
	183 707
	183 707

	Руанда
	Продление проекта по укреплению организационной инфраструктуры (фаза XI)
	180 000
	180 000

	Сент-Винсент и Гренадины 
	Продление проекта по укреплению организационной инфраструктуры (фаза IX)
	180 000
	180 000

	Самоа
	Продление проекта по укреплению организационной инфраструктуры (фаза XIII)
	180 000
	180 000

	Судан
	Продление проекта по укреплению организационной инфраструктуры (фаза XI)
	386 471
	386 471

	Тонга
	Продление проекта по укреплению организационной инфраструктуры (фаза XI)
	180 000
	180 000

	Тувалу
	Продление проекта по укреплению организационной инфраструктуры (фаза X)
	180 000
	180 000

	Зимбабве
	Продление проекта по укреплению организационной инфраструктуры (фаза XIII)
	392 782
	392 782

	Итого для A1
	3 969 119
	3 969 119

	A2: Подготовка проектов для кигалийских планов регулирования ГФУ (КПР)

	Сент-Китс и Невисa
	Подготовка КПР (этап I)
	65 000
	65 000

	Промежуточный итог A2
	65 000
	65 000

	Эксплуатационные расходы учреждения
	8 450
	8 450

	Итого для A2 
	73 450
	73 450

	A3: Техническая помощь для подготовки докладов о проверке потребления ГФУ и/или ГХФУ

	Бенин
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Чад
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Острова Кука
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Эсватини
	Доклад о проверке для этапа II ПОДПО и этапа I КПР 
	45 000
	45 000

	Эфиопия
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Фиджи
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Гамбия
	Доклад о проверке для этапа II ПОДПО и этапа I КПР 
	45 000
	45 000

	Гренада
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Гвинея-Биссау
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Кирибати
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Лаосская Народно-Демократическая Республика
	Доклад о проверке для этапа II ПОДПО и этапа I КПР 
	45 000
	45 000

	Лесото 
	Доклад о проверке для этапа II ПОДПО и этапа I КПР 
	45 000
	45 000

	Мали
	Доклад о проверке для этапа II ПОДПО
	30 000
	30 000

	Маршалловы острова
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Микронезия (Федеральные Штаты)
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Монголия
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Науру
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Ниуэ
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Палау
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Парагвай
	Доклад о проверке для этапа II ПОДПО
	30 000
	30 000

	Республика Молдова 
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Руанда
	Доклад о проверке для этапа II ПОДПО и этапа I КПР 
	45 000
	45 000

	Сент-Люсия
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Самоа
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Сейшелы
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Сьерра-Леоне 
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Соломоновы Острова
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Того
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Тонга
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Тувалу
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Уганда
	Доклад о проверке для этапа II ПОДПО
	30 000
	30 000

	Вануату
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Замбия
	Доклад о проверке для этапа II ПОДПО
	30 000
	30 000

	Зимбабве
	Доклад о проверке для этапа I КПР
	30 000
	30 000

	Промежуточный итог для A3
	1 095 000
	1 095 000

	Эксплуатационные расходы учреждения
	142 350
	142 350

	Итого для A3
	1 237 350
	1 237 350

	Итого для A1, A2, A3
	5 129 119
	5 129 119

	Эксплуатационные расходы учреждения для A1, A2, A3
	150 800
	150 800

	Общий итог
	5 279 919
	5 279 919


a ЮНИДО является сотрудничающим учреждением-исполнителем
РАЗДЕЛ A: МЕРОПРИЯТИЯ, РЕКОМЕНДОВАННЫЕ ДЛЯ ОБЩЕГО УТВЕРЖДЕНИЯ
A1: Продление проектов по укреплению организационной инфраструктуры
Описание проекта
ЮНЕП представила заявки на продление проектов по укреплению организационной инфраструктуры (УОИ) для стран, перечисленных в разделе A1 таблицы 1. Описание этих проектов представлено в приложении I к настоящему документу.
Замечания секретариата
Секретариат рассмотрел заявки на продление 18 проектов по укреплению организационной инфраструктуры на предмет их соответствия руководящим принципам[footnoteRef:2] и соответствующим решениям, касающимся критериев приемлемости и объемов финансирования. Заявки были сверены с первоначальными планами работы предыдущей фазы, данными, представленными в страновой программе (СП) и в соответствии со статьей 7, последним докладом о реализации планов организационной деятельности по поэтапному отказу от ГХФУ (ПОДПО), докладом учреждения о ходе реализации проекта и другими соответствующими решениями совещания Сторон. Было отмечено, что все 18 стран представили свои данные в соответствии со статьей 7 и свою страновую программу (СП) на 2024 или 2025 год. Шестнадцать стран соблюдают контрольные показатели по Монреальскому протоколу и представленные в их докладах данные о годовом потреблении ГХФУ и ГФУ не превышают годового максимально допустимого потребления, указанного в их соглашениях по ПОДПО и по КПР с Исполнительным комитетом. Кроме того, все представленные заявки включали оценку показателей эффективности, риска и устойчивости проекта, а также достижения целей по укреплению организационной инфраструктуры в соответствии с решением 91/63 b). [2:  Решение 91/63: b) утвердить пересмотренный формат для заключительных докладов и заявок на продление финансирования УОИ и соответствующие показатели эффективности; и c) предложить странам, действующим в рамках статьи 5, через двусторонние учреждения и учреждения-исполнители использовать пересмотренный формат, упомянутый в подпункте b) выше, для всех заявок на продление финансирования УОИ начиная с первого совещания Исполнительного комитета в 2023 году.] 

В случае Монголии секретариат отметил, что указанное в докладе о СП потребление ГФУ в стране на 2025 год составило 67 925 тонн экв. СО2, что выше базового и максимального допустимого уровня потребления в 57 309 тонн экв. СО2. Данные в соответствии со статьей 7 за 2025 год пока не были представлены. Секретариат отметил, что Монголия входит в список сторон, перечисленных в решении XXXV/16 тридцать пятого совещания сторон, касающемся последствий пандемии COVID-19 для базового потребления ГФУ некоторыми сторонами. Поэтому рекомендация по заявке о продлении УОИ для Монголии будет сделана в порядке исключения, с учетом положения Монголии как стороны, упомянутой в решении XXXV/16.
В случае Сент-Винсента и Гренадин секретариат принял к сведению решение XXXVII/14 сторон, посвященное несоблюдению сторонами Монреальского протокола по веществам, разрушающим озоновый слой, и тот факт, что, согласно докладу о СП и данным по статье 7 за 2025 год уровень потребления ГФУ в стране не превышает контрольных пределов Монреальского протокола. Поэтому рекомендация о продлении проекта об УОИ для Сент-Винсента и Гренадин будет сделана без ущерба для функционирования механизма Монреальского протокола по рассмотрению случаев несоблюдения.
Рекомендация секретариата
Секретариат рекомендует общее утверждение заявок на продление проектов по укреплению институциональной инфраструктуры для Камбоджи, Эритреи, Эсватини, Гамбии, Гренады, Кении, Либерии, Монголии, Ниуэ, Палау, Республики Молдовы, Руанды, Сент-Винсента и Гренадин, Самоа, Судана, Тонги, Тувалу и Зимбабве на уровнях финансирования, указанных в разделе А1 таблицы 1 настоящего документа при том понимании, что продление проекта для Монголии будет сделано в порядке исключения, с учетом положения Монголии как стороны, перечисленной в решении XXXV/16 тридцать пятого совещания сторон, касающемся последствий пандемии COVID-19 для базового потребления ГФУ некоторыми сторонами, и что продление проекта для Сент-Винсента и Гренадин делается без ущерба для функционирования механизма Монреальского протокола по рассмотрению случаев несоблюдения. Исполнительный комитет, возможно, пожелает довести до сведения вышеупомянутых правительств замечания, представленные в приложении II к настоящему документу.
A2: Подготовка проекта кигалийских планов регулирования ГФУ
Описание проекта
В качестве ведущего учреждения-исполнителя ЮНЕП представила заявку на подготовку этапа I КПР, в которой ЮНИДО указана сотрудничающим учреждением исполнителем, для одной страны, как это указано в разделе A2 таблицы 1.
Как ведущее учреждение-исполнитель для Сент-Китс и Невис, ЮНЕП представила описание мероприятий, необходимых для подготовки этапа I КПР и соответствующий бюджет по каждому из мероприятий, используя формат заявок на подготовку проекта для КПР. В качестве сотрудничающего учреждения-исполнителя для Сент-Китс и Невис, ЮНИДО запросила 35 000 долларов США плюс эксплуатационные расходы учреждения в размере 2 450 долларов США[footnoteRef:3]. [3: ] 

Замечания секретариата
При рассмотрении заявки секретариат принял во внимание руководящие принципы финансирования подготовки КПР, изложенные в решении 87/50; мероприятия, предлагаемые для подготовки проекта и их связь с мероприятиями, способствующими реализации проектов в стране.
Заявка для Сент-Китс и Невис включает в себя данные о потреблении ГФУ в чистом виде и в составе смесей за период с 2023 по 2025 годы. Подготовка мероприятий в рамках проекта включает общенациональное исследование и сбор данных о потреблении ГФУ; анализ использования ГФУ и его альтернатив; обзор соответствующих национальных инициатив, направлений политики и законодательства, связанных с поэтапным сокращением использования ГФУ; оценку потребностей в секторе обслуживания холодильного оборудования и кондиционеров воздуха (ХКВ); подготовку плана коммуникации и информационно-просветительских мероприятий; и разработку всеобъемлющей стратегии поэтапного сокращения потребления ГФУ.
Секретариат отметил, что страна ратифицировала Кигалийскую поправку[footnoteRef:4], что правительство предоставило рекомендательное письмо в поддержку подготовки проекта; и что запрашиваемое финансирование соответствует решению 87/50. Секретариат также принял к сведению указание ЮНЕП, что для Сент-Китс и Невис подготовка проекта в рамках общей стратегии КПР будет опираться на работу, проделанную в ходе подготовительных мероприятий по поэтапному сокращению использования ГФУ, которые способствовали ратификации Кигалийской поправки в стране. [4:  Сент-Китс и Невис ратифицировали Кигалийскую поправку 29 августа 2025 года.] 

Рекомендация секретариата
Секретариат рекомендует общее утверждение подготовки проекта для этапа I кигалийского плана регулирования для Сент-Китс и Невис на уровне финансирования, указанном в разделе А2 таблицы 1.
A3: Техническая помощь при подготовке доклада о проверке потребления ГФУ и/или ГХФУ
Описание проекта
В соответствии с решением 61/46 c)[footnoteRef:5] секретариат отобрал несколько стран с низким объемом потребления (НОП), подпадающих под действие статьи 5, с целью проверки соблюдения ими соглашений о планах организационной деятельности по поэтапному отказу от ГХФУ (ПОДПО). В качестве ведущего/назначенного учреждения-исполнителя ЮНЕП запрашивает финансирование для проверки этапа II ПОДПО для Мали, Парагвая, Уганды и Замбии, как показано в разделе А3 таблицы 1. [5:  Секретариату было поручено на первом совещании каждого года предоставлять Исполнительному комитету список стран, составляющих 20% от числа стран с базовым уровнем потребления ГХФУ не более 360 метрических тонн и утвержденным ПОДПО для утверждения финансирования для этих стран в целях проверки соблюдения ими соглашения по ПОДПО за данный год.] 

В соответствии с решением 96/22 a) i)[footnoteRef:6] секретариат подготовил список стран с целью проверки соблюдения ими соглашений по КПР. В качестве ведущего/назначенного учреждения-исполнителя ЮНЕП запрашивает финансирование для проверки этапа I КПР для Бенина, Чада, Островов Кука, Эфиопии, Фиджи, Гренады, Гвинеи-Биссау, Кирибати, Маршалловых Островов, Федеральных Штатов Микронезии, Монголии, Науру, Ниуэ, Палау, Республики Молдовы, Сент-Люсии, Самоа, Сейшелов, Сьерра-Леоне, Соломоновых Островов, Того, Тонги, Тувалу, Вануату и Зимбабве, как показано в разделе А3 таблицы 1. [6:  Секретариату было поручено предоставлять Исполнительному комитету на первом совещании каждого года список стран со средним потреблением ГФУ в секторе обслуживания в базовые годы в объеме 360 тонн (т) и ниже, которые запланировали получение транша в рамках своих планов реализации Кигалийской поправки по ГФУ (КПР) на следующий год и ранее не получали финансирования для проведения таких проверок и включить в этот список страны, среднее потребление ГФУ в секторе обслуживания которых в базовые годы превышает 360 т, но которые приняли решение получать финансирование как страны НОП в соответствии с решением 92/36 c).] 

В соответствии с решением 96/22 b)[footnoteRef:7], в качестве ведущего/назначенного учреждения-исполнителя ЮНЕП запрашивает также финансирование на проведение комплексной проверки этапа I КПР и этапа II ПОДПО для Эсватини, Гамбии, Лаосской Народно-Демократической Республики, Лесото и Руанды. [7:  сохранять бюджет, рекомендованный для проведения проверки потребления ГФУ в странах с объемом потребления до 360 т в секторе обслуживания в базовые годы, в пределах 30 000 долл. США или 45 000 долл. США, когда проводится одновременная проверка потребления ГФУ и ГХФУ.] 

Во исполнение соответствующих решений, ЮНЕП представляет заявки на техническую помощь при подготовке доклада о проверке потребления ГФУ и/или ГХФУ для 34 стран в качестве ведущего/назначенного учреждения-исполнителя, как показано в разделе А3 таблицы 1.
Замечания секретариата
Секретариат отметил, что запрашиваемые объемы финансирования соответствуют финансированию, утвержденному для аналогичных проверок на предыдущих совещаниях и отметил далее, что доклады о проверке должны быть представлены как минимум за 10 недель до совещания Исполнительного комитета, на котором должен быть утвержден следующий транш финансирования ПОДПО или КПР.
В случае Лесото назначенным учреждением-исполнителем для этапа II ПОДПО является правительство Германии, а ЮНЕП выступает назначенным учреждением-исполнителем для этапа I КПР. В результате обсуждения между учреждениями-исполнителями, ЮНЕП согласилась провести комбинированную проверку для Лесото, что и было отражено в таблице выше.
Рекомендация секретариата
Секретариат рекомендует общее утверждение технической помощи для подготовки докладов о проверке, как указано ниже, на уровне финансирования, отраженном в разделе А3 таблицы 1, при том понимании, что доклады о проверке должны быть представлены как минимум за 10 недель до соответствующего совещания Исполнительного комитета, на котором предполагается утверждение следующего транша финансирования в рамках ПОДПО или КПР:
потребление ГФУ для этапа I кигалийского плана регулирования ГФУ (КПР) для Бенина, Чада, Островов Кука, Эфиопии, Фиджи, Гренады, Гвинеи-Биссау, Кирибати, Маршалловых островов, Федеральных Штатов Микронезии, Монголии, Науру, Ниуэ, Палау, Республики Молдовы, Сент-Люсии, Самоа, Сейшел, Сьерра-Леоне, Соломоновых островов, Того, Тонги, Тувалу, Вануату и Зимбабве;
потребление ГХФУ для этапа II плана организационной деятельности по поэтапному отказу от ГХФУ (ПОДПО) для Мали, Парагвая, Уганды и Замбии; и
потребление ГФУ и ГХФУ для этапа I КПР и этапа II ПОДПО для Эсватини, Гамбии, Лаосской Народно-Демократической Республики, Лесото и Руанды.
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Annex I
INSTITUTIONAL STRENGTHENING PROJECT PROPOSALS[footnoteRef:8] [8:  Data as at December 2024 are based on document UNEP/OzL.Pro/ExCom/97/14.] 

Cambodia: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-02
	30,000

	Phase II:
	Dec-03
	100,000

	Phase III:
	Nov-05
	112,667

	Phase IV:
	Nov-07
	112,667

	Phase V:
	Jul-09
	112,667

	Phase VI:
	Jul-11
	112,667

	Phase VII:
	Jul-13
	112,667

	Phase VIII:
	May-15
	112,667

	Phase IX:
	Jul-17
	144,214

	Phase X:
	May-19
	144,214

	Phase XI:
	Jul-21
	144,214

	Phase XII:
	Jun-23
	298,523

	Total:
	1,537,166

	Amount requested for renewal (phase XIII) (US $):
	298,522

	Amount recommended for approval for phase XIII (US $): 
	298,522

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XIII to the Multilateral Fund (US $):
	298,522

	Date of approval of country programme:
	2003

	Date of approval of HCFC phase-out management plan:
	2010

	Date of approval of Kigali HFC implementation plan:
	2023

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.5

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	15.0

	(c)	Annex E, (methyl bromide) (average 1995-1998)
	0.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	1,263,376

	Latest reported ODS consumption (2025) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	4.76

	(c)	Annex E, (methyl bromide)
	0.00

		Total:
	4.76

	(d)	Annex F (HFCs) (CO2-eq tonnes) as per Article 7:
	809,514

	Year of reported country programme implementation data:
	2025

	Amount approved for projects (as at December 2025) (US $):
	6,050,605

	Amount disbursed (as at December 2024) (US $):
	4,970,955

	ODS to be phased out (as at December 2025) (ODP tonnes):
	153.6

	ODS phased out (as at December 2024) (ODP tonnes):
	96.7



1. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	Investment projects:
	1,132,796

	Institutional strengthening:
	1,537,166

	Project preparation, technical assistance, training and other non-investment projects:
	3,380,643

	Total:
	6,050,605

	HFC activities funded from additional voluntary contributions
	150,000



Progress report
The national ozone unit (NOU) of Cambodia implemented phase XII of the institutional strengthening (IS) project, achieving all seven objectives based on the performance indicators reported. The NOU enforced the HCFC and HFC licensing and quota system through the Sub-decree on ODS Management 2021, supported by an electronic licensing system fully linked to the National Single Window since August 2024. From January 2026, the system was modified to manage HFC quotas in CO2‑equivalent tonnes, enabling quota use to be tracked against Cambodia’s HFC phase-down obligations. Additional monitoring mechanisms, including mandatory labelling of HCFC containers and market inspections, were maintained to prevent illegal trade. Country programme and Article 7 data were submitted in a timely manner through collaboration with the General Department of Customs and Excise on data sharing and reconciliation. The NOU coordinated with stakeholders to complete the fifth tranche of the HCFC phase-out management plan (HPMP) and to prepare and implement additional projects, including stage I of the Kigali HFC implementation plan (KIP), the energy-efficiency project, the national inventory of ODS banks and the sixth tranche of the HPMP, supported by increased Government-funded NOU capacity for Kigali Amendment activities. Public awareness activities were conducted, and the NOU participated in regional and global Montreal Protocol meetings. 
Plan of action
In phase XIII of the IS project, the NOU will concentrate on: implementing and enforcing the HCFC and HFC quota and licensing system; working with customs to monitor legal trade in ODS and HFCs and track import and export statistics under the new Harmonized System (HS) code system (AHTN 2028[footnoteRef:9]); working with relevant authorities toward the planned ban on imports of HCFC-based refrigeration and air‑conditioning (RAC) equipment and R-410A-based residential air conditioners by 1 January 2029, including consideration of national customs codes for RAC equipment; conducting regular data collection and reconciliation to ensure timely Article 7 and country programme reporting; coordinating implementation of approved Multilateral Fund projects; updating the communication and outreach strategy; continuing information dissemination and international and regional cooperation; and integrating gender mainstreaming, including efforts to increase women’s participation in training, inspections and awareness activities. [9:  The ASEAN Harmonised Tariff Nomenclature 2028 (AHTN 2028) is the 8-digit commodity nomenclature standard for the Association of Southeast Asian Nations (ASEAN) set to align with the World Customs Organization’s HS 2028 system.] 

Sustainability and risk assessment
The successful implementation of the IS project in Cambodia relies on stable financial support from the Multilateral Fund, continued Government ownership and stakeholder cooperation. The NOU has maintained stable staffing and daily operations, with support from senior management and guidance from the Steering Committee. Sustainability is further supported by the electronic licensing system linked to the National Single Window, data reconciliation with Customs, and continued enforcement of the HCFC and HFC licensing and quota system. The Government did not identify major risks to the achievement of IS objectives; however, continued coordination with customs, stakeholders and implementing agencies will be needed to sustain ODS phase-out and support HFC phase-down obligations.
Eritrea: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-05 & Apr‑08
	74,000

	Phase II:
	Dec-12
	60,000

	Phase III:
	Dec-16
	85,000

	Phase IV:
	Dec-19
	85,000

	Phase V:
	Jul-21
	85,000

	Phase VI:
	Jun-23
	180,000

		Total:
	569,000

	Amount requested for renewal (phase VII) (US $):
	180,000

	Amount recommended for approval for phase VII (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VII to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	2008

	Date of approval of HCFC phase-out management plan:
	2012

	Date of approval of Kigali HFC implementation plan:
	2025

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	1.1

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.5

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	169,249

	Latest reported ODS consumption (2025) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.0

	(b)	Annex C, Group I (HCFCs)
	0.36

	(c)	Annex E (methyl bromide)
	0.0

		Total:
	0.36

	(d)	Annex F (HFCs) (CO2-eq tonnes) as per Article 7:
	157,324

	Year of reported country programme implementation data:
	2025

	Amount approved for projects (as at December 2025) (US $):
	2,397,497

	Amount disbursed (as at December 2024) (US $):
	1,559,130

	ODS to be phased out (as at December 2025) (ODP tonnes):
	9.2

	ODS phased out (as at December 2024) (ODP tonnes):
	4.9



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	Investment projects:
	587,859

	Institutional strengthening:
	569,000

	Project preparation, technical assistance, training and other non-investment projects:
	1,240,638

	Total:
	2,397,497

	HFC activities funded from additional voluntary contributions
	95,000



Progress report
Phase VI of the IS project in Eritrea was implemented with four of the seven objectives fully achieved, based on the performance indicators, and three partially achieved. During the reporting period, the NOU coordinated implementation of stage II of the HPMP, prepared and submitted stage I of the KIP, and implemented IS activities, including awareness programmes and training for RAC technicians and customs officers. The NOU was staffed by four members, including an additional staff member to support data collection, reporting and monitoring. Strong collaboration was maintained with RAC experts, importers and other key stakeholders. More than 80 refrigerant cylinders were inspected between 2023 and 2025, with one case of counterfeit refrigerant detected. Eritrea submitted Article 7 and country programme data to the Ozone and Fund Secretariats, respectively, and sex-disaggregated participation data were collected.
Plan of action
During phase VII of the IS project, the Department of Environment, through the NOU, will continue to support compliance with the Montreal Protocol control measures by coordinating activities for the gradual phase-out of HCFCs and for HFC phase-down. Priority will be given to maintaining the licensing and quota system, strengthening collaboration with key stakeholders, and sustaining data collection, reporting and monitoring capacity. Implementation of stage II of the HPMP and stage I of the KIP will continue, including training for RAC technicians and customs officers. Awareness-raising activities, including stakeholder workshops and targeted publications, will be conducted to support effective implementation. The NOU will strengthen cooperation with Customs to monitor and prevent illegal trade, integrate gender considerations into project activities, and support efforts to ban high-GWP HFC-based residential and commercial refrigeration equipment by 2028.
Sustainability and risk assessment
The Department of Environment, as the national focal point for Multilateral Environmental Agreements (MEAs), including the Montreal Protocol, provides strong institutional support for project implementation. The Department contributes counterpart funding and has the human and infrastructure capacity to sustain project activities. Regular audits by the Office of the Auditor General support financial accountability and sound management. Illegal trade remains a possible risk, although strict border control measures are in place; this risk will be mitigated through continued cooperation with Customs, inspection activities and training of customs officers. These measures, together with strong Government ownership, support the long-term sustainability of project outcomes and minimize implementation risks.
Eswatini: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Dec-94
	76,072

	Phase II:
	Dec-03
	58,344

	Phase III:
	Nov-07
	60,000

	Phase IV:
	Nov-09 & Apr-10
	60,000

	Phase V:
	Dec-13
	60,000

	Phase VI:
	May-19
	85,000

	Phase VII:
	Jul-21
	85,000

	Phase VIII:
	Jun-23
	180,000

	Total:
	664,416

	Amount requested for renewal (phase IX) (US $):
	180,000

	Amount recommended for approval for phase IX (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase IX to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	1994

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of Kigali HFC implementation plan:
	2024

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.00

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	1.73

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.60

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	105,500

	Latest reported ODS consumption (2025) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.0

	(b)	Annex C, Group I (HCFCs)
	0.41

	(c)	Annex E (methyl bromide)
	0.0

		Total:
	0.41

	(d)	Annex F (HFCs) (CO2-eq tonnes) as per Article 7:
	74,942

	Year of reported country programme implementation data:
	2025

	Amount approved for projects (as at December 2025) (US $):
	3,372,218

	Amount disbursed (as at December 2024) (US $):
	2,645,503

	ODS to be phased out (as at December 2025) (ODP tonnes):
	39.2

	ODS phased out (as at December 2024) (ODP tonnes):
	34.4



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	Investment projects:
	1,049,155

	Institutional strengthening:
	664,416

	Project preparation, technical assistance, training and other non-investment projects:
	1,658,648

	Total:
	3,372,218

	HFC activities funded from additional voluntary contributions
	95,000



Progress report
During phase VIII, the NOU of Eswatini continued to coordinate Montreal Protocol activities in collaboration with government institutions, industry stakeholders and training institutions. The NOU achieved six of the seven objectives, based on the performance indicators, with one partially achieved owing to delays in the submission of 2023 and 2024 country programme data. Key achievements included the gazetting of the ODS and HFC regulations, enforcement of the HCFC and HFC licensing and quota system, capacity-building for customs and enforcement officers, submission of stage I of the KIP, and reporting of ODS and HFC consumption data to the Fund and Ozone Secretariats. The NOU also developed a communication and awareness strategy, commemorated World Ozone Day, and hosted the 2024 World Refrigeration Day Sustainable Cooling Summit. Two female RAC technicians participated in the Cool Training Programme in September 2025 and have since been trained as assessors and refrigeration trainers, mentoring six other female technicians. A dedicated data team was established to support timely reporting, and 2025 country programme data were submitted on time.  
Plan of action
In the upcoming phase IX of the IS project, the NOU will focus on: strengthening public awareness activities targeting consumers, equipment distributors, and marginalized and rural communities to support the ban on HCFC-based equipment imports; continuing capacity-building for RAC technicians, customs, and other border enforcement agencies, including a certified low-GWP refrigerant course for the two female technicians in late 2026, who will continue as trainers and mentors; prioritizing operationalization of the refrigerant recovery system; strengthening enforcement of the ODS and HFC Regulations (2025); continuing implementation of the licensing and quota system, supported by an electronic licensing system expected to be operational by September 2026; completing registration and use of the iPIC system to prevent illegal trade; collaborating with the Department of Energy on energy efficiency regulations; and finalizing a gender strategy by March 2027. These actions will support Eswatini in maintaining compliance with the Montreal Protocol and achieving the total phase-out of HCFCs by 31 December 2029.
Sustainability and risk assessment
The Government of Eswatini has designated a permanent officer as Ozone Coordinator within the NOU, supporting continuity of implementation in the event of changes in project staff. The NOU operates within the Eswatini Environment Authority and follows established government financial and administrative procedures, with project activities subject to regular oversight and annual audits. The National Ozone Steering Committee provides additional guidance and supports coordination among key stakeholders. Sustainability is further strengthened through capacity-building for customs officers, enforcement agencies and RAC technicians, as well as through the ODS and HFC Regulations (2025), which provide the legal framework for continued enforcement and monitoring of controlled substances. The risk of HCFC-22 smuggling, which may increase as import quotas are reduced, is being mitigated through the introduction of end-user declaration forms, joint inspections with Customs and Police at importer and workshop premises, and the continued use of electronic licences uploaded directly to the ASYCUDA customs system to prevent counterfeiting and enable real-time verification.
Gambia (the): Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	May-96
	47,686

	Phase II:
	Mar-00
	31,640

	Phase III:
	Dec-03
	36,573

	Phase IV:
	Apr-06
	59,971

	Phase V:
	Apr-08
	60,000

	Phase VI:
	Jul-10
	60,000

	Phase VII:
	Jul-12
	60,000

	Phase VIII:
	May-14
	60,000

	Phase IX:
	Dec-16
	85,000

	Phase X:
	May-19
	85,000

	Phase XI:
	Jul-21
	85,000

	Phase XII:
	Jun-23
	180,000

		Total:
	850,870

	Amount requested for renewal (phase XIII) (US $):
	180,000

	Amount recommended for approval for phase XIII (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XIII to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	1996

	Date of approval of HCFC phase-out management plan:
	2011

	Date of approval of Kigali HFC implementation plan:
	2024

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	1.5

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	271,515

	Latest reported ODS consumption (2025) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	0.19

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	0.19

	(d)	Annex F (HFCs) (CO2-eq tonnes) as per Article 7:
	193,479

	Year of reported country programme implementation data:
	2025

	Amount approved for projects (as at December 2025) (US $):
	3,037,232

	Amount disbursed (as at December 2024) (US $):
	2,385,644

	ODS to be phased out (as at December 2025) (ODP tonnes):
	49.0

	ODS phased out (as at December 2024) (ODP tonnes):
	43.1



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	Investment projects:
	553,518

	Institutional strengthening:
	850,870

	Project preparation, technical assistance, training and other non-investment projects:
	1,632,844

	Total:
	3,037,232

	HFC activities funded from additional voluntary contributions
	95,000



Progress report
The NOU of the Gambia coordinated and implemented Montreal Protocol activities during the phase XII reporting period, including activities related to stage I of the KIP and stage II of the HPMP. The NOU achieved five of the seven objectives, based on the performance indicators, with two partially achieved. The NOU comprises three full-time staff, including one additional person reflecting the expanded Montreal Protocol portfolio. Key achievements included the development of revised ODS regulations incorporating HFC control measures, progress on an online permit system, capacity-building for customs and enforcement officers and RAC technicians, awareness-raising activities, including World Ozone Day celebrations, and strengthened inter-agency collaboration through regular steering committee meetings. The NOU also ensured the timely submission of 2025 Article 7 and country programme data, supported the female RAC association in developing its constitution, and organized dedicated training for female technicians.
Plan of action
In the upcoming phase XIII of the IS project, the NOU will focus on finalizing the revised ODS regulations; strengthening implementation and enforcement of the licensing and quota system, including deployment of an online licensing and quota management system; expanding capacity-building for customs and enforcement officers and RAC technicians, with increased emphasis on certification and gender inclusion; supporting the official registration of the female RAC association; finalizing a communication and awareness strategy; developing a project proposal for the inventory of banks of waste controlled substances; submitting the second tranche of stage I of the KIP and third tranche of stage II of the HPMP; and supporting compliance with the HFC phase-down and HCFC phase-out schedules.
Sustainability and risk assessment
The sustainability of the programme is supported by established institutional frameworks, inter‑ministerial collaboration and stakeholder engagement. Key risks relate to illegal cross-border trade in refrigerants, particularly blended substances imported in small quantities. To mitigate these risks, the Government will enhance awareness of controlled substances, strengthen joint enforcement operations at entry points, maintain updated importer registers, continue capacity-building, and improve monitoring systems to support sustained compliance with Montreal Protocol obligations.
Grenada: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-00 and Dec-04
	51,900

	Phase II:
	Nov-06 
	60,000

	Phase III:
	Apr-10
	52,500

	Phase IV:
	Jul-12
	60,000

	Phase V:
	Nov-15
	85,000

	Phase VI:
	Jun-18
	85,000

	Phase VII:
	Jul-21
	85,000

	Total:
	479,400

	Amount requested for renewal (phase VIII) (US $):
	180,000

	Amount recommended for approval for phase VIII (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	2000

	Date of approval of HCFC phase-out management plan:
	2010

	Date of approval of Kigali HFC implementation plan:
	2023

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	0.8

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	52,815

	Latest reported ODS consumption (2024) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	0.02

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	0.02

	(d)	Annex F (HFCs) (CO2-eq tonnes) as per Article 7:
	48,400

	Year of reported country programme implementation data:
	2025

	Amount approved for projects (as at December 2025) (US $):
	2,076,645

	Amount disbursed (as at December 2024) (US $):
	1,386,074

	ODS to be phased out (as at December 2025) (ODP tonnes):
	9.8

	ODS phased out (as at December 2024) (ODP tonnes):
	8.4



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	Investment projects:
	328,392

	Institutional strengthening:
	479,400

	Project preparation, technical assistance, training and other non-investment projects:
	1,268,853

	Total:
	2,076,645

	HFC activities funded from additional voluntary contributions
	50,000



Progress report
Phase VII of the IS project for Grenada supported the country in maintaining compliance with the Montreal Protocol and its Kigali Amendment. The NOU achieved five of the seven objectives, based on the performance indicators, with two partially achieved. Although implementation was affected by limited NOU capacity and external factors, including COVID-19 pandemic disruptions, changes in Government and Hurricane Beryl, the project was completed with the participation of key national stakeholders and support from UNEP. The recruitment of the National Ozone Assistant in January 2025 contributed to strengthened and timely reporting, coordination and activity implementation. The project supported ODS legislation and regulations, including the administrative ban on HCFC-based equipment implemented and enforced since December 2024, and progress on the revised Montreal Protocol Substances Bill which is expected to restrict imports of certain RAC equipment based on GWP thresholds. Grenada continued data reporting, stakeholder engagement, coordination of stage II of the HPMP and stage I of the KIP, awareness-raising, participation in regional and international Montreal Protocol meetings, and gender mainstreaming through awareness activities and stakeholder engagement.
Plan of action
Under phase VIII, the Government of Grenada will continue to build national capacity, coordinate activities for HCFC phase-out and HFC phase-down, and promote low-GWP, energy-efficient alternatives. Having complied with the baseline HFC consumption freeze, the Government will strengthen institutional arrangements for implementation of stage I of the KIP, with continued support from UNEP, the Steering Committee and national focal points. The NOU will strengthen internal coordination, including through the planned recruitment of a Project Officer to support reporting, monitoring and project coordination; continue implementing and strengthening the HCFC and HFC licensing and quota systems; coordinate and monitor activities under stage II of the HPMP and stage I of the KIP; and work with stakeholders in the RAC sector through training and capacity development. The NOU will maintain Article 7 and country programme data reporting and active participation in Montreal Protocol meetings. Public awareness will be expanded through digital, print, social and traditional media, and gender mainstreaming will be supported through consultations with gender-focused stakeholders and targeted actions to promote women’s participation in the refrigeration servicing sector.
Sustainability and risk assessment
The NOU functions within the Department of Renewable Energy in the Ministry of Climate Resilience, the Environment and Renewable Energy, with oversight from the Office of the Permanent Secretary. The NOU work programme is integrated into the Department and Ministry workplans and supported by Government in-kind contributions, contributing to the sustainability of the IS project. Potential risks relate to NOU capacity and external disruptions, including natural disasters, changes in Government and interruptions to in-person activities. These risks will be mitigated through strengthened internal coordination, the planned recruitment of a Project Officer, flexible work planning, diversified communication channels and continued integration of NOU activities into Ministry plans. Interim progress reports to UNEP will support early identification of implementation issues and timely technical support where needed.
Kenya: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-93
	197,712

	Phase II:
	Jul-98
	131,834

	Phase III:
	Dec-00
	131,569

	Phase IV:
	Nov-02
	171,153

	Phase V:
	Dec-04
	162,197

	Phase VI:
	Jul-07-Jul-08
	151,666

	Phase VII:
	Jul-09
	107,431

	Phase VIII:
	Dec-10
	151,667

	Phase IX:
	Apr-13
	151,667

	Phase X:
	May-15
	151,667

	Phase XI:
	Nov-17
	194,134

	Phase XII:
	Dec-20
	194,134

	Phase XIII:
	Jun-23
	401,857

		Total:
	2,298,688

	Amount requested for renewal (phase XIV) (US $):
	401,857

	Amount recommended for approval for phase XIV (US $): 
	401,857

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XIV to the Multilateral Fund (US $):
	401,857

	Date of approval of country programme:
	1994

	Date of approval of HCFC phase-out management plan:
	2012

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	1.1

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	52.2

	(c)	Annex E (methyl bromide) (average 1995-1998)
	217.5

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	1,543,824

	Latest reported ODS consumption (2024) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	6.07

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	6.07

	(d)	Annex F (HFCs) (CO2-eq tonnes) as per Article 7:
	890,579

	Year of reported country programme implementation data:
	2024

	Amount approved for projects (as at December 2025) (US $):
	10,147,108

	Amount disbursed (as at December 2024) (US $):
	8,929,058

	ODS to be phased out (as at December 2025) (ODP tonnes):
	675.5

	ODS phased out (as at December 2024) (ODP tonnes):
	707.3



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	5,913,439

	(b)	Institutional strengthening:
	2,298,688

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	1,934,981

		Total:
	10,147,108

	(d)	HFC activities funded from additional voluntary contributions
	150,000



Progress report
Phase XIII of the IS project in Kenya strengthened the national institutional framework for the Montreal Protocol and was implemented with four of the seven objectives fully achieved, based on the performance indicators, and three partially achieved. The revised Environmental Management and Coordination (Controlled Substances) Regulations were gazetted on 28 February 2025, incorporating the HFC licensing and quota system and an import ban on HCFC-based equipment. The NOU continued to implement the ODS regulations through enforcement of the HCFC licensing and quota system, coordinated activities under stage II of the HPMP, and conducted training for customs officers and RAC technicians to strengthen enforcement and compliance capacity. Article 7 and country programme data were reported. The NOU collected data on female participation in RAC training and awareness activities to support gender mainstreaming, participated in regional network and Montreal Protocol meetings, and conducted awareness activities, including World Ozone Day, media engagement and stakeholder workshops. The IS report noted, however, that HFC baseline data for previous years were inaccurate owing to voluntary reporting prior to the establishment of the mandatory HFC licensing and quota system. The additional time needed to review and reconcile the HFC baseline data affected the timing of the preparation of stage I of the KIP and the third tranche of stage II of the HPMP.
Plan of action
In phase XIV, the NOU of Kenya, in collaboration with stakeholders and partners, will continue implementing the IS project, coordinating stage II of the HPMP and supporting HFC phase-down activities under the Kigali Amendment. The NOU will convene regular meetings of the National Committee on Controlled Substances (NACODS), and support implementation of the Environmental Management and Coordination (Controlled Substances) Regulations, including through multi-agency enforcement and awareness activities for importers, intermediaries, and the general public. The NOU will establish a single window system linking the National Environment Management Authority (NEMA), the NOU and the Kenya Revenue Authority (KRA), support timely Article 7 and country programme data reporting, and train RAC technicians, customs officers and other enforcement officers. Awareness activities, including World Ozone Day, will be guided by a communication and awareness plan informed by stakeholder feedback. The NOU will facilitate stakeholder agreements, coordinate progress and expenditure reporting and tranche submissions, participate in regional and international Montreal Protocol meetings, and implement gender strategies through a database of female RAC technicians, trainers and women in RAC equipment shops.
Sustainability and risk assessment
The Ministry of Environment, Climate Change and Forestry provides counterpart support and has the institutional capacity to support project implementation. The NOU operates within a framework comprising the NACODS and strengthened inter-agency coordination with NEMA and the KRA. The project is subject to annual audits by the Office of the Auditor General. Potential risks to continuity during phase XIV include political and institutional changes. These risks will be mitigated through the existing institutional framework, NACODS oversight, the proposed single-window system and formal data-sharing mechanisms consistent with the Data Protection Act. With strong institutional ownership and regular auditing mechanisms in place, the project is expected to be implemented in a manner that promotes sustainability and minimizes potential risks. 
Liberia: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Dec-03
	127,820

	Phase II:
	Mar-07
	85,213

	Phase III:
	Apr-09
	85,213

	Phase IV:
	Apr-11
	85,213

	Phase V:
	Apr-13
	85,213

	Phase VI:
	Nov-15
	109,073

	Phase VII:
	Nov-17
	109,073

	Phase VIII:
	May-19
	109,073

	Phase IX:
	Jul-21
	109,073

	Phase X:
	Jun-23
	225,780

	Total:
	1,130,744

	Amount requested for renewal (phase XI) (US $):
	225,780

	Amount recommended for approval for phase XI (US $): 
	225,780

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XI to the Multilateral Fund (US $):
	225,780

	Date of approval of country programme:
	2003

	Date of approval of HCFC phase-out management plan:
	2011

	Date of approval of Kigali HFC implementation plan:
	2024

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	5.3

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	180,909

	Latest reported ODS consumption (2025) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	1.38

	(c)	Annex E (methyl bromide)
	0.00

	Total:
	1.38

	(d)	Annex F (HFCs) (CO2-eq tonnes) as per Article 7:
	121,242

	Year of reported country programme implementation data:
	2025

	Amount approved for projects (as at December 2025) (US $):
	3,785,729

	Amount disbursed (as at December 2024) (US $):
	2,819,441

	ODS to be phased out (as at December 2025) (ODP tonnes):
	75.1

	ODS phased out (as at December 2024) (ODP tonnes):
	47.3



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	848,861

	(b)	Institutional strengthening:
	1,130,744

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	1,806,125

		Total:
	3,785,729

	(d)	HFC activities funded from additional voluntary contributions
	95,000



Progress report
The implementation of Montreal Protocol activities in Liberia proceeded on schedule during phase X with the NOU achieving all seven objectives, based on the performance indicators. The NOU carried out activities including: revision of the Montreal Protocol Controlled Substances Regulations to include Kigali Amendment provisions; adoption of the revised 2022 HS customs codes; enforcement of the HCFC and HFC licensing and quota systems; training of customs and law enforcement officers, and RAC technicians; celebration of International Ozone Day; country programme and Article 7 data reporting; awareness workshops on HCFC phase-out, HFC phase-down, alternative technologies and the revised regulations; and launch of the electronic ODS and HFC licensing and quota system in December 2025, followed by NOU and importer training in 2026. While the ban on ODS-based equipment is not yet formally in place, interim controls have been applied through reduced import quotas, market inspections and continued engagement with relevant authorities.
Plan of action
In the upcoming phase XI of the IS project, the NOU will concentrate on: maintaining compliance through enforcement of the import licensing and quota system; monitoring HFC imports and consumption at the baseline level; completing training for remaining importers and fully operationalizing the online HCFC and HFC licensing and quota system; implementing training for refrigeration technicians and the energy‑efficiency project to establish minimum energy performance standards (MEPS) for RAC equipment; training additional customs and law enforcement officers to support enforcement of the Montreal Protocol Controlled Substances Regulations; continuing consultations toward the formal implementation of the ban on ODS‑based equipment under the existing regulations; maintaining gender participation, including support for women’s participation in RAC training and certification; continuing targeted awareness-raising through media outreach, inspections, consultations and information materials; ensuring timely data reporting; strengthening function-based NOU responsibilities and monitoring; and participating in regional and international meetings, border dialogues and South-South cooperation.
Sustainability and risk assessment
The sustainability of the IS project in Liberia is supported by the institutional role of the Environmental Protection Agency (EPA), established regulatory frameworks, trained NOU personnel, and collaboration with key stakeholders and implementing partners. While no major operational or financial risks are anticipated, the EPA has strengthened its financial control, monitoring and management systems, including reforms to improve transparency, oversight and accountability. To address any implementation risks, the EPA project monitoring unit will monitor implementation and report issues that may affect continuity, while the EPA Audit Unit will conduct periodic internal audits to support financial accountability and risk management. These arrangements will support continuity of IS, HPMP and KIP activities during 2026–2029.
Mongolia: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul-99
	74,580

	Phase II:
	Mar-02
	57,200

	Phase III:
	Jul-04
	57,198

	Phase IV:
	Nov-06
	60,000

	Phase V:
	Jul-08
	60,000

	Phase VI:
	Apr-10
	42,500

	Phase VII:
	Jul-11
	60,000

	Phase VIII:
	Jul-13
	60,000

	Phase IX:
	May-15
	60,000

	Phase X:
	Jul-17
	85,000

	Phase XI:
	May-19
	85,000

	Phase XII:
	Jul-21
	85,000

	Phase XIII:
	Jun-23
	180,000

	
	Total
	966,478

	Amount requested for renewal (phase XIV) (US $):
	180,000

	Amount recommended for approval for phase XIV (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XIV to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	1999

	Date of approval of HCFC phase-out management plan:
	2011

	Date of approval of Kigali HFC implementation plan:
	2025

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	1.4

	(c)	Annex E, (methyl bromide) (average 1995-1998)
	0.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	57,309

	Latest reported ODS consumption (2024) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	0.39

	(c)	Annex E, (methyl bromide)
	0.00

		Total:
	0.39

	(d)	Annex F (HFCs) (CO2-eq tonnes) as per Article 7:
	55,608

	Year of reported country programme implementation data:
	2025

	Amount approved for projects (as at December 2025) (US $):
	3,327,397

	Amount disbursed (as at December 2024) (US $):
	2,508,787

	ODS to be phased out (as at December 2025) (ODP tonnes):
	15.0

	ODS phased out (as at December 2024) (ODP tonnes):
	13.4



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	591,555

	(b)	Institutional strengthening:
	966,478

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	1,769,364

		Total:
	3,327,397

	(d)	HFC activities funded from additional voluntary contributions
	95,000



Progress report 
The NOU of Mongolia made progress on all planned activities under phase XIII of the IS project, with six of the seven objectives fully achieved, based on the performance indicators, and one partially achieved. Mongolia implemented the HCFC and HFC licensing and quota system, including the launch of an online e-licensing system in February 2025, through which 1,407 importers obtained permits. Article 7 and country programme data were submitted during the reporting period, and Mongolia remains in compliance with the Montreal Protocol HCFC phase-out schedule. The 2025 HFC import quota level exceeded the freeze level following quota adjustments made in consideration of MOP decision XXXV/16; however, the 2026 HFC quota was set within the freeze level. The NOU organized stakeholder meetings, awareness-raising activities and customs training, coordinated implementation of stage II of the HPMP, and secured approval of stage I of the KIP. The NOU and relevant authorities participated in the majority of Montreal Protocol meetings. Gender mainstreaming activities included the collection of sex-disaggregated data and preparations for a gender survey to inform phase XIV activities.
Plan of action
In phase XIV, the NOU will implement the HCFC and HFC licensing and quota system and strengthen quota allocation under the KIP by prioritizing subsectors and substances to reduce imports of high-GWP HFCs. The NOU will implement KIP and HPMP activities, build customs and enforcement capacity, support the RAC association, cross-check trade data, and submit data reports to the Ozone and the Fund Secretariats. Phase XIV will also support formalization of the ban on imports of HCFC-based equipment, a feasibility study on restrictions on equipment using high-GWP HFCs, and policy coordination with the Ministry of Environment and Climate Change on the online licensing system and safety standards for alternative refrigerants. Awareness-raising will continue, including World Ozone Day celebrations. Gender mainstreaming will be guided by the gender survey, with an action plan and MOUs with gender-focused organizations to promote women’s participation in the RAC sector.
Sustainability and risk assessment
The IS project can be successfully implemented in Mongolia under conditions of stable funding from the Multilateral Fund. Risks include frequent staff turnover within the NOU and potential institutional discontinuity arising from changes in institutional arrangements; these are being addressed through proposed structural changes to strengthen the oversight and involvement of the Ministry of Environment and Climate Change in project implementation. Increased high-level commitment to a stable NOU will support the smooth management of project implementation and the sustainability of the ODS phase-out and HFC phase‑down. Stakeholders, relevant associations and government agencies actively participate in the development of recommendations and amendments to laws and regulations, as well as in public awareness and promotional activities, ensuring shared ownership and long-term sustainability.
Niue: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Dec-04 & Nov-06
	25,100

	Phase II:
	Nov-07
	60,000

	Phase III:
	Nov-09
	60,000

	Phase IV:
	Jul-11
	60,000

	Phase V:
	Jul-13
	60,000

	Phase VI:
	Nov-15
	80,000

	Phase VII:
	Dec-18
	56,194

	Phase VIII:
	Jul-21
	85,000

	Phase IX:
	Jun-23
	100,000

		Total:
	586,294

	Amount requested for renewal (phase X) (US $):
	100,000*

	Amount recommended for approval for phase X (US $): 
	100,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase X to the Multilateral Fund (US $):
	100,000

	Date of approval of country programme:
	2004

	Date of approval of HCFC phase-out management plan:
	2011

	Date of approval of Kigali HFC implementation plan:
	2024

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	0

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	236

	Latest reported ODS consumption (2024) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0

	(b)	Annex C, Group I (HCFCs)
	0

	(c)	Annex E (methyl bromide)
	0

		Total:
	0

	(d)	Annex F (HFCs) (CO2-eq tonnes) as per Article 7:
	0

	Year of reported country programme implementation data:
	2025

	Amount approved for projects (as at December 2025) (US $):
	917,321

	Amount disbursed (as at December 2024) (US $):
	668,783

	ODS to be phased out (as at December 2025) (ODP tonnes):
	0**

	ODS phased out (as at December 2024) (ODP tonnes):
	0


* The Government of Niue has requested US $100,000 for phase X while noting that this is less than the US $180,000 available to LVC countries.
**Very low ODS to be phased out; rounding of figures to two digits shows zero ODP tonnes. 

Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	0

	(b)	Institutional strengthening:
	586,294

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	331,027

		Total:
	917,321

	(d)	HFC activities funded from additional voluntary contributions
	50,000



Progress report
Phase IX of the IS project supported Niue in maintaining compliance with HCFC phase-out obligations. Five of the seven objectives were fully achieved, based on the performance indicators, with two partially achieved. Niue continued to enforce the HFC licensing and quota system, and Article 7 and country programme data were submitted to the Ozone and Fund Secretariats, respectively. HCFC and other ODS consumption were maintained at zero through legislative, capacity-building and awareness-raising measures. All imported RAC equipment and refrigerants were inspected through coordination between the NOU, Customs Authority and Port Control Authority. World Ozone Day activities were organized with the assistance of the Steering Committee. Niue actively participated in regional network meetings, although was unable to attend the OEWG and MOP meetings in 2024 and 2025. Gender mainstreaming was promoted through participation in awareness activities, the Steering Committee and Montreal Protocol project implementation. Niue also commenced implementation of stage II of the HPMP, stage I of the KIP, the national inventory of unwanted controlled substances, and the energy-efficiency project.
Plan of action
In phase X, the NOU will continue to enforce the HFC licensing and quota system; conduct joint inspections with Customs and importers; undertake quarterly trade-data reconciliation; and implement PACHS22,[footnoteRef:10] including individual HS codes for HFCs and blends. To support effective delivery with limited staffing, the NOU will streamline cross-cutting activities across projects, with guidance from the Director of the Department of Environment, the National ODS Steering Committee and UNEP, and targeted technical assistance where needed. The NOU will coordinate stage II of the HPMP, submit Article 7 and country programme reports, continue awareness-raising on HCFC phase-out and HFC phase-down, including World Ozone Day, and make arrangements to participate in regional and international Montreal Protocol meetings. Gender mainstreaming will continue to be integrated into the IS project and other Multilateral Fund‑supported projects, including by promoting equal access to information, encouraging women officers from relevant government departments to participate in Montreal Protocol activities, and collaborating with the National Council of Women on outreach opportunities. [10:  Pacific Harmonized Commodity Description and Coding System 2022] 

Sustainability and risk assessment
The IS project can be successfully implemented in Niue under conditions of stable funding from the Multilateral Fund. Stakeholders, relevant associations, ministries and agencies actively participate in regulatory, public awareness and promotional activities. The NOU is guided by the Steering Committee, comprising key line ministries, the RAC sector and other relevant agencies. Given that Niue has one full‑time NOU officer, risks relate to institutional continuity, management of the expanded Montreal Protocol portfolio and access to import data. These risks will be mitigated through strengthened documentation and handover arrangements, and continued coordination with Customs on data sharing and reconciliation. Steering Committee engagement will be supported through early circulation of documents, virtual participation where needed, and follow-up on minutes and action points.
Palau: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-02
	34,000

	Phase II:
	Jul-06 and Nov-07
	41,333

	Phase III:
	Nov-09
	60,000

	Phase IV:
	Jul-11
	60,000

	Phase V:
	Jul-13
	60,000

	Phase VI:
	May-15
	60,000

	Phase VII:
	Nov-17
	85,000

	Phase VIII:
	May-19
	85,000

	Phase IX:
	Jul-21
	85,000

	Phase X:
	Jun-23
	180,000

		Total:
	750,333

	Amount requested for renewal (phase XI) (US $):
	180,000

	Amount recommended for approval for phase XI (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XI to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	2002

	Date of approval of HCFC phase-out management plan:
	2011

	Date of approval of Kigali HFC implementation plan:
	2024

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	0.2

	(c)	Annex E, (methyl bromide) (average 1995-1998)
	0.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	10,368

	Latest reported ODS consumption (2025) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	0.01

	(c)	Annex E, (methyl bromide)
	0.00

		Total:
	0.01

	(d)	Annex F (HFCs) (CO2-eq tonnes) as per Article 7:
	8,861

	Year of reported country programme implementation data:
	2025

	Amount approved for projects (as at December 2025) (US $):
	1,471,601

	Amount disbursed (as at December 2024) (US $):
	941,371

	ODS to be phased out (as at December 2025) (ODP tonnes):
	1.9

	ODS phased out (as at December 2024) (ODP tonnes):
	1.5



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	0

	(b)	Institutional strengthening:
	750,333

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	721,268

		Total:
	1,471,601

	(d)	HFC activities funded from additional voluntary contributions
	50,000



Progress report
Under phase X of the IS project, the Government of Palau sustained effective NOU operations, with five of the seven objectives fully achieved, based on the performance indicators, and two partially achieved. The NOU enforced the HCFC and HFC licensing and quota systems and the ban on HCFC-based equipment, with HCFC consumption maintained well below the maximum allowable consumption. A new National Ozone Officer was recruited during the reporting period and received capacity-building support from UNEP. Article 7 and country programme data for 2024 and 2025 were submitted to the Ozone and Fund Secretariats, although the HFC data reconciliation process delayed the submission of the 2024 CP data. A draft amendment to introduce mandatory controls on HFC-based equipment was finalized and submitted to the President's Office for signature. The NOU hosted the regional network meeting in Koror in June 2024 and participated in all other regional meetings. The NOU organized World Ozone Day celebrations, school visits, and community outreach. Gender mainstreaming was integrated throughout, with female participation across NOU-organized activities such as awareness programmes, and the planning and implementation of the Montreal Protocol projects through the Steering Committee.
Plan of action
In phase XI, the NOU will continue to implement the licensing and quota systems for HCFCs and HFCs and the import ban on HCFC-based equipment; implement the revised regulation to introduce mandatory controls on HFC-based equipment once gazetted; coordinate the implementation of stage II of the HPMP, stage I of the KIP, the national inventory of ODS banks, and the energy‑efficiency project; actively engage the Steering Committee and RAC Association in the planning and implementation of Montreal Protocol obligations; and conduct public awareness activities, annual World Ozone Day celebrations, and participate in regional and international Montreal Protocol meetings. The NOU will maintain quarterly reconciliation with Customs to ensure timely submission of Article 7 and country programme data. Gender mainstreaming will be integrated into all projects, including activities to encourage young women to consider careers in the RAC sector.
Sustainability and risk assessment
The IS project can be successfully implemented in Palau under conditions of stable funding from the Multilateral Fund. Stakeholders, relevant associations, ministries, and agencies actively participate in the development of recommendations and amendments to laws and regulations, as well as public awareness and promotional activities. The NOU is continuously guided by the Steering Committee, comprising key ministries, the RAC sector, and other relevant agencies. Tourism, construction, and urbanization in Palau present a risk of increasing demand for high-GWP HFC equipment, which could complicate the HFC phase‑down schedule; this is being mitigated through the introduction of regulatory controls on high‑GWP equipment and strengthened enforcement. Awareness activities overlap across the IS, KIP, and HPMP projects so to prevent double-counting, the NOU will maintain a tracking table separating activities, budgets, outputs and supporting documents by project.
Republic of Moldova: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul-98
	90,400

	Phase II:
	Mar-02
	69,334

	Phase III:
	Jul-04
	69,334

	Phase IV:
	Apr-06
	69,334

	Phase V:
	Apr-08
	69,334

	Phase VI:
	Jul-10
	69,334

	Phase VII:
	Jul-12
	46,709

	Phase VIII:
	May-14
	69,334

	Phase IX:
	Dec-16
	69,423

	Phase X:
	Dec-18
	85,831

	Phase XI:
	Jul-21
	82,718

	Phase XII:
	Jun-23
	183,707

		Total:
	974,793

	Amount requested for renewal (phase XIII) (US $):
	183,707

	Amount recommended for approval for phase XIII (US $): 
	183,707

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XIII to the Multilateral Fund (US $):
	183,707

	Date of approval of country programme:
	1998

	Date of approval of HCFC phase-out management plan:
	2011

	Date of approval of Kigali HFC implementation plan:
	2025

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	1.0

	(c)	Annex E (methyl bromide) (average 1995-1998)
	7.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	521,391

	Latest reported ODS consumption (2024) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs) 
	0.36

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	0.36

	(d)	Annex F (HFCs) (CO2-eq tonnes) as per Article 7:
	395,434

	Year of reported country programme implementation data:
	2024

	Amount approved for projects (as at December 2025) (US $):
	3,773,022

	Amount disbursed (as at December 2024) (US $):
	2,939,854

	ODS to be phased out (as at December 2025) (ODP tonnes):
	104.7

	ODS phased out (as at December 2024) (ODP tonnes):
	94.8



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	753,914

	(b)	Institutional strengthening:
	974,793

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	2,044,316

		Total:
	3,773,022

	(d)	HFC activities funded from additional voluntary contributions
	0


Progress report
During phase XII of the IS project, the Republic of Moldova strengthened its legislative framework for the control of HCFCs and HFCs, including through the ratification of the Kigali Amendment on 22 September 2023 and the adoption of Law No. 43/2023, which aligned with European Union (EU) standards, froze HFC consumption in 2024, established an HFC quota system, and introduced bans on the placing on the market, use and installation of certain products and equipment relying on high-GWP HFCs. Six of the seven objectives were achieved, based on the performance indicators, with one partially achieved. The strengthened quota and certification mechanisms include procedures for proportional allocation where requests exceed national limits and fair procedures for new market entrants. HFC reduction was further supported through the Low Emission Development Programme 2030 and the National HFC Phase-down Programme 2025–2045. Gender mainstreaming was advanced through the engagement of a gender expert. The Montreal Protocol Unit (MPU) also participated in regional network meetings and capacity-building activities, together with customs officers and environmental inspectors, to strengthen institutional and enforcement capacity. 
Plan of action
During phase XIII, the MPU will focus on maintaining compliance with the Montreal Protocol and the agreement with the Executive Committee, including through continued implementation of stage III of the HPMP and implementation of stage I of the KIP. Activities will include continued implementation and enforcement of the HCFC and HFC licensing and quota systems, further development and updating of national legislation, including alignment with updated EU regulations on fluorinated greenhouse gases and ODS, timely reporting of country programme and Article 7 data, updating training materials, and providing training and refresher activities for customs officers, environmental inspectors and RAC technicians. The MPU will continue to coordinate with the Ministry of Environment, Environmental Agency, Customs Service, Environmental Protection Inspectorate, RAC Association, Technical University of Moldova and training institutions. The MPU will also continue awareness-raising activities, including World Refrigeration Day and World Ozone Day, promote gender mainstreaming in HPMP, KIP and related HFC phase-down activities, and support other approved Multilateral Fund projects, including activities related to the inventory of banks of used or unwanted controlled substances and energy efficiency in the context of the HFC phase‑down.
Sustainability and risk assessment
The current implementation modality is reported to be functioning well, supported by Government oversight, the Steering Committee for Montreal Protocol projects, cooperation with customs and environmental enforcement authorities, and continued engagement with the RAC sector and training institutions. UNEP does not foresee particular risks to IS implementation or compliance obligations in the absence of Government restructuring, civil unrest or other force majeure circumstances. At the same time, the MPU is operating with a lean team and no dedicated project management unit, while coordinating an expanded portfolio that includes the IS project, stage III of the HPMP, stage I of the KIP, energy‑efficiency activities, awareness-raising and website functions. Continued IS support, refresher training, institutional coordination and sustained engagement of national stakeholders will therefore remain important to maintain implementation capacity and compliance. Gender mainstreaming has progressed through training, expert support and the collection of sex-disaggregated data, and continued follow-up will support its more systematic integration across project planning and implementation.
Rwanda: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-02 & Dec-03
	86,600

	Phase II:
	Nov-06
	56,148

	Phase III:
	Apr-09
	60,000

	Phase IV:
	Jul-11
	60,000

	Phase V:
	Jul-13
	60,000

	Phase VI:
	Nov-15
	85,000

	Phase VII:
	Nov-17
	85,000

	Phase VIII:
	Dec-19
	85,000

	Phase IX:
	Jul-21
	85,000

	Phase X:
	Jun-23
	180,000

		Total:
	842,748

	Amount requested for renewal (phase XI) (US $):
	180,000

	Amount recommended for approval for phase XI (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XI to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	2003

	Date of approval of HCFC phase-out management plan:
	2011

	Date of approval of Kigali HFC implementation plan:
	2024

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	4.1

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	338,197

	Latest reported ODS consumption (2024) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	0.97

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	0.97

	(d)	Annex F (HFCs) (CO2-eq tonnes) as per Article 7:
	181,430

	Year of reported country programme implementation data:
	2025

	Amount approved for projects (as at December 2025) (US $):
	2,999,625

	Amount disbursed (as at December 2024) (US $):
	2,342,980

	ODS to be phased out (as at December 2025) (ODP tonnes):
	49.3

	ODS phased out (as at December 2024) (ODP tonnes):
	32.4



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	484,560

	(b)	Institutional strengthening:
	842,748

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	1,672,318

		Total:
	2,999,625

	(d)	HFC activities funded from additional voluntary contributions
	95,000



Progress report
Phase X of the IS project supported Rwanda in maintaining compliance with the Montreal Protocol and implementing planned activities under stage II of the HPMP and stage I of the KIP. All seven objectives were achieved, based on the performance indicators. The NOU strengthened enforcement of the HCFC and HFC licensing and quota system and operationalized the upgraded e-Registry to support the monitoring and reporting of controlled substances. Training was provided to customs officers, clearing agents, cargo inspectors and RAC technicians to enhance enforcement and promote low-GWP alternatives. Rwanda submitted 2024 Article 7 and 2025 country programme data within the established deadlines. Awareness‑raising activities included World Ozone Day celebrations, public lectures, media outreach and stakeholder campaigns. Gender mainstreaming was supported through improved sex-disaggregated data reporting, female participation in customs training and a regional workshop for female RAC technicians.
Plan of action
During phase XI, Rwanda will continue to sustain HCFC phase-out and advance HFC phase-down in line with the Kigali Amendment. To address the expanded Montreal Protocol workload, the NOU will be supported by two additional IS-funded project staff for implementation, reporting, stakeholder coordination, quota monitoring and support to stage II of the HPMP and stage I of the KIP. The NOU will initiate stakeholder consultations and legal review to amend Ministerial Order No. 004/2021, including administrative and financial penalties, and will continue enforcing the HCFC and HFC licensing and quota system through the upgraded e-Registry, quota verification, importer engagement and coordination with RRA/Customs. The NOU will also strengthen data management, support timely Article 7 and country programme reporting, promote RAC technician training and low-GWP alternatives, conduct awareness activities, participate in Montreal Protocol meetings, and integrate gender mainstreaming through sex‑disaggregated data, women’s participation in RAC training and engagement of female RAC technicians and associations.
Sustainability and risk assessment
The sustainability of the IS project is supported by two Government-funded core NOU staff, who provide technical leadership and institutional continuity, and in phase XI by two additional IS-funded project support staff who will assist with the expanded Montreal Protocol workload, including implementation, reporting, stakeholder coordination and monitoring. Sustainability is further supported by the upgraded e‑Registry, the HCFC and HFC licensing and quota system, Government in-kind contributions, and the National Ozone Steering Committee, which brings together key public institutions, regulatory bodies and private-sector representatives, including from the RAC industry. No major risks have been identified that could affect Rwanda’s compliance or achievement of project objectives. Continued attention will be given to maintaining effective coordination, timely reporting, data management and enforcement capacity as Rwanda implements stage II of the HPMP, stage I of the KIP and other Montreal Protocol activities. 
Saint Vincent and the Grenadines: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul-98
	34,239

	Phase II:
	Apr-04 & Apr-05
	43,130

	Phase III:
	Nov 06
	60,000

	Phase IV:
	Jul-09 & Dec-10
	60,000

	Phase V:
	Apr-12
	60,000

	Phase VI:
	Nov-14
	60,000

	Phase VII:
	Nov-17
	85,000

	Phase VIII:
	Nov-21
	85,000

		Total:
	487,369

	Amount requested for renewal (phase IX) (US $):
	180,000

	
Amount recommended for approval for phase IX (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase IX to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	1998

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	0.3

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	25,280

	Latest reported ODS consumption (2025) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0

	(b)	Annex C, Group I (HCFCs)
	0

	(c)	Annex E (methyl bromide)
	0

		Total:
	0

	(d)	Annex F (HFCs) (CO2-eq tonnes) as per Article 7:
	17,599

	Year of reported country programme implementation data:
	2025

	Amount approved for projects (as at December 2025) (US $):
	1,912,393

	Amount disbursed (as at December 2024) (US $):
	1,401,235

	ODS to be phased out (as at December 2025) (ODP tonnes):
	2.3

	ODS phased out (as at December 2024) (ODP tonnes):
	2.3



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	274,447

	(b)	Institutional strengthening:
	487,369

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	1,150,577

		Total:
	1,912,393

	(d)	HFC activities funded from additional voluntary contributions
	50,000



Progress report
Phase VIII of the IS project for Saint Vincent and the Grenadines continued to support the implementation of Montreal Protocol activities with the participation of key national stakeholders and technical assistance from UNEP, with four of the seven objectives fully achieved, based on the performance indicators, and three partially achieved. Implementation of planned activities was delayed owing to administrative challenges, noting that phase VIII of the IS project coincided with the COVID-19 pandemic, the eruption of La Soufrière volcano in April 2021, and Hurricane Beryl in July 2024. Notwithstanding the challenges, during the reporting period, the country maintained zero consumption of HCFCs, ahead of the Montreal Protocol schedule, including through an administrative ban on HCFC refrigerant imports effective from 1 January 2025, and continued to implement the HCFC licensing and quota system and related import controls. However, HFC consumption reported for 2024 exceeded the country's consumption limit, resulting in non‑compliance under MOP Decision XXXVII/14. In response, the NOU halted import licence issuance and worked closely with UNEP on measures to return to compliance, with 2025 data confirming consumption within the limit. During the reporting period, the NOU also continued data reporting, customs coordination, stakeholder consultations, awareness-raising activities, participation in regional and international Montreal Protocol meetings, and work to strengthen the revised regulatory framework for HFC controls. In addition, the NOU submitted the final tranche of stage I of the HPMP and the project to prepare a national inventory of waste ODS banks to the 97th meeting of the Executive Committee.
Plan of action
As part of phase IX, the Government of Saint Vincent and the Grenadines will continue to support activities to sustain the phase-out of HCFCs, strengthen implementation of the Kigali Amendment, and prepare and implement stage I of the KIP. The NOU will continue to implement the licensing and quota system for HCFCs and HFCs, work with Customs, importers, and other stakeholders to further strengthen the HFC quota system, and finalize the revised Montreal Protocol regulations to provide a legislative basis for the HFC quota system, technician and supplier licensing, and the establishment of an Ozone National Fund. The NOU will support completion of HPMP and energy-efficiency activities, implement the project to prepare a national inventory of ODS banks, and develop a communication strategy to guide public awareness campaigns. The NOU will maintain active participation in regional and international Montreal Protocol meetings and promote women's participation in the RAC sector through consultations with gender‑focused ministries and organizations.
Sustainability and risk assessment
The NOU functions within the Department of Sustainable Development in the Ministry of Tourism, Civil Aviation and Sustainable Development and follows reporting procedures established by the Ministry, with oversight from the Office of the Permanent Secretary. The national work programme is incorporated within the Ministry's portfolio and is supported by Government in-kind contributions. To mitigate risks related to implementation of the expanded portfolio of projects, the NOU will recruit additional project support staff, strengthen inter-ministerial cooperation, and maintain close collaboration with UNEP.
Samoa: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	May-97
	33,900

	Phase II:
	Apr-03
	26,000

	Phase III:
	Nov-05
	60,000

	Phase IV:
	Nov-07
	60,000

	Phase V:
	Jul-09
	60,000

	Phase VI:
	Jul-11
	60,000

	Phase VII:
	Jul-13
	60,000

	Phase VIII:
	May-15
	60,000

	Phase IX:
	Nov-17
	85,000

	Phase X:
	May-19
	85,000

	Phase XI:
	Jul-21
	85,000

	Phase XII:
	Jun-23
	180,000

		Total:
	854,900

	Amount requested for renewal (phase XIII) (US $):
	180,000

	Amount recommended for approval for phase XIII (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XIII to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	1997

	Date of approval of HCFC phase-out management plan:
	2011

	Date of approval of Kigali HFC implementation plan:
	2024

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	0.3

	(c)	Annex E, (methyl bromide) (average 1995-1998)
	0.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	20,557

	Latest reported ODS consumption (2024) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0

	(b)	Annex C, Group I (HCFCs)
	0

	(c)	Annex E, (methyl bromide)
	0

		Total:
	0

	(d)	Annex F (HFCs) (CO2-eq tonnes) as per Article 7:
	7,264

	Year of reported country programme implementation data:
	2025

	Amount approved for projects (as at December 2025) (US $):
	2,032,781

	Amount disbursed (as at December 2024) (US $):
	1,432,310

	ODS to be phased out (as at December 2025) (ODP tonnes):
	4.4

	ODS phased out (as at December 2024) (ODP tonnes):
	3.9



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	47,906

	(b)	Institutional strengthening:
	854,900

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	1,129,976

		Total:
	2,032,781

	(d)	HFC activities funded from additional voluntary contributions
	50,000



Progress report
Phase XII of the IS project supported Samoa in maintaining an effective institutional framework for implementation of the Montreal Protocol. Five of the seven objectives were fully achieved, based on the performance indicators, with two partially achieved. The NOU, under the Meteorology Division of the Ministry of Natural Resources and Environment (MNRE), maintained coordination mechanisms with public and private sector stakeholders through the National Ozone Steering Committee and stakeholder committees. Samoa submitted 2024 Article 7 and country programme data to the Ozone and Fund Secretariats, respectively. Compliance was sustained through legislative measures, the HCFC and HFC licensing and quota systems, monitoring of ODS imports, capacity-building, stakeholder engagement and public awareness activities. Key achievements included completion of the first tranche of stage II of the HPMP and commencement of stage I of the KIP, the national inventory of unwanted controlled substances and the energy-efficiency project. Gender mainstreaming was encouraged through stakeholder engagement and participation in NOU activities.
Plan of action
During phase XIII, Samoa will continue to strengthen implementation of the Montreal Protocol by enforcing the HCFC and HFC licensing and quota systems; supporting the approval and implementation of the Refrigerant Management Regulations, including controls on alternatives and other refrigerants; supporting adoption of PACHS22 to improve the classification of HFCs and blends; strengthening Customs coordination and use of the import-permit database and supporting records to ensure timely submission of Article 7 and country programme data; and maintaining active engagement of the National Ozone Committee, RACAS and other stakeholders. The NOU will also coordinate implementation of the second tranche of stage II of the HPMP and the first tranche of stage I of the KIP, the national inventory of unwanted controlled substances and the energy-efficiency project; organize World Ozone Day and other awareness activities; participate in regional and international meetings; and continue integrating gender mainstreaming into IS phase XIII activities, including through the stakeholder survey and collaboration with the Ministry of Women, Community and Social Development.
Sustainability and risk assessment
The IS project is expected to continue supporting Samoa’s compliance with the Montreal Protocol, building on an established NOU, active stakeholder engagement and regular coordination through the National Ozone Committee, which includes relevant ministries, enforcement agencies and the RAC sector. Potential risks relate to the continued use of PACHS17 pending adoption of PACHS22, which may affect the accurate identification and recording of HFCs and blends in the customs system, as well as political changes, Government restructuring and budget-cycle constraints, including early or short-notice budget closures, which may delay activity implementation, procurement and approvals. These risks will be mitigated through earlier planning of activities and procurement, strengthened coordination with MNRE Finance and the Ministry of Finance, continued targeted awareness for importers and customs brokers, and support to Customs to improve HFC classification and data reconciliation.
Sudan (the): Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-94
	190,179

	Phase II:
	Jul-99
	126,786

	Phase III:
	Jul-01
	126,786

	Phase IV:
	Apr-04
	145,860

	Phase V:
	Jul-09
	109,395

	Phase VI:
	Dec-10
	145,860

	Phase VII:
	Apr-13
	145,860

	Phase VIII:
	Nov-15
	186,701

	Phase IX:
	Jun-18
	186,683

	Phase X:
	Nov-21
	186,701

		Total:
	1,550,811

	Amount requested for renewal (phase XI) (US $):
	386,471

	Amount recommended for approval for phase XI (US $): 
	386,471

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XI to the Multilateral Fund (US $):
	386,471

	Date of approval of country programme:
	1994

	Date of approval of HCFC phase-out management plan:
	2012

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	52.7

	(c)	Annex E (methyl bromide) (average 1995-1998)
	3.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	Not available

	Latest reported ODS consumption (2024) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	2.65

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	2.65

	(d)	Annex F (HFCs) (CO2-eq tonnes) as per Article 7:
	137,259

	Year of reported country programme implementation data:
	2025

	Amount approved for projects (as at December 2025) (US $):
	9,978,231

	Amount disbursed (as at December 2024) (US $):
	8,247,246

	ODS to be phased out (as at December 2025) (ODP tonnes):
	679.5

	ODS phased out (as at December 2024) (ODP tonnes):
	667.1



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	6,753,726

	(b)	Institutional strengthening:
	1,550,811

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	1,673,693

		Total:
	9,978,231

	(d)	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During the reporting period, Sudan continued to implement phase X of the IS project and undertake preparatory work towards ratification of the Kigali Amendment. Five of the seven objectives were fully achieved, based on the performance indicators, and two were partially achieved. Implementation took place under challenging conditions due to the conflict that began in April 2023, which disrupted institutional operations and limited field-level activities. Notwithstanding these constraints, the NOU maintained core functions through remote coordination and flexible implementation arrangements. Sudan continued to enforce its HCFC licensing and quota system, monitor HCFC and HFC imports with the Customs Department, and maintain compliance with its HCFC control obligations. Capacity-building included training 38 customs officers on HS codes and illegal trade prevention, and training RAC technicians on good servicing practices and the safe handling of flammable refrigerants. An Accession Bill for the Kigali Amendment was prepared and submitted to the Ministerial Council. Article 7 and country programme data for 2022, 2023 and 2024 were submitted, although not all by the established deadlines; the 2025 country programme data were submitted by the 1 May deadline. Awareness activities reached schools, stakeholders and displaced communities, gender considerations were incorporated into project activities, and Sudan participated in regional and international Montreal Protocol meetings. 
Plan of action
For the period June 2026 to May 2029 (phase XI), Sudan will continue implementing institutional strengthening activities to support compliance with the Montreal Protocol and prepare for ratification of the Kigali Amendment and HFC phase-down obligations. Planned activities include updating national regulations to reflect Kigali Amendment provisions; following up on the ratification process, including the remaining approval steps through the Sovereignty Council; strengthening the licensing and quota system; establishing an online licensing system linked with customs and main ports; improving the recording and verification of import and export data; and enhancing enforcement measures to prevent illegal trade. Sudan will also continue capacity-building for customs and enforcement officers, RAC technicians and other stakeholders; implement a structured communication and awareness plan; and organize annual World Ozone Day activities. Given the continued reliance on remote coordination, the NOU will formalize decisions and follow-up actions through official records, directives and correspondence to support institutional memory. The NOU will continue to participate in regional network and international Montreal Protocol meetings and strengthen cooperation with national stakeholders and regional partners. Gender mainstreaming will continue to be integrated into project planning and implementation, including through sex-disaggregated data collection, training for women in the RAC sector and support for women’s participation in Montreal Protocol-related activities.
Sustainability and risk assessment
The sustainability of Sudan’s Montreal Protocol activities is supported by the continued operation of the NOU within the Higher Council for Environment and Natural Resources (HCENR), the integration of Montreal Protocol activities into HCENR work plans, and the involvement of the National Ozone Steering Committee and other stakeholders. Continued institutional strengthening support will be important to preserve national capacity, sustain compliance with HCFC phase-out obligations, and prepare for future HFC phase-down measures following ratification of the Kigali Amendment. Sustained awareness activities and gender mainstreaming will further support long-term compliance. The main risks to implementation relate to the ongoing conflict, political and economic instability, limited field access, constraints associated with remote coordination, and challenges related to resource mobilization and policy continuity. These factors could delay policy approval, project implementation, stakeholder engagement and data collection. To mitigate these risks, Sudan will continue using online platforms, virtual briefings, targeted communications and flexible implementation arrangements, while strengthening engagement with key ministries and technical focal points. UNEP will continue to provide remote technical support and adapt implementation arrangements as needed to maintain continuity under challenging circumstances.
Tonga: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-02
	19,700

	Phase II:
	Jul-06 and Nov-07
	36,566

	Phase III:
	Nov-09 
	60,000

	Phase IV:
	Jul-11
	60,000

	Phase V:
	Jul-13
	60,000

	Phase VI:
	May-15
	60,000

	Phase VII:
	Nov-17
	85,000

	Phase VIII:
	May-19
	85,000

	Phase IX:
	Ju-21
	85,000

	Phase X:
	Jun-23
	180,000

	Total:
	731,266

	Amount requested for renewal (phase XI) (US $):
	180,000

	Amount recommended for approval for phase XI (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XI to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	2002

	Date of approval of HCFC phase-out management plan:
	2011

	Date of approval of Kigali HFC implementation plan:
	2024

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	0.1

	(c)	Annex E, (methyl bromide) (average 1995-1998)
	0.2

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	7,676

	Latest reported ODS consumption (2024) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0

	(b)	Annex C, Group I (HCFCs)
	0

	(c)	Annex E, (methyl bromide)
	0

		Total:
	0

	(d)	Annex F (HFCs) (CO2-eq tonnes) as per Article 7:
	5,112

	Year of reported country programme implementation data:
	2025

	Amount approved for projects (as at December 2025) (US $):
	1,562,520

	Amount disbursed (as at December 2024) (US $):
	952,488

	ODS to be phased out (as at December 2025) (ODP tonnes):
	1.4

	ODS phased out (as at December 2024) (ODP tonnes):
	1.1



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	0

	(b)	Institutional strengthening:
	731,266

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	831,254

		Total:
	1,562,520

	(d)	HFC activities funded from additional voluntary contributions
	50,000



Progress report
Phase X of the IS project supported the Government of Tonga in complying with HCFC phase-out obligations under the Montreal Protocol and the initial obligations of the Kigali Amendment. Five of the seven objectives were fully achieved, based on the performance indicators, and two were partially achieved. The IS project was implemented in a complementary manner with the first tranches of stage II of the HPMP and stage I of the KIP, the national inventory of unwanted controlled substances, and the energy-efficiency project. Compliance was sustained through a holistic approach comprising legislative measures, the HCFC and HFC licensing and quota system, import monitoring, capacity-building, the involvement of the National Ozone Advisory Committee and the RAC Association, and awareness-raising activities. Article 7 and country programme data were submitted throughout the reporting period, although the 2024 CP data submission was delayed due to HFC data reconciliation with Customs and 2025 Article 7 data have yet to be submitted. To strengthen future reporting, the NOU developed a permit and import database and moved to monthly reconciliation with Customs. Drafting of the Ozone Layer Protection Regulations was initiated. Implementation and monitoring in the outer islands were strengthened through the establishment of an Outer Island Ozone Technical Officer position.
Plan of action
In phase XI, building on achievements to date, the NOU will continue to enforce the HCFC and HFC licensing and quota systems and strengthen monthly reconciliation of import permits, customs records and actual import documentation to support timely Article 7 and country programme data reporting. Pending full implementation of HS 2022, the NOU will strengthen cooperation with Customs, conduct physical inspections of refrigerant imports, and provide targeted awareness to importers and customs brokers on proper identification and recording of HFCs and HFC blends. The NOU will coordinate implementation of stage II of the HPMP, stage I of the KIP, the national inventory of unwanted controlled substances and the energy-efficiency project, and support the finalization, gazetting and implementation of the Ozone Layer Protection Regulations. The NOU will also continue awareness-raising activities, participate in regional and international Montreal Protocol meetings, and integrate gender mainstreaming into IS project activities.
Sustainability and risk assessment
The IS project can be successfully implemented in Tonga under conditions of stable funding from the Multilateral Fund. Stakeholders, relevant associations, ministries and agencies actively participate in regulatory, public awareness and promotional activities, and the National Ozone Advisory Committee guides the NOU in implementing the Montreal Protocol. Since Tonga has yet to complete the transition to WCO HS 2022, expected by December 2026, there is a risk that HFCs and HFC blends may not be accurately identified and recorded in the customs system. This risk will be mitigated through continued cooperation with Customs, physical inspection of refrigerant imports, and targeted awareness for importers and customs brokers.
Tuvalu: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-02
	17,500

	Phase II:
	Nov-06 & Nov-08
	37,583

	Phase III:
	Dec-10
	60,000

	Phase IV:
	Jul-12
	60,000

	Phase V:
	May-14
	60,000

	Phase VI:
	May-16
	83,870

	Phase VII:
	Dec-18
	80,000

	Phase VIII:
	Jul-21
	85,000

	Phase IX:
	Jun-23
	180,000

		Total:
	663,953

	Amount requested for renewal (phase X) (US $):
	180,000

	Amount recommended for approval for phase X (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase X to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	2002

	Date of approval of HCFC phase-out management plan:
	2011

	Date of approval of Kigali HFC implementation plan:
	2024

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	0.1

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	2,648

	Latest reported ODS consumption (2024) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	0

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0

		Total:
	0

	(d)	Annex F (HFCs) (CO2-eq tonnes) as per Article 7:
	613

	Year of reported country programme implementation data:
	2025

	Amount approved for projects (as at December 2025) (US $):
	1,101,929

	Amount disbursed (as at December 2024) (US $):
	723,439

	ODS to be phased out (as at December 2025 (ODP tonnes):
	0.5

	ODS phased out (as at December 2024) (ODP tonnes):
	0.3



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	0

	(b)	Institutional strengthening:
	663,953

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	437,976

		Total:
	1,101,929

	(d)	HFC activities funded from additional voluntary contributions
	50,000



Progress report
Phase IX of the IS project was implemented by the Government of Tuvalu, with four of the seven objectives fully achieved, based on the performance indicators, and three partially achieved. The HCFC and HFC licensing and quota system is fully operational, and the Ozone Layer Protection and Refrigerant Management Amendment Act was gazetted in 2023, strengthening the regulatory framework for HFC controls. The MOU between the Environment Department and Customs Department supported trade monitoring and enforcement, and no imports of CFCs or illegal ODS were reported during the reporting period. The NOU managed the HPMP and worked closely with the RAC Association and the National Steering Committee. Article 7 and country programme data for 2023 and 2024 were submitted, with 2025 country programme data submitted by the 1 May deadline. The celebration of World Ozone Day 2025 was cancelled following the resignation of the National Ozone Officer. A replacement National Ozone Officer and an NOU assistant were recruited in 2025 and UNEP provided initial capacity-building support, with further training planned in 2026. Gender mainstreaming was integrated throughout project activities.
Plan of action
In phase X, the NOU will continue to enforce the HCFC and HFC licensing and quota system, implement PACHS22, compile data for individual HS codes for HFCs and blends, undertake quarterly reconciliation with Customs, and use an annual reporting calendar and import permit database to support timely Article 7 and country programme data reporting. The NOU will coordinate implementation of stage II of the HPMP, stage I of the KIP, the national inventory of ODS banks and the energy-efficiency project, supported by a financial tracking table. It will also organize World Ozone Day activities, develop awareness materials, participate in regional and international meetings, and strengthen institutional memory and continuity through a centralized database, standard operating procedures, handover notes and activity trackers. Gender mainstreaming will be integrated into the IS project.
Sustainability and risk assessment
The IS project can be successfully implemented in Tuvalu under conditions of stable funding from the Multilateral Fund. Stakeholders, relevant associations, ministries and agencies actively participate in the development of recommendations and amendments to laws and regulations, as well as in public awareness and promotional activities. The NOU is continuously guided by the Steering Committee, comprising key line ministries, the RAC sector and other relevant agencies. Risks include potential disruption to institutional continuity arising from NOU staffing changes; these will be mitigated through the establishment of a centralized database, standard operating procedures, handover notes and activity trackers to preserve institutional memory. Since Tuvalu has yet to complete the transition to PACHS22, expected by June 2026, there is also a risk that HFCs and HFC blends may not be accurately identified in the customs system; this will be mitigated through continued cooperation with Customs and physical verification of import documents pending full implementation.
Zimbabwe: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul-94
	193,287

	Phase II:
	Jul-99
	128,857

	Phase III:
	Jul-01
	128,857

	Phase IV:
	Jul-04
	148,242

	Phase V:
	Nov-06
	148,242

	Phase VI:
	Nov-09 
	148,241

	Phase VII:
	Apr-13
	148,242

	Phase VIII:
	May-15
	148,242

	Phase IX:
	Jul-17
	189,750

	Phase X:
	May-19
	189,750

	Phase XI:
	Jul-21
	189,750

	Phase XII:
	Jun-23
	392,782

		Total:
	2,154,242

	Amount requested for renewal (phase XIII) (US $):
	392,782

	Amount recommended for approval for phase XIII (US $): 
	392,782

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XIII to the Multilateral Fund (US $):
	392,782

	Date of approval of country programme:
	1994

	Date of approval of HCFC phase-out management plan:
	2011

	Date of approval of Kigali HFC implementation plan:
	2024

	Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	17.8

	(c)	Annex E (methyl bromide) (average 1995-1998)
	557.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	1,210,624

	Latest reported ODS consumption (2025) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	2.26

	(c)	Annex E, (methyl bromide)
	0.00

		Total:
	2.26

	(d)	Annex F (HFCs) (CO2-eq tonnes) as per Article 7:
	790,887

	Year of reported country programme implementation data:
	2025

	Amount approved for projects (as at December 2025) (US $):
	14,010,923

	Amount disbursed (as at December 2024) (US $):
	13,011,369

	ODS to be phased out (as at December 2025) (ODP tonnes):
	611.0

	ODS phased out (as at December 2024) (ODP tonnes):
	505.4



Summary of activities and funds approved by the Executive Committee:

	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	8,813,775

	(b)	Institutional strengthening:
	2,154,242

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	3,042,907

		Total:
	14,010,923

	(d)	HFC activities funded from additional voluntary contributions
	180,000



Progress report
Phase XII of the IS project in Zimbabwe was successfully implemented, five of the seven objectives fully achieved, based on the performance indicators, and two partially achieved. The licensing system for controlled substances was upgraded to a fully electronic system integrated into the Zimbabwe Electronic Single Window, and HFCs were included in the quota allocation system following establishment of the national baseline. Article 7 data were submitted on time throughout the reporting period. Country programme data for 2023 and 2024 were delayed owing to the national consumption survey conducted in 2024 for preparation of stage I of the KIP, while 2025 country programme data were submitted well in advance of the deadline. A Partnership Agreement with the Zimbabwe Revenue Authority was signed on 15 October 2024 to strengthen ODS and HFC trade monitoring, and 91 customs officers were trained on combating illegal trade. RAC technicians were trained on low-GWP and flammable refrigerants. Awareness activities included World Ozone Day commemorations, media workshops and school competitions, and the Ozone Officer participated in regional Montreal Protocol meetings. Gender mainstreaming included a survey of 95 RAC technicians, a workshop for 40 female RAC professionals, and finalization of a gender action plan.
Plan of action
In phase XIII, the NOU will strengthen implementation of the electronic licensing system and review regulations to tighten HFC control measures and support complete HCFC phase-out. Training of customs officers will focus on 2022 HS codes, detection of mislabelled or concealed substances, and common smuggling schemes. The NOU will promote border dialogues with neighbouring countries and strengthen information exchange through the reinstated iPIC platform. RAC technician training on hydrocarbons and other low-GWP alternatives will continue, alongside establishment of the technician certification programme under the HPMP. The NOU will coordinate implementation of stage II of the HPMP, stage I of the KIP, the lifecycle refrigerant management project and the national inventory of ODS banks. Awareness activities will follow the national communication and awareness plan and promote zero-ODP and low- or zero-GWP energy-efficient technologies. Gender mainstreaming will continue through the gender action plan and technician registry.
Sustainability and risk assessment
UNEP/OzL.Pro/ExCom/98/15
Annex I
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The NOU operates within the Department of Climate Change Management in the Ministry of Environment, Climate and Wildlife and receives administrative support from the Ministry. Institutional continuity is supported by the National Ozone Project Steering Committee and two Government employees designated to become familiar with project activities. The project is subject to periodic internal and external audits to ensure financial management and accountability. To support implementation, consultants will be engaged for specific technical tasks, and Department staff will provide additional support when workloads are high. The availability of Vocational Training Centre facilities for technician training is an operational risk, mitigated through advance scheduling and the use of recovery, recycling and reclamation centres as alternative venues.
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Приложение II

ПРОЕКТ МНЕНИЙ ИСПОЛНИТЕЛЬНОГО КОМИТЕТА ПО ПРОДЛЕНИЮ ПРОЕКТОВ ПО УКРЕПЛЕНИЮ ОРГАНИЗАЦИОННОЙ ИНФРАСТРУКТУРЫ, ПРЕДСТАВЛЕННЫХ НА 98-М СОВЕЩАНИИ


Камбоджа
1. Исполнительный комитет рассмотрел доклад, представленный вместе с заявкой на продление проекта по укреплению организационной инфраструктуры для Камбоджи (фаза XIII), и с удовлетворением отметил, что правительство представило свой страновой доклад и данные в соответствии со статьей 7 на 2025 год, что свидетельствует о соблюдении Камбоджей положений Монреальского протокола, включая замораживание объемов потребления ГФУ в соответствии с Кигалийской поправкой. Комитет отметил продолжающееся укрепление системы лицензирования и квотирования ГХФУ и ГФУ в рамках подзаконного акта об управлении ОРВ 2021 года, в том числе полную интеграцию онлайновой системы лицензирования и квотирования с национальной системой единого окна и управление квотами ГФУ в тоннах СО2-эквивалента. Комитет отметил также прогресс в осуществлении плана организационной деятельности по поэтапному отказу от ГХФУ, этапа I кигалийского плана регулирования ГФУ, проекта в области энергоэффективности и национального реестра банков ОРВ. Отмечая усилия правительства Камбоджи, Комитет выразил надежду, что в ближайшие три года правительство Камбоджи будет продолжать успешное осуществление мероприятий, обеспечивающих соблюдение мер регулирования в рамках Монреальского протокола.
Эритрея
Исполнительный комитет рассмотрел доклад, представленный вместе с заявкой на продление проекта по укреплению организационной инфраструктуры для Эритреи (фаза VII) и с удовлетворением отметил, что Эритрея представила данные в соответствии со статьей 7 за 2025 год, свидетельствующие, что страна соблюдает положения Монреальского протокола. Комитет принял к сведению, что Эритрея обладает действующей системой лицензирования и квотирования ГХФУ и ГФУ. Комитет также отметил усилия Эритреи по сокращению потребления ГХФУ, созданию условий для утверждения этапа I кигалийского плана регулирования ГФУ и укреплению мониторинга контролируемых веществ и в связи с этим выразил надежду, что в ближайшие три года правительство Эритреи будет продолжать успешное осуществление мероприятий, обеспечивающих соблюдение мер регулирования в рамках Монреальского протокола.
Эсватини
Исполнительный комитет рассмотрел доклад, представленный вместе с заявкой на продление проекта по укреплению организационной инфраструктуры для Эсватини (фаза IX) и с удовлетворением отметил, что Эсватини соблюдает положения Монреальского протокола. Комитет приветствовал своевременное представление данных по страновой программе за 2025 год и создание специальной группы по сбору данных в поддержку дальнейшего своевременного представления таких данных. Комитет отметил также публикацию в официальном бюллетене положений об озоноразрушающих веществах и ГФУ (2025 г.) и системе лицензирования и квотирования. Комитет высоко оценил усилия правительства Эсватини по сокращению потребления ГХФУ и призвал его продолжать осуществление этапа II плана организационной деятельности по поэтапному отказу от ГХФУ и этапа I кигалийского плана регулирования ГФУ. Отмечая усилия правительства Эсватини, Комитет выразил надежду, что в ближайшие три года правительство Эсватини будет продолжать успешное осуществление мероприятий, обеспечивающих соблюдение Монреальского протокола и Кигалийской поправки к нему.
Гамбия
Исполнительный комитет рассмотрел доклад, представленный вместе с заявкой на продление проекта по укреплению организационной инфраструктуры для Гамбии (фаза XIII) и с удовлетворением отметил, что Гамбия представила данные в соответствии со статьей 7 и данные по страновой программе за 2025 год секретариату по озону и секретариату Фонда соответственно, что свидетельствует о соблюдении страной графика поэтапного сокращения Монреальского протокола. Комитет отметил, что правительство Гамбии внедрило обязательные меры регулирования импорта ОРВ посредством системы лицензирования и квотирования, и призвал его завершить  пересмотр правил регулирования ОРВ, включающих меры регулирования ГФУ. Комитет отметил усилия правительства Гамбии по сокращению потребления ГХФУ и ГФУ и в связи с этим выразил надежду, что в ближайшие три года правительство Гамбии будет продолжать успешное осуществление мероприятий, обеспечивающих соблюдение мер регулирования в рамках Монреальского протокола и Кигалийской поправки к нему.
Гренада
Исполнительный комитет рассмотрел доклад, представленный вместе с заявкой на продление проекта по укреплению организационной инфраструктуры для Гренады (фаза VIII) и с удовлетворением отметил, что Гренада представила данные в соответствии со статьей 7 и данные страновой программы секретариату по озону и секретариату Фонда соответственно, свидетельствующие о том, что страна соблюдает положения Монреальского протокола. Комитет высоко оценил усилия, приложенные правительством для завершения фазы VII, несмотря на трудности, а также продолжающееся внедрение систем лицензирования и квотирования ГХФУ и ГФУ, административный запрет на оборудование на основе ГХФУ и прогресс в работе над пересмотренным законопроектом о веществах Монреальского протокола, направленным на усиление контроля за холодильным и кондиционерным оборудованием на основе пороговых значений потенциала глобального потепления. Отметив усилия правительства Гренады, Комитет выразил надежду, что в течение следующих трех лет правительство Гренады будет продолжать успешное осуществление мероприятий в поддержку соблюдения мер регулирования Монреальского протокола.
Кения
Исполнительный комитет рассмотрел доклад, представленный вместе с заявкой на продление проекта по укреплению организационной инфраструктуры для Кении (фаза XIV) и с удовлетворением отметил, что Кения представила данные в соответствии со статьей 7 и данные по страновой программе за 2024 год, свидетельствующие о том, что страна соблюдает положения Монреальского протокола. Комитет отметил, что 28 февраля 2025 года в официальном бюллетене были опубликованы пересмотренные Правила управления и координации в сфере охраны окружающей среды (контролируемые вещества), включающие систему лицензирования и квотирования ГФУ, а также запрет на импорт оборудования на основе ГХФУ. Комитет отметил, что Кения создала действующую систему лицензирования и квотирования и осуществила мероприятия в рамках плана организационной деятельности по поэтапному отказу от ГХФУ. Признавая усилия правительства Кении, Комитет выразил надежду, что в ближайшие три года правительство продолжит успешное осуществление мероприятий, обеспечивающих соблюдение Монреальского протокола.
Либерия
Исполнительный комитет рассмотрел доклад, представленный вместе с заявкой на продление проекта по укреплению организационной инфраструктуры для Либерии (фаза XI) и с удовлетворением отметил, что Либерия представила данные в соответствии со статьей 7, свидетельствующие о том, что она соблюдает положения Монреальского протокола. Комитет принял к сведению пересмотр Правил в отношении контролируемых веществ Монреальского протокола и включение в них положений Кигалийской поправки, укрепление системы лицензирования и квотирования ГХФУ и ГФУ, в том числе запуск онлайновой системы, и осуществление мероприятий в рамках плана организационной деятельности по поэтапному отказу от ГХФУ и кигалийского плана регулирования ГФУ. Отмечая усилия правительства Либерии, Комитет выразил надежду, что в ближайшие три года правительство Либерии продолжит успешное осуществление мероприятий для соблюдения мер регулирования в рамках Монреальского протокола и Кигалийской поправки к нему.
Монголия
Исполнительный комитет рассмотрел доклад, представленный вместе с заявкой на продление проекта по укреплению организационной инфраструктуры для Монголии (фаза XIV) и с удовлетворением отметил, что Монголия представила данные на 2024 год в соответствии со статьей 7 Монреальского протокола в секретариат по озону и данные по страновой программе на 2025 год в секретариат Фонда, что свидетельствует о соблюдении графика Монреальского протокола по поэтапному отказу от ГХФУ. Комитет отметил, что после утверждения на 97-м совещании этапа I кигалийского плана регулирования ГФУ и условий, изложенных в решении 97/63, правительство продолжило укреплять меры регулирования ГФУ, в том числе посредством установления квот на ГФУ в 2026 году в пределах замороженного объема потребления и за счет запуска онлайновой системы лицензирования. Комитет отметил также продолжающееся укрепление системы лицензирования и квотирования. Признавая усилия правительства Монголии, Комитет выразил надежду, что в последующие три года правительство Монголии продолжит успешное осуществление мероприятий, обеспечивающих соблюдение мер регулирования Монреальского протокола, в том числе Кигалийских поправок к нему.
Ниуэ
Исполнительный комитет рассмотрел доклад, представленный вместе с заявкой на продление проекта по укреплению организационной инфраструктуры для Ниуэ (фаза X) и с удовлетворением отметил, что Ниуэ представил данные на 2024 год в соответствии со статьей 7 Монреальского протокола в секретариат по озону и данные по страновой программе на 2024 и 2025 годы в секретариат Фонда, что свидетельствует о соблюдении страной положений Монреальского протокола. Комитет отметил, что правительство Ниуэ поддерживает нулевое потребление ГХФУ с 2011 года и ввело обязательное регулирование ГФУ посредством национальной системы лицензирования и квотирования. Комитет принял также к сведению, что Ниуэ начал осуществление этапа I кигалийского плана регулирования ГФУ и этапа II плана организационной деятельности по поэтапному отказу от ГХФУ, и с удовлетворением отметил, что правительство запросило финансирование для осуществления фазы X проекта по укреплению организационной инфраструктуры на уровне меньше минимального. Признавая усилия правительства Ниуэ, Комитет выразил надежду, что в ближайшие три года правительство Ниуэ продолжит успешное осуществление мероприятий, обеспечивающих соблюдение мер регулирования в рамках Монреальского протокола.
Палау
Исполнительный комитет рассмотрел доклад, представленный вместе с заявкой на продление проекта по укреплению организационной инфраструктуры для Палау (фаза XI) и с удовлетворением отметил, что Палау представил данные в соответствии со статьей 7 и данные страновой программы на 2025 год комитету по озону и комитету Фонда соответственно, что свидетельствует о соблюдении страной положений Монреальского протокола. Комитет высоко оценил усилия правительства по поддержанию потребления ГХФУ на уровне значительно ниже максимально допустимого, обеспечению соблюдения запрета на оборудование на основе ГХФУ и внедрению системы лицензирования и квотирования ГФУ и принял к сведению завершение проекта закона о внедрении обязательного регулирования оборудования на основе ГФУ. Признавая усилия правительства Палау, Комитет выразил надежду, что в ближайшие три года правительство Палау будет с успехом продолжать осуществление мероприятий в поддержку соблюдения мер регулирования Монреальского протокола.
Республика Молдова
Исполнительный комитет рассмотрел доклад, представленный вместе с заявкой на продление проекта по укреплению организационной инфраструктуры для Республики Молдовы (фаза XIII) и с удовлетворением отметил, что Республика Молдова представила данные в соответствии со статьей 7 и данные страновой программы на 2024 год комитету по озону и комитету Фонда соответственно, что свидетельствует о соблюдении страной положений Монреальского протокола. Исполнительный комитет принял к сведению, что правительство укрепило свои законодательно-правовые рамки в отношении регулирования ГХФУ и ГФУ, в том числе посредством ратификации Кигалийской поправки, внедрения системы квотирования ГФУ и введения ограничений на некоторые виды продукции и оборудования на основе ГФУ с высоким ПГП. Комитет отметил также продолжающееся осуществление этапа III плана организационной деятельности по поэтапному отказу от ГХФУ, запланированное осуществление этапа I кигалийского плана регулирования ГФУ и экспериментального проекта по укреплению энергоэффективности заместительных технологий и оборудования в контексте поэтапного сокращения использования ГФУ. Признавая усилия правительства Республики Молдовы, Комитет выразил надежду, что в следующие три года правительство Республики Молдовы продолжит успешное осуществление мероприятий в поддержку соблюдения мер регулирования Монреальского протокола.
Руанда
Исполнительный комитет рассмотрел доклад, представленный вместе с заявкой на продление проекта по укреплению организационной инфраструктуры для Руанды (фаза XI) и с удовлетворением отметил, что Руанда представила данные за 2024 год в соответствии со статьей 7 и данные по страновой программе за 2025 год, что свидетельствует о соблюдении страной положений Монреальского протокола. Комитет принял к сведению, что Руанда продолжает внедрять систему лицензирования и квотирования ГХФУ и ГФУ, поддерживаемую модернизированным онлайновым реестром и мероприятиями в рамках плана организационной деятельности по поэтапному отказу от ГХФУ и кигалийского плана регулирования ГФУ. Признавая усилия правительства Руанды, Комитет выразил надежду, что в ближайшие три года правительство Руанды продолжит успешно осуществлять мероприятия в поддержку соблюдения мер регулирования Монреальского протокола.
Сент-Винсент и Гренадины
Исполнительный комитет рассмотрел доклад, представленный вместе с заявкой на продление проекта по укреплению организационной инфраструктуры для Сент-Винсента и Гренадин (фаза IX) и с удовлетворением отметил, что Сент-Винсент и Гренадины представили данные в соответствии со статьей 7 и данные по страновой программе за 2025 год комитету по озону и комитету Фонда соответственно, указывающие, что страна поддерживает потребление ГХФУ на нулевом уровне и сообщила о потреблении ГФУ в пределах установленного лимита на 2025 год. Комитет отметил, что после превышения в 2024 году установленного в стране лимита потребления ГФУ, как это отражено в Решении XXXVII/14 тридцать седьмого совещания сторон, правительство при поддержке ЮНЕП приняло меры по укреплению системы лицензирования и квотирования ГФУ и подготовке проектного предложения для этапа I кигалийского плана регулирования ГФУ. Комитет отметил усилия правительства Сент-Винсента и Гренадин и выразил надежду, что в следующие три года правительство Сент-Винсента и Гренадин продолжит успешное выполнение мероприятий в поддержку соблюдения мер регулирования Монреальского протокола.
Самоа
Исполнительный комитет рассмотрел доклад, представленный вместе с заявкой на продление проекта по укреплению организационной инфраструктуры для Самоа (фаза XIII) и с удовлетворением отметил, что Самоа представило данные в соответствии со статьей 7 за 2024 года в секретариат по озону и данные страновой программы за 2025 год в секретариат Фонда, что свидетельствует о соблюдении страной положений Монреальского протокола. Комитет отметил, что Самоа продолжает внедрять систему лицензирования и квотирования ГХФУ и ГФУ и сотрудничать с соответствующими заинтересованными сторонами по этапу II плана организационной деятельности по поэтапному отказу от ГХФУ, этапу I кигалийского плана регулирования ГФУ и другим мероприятиям, финансируемым Многосторонним фондом. Комитет также отметил усилия Самоа по улучшению процедуры представления данных и продвижению правил управления хладагентами и Тихоокеанской гармонизированной системы описания и кодирования товаров 2022 года. Признавая усилия правительства Самоа, комитет выразил надежду, что в следующие три года правительство Самоа будет продолжать успешное осуществление мероприятий в поддержку соблюдения мер регулирования Монреальского протокола.
Судан
Исполнительный комитет рассмотрел доклад, представленный вместе с заявкой на продление проекта по укреплению организационной инфраструктуры для Судана (фаза XI) и с удовлетворением отметил представление данных в соответствии со статьей 7 и данных страновой программы за 2022, 2023 и 2024 годы в секретариат по озону и секретариат Фонда соответственно, а также своевременное представление данных по страновой программе за 2025 год, свидетельствующих о том, что Судан соблюдает график поэтапного отказа от ГХФУ, установленный Монреальским протоколом. Комитет высоко оценил неустанные усилия Судана, несмотря на сложные национальные обстоятельства, по обеспечению соблюдения системы лицензирования и квот, а также продолжению реализации мероприятий в рамках плана организационной деятельности по поэтапному отказу от ГХФУ и отметил прогресс в подготовке ратификации Кигалийской поправки. Признавая усилия правительства Судана, Комитет выразил надежду, что в следующие три года правительство Судана ратифицирует Кигалийскую поправку и продолжит успешное выполнение мероприятий в поддержку соблюдения мер регулирования, установленных Монреальским протоколом.
Тонга
Исполнительный комитет рассмотрел доклад, представленный вместе с заявкой на продление проекта по укреплению организационной инфраструктуры для Тонги (фаза XI) и с удовлетворением отметил, что Тонга представила данные в соответствии со статьей 7 на 2024 год в секретариат по озону и данные по страновой программе за 2024 и 2025 годы в секретариат Фонда, что свидетельствует о соблюдении страной положений Монреальского протокола и Кигалийской поправки к нему.  Комитет высоко оценил усилия правительства по поддержанию потребления ГХФУ на нулевом уровне, по внедрению обязательного регулирования ГФУ посредством национальной системы лицензирования и квотирования и поддержанию запрета оборудования на основе ГХФУ. Признавая усилия правительства Тонги, Комитет выразил надежду, что в ближайшие три года правительство Тонги будет продолжать успешное осуществление мероприятий, обеспечивающих соблюдение мер регулирования Монреальского протокола.

Тувалу
Исполнительный комитет рассмотрел доклад, представленный вместе с заявкой на продление проекта по укреплению организационной инфраструктуры для Тувалу (фаза X) и с удовлетворением отметил, что Тувалу представило данные в соответствии со статьей и данные страновой программы за 2024 год секретариату по озону и секретариату Фонда соответственно и что данные по страновой программе за 2025 год были представлены досрочно, что свидетельствует о соблюдении страной положений Монреальского протокола, включая Кигалийскую поправку к нему. Комитет высоко оценил усилия правительства по поддержанию потребления ГХФУ на нулевом уровне посредством системы лицензирования и квотирования ГХФУ и ГФУ, и публикацию в 2023 году в официальном бюллетене Закона о защите озонового слоя и регулировании оборота хладагентов. Признавая усилия правительства Тувалу, Комитет выразил надежду, что в ближайшие три года правительство Тувалу продолжит успешное осуществление мероприятий в поддержку соблюдения мер регулирования Монреальского протокола.
Зимбабве
Исполнительный комитет рассмотрел доклад, представленный вместе с заявкой на продление проекта по укреплению организационной инфраструктуры для Зимбабве (фаза XIII) и с удовлетворением отметил, что Зимбабве досрочно представило данные в соответствии со статьей 7 и данные по страновой программе за 2025 год в секретариат по озону и секретариат Фонда соответственно, которые свидетельствуют о соблюдении страной положений Монреальского протокола, в том числе цели по замораживанию объемов потребления ГФУ в рамках Кигалийской поправки. Комитет высоко оценил усилия правительства по внедрению электронной системы лицензирования и квотирования в рамках единого электронного окна Зимбабве, укреплению сотрудничества с национальным управлением по налогам и осуществлению других мероприятий в рамках плана организационной деятельности по поэтапному отказу от ГХФУ и Кигалийскому плану регулирования ГФУ. Признавая усилия правительства Зимбабве, Комитет выразил надежду, что в ближайшие три года правительство Зимбабве продолжит успешное осуществление деятельности в поддержку соблюдения мер регулирования Монреальского протокола.

	
	
	
	
	




Документы, подготовленные к совещанию Исполнительного комитета Многостороннего фонда для осуществления Монреальского протокола, не предрешают ни одного из решений, которые Исполнительный комитет может принять после выпуска документа.
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