| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/77/11 10 November 2016 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Seventy-seventh Meeting

Montreal, 28 November - 2 December 2016

CONSOLIDATED PROGRESS REPORT AS AT 31 DECEMBER 2015

# The consolidated progress report summarises progress and financial information provided by bilateral and implementing agencies as of 31 December 2015 in their respective progress reports submitted to the Secretariat, and consists of:

Executive Summary

# Part I:	Implementation progress as at 31 December 2015 (cumulative)

# Part II:	Project implementation progress in 2015

# Part III:	Additional comments and recommendations by the Secretariat

# Annex I:	Project implementation data in 2015 by country

Annex II:	HCFC phase-out management plan (HPMP) by country as at 31 December 2015

# Annex III:	An analysis of data from the progress reports

# Executive summary

# The following is a summary of progress in the implementation of projects and activities supported by the Multilateral Fund up to 31 December 2015 for the year 2015, and cumulative since 1991 (Annex III provides a detailed analysis of the data contained in the progress reports):

## Phase-out: In 2015, 5,511.8 ODP tonnes of consumption and 2,912 ODP tonnes of production were phased out and an additional 1,704.8 ODP tonnes of consumption were approved for phase-out. Since 1991, 282,696 ODP tonnes of consumption and 204,189 ODP tonnes of production had been phased out at the end of 2015, of an expected total of 468,233 ODP tonnes from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2015, US $117.5 million was disbursed and US $97.22 million was planned for disbursement based on the 2014 progress report representing a rate of disbursement of 121 per cent of that planned. Cumulatively, US $2.69 billion had been disbursed out of the total US $2.99 billion approved for disbursement (excluding agency fees). This represents a rate of disbursement of 90 per cent. In 2015, US $170.84 million was approved for implementation;

## Cost-effectiveness (in ODP): Since 1991, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $7.66/kg. The cost-effectiveness for the production sector was US $4.24/kg. The average cost-effectiveness of investment projects per ODP tonne was US $4.10/kg for completed projects and US $47.51/kg for ongoing projects;

## Number of projects completed: In 2015, 218 projects were completed. Since 1991, 6,649 projects of the 7,567 projects (excluding closed or transferred projects) financed by the Multilateral Fund were completed. This represents a completion rate of 88 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2015 were completed on average 48 months after their approval. Since 1991, the average time for completion of investment projects has been 36 months after their approval. First disbursements under these projects occurred, on average, 15 months after they had been approved;

## Speed of delivery – non-investment projects: Projects that were completed in 2015 were completed on average 39 months after their approval. Since 1991, the average time for completion of non-investment projects has been 37 months after their approval. First disbursements under these projects occurred, on average, 11 months after they had been approved;

## Project preparation: Of the 1,600 project preparation activities approved by the end of 2015, 1,480 have been completed. In 2015, 31 project preparation activities were approved and 23 were completed leaving 120 ongoing;

## Implementation delays: There were a total of 246 ongoing investment projects under implementation at the end of 2015. These projects, on average, are experiencing a delay of 26 months. However, projects classified as “projects with implementation delays” that are subject to the procedures of project cancellation amount to 16 projects (as multi-year agreements (MYAs) are not subject to those procedures); and

## MYAs: In 2015, bilateral and implementing agencies were implementing three MYAs for CFC or ODS phase-out plans, one MYA for CTC phase-out plan, five MYAs for methyl bromide (MB) consumption, one MYA for accelerated CFC production, one MYA for MB production, 154 MYAs for HCFC phase-out management plans (HPMPs) and one MYA for the HCFC production phase-out management plan (HPPMP) in China. Since 1991, 338 MYAs have been approved and 166 MYAs have been completed.

Part I: Implementation progress as at 31 December 2015 (cumulative)

# As of that date, the Executive Committee had approved approximately US $3.32 billion consisting of US $2.99 billion for the implementation of investment and non-investment projects and US $337.41 million for agency fees and administrative support, as shown in Table 1. In 2015, 383 new projects and activities were approved. This level of funding is expected to result in the phase-out of 468,233 ODP tonnes of ODS consumption and production.

Table 1: Approved funding by sector and agency as at 31 December 2015

| Sector | Approved funding (US $) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | UNDP | UNEP | UNIDO | World Bank | Bilateral | Total |
| Aerosol | 26,675,161 | 882,689 | 34,414,001 | 22,984,030 | 2,111,400 | 87,067,281 |
| Destruction | 3,629,626 | 232,200 | 5,373,277 | 400,000 | 1,795,000 | 11,430,103 |
| Fire fighting | 50,000 | 0 | 0 | 0 | 0 | 50,000 |
| Foam | 173,043,155 | 0 | 88,640,022 | 135,816,693 | 8,103,002 | 405,602,871 |
| Halon | 4,996,973 | 767,640 | 1,810,064 | 70,221,038 | 6,147,361 | 83,943,076 |
| Fumigants | 20,082,828 | 2,650,504 | 78,213,368 | 5,837,887 | 18,300,403 | 125,084,989 |
| Multiple sectors | 0 | 0 | 139,440 | 2,341,168 | 0 | 2,480,608 |
| Other | 0 | 0 | 11,317,246 | 5,059,360 | 0 | 16,376,606 |
| Phase-out plan | 229,433,646 | 42,030,895 | 252,163,436 | 185,932,969 | 50,040,514 | 759,601,460 |
| Process agent | 1,286,923 | 0 | 6,337,359 | 114,342,497 | 0 | 121,966,779 |
| Production | 1,373,900 | 0 | 50,522,227 | 359,729,770 | 10,000,000 | 421,625,897 |
| Refrigeration | 135,505,397 | 13,501,555 | 177,436,529 | 181,169,335 | 39,821,168 | 547,433,985 |
| Several | 52,941,131 | 202,476,052 | 14,478,771 | 27,650,089 | 4,512,914 | 302,058,957 |
| Solvents | 63,700,008 | 198,860 | 23,247,023 | 10,147,394 | 2,512,738 | 99,806,023 |
| Sterilant | 417,628 | 0 | 0 | 661,227 | 0 | 1,078,855 |
| Sub-total | 713,136,376 | 262,740,395 | 744,092,762 | 1,122,293,457 | 143,344,500 | 2,985,607,490 |
| Administrative costs | 96,806,287 | 22,597,747 | 94,817,988 | 109,831,157 | 13,358,232 | 337,411,411 |
| Total | 809,942,663 | 285,338,142 | 838,910,750 | 1,232,124,615 | 156,702,732 | 3,323,018,901 |

# A summary of the status of projects, by category, is presented in Table 2. Of the 7,567 projects approved, 2,831 (about 37 per cent) are classified as investment projects. Investment projects represent around US $2.42 billion of the US $2.99 billion approved (81 per cent of the total funds approved). The second largest number of projects, in terms of approved funding, is classified as technical assistance, for which the Executive Committee has approved a total of over US $273.62 million. By the end of 2015, 100 per cent of country programme (CP) preparation projects had been completed; 92 per cent of the funds allocated for project preparation activities had been disbursed; 91 per cent of investment projects, and 79 per cent of demonstration projects had been completed; and 85 per cent of approved funds had been disbursed for IS projects.

Table 2: Status of project implementation by category

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 165 | 165 | 100 | 7,266,559 | 7,279,345 | -12,786 | 100 |
| Demonstration | 120 | 95 | 79 | 57,487,993 | 46,782,604 | 10,705,390 | 81 |
| Institutional strengthening (IS) | 1,039 | 869 | 84 | 115,157,676 | 98,027,815 | 17,129,860 | 85 |
| Investment | 2,831 | 2,585 | 91 | 2,423,316,133 | 2,201,037,562 | 222,278,570 | 91 |
| Project preparation | 1,600 | 1,480 | 93 | 82,954,067 | 76,310,100 | 6,643,967 | 92 |
| Technical assistance | 1,488 | 1,131 | 76 | 273,619,290 | 231,007,988 | 42,611,302 | 84 |
| Training | 324 | 324 | 100 | 25,805,772 | 25,814,358 | -8,586 | 100 |
| Total | 7,567 | 6,649 | 88 | 2,985,607,490 | 2,686,259,773 | 299,347,717 | 90 |

*Excludes closed and transferred projects.

** Excludes agency fees/administrative costs.

# Table 3 presents an overview of status of project implementation by year. Of the US $2.99 billion in approved funding (including adjustments), US $2.69 billion has been disbursed. In 2015, US $117.5 million was disbursed. Projects approved by the Executive Committee have thus far resulted in the permanent annual phase-out of 486,885 ODP tonnes of consumption and production. All projects and activities approved between 1991 and the end of 2003 (with the exception of 1999 and 2002) have now been completed.

Table 3: Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1991 | 68 | 68 | 100 | 7,950,771 | 7,950,771 | 0 | 100 |
| 1992 | 176 | 176 | 100 | 41,261,376 | 41,261,376 | 0 | 100 |
| 1993 | 217 | 217 | 100 | 73,198,586 | 73,198,587 | 0 | 100 |
| 1994 | 379 | 379 | 100 | 128,630,290 | 128,643,077 | -12,787 | 100 |
| 1995 | 355 | 355 | 100 | 111,188,309 | 111,188,308 | 0 | 100 |
| 1996 | 257 | 257 | 100 | 83,813,027 | 83,813,028 | -1 | 100 |
| 1997 | 532 | 532 | 100 | 154,314,939 | 154,314,942 | -3 | 100 |
| 1998 | 422 | 422 | 100 | 99,680,368 | 99,680,367 | 1 | 100 |
| 1999 | 546 | 545 | 100 | 152,703,846 | 152,706,276 | -2,430 | 100 |
| 2000 | 426 | 426 | 100 | 109,540,652 | 109,546,183 | -5,531 | 100 |
| 2001 | 427 | 427 | 100 | 130,138,759 | 130,138,758 | 2 | 100 |
| 2002 | 358 | 356 | 99 | 162,045,815 | 161,941,867 | 103,948 | 100 |
| 2003 | 247 | 247 | 100 | 157,043,048 | 157,043,467 | -419 | 100 |
| 2004 | 271 | 270 | 100 | 162,382,590 | 162,382,035 | 555 | 100 |
| 2005 | 255 | 252 | 99 | 182,691,015 | 178,833,088 | 3,857,928 | 98 |
| 2006 | 261 | 258 | 99 | 121,000,997 | 120,428,570 | 572,427 | 100 |
| 2007 | 213 | 211 | 99 | 120,220,642 | 119,632,156 | 588,486 | 100 |
| 2008 | 355 | 344 | 97 | 122,863,131 | 121,081,151 | 1,781,980 | 99 |
| 2009 | 322 | 308 | 96 | 74,428,123 | 71,875,113 | 2,553,010 | 97 |
| 2010 | 229 | 206 | 90 | 85,967,263 | 79,815,532 | 6,151,730 | 93 |
| 2011 | 266 | 201 | 76 | 206,434,884 | 184,365,294 | 22,069,590 | 89 |
| 2012 | 184 | 94 | 51 | 104,033,633 | 71,637,076 | 32,396,557 | 69 |
| 2013 | 186 | 60 | 32 | 126,806,448 | 86,532,040 | 40,274,408 | 68 |
| 2014 | 232 | 34 | 15 | 96,429,562 | 57,302,906 | 39,126,656 | 59 |
| 2015 | 383 | 4 | 1 | 170,839,416 | 20,947,806 | 149,891,610 | 12 |
| Total | 7,567 | 6,649 | 88 | 2,985,607,490 | 2,686,259,773 | 299,347,717 | 90 |

*Excludes closed and transferred projects.

** Excludes agency fees/administrative costs.

Part II:	 Project implementation progress in 2015

# Based on planned completion dates reported in the 2014 progress report, and the results reported in the 2015 progress reports, the agencies completed 52 per cent of the projects they had planned to complete in 2015 and met 51 per cent of the phase-out target planned; however, of the 333 ongoing projects excluding IS and project preparation, 214 have been delayed since the 2014 progress report. Additional status reports were requested to address any implementation impediment that caused the delay.

# The agencies had planned disbursements in 148 countries or regions, and achieved an overall rate of disbursement of 121 per cent in 2015. On a country basis, 62 countries or regions had a disbursement rate of over 85 per cent while 49 countries or regions had a disbursement rate of below 50 per cent planned in 2015.

# The consolidated progress report summarises progress and financial information on the following ongoing projects and identifies project implementation impediments that are common to more than one implementing agency on those projects:

## CFC- and ODS-related projects, including terminal phase-out management plans (TPMPs), national phase-out plans (NPPs), accelerated production CFC and refrigerant management plans (RMPs);

## Projects for the phase-out of consumption and of production of MB;

## Other non-HCFC projects (metered-dose inhalers (MDIs), ODS waste disposal, chillers and halon banking);

## Projects related to the phase-out of HCFCs, including project preparation, demonstration projects, HPMPs, HPPMPs (production sector) and survey of ODS alternatives;

## IS projects; and

## Administrative costs.

CFC- and ODS-related activities

# As of 31 December 2015, a total of five MYAs for the phase-out of CFC and ODS were still ongoing. All phase-out activities associated with 139 MYAs have been completed, pending only the financial closure and the submission of project completion reports, where applicable. The ongoing CFC- and ODS-related MYA activities are indicated in Table 4. The project in Yemen is addressed in Part III of the present document under “Security issues”.

Table 4: Ongoing CFC- and ODS-related MYA activities

| Agreement | Approved funding plus adjustments (US $) | Funds disbursed (US $) | Balance (US $) | % disbursed | Planned date of completion* |
| --- | --- | --- | --- | --- | --- |
| India CTC phase-out | 51,713,195 | 50,149,927 | 1,563,268 | 97 | Nov-2017 |
| India accelerated CFC production | 3,486,900 | 2,113,000 | 1,373,900 | 61 | Nov-2017 |
| Iraq ODS phase-out | 6,297,530 | 4,787,579 | 1,509,951 | 76 | Dec-2016 |
| Kuwait ODS phase-out | 459,473 | 441,230 | 18,243 | 96 | Dec-2016 |
| Yemen ODS phase-out | 1,825,500 | 1,494,800 | 330,700 | 82 | Dec-2018 |

# * MYAs may include more than one tranche with different approved completion dates. The approved date of completion indicated in this table is for the last tranche that will be implemented for an MYA.

# At its 75th meeting, the Executive Committee inter alia agreed to amend its CTC agreement with India, transfer the World Bank’s component to UNDP with a revised completion date of the end of 2016, noting that any remaining funds would be returned to the Multilateral Fund at the first meeting of the Executive Committee in 2017, requested UNDP to undertake a study on the country’s use of CTC for feedstock applications and to make the results of the study available to the Executive Committee by the end of 2016, and requested the World Bank, together with the Governments of France, Germany and Japan, and UNDP and UNIDO as cooperating implementing agencies, to submit the project completion reports on the phase-out of CTC consumption and production to the last meeting of the Executive Committee in 2017 (decision 75/19(b)). However, UNDP indicated that all project activities are completed and independently verified but the project would not be completed until November 2017 (IND/PHA/71/INV/451, IND/PHA/71/TAS/448, and IND/PHA/75/INV/464). UNDP acknowledged the change in planned completion date and its variance from the decision. The Executive Committee may wish to consider whether to extend the completion date of December 2016 agreed under decision 75/19(b) to November 2017.

Projects for the phase-out of consumption and production of MB

# One-hundred Article 5 countries have received support for MB phase-out activities. As of 31 December 2015, there were ten ongoing individual projects addressing MB phase-out in eight countries and one region including one demonstration, three investment, five technical assistance and one preparation project. Seven of these projects have planned completion dates in 2016. Those MB projects with a planned completion date beyond December 2016 include one investment and two technical assistance projects. Also, five MYAs for the phase-out of MB consumption in five Article 5 countries and one MYA for the phase-out of MB production in one Article 5 country (China) were still ongoing (Table 5).

Table 5: Ongoing MB MYA activities

| Agreement | Approved funding plus adjustments (US $) | Funds disbursed (US $) | Balance (US $) | % disbursed | Planned date of completion |
| --- | --- | --- | --- | --- | --- |
| Consumption |  |  |  |  |  |
| Chile | 1,730,917 | 1,714,495 | 16,422 | 99 | Jun-2016 |
| China | 14,789,339 | 14,653,104 | 136,235 | 99 | Dec-2018 |
| Guatemala | 2,068,047 | 1,328,713 | 739,334 | 64 | Jun-2017 |
| Libya | 1,243,000 | 963,112 | 279,888 | 77 | Jun-2017 |
| Mexico | 9,215,731 | 8,527,620 | 688,111 | 93 | Jul-2016 |
| Production |  |  |  |  |  |
| China | 9,788,885 | 8,611,687 | 1,177,198 | 88 | Dec-2018 |

# The Secretariat noted that every ongoing MB project was delayed. There was no, or limited disbursement, for several technical assistance projects approved at the 73rd and 74th meetings. The project in the consumption sector in China was completed on 31 December 2015 and therefore funds should be returned by 31 December 2016; however, UNIDO requested an extension to December 2018. The Executive Committee may wish to note that the MB project in the consumption sector was completed and unused funds should be returned by December 2016 when considering the extension of the planned completion date to December 2018.

# UNEP reported that the stand-alone project for the phase-out of the consumption of MB in Trinidad and Tobago (TRI/FUM/65/TAS/28) is now completed.

MDIs, ODS disposal, chillers and halon banking

MDI projects

# The Executive Committee has approved 23 MDI projects amounting to US $48.97 million including 12 investment and 11 technical assistance projects. Twenty projects have been completed and three investment projects are under implementation. All activities for the MDI investment project in Pakistan have been completed except the verification. The project in Egypt has been delayed by 18 months pending the agreement of the beneficiary for counterpart funding. The project is now expected to be completed in 2018. Ninety-eight per cent of the funds have been disbursed for the MDI project in China but UNIDO has delayed the planned completion date by 26 months (i.e. to 2018 to avoid the need to report any possible delays in future. This issue is addressed in Part III of the present document under “Extending planned completion dates beyond expected completion”.

ODS waste disposal

# The Executive Committee has approved 37 ODS waste disposal projects including 16 demonstration projects, three technical assistance projects and 18 project preparation activities in 15 countries, three regions (Africa, Europe and Central Asia, and Asia and the Pacific), and one global. So far, 21 projects have been completed including two demonstration, one technical assistance and 18 project preparation, leaving 14 demonstration projects and two technical assistance projects under implementation. All of the ongoing ODS disposal projects have been delayed since the last report except one that had an original planned completion date of January 2018 (Brazil) but has disbursed less than one per cent (US $7,962) of the approved funds (US $1,490,000). There has been no disbursement for two projects (Algeria and Lebanon) that were both approved in 2014. By contrast, 100 per cent of approved funds have been disbursed for the project in China but the planned completion date has been extended by six months from the 2014 progress report. The Executive Committee may wish to request the relevant bilateral and implementing agencies to submit annual reports for all pilot demonstration projects for ODS disposal starting from the 78th meeting as projects with specific reporting requirements until these projects are completed.

# Chiller projects

# The Executive Committee has approved 20 chiller projects amounting to US $11.76 million. Sixteen projects have been completed (seven demonstration, eight investment and one technical assistance projects) and four demonstration projects are under implementation. All of the ongoing chiller projects were approved not later than April 2006. There has been limited disbursement in the chiller project in Brazil (BRA/REF/47/DEM/275) where US $144,082 of US $1 million has been disbursed but the project is fully operational. The last remaining components of the World Bank’s global chiller project (GLO/REF/47/DEM/268) are at a very early stage of implementation and only US $1,754,135 has been disbursed of the US $3,735,556 approved. The last component of the bilateral global chiller project is also at an early stage of implementation and there remains a balance of US $312,587 out of US $1 million. Although completion dates have been extended for the four ongoing chiller projects, given the excessive delay in implementation, agencies should report under specific reporting requirements until all projects are completed. The Executive Committee may wish to request bilateral and implementing agencies to submit reports for all ongoing chiller projects starting from the 78th meeting as projects with specific reporting requirements until these projects are completed.

Halon banking

# The Executive Committee has approved 36 halon banking projects including 35 technical assistance and one training projects in 22 countries, three regions (Africa, Latin America and the Caribbean, and Asia and the Pacific), and one global. All these projects have been completed. The technical assistance project that was under implementation in Iran (Islamic Republic of) (IRA/HAL/63/TAS/198) was completed without the installation of the equipment; the remaining funds will be returned to the Fund.

Projects related to the phase-out of HCFCs

HPMP preparation and other project preparation

# The Executive Committee has approved US $33.28 million for 422 project preparation activities in 145 Article 5 countries to address HCFC control measures. Implementation of these activities resulted in the approval of stages I and II of HPMPs in 142 Article 5 countries. Three-hundred and three project preparation activities have been completed. The remaining 119 projects are still under implementation.

# Twenty-nine preparatory activities (most of which are for HPMP preparation) are classified as ongoing but have a balance of over US $1.1 million of the approved US $1.9 million but projects were approved at the 75th or 76th meeting. The Executive Committee may wish to request bilateral and implementing agencies to report project preparation activities completed once the HPMP is approved by the Executive Committee and to return fund balances from the preparation activities no later than 12 months after the approval of the HPMP.

HCFC demonstration projects

# The Executive Committee has approved 19 HCFC demonstration projects including ten in the foam sector, seven in the refrigeration sector and two in the solvent sector. Eight foam, four refrigeration and one solvent demonstration projects have been completed. The remaining six projects under implementation are planned for completion in 2016 and 2017. Two of these projects were approved at the 75th meeting but work plans are progressing and the two PRAHA refrigeration demonstration projects have had successful results but are still considered ongoing.

# HPMPs

# As of 31 December 2015, the Executive Committee has approved HPMP activities in 142 countries valued at US $620.47 million in principle for which US $531.19 million has been approved for tranche activities. The Executive Committee has approved stage I of HPMPs for 142 countries and stage II of HPMPs for 14 countries. It also approved 76 HCFC individual projects including two investment, 73 technical assistance projects and one training activity. Thirty projects have been completed. Of the remaining 46 projects still under implementation, 24 will be completed in 2016, 21 in 2017 and one in 2018. With the exception of the stand-alone project in Syrian Arab Republic, all investment projects have been subsumed in the relevant HPMPs.

# The 142 approved HPMPs address compliance with the 2015 and 2020 targets, and the complete phase-out of HCFCs in 2040 as follows:

## Sixteen countries (five low-volume-consuming (LVC) and 11 non-LVC countries) address compliance for the period 2011 to 2015;

## One-hundred and nine countries (59 LVC and 38 non-LVC countries, plus the 12 Pacific Island Countries (PICs)) address compliance for 2011 to 2020;

## Six countries address compliance for 2011 to 2025;

## Eleven LVC countries (Bhutan, Cambodia, Croatia, Guyana, Kyrgyzstan, Maldives, Mauritius, Namibia, Papua New Guinea, Saint Vincent and the Grenadines, and Seychelles) will phase out HCFCs well in advance of the 2040 compliance target (Croatia by 2014, and the others by 2020 or 2025).

# Of the 142 HPMPs (representing 615 tranches) approved by the Executive Committee to-date, 225 tranches have been completed and 390 are ongoing of which 160 have had delays reported since the 2014 progress report. Additional status reports are requested on projects with specific implementation impediment. An indicator for most agencies for the initiation of project activities is the signing of relevant agreements. Of the ongoing tranches, the Secretariat’s review of the database indicates that the required agreement or project document has not been signed for 26 countries. Status reports on the signing of required agreements are requested for these projects. Another indicator of progress of an HPMP is disbursement. Annex II summarizes by country the total funding approved and funds disbursed (as of 31 December 2015) for HPMP phase-out activities. Thirteen countries have disbursed less than 20 per cent of the approved funds for their overall HPMPs. Status reports are requested for those HPMPs that have low disbursement.

# At its 75th meeting, the Executive Committee requested the agencies to ensure consistency between funding disbursement data in the tranche requests and the annual progress reports (decision 76/14(b)). However, the Secretariat noted that a number of tranches appear to have been approved without the previous tranche having achieved the required 20 per cent disbursement rate according to the information contained in the progress report (i.e. Bahrain (BAH/PHA/68/TAS/28) (UNEP); Brazil (BRA/PHA/73/INV/306, BRA/PHA/74/INV/307) (UNDP); Chile (CHI/PHA/71/INV/179 and CHI/PHA/71/TAS/180) (UNDP and UNEP); and Mexico (MEX/PHA/71/INV/168) (UNDP). Furthermore, the disbursements in annual progress report was not consistent with that reported in tranche requests per decision 76/14(b) for HPMPs in three countries under World Bank implementation: China (CPR/PHA/75/INV/563 and CPR/PRO/74/INV/561); Indonesia (IDS/PHA/64/INV/191 and IDS/PHA/71/INV/202); and Thailand (THA/PHA/68/INV/161 and THA/PHA/68/INV/162). The Executive Committee may wish to request implementing agencies to revise their progress report disbursement data for those tranches of HPMPs, as appropriate, to be in line with decision 76/14(b).

HPPMP

# As of 31 December 2015, the Executive Committee has approved the HPPMP for one Article 5 country (China). Of the US $95 million approved, US $66.2 million has been disbursed to final beneficiary enterprises. Upon approval of the verification report at the 77th meeting, the remaining funds will be released from the World Bank to the Government of China to complete stage I activities.

Survey of ODS alternatives

# As of 31 December 2014, the Executive Committee has approved 129 surveys of ODS alternatives in 126 countries amounting to US $8.71 million. So far, one project has been completed and 128 projects are still under implementation. The Secretariat assessed the status of the implementation of these surveys based on the updated data provided in September 2016. The following table characterizes the status of progress based on the milestones achieved toward completion of the surveys. The table shows that 71 of the 128 surveys were underway or completed as of September 2016. The Executive Committee may wish to urge implementing agencies to take appropriate actions to complete and submit the reports of the surveys of ODS alternatives by January 2017 to enable the Secretariat to provide an analysis of the results of such surveys for consideration of the Executive Committee at its 78th meeting, in line with decision 74/53(h).

Table 6: Status of ODS alternative survey in steps toward completion by number of surveys

| Steps toward completion | Number of surveys |
| --- | --- |
| No activity/security situation | 4 |
| Template provided to national ozone unit for data collection | 1 |
| Agreement signed | 7 |
| Consultant not hired | 8 |
| Consultant hired | 29 |
| National team trained to conduct study | 8 |
| Survey underway | 68 |
| Survey draft completed | 3 |
| Total | 128 |

IS projects

# Funding for IS projects has been approved in the amount of US $115.01 million, and projects are ongoing in 137 countries. Implementation of a number of IS projects has been delayed by a number of issues, inter alia, the establishment of a funding transfer mechanism, security situation in the country, submission of required expenditure and progress reports by the Government, appointment of a national ozone officer (NOO), delay in making the first disbursement. The issues identified during the review of the IS projects are addressed in the individual agencies’ progress reports. For other IS projects for which funding is not requested at the 77th meeting, status reports were requested.

# There were four ongoing IS projects with 100 per cent disbursement. Five countries had two or three IS projects ongoing at the same time. The Executive Committee may wish to decide that no more than two IS projects should be ongoing at the same time.

Administrative costs

# Of the net US $2,985,607,490 approved for project implementation, US $337,411,411 has been disbursed for administrative costs resulting in an overall administrative cost ratio of 11.3 per cent since 1991. In 2015, of the US $170,839,416 approved, US $17,887,023 has been disbursed for administrative costs resulting in an overall administrative cost ratio of 10.5 per cent.

Part III: Additional comments and recommendations of the Secretariat

# This part addresses additional issues that have been identified during the review of the agencies’ progress reports. Most of the issues are addressed in detail in the individual progress reports. It concludes with recommendations.

Additional comments

Security issues

# There are 26 ongoing projects in three countries with security issues. Of the US $12,408,580 approved for the ongoing projects, US $8,280,550 has been disbursed, however with little disbursement occurred in 2016. The Executive Committee has extended completion dates for the activities in two countries namely Iraq and Yemen. The Secretariat will continue monitoring the status of implementation of these activities; however, UNIDO has requested an extension of the completion dates until December 2018 for Yemen or to cancel the tranches and reactivate the project only once conditions in the country improve.

Additional status reports/reports on implementation delays

# The review of the 2015 progress report has enabled the Secretariat to identify 16 projects with implementation delays that are subject to procedures for project cancellation. Appendix I of Annex III to the present document presents those projects classified with implementation delays for which a report will be due at the 78th meeting. The Secretariat also identified a number of issues for which 119 additional status reports are recommended. The reasons for requesting those reports are discussed in the individual agencies’ progress reports. Appendix II of Annex III to the present document contains a list of those projects.

Extending planned completion dates beyond expected completion

# Implementing agencies indicated in three cases that they were extending the planned completion beyond the expected completion dates to account for unanticipated delays. This was done in the case of an MDI project (MEX/PHA/73/INV/174) where the expected completion was in 2017 but the agency listed a date in 2018. This was also the case where a project was completed in the MB consumption sector (CPR/PHA/71/INV/533) but the project was listed as ongoing with a planned completion date extended to match that of the production sector project (CPR/PHA/73/INV/547) with a view toward one combined project completion report for two different projects. In another case, a project was listed as ongoing with only 23 per cent of funds disbursed (MDV/REF/38/TAS/05); however, the project was actually completed but the planned completion date continued to be extended and the balances were not returned. The Executive Committee may wish to reiterate that latest planned completion dates in annual progress reports should represent the agency’s best estimation of the expected completion date and that project completion reports should continue to be provided by agreement or project approval as applicable without combining reports from different agreements or approvals.

Ongoing projects with 100 per cent of funds disbursed

# There are 21 ongoing projects that have disbursed 100 per cent of approved funds. Nine of those countries had disbursed all project funds since the last progress report. Classifying a project as ongoing delays the due date for project completion reports. Moreover, continuing to classify a project as ongoing with no funds remaining for activities could risk incurring additional costs. The Executive Committee may wish to decide that projects where 100 per cent of funds have been disbursed should be completed within one year from the time when full disbursements are reported.

Servicing sector

# At the inter-agency coordination meeting, the Secretariat requested the implementing agencies to characterize progress and activities associated with HPMPs with respect to the following enabling activities: policy and regulations (strengthening legal frameworks), training of customs officers, training of servicing technicians, technician certification, industry associations, establishing recovery reclamation centres, activities in the assembly and installation sub-sector, phase-out of HCFCs in the flushing sector, capacity building activities and awareness activities. The implementing agencies, in particular UNEP due to the large number of servicing sector activities under its implementation, made a great effort to provide this data in addition to its normal progress reporting requirements. This section of the report summarizes some of the characteristics of those activities.

# The information provided related to, inter alia: import/quota (permits) and licensing systems; bans on equipment and blends; the incorporation of training in the curricula for customs officers and refrigeration technicians; the establishment of customs codes for controlled HFCs; the need for training to further understand how to address emerging alternatives; technician certification programmes in place; industry associations and their involvement in implementing activities under the HPMPs; and recovery/reclamation, flushing, awareness raising and capacity building.

# The Secretariat noted that the information collected, although incomplete, has been useful to have a better understanding of the activities in the refrigeration servicing sector. The Secretariat will discuss with the implementing agencies the analysis of the information gathered and if there would be a need for providing additional information in the context of the progress reports.

Recommendation

# The Executive Committee may wish:

## To note:

### The consolidated progress report of the Multilateral Fund as at 31 December 2015 contained in document UNEP/OzL.Pro/ExCom/77/11;

### With appreciation, the efforts undertaken by bilateral and implementing agencies in reporting the 2015 activities;

### That the bilateral and implementing agencies would report to the 78th meeting on 16 projects with implementation delays and 119 projects recommended for additional status reports, as contained in Appendices I and II, respectively, of Annex III to document UNEP/OzL.Pro/ExCom/77/11;

## To consider whether to extend the approved completion dates for the following projects:

### CTC phase-out plan in India (IND/PHA/71/INV/451, IND/PHA/71/TAS/448, and IND/PHA/75/INV/464), to November 2017;

### ODS multi-year agreement in Yemen, to December 2018, or to cancel the tranches and reactivate the project only once conditions in the country improve;

### Methyl bromide project in China, to December 2018 to allow for the submission of one project completion report for both the consumption and production sectors, noting that activities in the consumption sector have been completed and unused funds should be returned by 31 December 2016;

## To request bilateral and implementing agencies:

### To submit annual reports for all pilot demonstration projects for ODS disposal starting from the 78th meeting as projects with specific reporting requirements until these projects are completed;

### To submit reports for all ongoing chiller projects starting from the 78th meeting as projects with specific reporting requirements until these projects are completed;

### To report project preparation activities completed once the HCFC phase-out management plan (HPMP) is approved by the Executive Committee and to return fund balances from the preparation activities no later than 12 months after the approval of the HPMP;

### To request implementing agencies to revise their progress report disbursement data for the following tranches of HPMPs, as appropriate, to be in line with decision 76/14(b): BAH/PHA/68/TAS/28 (UNEP); BRA/PHA/73/INV/306 and BRA/PHA/74/INV/307 (UNDP); CHI/PHA/71/INV/179 (UNDP); CHI/PHA/71/TAS/180 (UNEP); CPR/PHA/75/INV/563 and CPR/PRO/74/INV/561 (World Bank); IDS/PHA/64/INV/191 and IDS/PHA/71/INV/202 (World Bank); MEX/PHA/71/INV/168 (UNDP); and THA/PHA/68/INV/161 and THA/PHA/68/INV/162 (World Bank);

### To urge bilateral and implementing agencies to take appropriate actions to complete and submit the reports of the surveys of ODS alternatives by January 2017 to enable the Secretariat to provide an analysis of the results of such surveys for consideration of the Executive Committee at its 78th meeting, in line with decision 74/53(h);

### To decide:

### That no more than two institutional strengthening projects should be ongoing at the same time;

### That projects where 100 per cent of the funds have been reported disbursed should be completed within one year from the time when full disbursements are reported; and

### To reiterate that latest planned completion dates in annual progress reports should represent the agency’s best estimation of the expected completion date and that project completion reports should continue to be provided by agreement or project approval as applicable without combining reports from different agreements or approvals.

Annex I

PROJECT IMPLEMENTATION IN 2015 BY COUNTRY

| Country | Phased out in 2015 | Percentage of planned phase-out achieved in 2015 (%) | Estimated funds disbursed in 2015 (US$) | Funds disbursed in 2015 (US$) | Percentage of funds disbursed over estimation in 2015 (%) | Percentage of planned projects completed in 2015 (%) |
| --- | --- | --- | --- | --- | --- | --- |
| Afghanistan | 0.0 |  | 271,493 | 26,101 | 10 | 67 |
| Albania | 0.0 |  | 61,489 | 44,060 | 72 | 33 |
| Algeria | 0.0 |  | 221,700 | 74,022 | 33 |  |
| Angola | 0.0 |  | 69,027 | 91,882 | 133 | 67 |
| Antigua and Barbuda | 0.0 |  | 26,265 | 7,650 | 29 | 25 |
| Argentina | 90.0 | 100 | 1,959,934 | 1,439,939 | 73 | 67 |
| Armenia | 0.0 |  | 104,106 | 104,878 | 101 | 100 |
| Bahamas (the) | 0.2 | 100 | 100,460 | 22,194 | 22 | 100 |
| Bahrain | 0.0 |  | 225,980 | 36,621 | 16 | 0 |
| Bangladesh | 0.0 |  | 206,009 | 171,641 | 83 | 0 |
| Barbados | 0.0 |  | 56,500 | 44,633 | 79 | 100 |
| Belize | 0.0 |  | 0 | 30,680 |  | 100 |
| Benin | 1.0 | 100 | 143,000 | 67,141 | 47 | 50 |
| Bhutan | 0.0 |  | 70,006 | 38,258 | 55 | 0 |
| Bolivia (Plurinational State of) | 0.0 |  | 0 | 94,623 |  | 100 |
| Bosnia and Herzegovina | 0.9 | 100 | 118,846 | 155,528 | 131 | 100 |
| Botswana | 0.0 |  | 53,888 | 0 | 0 | 0 |
| Brazil | 18.2 |  | 5,290,598 | 5,014,452 | 95 | 100 |
| Brunei Darussalam | 0.2 | 0 | 53,240 | 42,300 | 79 | 0 |
| Burkina Faso | 0.0 |  | 99,760 | 69,792 | 70 | 100 |
| Burundi | 0.0 |  | 71,956 | 73,962 | 103 | 0 |
| Cambodia | 0.0 |  | 163,256 | 44,249 | 27 | 50 |
| Cameroon | 6.4 | 100 | 159,664 | 142,560 | 89 | 33 |
| Cabo Verde | 0.0 |  | 65,000 | 44,077 | 68 | 100 |
| Central African Republic (the) | 0.0 |  | 64,973 | 0 | 0 |  |
| Chad | 0.0 |  | 32,025 | 76,330 | 238 | 33 |
| Chile | 14.5 | 0 | 867,704 | 444,106 | 51 | 50 |
| China | 4,694.1 | 88 | 39,851,892 | 62,951,474 | 158 | 21 |
| Colombia | 2.9 | 0 | 753,911 | 815,474 | 108 | 50 |
| Comoros (the) | 0.0 |  | 95,400 | 81,684 | 86 | 100 |
| Congo (the) | 0.0 |  | 76,489 | 59,836 | 78 | 100 |
| Cook Islands (the) | 0.0 |  | 3,143 | 0 | 0 | 100 |
| Costa Rica | 0.0 |  | 127,048 | 144,382 | 114 |  |
| Cote d’Ivoire | 0.0 |  | 172,430 | 31,055 | 18 | 100 |
| Croatia | 0.0 |  | 254,300 | 175,603 | 69 | 75 |
| Cuba | 5.4 |  | 627,389 | 908,985 | 145 |  |
| Cyprus | 0.0 |  | 0 | 0 |  |  |
| Democratic People's Republic of Korea (the) | 0.0 |  | 323,728 | 158,559 | 49 | 75 |
| Democratic Republic of the Congo (the) | 0.0 | 0 | 115,885 | 40,537 | 35 | 0 |
| Djibouti | 0.0 |  | 65,000 | 24,004 | 37 | 100 |
| Dominica | 0.0 |  | 7,243 | 0 | 0 |  |
| Dominican Republic (the) | 0.4 |  | 242,412 | 495,714 | 204 |  |
| Ecuador | 0.0 |  | 157,108 | 162,944 | 104 | 100 |
| Egypt | 0.0 |  | 1,815,027 | 808,202 | 45 | 75 |
| El Salvador | 1.9 |  | 85,676 | 62,237 | 73 | 100 |
| Equatorial Guinea | 0.0 |  | 76,181 | 2,416 | 3 | 0 |
| Eritrea | 0.0 |  | 135,862 | 36,669 | 27 | 0 |
| Ethiopia | 0.0 |  | 22,500 | 22,099 | 98 | 50 |
| Fiji | 0.0 |  | 24,179 | 16,457 | 68 |  |
| Gabon | 0.0 |  | 73,166 | 8,151 | 11 | 100 |
| Gambia (the) | 0.0 |  | 56,760 | 15,000 | 26 | 0 |
| Georgia | 0.6 | 100 | 88,831 | 110,726 | 125 | 100 |
| Ghana | 1.3 |  | 202,298 | 247,374 | 122 | 0 |
| Grenada | 0.0 |  | 21,955 | 0 | 0 | 100 |
| Guatemala | 217.7 | 100 | 98,907 | 37,752 | 38 | 60 |
| Guinea | 1.2 | 100 | 19,691 | 27,633 | 140 | 67 |
| Guinea-Bissau | 0.1 | 100 | 15,974 | 63,000 | 394 | 100 |
| Guyana | 0.0 |  | 2 | 25,220 | 1261001 | 100 |
| Haiti | 0.0 |  | 84,637 | 96,308 | 114 | 0 |
| Honduras | 0.0 | 0 | 133,400 | 37,973 | 28 | 100 |
| India | 130.6 | 97 | 6,412,139 | 7,248,688 | 113 | 57 |
| Indonesia | 30.8 | 100 | 3,134,592 | 2,586,587 | 83 | 0 |
| Iran (Islamic Republic of) | 44.0 | 62 | 1,890,234 | 1,999,279 | 106 | 43 |
| Iraq | 0.0 | 0 | 1,459,158 | 1,065,566 | 73 | 40 |
| Jamaica | 0.0 |  | 115,585 | 99,630 | 86 | 100 |
| Jordan | 0.1 | 0 | 1,159,033 | 814,922 | 70 | 67 |
| Kenya | 0.0 |  | 158,717 | 97,360 | 61 | 50 |
| Kiribati | 0.0 |  | 16,421 | 16,525 | 101 | 50 |
| Kuwait | 0.0 | 0 | 289,143 | 101,330 | 35 | 0 |
| Kyrgyzstan | 0.0 | 0 | 10,209 | 16,983 | 166 | 100 |
| Lao People’s Democratic Republic (the) | 0.0 |  | 68,709 | 37,576 | 55 | 50 |
| Lebanon | 0.0 |  | 316,375 | 248,348 | 78 |  |
| Lesotho | 0.0 |  | 40,500 | 51,307 | 127 | 0 |
| Liberia | 0.0 |  | 75,496 | 86,465 | 115 | 50 |
| Libya | 0.0 |  | 144,883 | 116,870 | 81 |  |
| Madagascar | 0.0 |  | 66,000 | 73,746 | 112 | 100 |
| Malawi | 0.0 |  | 70,128 | 36,733 | 52 |  |
| Malaysia | 0.1 | 0 | 1,072,642 | 1,044,821 | 97 | 0 |
| Maldives | 0.0 |  | 243,476 | 96,707 | 40 | 33 |
| Mali | 0.0 |  | 123,220 | 3,026 | 2 | 100 |
| Malta | 0.0 |  | 0 | 0 |  |  |
| Marshall Islands (the) | 0.0 |  | 38,397 | 0 | 0 | 0 |
| Mauritania | 0.0 |  | 93,883 | 0 | 0 |  |
| Mauritius | 0.0 |  | 53,500 | 32,308 | 60 |  |
| Mexico | 63.4 | 0 | 3,494,650 | 2,484,134 | 71 | 80 |
| Micronesia (Federated States of) | 0.0 |  | 3,701 | 30,813 | 833 | 100 |
| Mongolia | 0.0 | 0 | 112,000 | 66,228 | 59 | 50 |
| Montenegro | 0.0 |  | 43,001 | 35,555 | 83 |  |
| Morocco | 0.0 |  | 311,681 | 44,793 | 14 | 100 |
| Mozambique | 0.4 | 100 | 46,400 | 67,452 | 145 | 50 |
| Myanmar | 0.0 |  | 254,942 | 1,237 | 0 | 0 |
| Namibia | 0.0 |  | 40,509 | 68,590 | 169 | 100 |
| Nauru | 0.0 |  | 1,878 | 0 | 0 | 0 |
| Nepal | 0.1 |  | 64,687 | 81,150 | 125 | 50 |
| Nicaragua | 0.0 | 0 | 13,207 | 38,737 | 293 | 67 |
| Niger (the) | 0.0 |  | 60,938 | 83,202 | 137 | 50 |
| Nigeria | 0.0 |  | 1,614,692 | 1,526,151 | 95 |  |
| Niue | 0.0 |  | 33,236 | 18,528 | 56 | 0 |
| Oman | 2.3 | 77 | 245,424 | 251,643 | 103 | 50 |
| Pakistan | 0.0 | 0 | 548,801 | 305,879 | 56 | 40 |
| Palau | 0.0 |  | 31,822 | 30,000 | 94 | 100 |
| Panama | 1.4 | 100 | 218,537 | 204,634 | 94 | 50 |
| Papua New Guinea | 0.0 |  | 34,867 | 43,966 | 126 |  |
| Paraguay | 0.8 | 100 | 109,681 | 100,169 | 91 | 100 |
| Peru | 0.0 |  | 231,114 | 62,788 | 27 |  |
| Philippines (the) | 0.0 |  | 551,692 | 389,653 | 71 | 40 |
| Qatar | 19.1 | 92 | 808,500 | 803,115 | 99 | 0 |
| Republic of Moldova (the) | 0.0 |  | 36,465 | 50,367 | 138 | 50 |
| Romania | 0.0 |  | 0 | 3 |  |  |
| Rwanda | 0.2 | 100 | 88,683 | 76,479 | 86 | 50 |
| Saint Kitts and Nevis | 0.0 | 0 | 52,000 | 0 | 0 | 100 |
| Saint Lucia | 0.0 |  | 46,262 | 4,000 | 9 | 0 |
| Saint Vincent and the Grenadines | 0.0 |  | 17,251 | 16,439 | 95 | 100 |
| Samoa | 0.0 |  | 34,998 | 30,000 | 86 | 100 |
| Sao Tome and Principe | 0.0 |  | 118,000 | 51,874 | 44 | 0 |
| Saudi Arabia | 0.0 | 0 | 1,993,991 | 1,736,618 | 87 | 0 |
| Senegal | 0.0 | 0 | 79,465 | 114,549 | 144 | 100 |
| Serbia | 0.0 |  | 377,137 | 235,630 | 62 | 50 |
| Seychelles | 0.0 | 0 | 141,050 | 107,443 | 76 | 0 |
| Sierra Leone | 0.0 |  | 94,606 | 32,900 | 35 | 0 |
| Slovenia | 0.0 |  |  | 0 |  |  |
| Solomon Islands | 0.0 |  | 33,560 | 14,125 | 42 | 0 |
| Somalia | 0.0 |  | 80,500 | 38,392 | 48 | 0 |
| South Africa | 0.0 |  | 730,001 | 322,698 | 44 |  |
| South Sudan | 0.0 |  | 34,990 | 0 | 0 | 0 |
| Sri Lanka | 0.4 | 100 | 131,103 | 76,989 | 59 | 100 |
| Sudan (the) | 0.0 |  | 272,105 | 156,180 | 57 | 67 |
| Suriname | 0.0 |  | 28,000 | 0 | 0 |  |
| Swaziland | 0.0 |  | 100,820 | 0 | 0 |  |
| Syrian Arab Republic | 0.0 |  | 108,541 | 195,513 | 180 |  |
| Thailand | 46.2 |  | 2,178,702 | 2,748,196 | 126 |  |
| The former Yugoslav Republic of Macedonia | 0.2 |  | 79,036 | 76,695 | 97 | 0 |
| Timor-Leste | 0.0 |  | 142,589 | 22,961 | 16 | 0 |
| Togo | 0.0 |  | 89,053 | 71,918 | 81 | 100 |
| Tonga | 0.0 |  | 36,774 | 32,550 | 89 | 100 |
| Trinidad and Tobago | 2.5 | 0 | 298,438 | 342,372 | 115 | 50 |
| Tunisia | 0.0 | 0 | 395,402 | 462,028 | 117 | 50 |
| Turkey | 16.3 | 100 | 593,475 | 371,173 | 63 | 50 |
| Turkmenistan | 0.0 |  | 81,813 | 89,745 | 110 | 100 |
| Tuvalu | 0.0 |  | 3,477 | 26,706 | 768 | 100 |
| Uganda | 0.0 |  | 62,386 | 1,886 | 3 | 50 |
| United Republic of Tanzania (the) | 0.0 | 0 | 5,001 | 0 | 0 | 0 |
| Uruguay | 2.3 |  | 198,048 | 180,108 | 91 | 100 |
| Vanuatu | 0.0 |  | 4,331 | 24,112 | 557 | 0 |
| Venezuela (Bolivarian Republic of) | 4.0 | 100 | 619,946 | 185,641 | 30 | 100 |
| Viet Nam | 89.4 |  | 3,247,976 | 2,383,979 | 73 | 100 |
| Yemen | 0.0 | 0 | 619,884 | 60,440 | 10 | 100 |
| Zambia | 0.0 |  | 127,494 | 11,647 | 9 | 50 |
| Zimbabwe | 0.0 | 0 | 118,539 | 78,730 | 66 | 67 |
| Region: AFR | 0.0 |  | 358,937 | 242,317 | 68 | 0 |
| Region: ASP | 0.0 |  | 113,775 | 161,923 | 142 | 33 |
| Region: EUR | 0.0 |  | 213,082 | 220,190 | 103 | 33 |
| Region: LAC | 0.0 |  | 50,000 | 0 | 0 | 100 |
| Global | 0.0 |  | 663,821 | 7,762,834 | 1169 | 83 |
| Grand total | 5,511.8 | 51 | 97,215,210 | 117,500,694 | 121 | 52 |

Annex II

HCFC PHASE-OUT MANAGEMENT PLAN (HPMP) BY COUNTRY 
AS AT 31 DECEMBER 2015

| Country | Approved phase-out (ODP tonnes) | Funds approved (US$) | Funds disbursed (US$) | Balance (US$) | Funds disbursed (%) |
| --- | --- | --- | --- | --- | --- |
| Afghanistan | 2.4 | 407,000 | 161,439 | 245,561 | 40 |
| Albania | 0.6 | 244,954 | 120,768 | 124,186 | 49 |
| Algeria | 13.5 | 1,809,240 | 64,241 | 1,744,999 | 4 |
| Angola | 1.6 | 156,444 | 68,674 | 87,770 | 44 |
| Antigua and Barbuda | 0.0 | 45,850 | 27,235 | 18,615 | 59 |
| Argentina | 82.4 | 10,650,154 | 8,494,977 | 2,155,177 | 80 |
| Armenia | 2.2 | 601,838 | 554,464 | 47,374 | 92 |
| Bahamas (the) | 0.4 | 183,342 | 134,787 | 48,555 | 74 |
| Bahrain | 6.4 | 814,455 | 33,105 | 781,350 | 4 |
| Bangladesh | 20.8 | 1,521,074 | 1,371,311 | 149,763 | 90 |
| Barbados | 0.0 | 124,000 | 0 | 124,000 | 0 |
| Belize | 0.0 | 140,000 | 140,000 | 0 | 100 |
| Benin | 2.4 | 306,314 | 198,160 | 108,154 | 65 |
| Bhutan | 0.0 | 282,000 | 253,766 | 28,234 | 90 |
| Bolivia (Plurinational State of) | 0.5 | 253,500 | 121,144 | 132,356 | 48 |
| Bosnia and Herzegovina | 6.0 | 760,261 | 667,706 | 92,555 | 88 |
| Botswana | 1.1 | 275,000 | 0 | 275,000 | 0 |
| Brazil | 295.6 | 25,996,427 | 9,487,874 | 16,508,553 | 36 |
| Brunei Darussalam | 0.6 | 242,900 | 140,622 | 102,278 | 58 |
| Burkina Faso | 2.0 | 390,000 | 327,200 | 62,800 | 84 |
| Burundi | 0.4 | 155,000 | 125,616 | 29,384 | 81 |
| Cambodia | 1.5 | 650,000 | 439,411 | 210,589 | 68 |
| Cameroon | 24.1 | 1,064,453 | 819,127 | 245,326 | 77 |
| Cabo Verde | 0.0 | 75,290 | 54,290 | 21,000 | 72 |
| Central African Republic (the) | 0.5 | 200,000 | 64,001 | 135,999 | 32 |
| Chad | 1.6 | 300,000 | 285,447 | 14,553 | 95 |
| Chile | 17.1 | 1,519,033 | 462,693 | 1,056,340 | 30 |
| China | 1,758.5 | 269,994,805 | 181,914,550 | 88,080,255 | 67 |
| Colombia | 135.9 | 9,539,617 | 6,676,539 | 2,863,078 | 70 |
| Comoros (the) | 0.0 | 79,000 | 44,000 | 35,000 | 56 |
| Congo (the) | 0.4 | 175,000 | 148,568 | 26,432 | 85 |
| Cook Islands (the) | 0.0 | 89,100 | 38,689 | 50,412 | 43 |
| Costa Rica | 15.4 | 991,522 | 875,624 | 115,898 | 88 |
| Cote d’Ivoire | 6.4 | 900,000 | 150,961 | 749,039 | 17 |
| Croatia | 8.1 | 812,162 | 752,800 | 59,362 | 93 |
| Cuba | 15.1 | 1,450,000 | 1,038,359 | 411,641 | 72 |
| Democratic People’s Republic of Korea (the) | 17.3 | 673,880 | 54,839 | 619,041 | 8 |
| Democratic Republic of the Congo (the) | 5.8 | 427,500 | 299,684 | 127,816 | 70 |
| Djibouti | 0.0 | 81,000 | 76,000 | 5,000 | 94 |
| Dominica | 0.0 | 82,250 | 10,026 | 72,224 | 12 |
| Dominican Republic (the) | 12.5 | 1,696,185 | 1,445,377 | 250,808 | 85 |
| Ecuador | 17.2 | 1,668,440 | 1,662,295 | 6,145 | 100 |
| Egypt | 166.1 | 7,571,840 | 4,231,406 | 3,340,434 | 56 |
| El Salvador | 6.5 | 774,277 | 549,971 | 224,306 | 71 |
| Equatorial Guinea | 0.6 | 145,000 | 96,947 | 48,053 | 67 |
| Eritrea | 0.0 | 80,000 | 43,778 | 36,222 | 55 |
| Ethiopia | 0.5 | 155,000 | 55,000 | 100,000 | 35 |
| Fiji | 0.0 | 182,000 | 135,385 | 46,615 | 74 |
| Gabon | 0.0 | 266,000 | 139,087 | 126,913 | 52 |
| Gambia (the) | 0.2 | 98,000 | 70,101 | 27,899 | 72 |
| Georgia | 1.2 | 350,000 | 248,608 | 101,392 | 71 |
| Ghana | 5.8 | 790,000 | 543,087 | 246,913 | 69 |
| Grenada | 0.0 | 105,000 | 52,071 | 52,929 | 50 |
| Guatemala | 2.9 | 327,855 | 215,408 | 112,447 | 66 |
| Guinea | 1.2 | 305,000 | 234,532 | 70,468 | 77 |
| Guinea-Bissau | 0.1 | 127,000 | 118,192 | 8,808 | 93 |
| Guyana | 0.3 | 281,182 | 58,930 | 222,252 | 21 |
| Haiti | 0.0 | 40,000 | 17,074 | 22,926 | 43 |
| Honduras | 2.0 | 314,835 | 225,571 | 89,264 | 72 |
| India | 341.8 | 21,294,490 | 16,505,370 | 4,789,120 | 78 |
| Indonesia | 123.3 | 11,572,962 | 6,392,894 | 5,180,068 | 55 |
| Iran (Islamic Republic of) | 172.5 | 9,934,338 | 8,402,978 | 1,531,360 | 85 |
| Iraq | 9.5 | 750,000 | 80,000 | 670,000 | 11 |
| Jamaica | 8.5 | 375,450 | 304,054 | 71,396 | 81 |
| Jordan | 15.9 | 3,366,017 | 2,360,579 | 1,005,438 | 70 |
| Kenya | 8.3 | 633,750 | 433,850 | 199,900 | 68 |
| Kiribati | 0.0 | 98,100 | 53,354 | 44,746 | 54 |
| Kuwait | 209.9 | 7,500,832 | 339,624 | 7,161,208 | 5 |
| Kyrgyzstan | 2.6 | 408,000 | 87,992 | 320,008 | 22 |
| Lao People's Democratic Republic (the) | 0.8 | 252,000 | 89,200 | 162,800 | 35 |
| Lebanon | 41.9 | 4,780,349 | 2,166,792 | 2,613,557 | 45 |
| Lesotho | 0.0 | 168,000 | 103,478 | 64,522 | 62 |
| Liberia | 2.0 | 283,500 | 161,256 | 122,244 | 57 |
| Libya | 24.1 | 1,717,950 | 0 | 1,717,950 | 0 |
| Madagascar | 0.9 | 280,000 | 247,122 | 32,878 | 88 |
| Malawi | 0.7 | 173,750 | 95,310 | 78,440 | 55 |
| Malaysia | 102.2 | 9,446,175 | 7,909,248 | 1,536,927 | 84 |
| Maldives | 0.6 | 1,050,000 | 704,195 | 345,805 | 67 |
| Mali | 0.8 | 267,401 | 215,427 | 51,974 | 81 |
| Marshall Islands (the) | 0.1 | 101,700 | 45,603 | 56,097 | 45 |
| Mauritius | 0.0 | 288,450 | 283,840 | 4,610 | 98 |
| Mexico | 483.6 | 21,252,718 | 10,777,368 | 10,475,350 | 51 |
| Micronesia (Federated States of) | 0.1 | 100,800 | 51,512 | 49,288 | 51 |
| Mongolia | 0.6 | 260,000 | 218,000 | 42,000 | 84 |
| Montenegro | 0.1 | 353,432 | 235,707 | 117,725 | 67 |
| Morocco | 11.0 | 1,248,999 | 980,524 | 268,475 | 79 |
| Mozambique | 0.3 | 150,000 | 54,980 | 95,020 | 37 |
| Myanmar | 0.4 | 159,000 | 1,237 | 157,763 | 1 |
| Namibia | 5.5 | 540,000 | 339,381 | 200,619 | 63 |
| Nauru | 0.0 | 66,600 | 43,747 | 22,853 | 66 |
| Nepal | 0.6 | 189,000 | 54,900 | 134,100 | 29 |
| Nicaragua | 0.7 | 214,500 | 109,199 | 105,301 | 51 |
| Niger (the) | 2.7 | 275,000 | 168,113 | 106,887 | 61 |
| Nigeria | 90.1 | 4,938,830 | 3,121,991 | 1,816,839 | 63 |
| Niue | 0.0 | 65,700 | 32,589 | 33,111 | 50 |
| Oman | 5.3 | 732,620 | 388,986 | 343,634 | 53 |
| Pakistan | 79.0 | 5,446,919 | 5,200,287 | 246,632 | 95 |
| Palau | 0.1 | 108,000 | 60,553 | 47,447 | 56 |
| Panama | 2.5 | 335,545 | 303,503 | 32,042 | 90 |
| Papua New Guinea | 0.8 | 690,000 | 340,346 | 349,654 | 49 |
| Paraguay | 6.3 | 567,000 | 273,169 | 293,831 | 48 |
| Peru | 2.7 | 253,000 | 50,445 | 202,555 | 20 |
| Philippines (the) | 40.0 | 3,328,575 | 2,186,975 | 1,141,600 | 66 |
| Qatar | 22.0 | 1,150,907 | 889,391 | 261,516 | 77 |
| Republic of Moldova (the) | 0.0 | 88,000 | 78,252 | 9,748 | 89 |
| Rwanda | 0.4 | 137,000 | 124,418 | 12,582 | 91 |
| Saint Kitts and Nevis | 0.3 | 147,600 | 58,400 | 89,200 | 40 |
| Saint Lucia | 0.1 | 125,998 | 113,736 | 12,262 | 90 |
| Saint Vincent and the Grenadines | 0.2 | 319,107 | 177,005 | 142,102 | 55 |
| Samoa | 0.1 | 133,650 | 71,252 | 62,398 | 53 |
| Sao Tome and Principe | 0.0 | 74,012 | 64,014 | 9,998 | 86 |
| Saudi Arabia | 219.2 | 8,562,575 | 3,520,541 | 5,042,034 | 41 |
| Senegal | 3.6 | 300,000 | 204,492 | 95,508 | 68 |
| Serbia | 5.2 | 857,760 | 357,482 | 500,278 | 42 |
| Seychelles | 1.4 | 540,000 | 304,308 | 235,692 | 56 |
| Sierra Leone | 0.2 | 98,000 | 81,870 | 16,130 | 84 |
| Solomon Islands | 0.7 | 175,500 | 109,515 | 65,985 | 62 |
| Somalia | 0.5 | 173,874 | 120,808 | 53,066 | 69 |
| South Africa | 66.8 | 4,552,849 | 2,068,242 | 2,484,607 | 45 |
| Sri Lanka | 1.3 | 389,000 | 301,447 | 87,553 | 77 |
| Sudan (the) | 39.0 | 3,799,913 | 1,311,468 | 2,488,445 | 35 |
| Suriname | 0.2 | 123,500 | 57,178 | 66,322 | 46 |
| Swaziland | 7.9 | 797,919 | 757,100 | 40,819 | 95 |
| Thailand | 149.7 | 14,826,285 | 2,569,884 | 12,256,401 | 17 |
| The former Yugoslav Republic of Macedonia | 1.9 | 728,954 | 554,941 | 174,013 | 76 |
| Timor-Leste | 0.0 | 244,620 | 163,031 | 81,589 | 67 |
| Togo | 0.9 | 315,000 | 218,086 | 96,914 | 69 |
| Tonga | 0.0 | 114,300 | 60,526 | 53,774 | 53 |
| Trinidad and Tobago | 6.7 | 1,229,733 | 503,370 | 726,363 | 41 |
| Tunisia | 4.5 | 678,575 | 117,031 | 561,544 | 17 |
| Turkey | 384.5 | 11,124,690 | 7,527,837 | 3,596,853 | 68 |
| Turkmenistan | 0.7 | 403,550 | 342,458 | 61,092 | 85 |
| Tuvalu | 0.0 | 82,800 | 44,398 | 38,402 | 54 |
| Uganda | 0.0 | 80,500 | 42,771 | 37,729 | 53 |
| United Republic of Tanzania (the) | 0.2 | 104,874 | 84,875 | 19,999 | 81 |
| Uruguay | 4.2 | 380,004 | 341,082 | 38,922 | 90 |
| Vanuatu | 0.1 | 133,650 | 71,919 | 61,731 | 54 |
| Venezuela (Bolivarian Republic of) | 23.3 | 1,894,500 | 1,274,165 | 620,335 | 67 |
| Viet Nam | 134.1 | 8,717,439 | 5,352,552 | 3,364,887 | 61 |
| Yemen | 11.6 | 625,000 | 176,907 | 448,093 | 28 |
| Zambia | 0.7 | 148,635 | 108,152 | 40,483 | 73 |
| Zimbabwe | 10.0 | 814,818 | 702,818 | 112,000 | 86 |
| Region: ASP | 0.0 | 240,000 | 120,225 | 119,775 | 50 |
| Grand total | 5,564.6 | 531,196,522 | 329,965,143 | 201,231,379 | 62 |

Annex III

ANALYSIS OF PROGRESS REPORT DATA

# This analysis provides an overview of projects that have been completed, projects that were still ongoing, and projects that have been closed or transferred as of 31 December 2015.

Completed Projects

# Overall, 99.8 per cent of the funds approved for completed investment projects have been disbursed. The reason that 100 per cent of funds have not been disbursed for completed projects is that it may take from six months to one year to finalise accounting records.

Completed investment projects

# Table 1 presents information on investment projects that have been completed since 1991. The table presents the data in total, followed by data according to region, sector, implementation characteristics, and disbursement method.

Table 1: Cumulative completed investment projects

| Item | Number of projects | Approved funds plus adjustment (US $) | Per cent of funds disbursed (%) | Consumption ODP phased out* | Production ODP phased out* | Average number of months from approval to first disbursement | Average number of months from approval to completion | Overall cost-effective-ness to the Fund (US$/kg.) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GRAND TOTAL | 2,585 | 1,913,933,017 | 100 | 265,800 | 201,277 | 15 | 36 | $4.10 |
| Region |  |  |  |  |  |  |  |  |
| Africa | 416 | 140,491,580 | 100 | 17,827 | 0 | 12 | 36 | $7.88 |
| Asia & Pacific | 1,414 | 1,358,628,576 | 100 | 206,650 | 181,327 | 16 | 36 | $3.50 |
| Europe | 129 | 60,951,977 | 100 | 7,696 | 175 | 10 | 32 | $7.74 |
| Latin America and Caribbean | 626 | 353,860,883 | 99 | 33,627 | 19,775 | 14 | 36 | $6.63 |
| Global | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Sector |  |  |  |  |  |  |  |  |
| Aerosol | 124 | 63,348,134 | 100 | 26,883 | 0 | 16 | 41 | $2.36 |
| Destruction | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Fire fighting | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Foam | 998 | 364,697,343 | 100 | 69,132 | 0 | 15 | 34 | $5.28 |
| Fumigants | 116 | 93,869,589 | 100 | 7,548 | 0 | 10 | 46 | $12.44 |
| Halon | 39 | 71,476,177 | 100 | 42,111 | 41,958 | 17 | 30 | $0.85 |
| Multiple sectors | 4 | 2,287,376 | 100 | 419 | 0 | 28 | 78 | $5.46 |
| Other | 8 | 16,059,360 | 100 | 1,574 | 0 | 12 | 20 | $10.20 |
| Phase-out plan | 469 | 313,068,074 | 99 | 47,112 | 10,988 | 12 | 36 | $5.39 |
| Process agent | 30 | 120,252,627 | 100 | 19,573 | 52,162 | 10 | 27 | $1.68 |
| Production | 57 | 346,093,481 | 100 | 0 | 96,169 | 9 | 18 | $3.60 |
| Refrigeration | 609 | 427,355,617 | 100 | 44,103 | 0 | 16 | 39 | $9.69 |
| Solvents | 128 | 94,351,384 | 100 | 7,285 | 0 | 19 | 32 | $12.95 |
| Sterilant | 3 | 1,073,855 | 100 | 60 | 0 | 15 | 34 | $17.77 |
| Implementation characteristics |  |  |  |  |  |  |  |  |
| Agency implementation | 1,629 | 697,000,848 | 100 | 91,972 | 17,381 | 11 | 34 | $6.37 |
| National implementation | 956 | 1,216,932,168 | 100 | 173,828 | 183,896 | 21 | 40 | $3.40 |
| Disbursement method |  |  |  |  |  |  |  |  |
| During implementation | 2,494 | 1,821,847,822 | 100 | 261,084 | 199,719 | 14 | 36 | $3.95 |
| After implementation | 50 | 17,166,608 | 100 | 2,512 | 0 | 23 | 25 | $6.83 |
| Retroactive funding | 36 | 14,138,587 | 100 | 2,100 | 500 | 15 | 8 | $5.44 |
| Country to final beneficiaries | 5 | 60,780,000 | 100 | 103 | 1,058 | 8 | 33 | $52.33 |

# As of 31 December 2015, investment projects representing around US $1.91 billion have been completed, resulting in the permanent phase-out of 467,077 ODP tonnes with an overall cost-effectiveness of US $4.10/kg ODP phased out.

# The average time from approval to first disbursement was 15 months and the average project duration was 36 months. Project duration is only slightly impacted by retroactive projects (i.e., projects funded after phase-out) since they represent only around 1.4 per cent of the total number of completed investment projects.

# On a regional basis, 1,414 investment projects were completed in the Asia and Pacific region, 626 investment projects in Latin America and the Caribbean, 416 in Africa, and 129 in Europe.

Completed non-investment projects

# Table 2 presents data on cumulative completed non-investment projects. Since 1991, 2,584 non-investment projects have been completed, representing funding support from the Multilateral Fund of around US $385.43 million. Ninety-nine (99) per cent of the funds for completed non-investment projects have been disbursed. Fifty-four (54) per cent of completed non-investment funding is in the sector identified as “several”, which means those projects that have an impact on more than one sector (such as UNEP’s clearinghouse and networking activities).

Table 2: Cumulative completed non-investment projects

| Item | Number of projects | Approved funds plus adjustment (US $) | Per cent of funds disbursed (%) | Average number of months from approval to first disbursement | Average number of months from approval to completion |
| --- | --- | --- | --- | --- | --- |
| GRAND TOTAL | 2,584 | 385,425,495 | 99 | 11 | 37 |
| Region |  |  |  |  |  |
| Africa | 736 | 65,748,212 | 98 | 11 | 38 |
| Asia & Pacific | 762 | 109,211,814 | 98 | 13 | 39 |
| Europe | 169 | 16,284,490 | 99 | 9 | 34 |
| Latin America and Caribbean | 631 | 73,354,278 | 99 | 12 | 41 |
| Global | 286 | 120,826,700 | 100 | 6 | 22 |
| Sector |  |  |  |  |  |
| Aerosol | 31 | 2,461,265 | 99 | 11 | 36 |
| Destruction | 3 | 830,464 | 95 | 13 | 37 |
| Fire fighting | 0 | 0 | 0 | n/a | n/a |
| Foam | 27 | 8,121,235 | 100 | 15 | 34 |
| Fumigants | 130 | 20,120,615 | 99 | 9 | 38 |
| Halon | 81 | 10,870,350 | 100 | 17 | 44 |
| Multiple sectors | 1 | 53,792 | 100 | 56 | 58 |
| Other | 1 | 76,499 | 100 | 7 | 38 |
| Phase-out plan | 271 | 26,726,002 | 94 | 11 | 37 |
| Process agent | 0 | 0 | 0 | n/a | n/a |
| Production | 1 | 40,000 | 100 | 4 | 4 |
| Refrigeration | 615 | 80,735,101 | 100 | 16 | 50 |
| Several | 1,390 | 232,196,997 | 99 | 9 | 31 |
| Solvents | 33 | 3,193,174 | 100 | 11 | 26 |
| Sterilant | 0 | 0 | 0 | n/a | n/a |
| Implementation characteristics |  |  |  |  |  |
| Agency implementation | 2,097 | 290,791,197 | 99 | 10 | 36 |
| National implementation | 487 | 94,634,297 | 99 | 15 | 42 |
| Disbursement method |  |  |  |  |  |
| During Implementation | 2,554 | 375,512,035 | 99 | 11 | 37 |
| After Implementation | 26 | 2,394,315 | 97 | 14 | 21 |
| Retroactive Funding | 0 | 0 | 0 | n/a | n/a |
| Country to final beneficiaries | 4 | 7,519,145 | 100 | 7 | 49 |

# The average time from approval to first disbursement for non-investment projects is much shorter than for investment projects (11 versus 15 months). Non-investment projects have been completed, on average, 37 months after they were approved by the Executive Committee. This figure is influenced by the large number of projects (1,390 of 2,584) classified in the sector called “several”, which had an average time from approval to completion of 31 months. Non-investment projects in the other sectors (e.g., inter alia, production and multiple sectors) were completed between 4 and 58 months after they had been approved.

# Almost all projects (2,097 of 2,584) were implemented by the agency concerned rather than through national implementation. Agency implementation of non-investment projects normally does not require legal agreements, which may explain the shorter period of time (36 months) compared with nationally-implemented non-investment projects (42 months).

# Non-investment projects include work programme activities, excluding project preparation.

Ongoing Projects

## Ongoing investment projects

# Table 3 presents information on the status of investment projects under implementation by region, sector, and implementation characteristics.

Table 3: Cumulative ongoing investment projects

| Item | Number of projects | Approved funds plus adjustment (US$) | Per cent of funds disbursed (%) | Number of projects disbursing | Per cent of projects disbursing (%) | Average number of months from approval to first disbursement | Average number of months from approval to planned completion | Average length of delay in project planned completion | Overall cost-effective-ness to the Fund (US$/kg.)* |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GRAND TOTAL | 246 | 494,699,450 | 56 | 159 | 65 | 11 | 51 | 26 | $47.51 |
| Region |  |  |  |  |  |  |  |  |  |
| Africa | 63 | 30,387,058 | 43 | 48 | 76 | 10 | 55 | 22 | $53.75 |
| Asia & Pacific | 112 | 406,313,291 | 60 | 77 | 69 | 12 | 54 | 33 | $47.62 |
| Europe | 17 | 12,916,176 | 64 | 10 | 59 | 9 | 42 | 17 | $33.96 |
| Latin America and Caribbean | 54 | 45,082,925 | 26 | 24 | 44 | 9 | 41 | 18 | $48.19 |
| Global | 0 | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Sector |  |  |  |  |  |  |  |  |  |
| Aerosol | 3 | 19,848,996 | 96 | 3 | 100 | 14 | 112 | 67 | $35.08 |
| Destruction | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Fire fighting | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Foam | 8 | 15,484,704 | 83 | 7 | 88 | 19 | 71 | 47 | $45.17 |
| Fumigants | 7 | 6,110,307 | 70 | 7 | 100 | 10 | 92 | 45 | $10.56 |
| Halon | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Multiple sectors | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Other | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Phase-out Plan | 218 | 366,729,059 | 51 | 135 | 62 | 11 | 48 | 23 | $63.73 |
| Process agent | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Production | 6 | 74,163,900 | 58 | 3 | 50 | 5 | 28 | 12 | $25.47 |
| Refrigeration | 4 | 12,362,484 | 77 | 4 | 100 | 8 | 92 | 60 | $47.55 |
| Solvents | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Sterilant | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Implementation characteristics |  |  |  |  |  |  |  |  |  |
| Agency implementation | 160 | 244,546,806 | 60 | 114 | 71 | 9 | 54 | 25 | $47.48 |
| National implementation | 86 | 250,152,644 | 52 | 45 | 52 | 14 | 44 | 29 | $47.53 |
| Disbursement method |  |  |  |  |  |  |  |  |  |
| During implementation | 224 | 197,834,645 | 47 | 143 | 64 | 11 | 51 | 25 | $33.84 |
| After implementation | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Retroactive funding | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Country to final beneficiaries | 22 | 296,864,805 | 62 | 16 | 73 | 9 | 47 | 33 | $65.00 |

*Based on the ODS to be phased out according to the proposal.

# There are currently 246 investment projects under implementation. These projects represent approved funding (plus adjustments) of over US $494.7 million. Around 56 per cent of the funds have already been disbursed. The overall average cost-effectiveness of ongoing investment projects is US $47.51/kg ODP to be phased out, as approved.

# Of the ongoing investment projects 46 per cent (112 out of 246) are for countries in the Asia and Pacific region, representing 82 per cent (US $406.31 million) of the funds approved for ongoing investment projects. The Latin American and the Caribbean region has 54 investment projects under implementation, valued at US $45.08 million, Africa has 63 projects (US $30.39 million) and Europe has 17 projects (US $12.92 million).

# About 74 per cent of the funds approved for ongoing investment projects, representing around US $366.73 million, are in the phase-out plan sector. The second largest funding allocation for ongoing investment projects is for the production sector (US $74.16 million) followed by the aerosol sector (US 19.85 million). The remaining sectors have the following number of investment projects under implementation: fumigants (7), foam (8) and refrigeration (4).

# Of the 246 ongoing investment projects, 65 per cent (159) have begun disbursing funds.

# Most ongoing investment projects are under agency implementation (160 projects) but there are 86 projects under national implementation. Of agency-implemented ongoing investment projects, 71 per cent have begun disbursement compared with 52 per cent of nationally-implemented ongoing investment projects.

# The average number of months from approval to first disbursement is 11 months. The average duration of an ongoing investment project is 51 months. Typically, ongoing investment projects are completed 26 months later than originally planned, which could be considered the average delay.

Ongoing non-investment projects

# Table 4 presents information on the status of non-investment projects under implementation by region, sector, and implementation characteristic.

Table 4: Cumulative ongoing non-investment projects

| Item | Number of projects | Approved funds plus adjustment (US$) | Per cent of funds disbursed (%) | Number of projects disbursing | Per cent of projects disbursing (%) | Average number of months from approval to first disbursement | Average number of months from approval to planned completion | Average length of delay in project planned completion |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GRAND TOTAL | 552 | 92,907,184 | 29 | 213 | 39 | 13 | 37 | 13 |
| Region |  |  |  |  |  |  |  |  |
| Africa | 189 | 17,324,070 | 22 | 68 | 36 | 12 | 35 | 11 |
| Asia & Pacific | 195 | 31,508,665 | 29 | 85 | 44 | 14 | 41 | 15 |
| Europe | 35 | 3,641,869 | 30 | 15 | 43 | 10 | 29 | 6 |
| Latin America and Caribbean | 127 | 17,698,024 | 19 | 43 | 34 | 14 | 37 | 13 |
| Global | 6 | 22,734,556 | 42 | 2 | 33 | 32 | 37 | 10 |
| Sector |  |  |  |  |  |  |  |  |
| Aerosol | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Destruction | 16 | 9,762,588 | 38 | 14 | 88 | 10 | 56 | 29 |
| Fire fighting | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Foam | 2 | 1,495,436 | 66 | 1 | 50 | 8 | 54 | 29 |
| Fumigants | 7 | 1,269,302 | 23 | 5 | 71 | 6 | 51 | 26 |
| Halon | 1 | 397,500 | 69 | 1 | 100 | 7 | 65 | 53 |
| Multiple sectors | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Other | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Phase-out Plan | 209 | 24,898,901 | 24 | 100 | 48 | 14 | 44 | 14 |
| Process agent | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Production | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Refrigeration | 13 | 7,203,787 | 43 | 8 | 62 | 28 | 69 | 39 |
| Several | 303 | 47,674,054 | 26 | 84 | 28 | 12 | 29 | 9 |
| Solvents | 1 | 205,616 | 0 | 0 | 0 | n/a | 29 | 15 |
| Sterilant | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Implementation characteristics |  |  |  |  |  |  |  |  |
| Agency implementation | 469 | 69,106,279 | 29 | 174 | 37 | 13 | 37 | 13 |
| National implementation | 83 | 23,800,905 | 28 | 39 | 47 | 13 | 36 | 11 |
| Disbursement method |  |  |  |  |  |  |  |  |
| During implementation | 552 | 92,907,184 | 29 | 213 | 39 | 13 | 37 | 13 |
| After implementation | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Retroactive funding | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Country to final beneficiaries | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |

# There are currently 552 non-investment projects under implementation, representing approved funding (plus adjustments) of around US $92.91 million. Roughly 29 per cent of the funds for ongoing non-investment projects have been disbursed.

# The largest amount of funding for non-investment projects, by region, is US $31.51 million for the Asia and the Pacific region. Funding for ongoing non-investment projects in other regions is as follows: Latin America and the Caribbean, US $17.7 million; Africa, US $17.32 million; and, Europe, US $3.64 million. Ongoing global activities are valued at a total of US $22.73 million.

# On a sectoral basis, most non-investment funding is applied to the “several” sector category (US $47.67 million for 303 projects). There are 13 ongoing non-investment projects in the refrigeration sector (US $7.2 million), 209 in the phase-out plan sector (US $24.9 million), two in the foam sector (US $1.5 million), 16 in the destruction sector (US $9.76 million), seven in the fumigant sector (US $1.27 million), one in the solvent sector (US $205,616) and one in the halon sector (US $397,500).

# Of the 552 ongoing non-investment projects, 39 per cent (213 projects) have begun disbursing funds.

# The average number of months from approval to first disbursement is 13 months. On average, ongoing non-investment projects are completed 37 months from the date of approval, which represents a delay of 13 months.

PROJECT PREPARATION

# Project preparation requests are included in annual work programmes and amendments to work programmes. Project preparation leads to investment projects in general and, in some cases, demonstration projects (in particular for MB) and the implementation of projects included in refrigerant management plans.

# Table 5 presents data on both completed and ongoing project preparation activities. The implementing agencies have completed 1,480 project preparation activities for which there remains a balance of US $ 142,910 that has not yet been disbursed. On average, it has taken 21 months to complete project preparation. Ongoing project preparation activities are expected to take 31 months to complete. This is 10 months longer than for completed project preparation. On a regional basis, most of the ongoing project development activities (58 per cent) are in Asia and the Pacific region. Most of the ongoing project preparation is occurring in the phase-out plan sector (US $2.88 million).

# Table 5: Project preparation

|  | COMPLETED PROJECT PREPARATION |  |  |  |  | ONGOING PROJECT PREPARATION |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Item | Number of projects | Approved funds plus adjustment (US$) | Per cent of funds disbursed (%) | Average number of months from approval to first disburse-ment | Average number of months from approval to completion | Number of projects | Approved funds plus adjust-ment (US$) | Funds disbursed (US$) | Per cent of funds disbursed (%) | Average number of months from approval to first disburse-ment | Average number of months from approval to planned completion | Balance (US$) |
| GRAND TOTAL | 1,480 | 74,147,119 | 100 | 6 | 21 | 120 | 8,527,900 | 2,026,842 | 24 | 10 | 31 | 6,501,058 |
| Agency |  |  |  |  |  |  |  |  |  |  |  |  |
| UNDP | 474 | 18,567,629 | 100 | 5 | 19 | 45 | 3,207,000 | 826,715 | 26 | 9 | 29 | 2,380,285 |
| UNEP | 175 | 7,857,449 | 100 | 10 | 31 | 17 | 697,600 | 152,953 | 22 | 14 | 32 | 544,647 |
| UNIDO | 443 | 18,003,614 | 99 | 6 | 25 | 38 | 2,811,250 | 612,301 | 22 | 9 | 36 | 2,198,949 |
| World Bank | 274 | 24,670,015 | 100 | 6 | 14 | 12 | 1,479,650 | 380,872 | 26 | 14 | 25 | 1,098,778 |
| Bilaterals | 114 | 5,048,412 | n/a | n/a | n/a | 8 | 332,400 | 54,000 | 16 | n/a | n/a | 278,400 |
| Region |  |  |  |  |  |  |  |  |  |  |  |  |
| Africa | 370 | 12,366,439 | 100 | 6 | 22 | 23 | 1,440,000 | 301,445 | 21 | 11 | 40 | 1,138,555 |
| Asia & Pacific | 558 | 36,125,897 | 100 | 6 | 21 | 70 | 5,494,900 | 1,260,735 | 23 | 11 | 29 | 4,234,165 |
| Europe | 105 | 4,725,099 | 100 | 6 | 21 | 6 | 200,000 | 48,328 | 24 | 9 | 26 | 151,672 |
| Latin Amer./Car. | 430 | 19,523,780 | 100 | 6 | 20 | 19 | 1,183,000 | 380,916 | 32 | 7 | 34 | 802,084 |
| Global | 17 | 1,405,905 | 100 | 6 | 16 | 2 | 210,000 | 35,417 | 17 | 5 | 16 | 174,583 |
| Sector |  |  |  |  |  |  |  |  |  |  |  |  |
| Aerosol | 45 | 1,254,557 | 100 | 6 | 17 | 0 | 0 | 0 | 0 | n/a | n/a | 0 |
| Destruction | 18 | 837,051 | 98 | 13 | 40 | 0 | 0 | 0 | 0 | n/a | n/a | 0 |
| Fire fighting | 0 | 0 | 0 | n/a | n/a | 1 | 50,000 | 0 | 0 | n/a | 24 | 50,000 |
| Foam | 223 | 7,986,167 | 100 | 4 | 18 | 33 | 2,938,000 | 644,533 | 22 | 10 | 32 | 2,293,467 |
| Fumigants | 117 | 3,009,343 | 99 | 5 | 17 | 1 | 35,000 | 0 | 0 | n/a | 31 | 35,000 |
| Halon | 27 | 836,728 | 100 | 5 | 19 | 0 | 0 | 0 | 0 | n/a | n/a | 0 |
| Multiple sectors | 3 | 139,440 | 100 | 3 | 34 | 0 | 0 | 0 | 0 | n/a | n/a | 0 |
| Other | 2 | 240,747 | 100 | 11 | 35 | 0 | 0 | 0 | 0 | n/a | n/a | 0 |
| Phase-out plan | 332 | 22,616,644 | 100 | 9 | 30 | 56 | 2,881,250 | 814,188 | 28 | 10 | 32 | 2,067,062 |
| Process agent | 9 | 694,384 | 100 | 8 | 19 | 0 | 0 | 0 | 0 | n/a | n/a | 0 |
| Production | 9 | 1,073,866 | 100 | 8 | 13 | 1 | 254,650 | 0 | 0 | n/a | 19 | 254,650 |
| Refrigeration | 356 | 11,596,102 | 100 | 6 | 20 | 27 | 2,219,000 | 467,950 | 21 | 10 | 29 | 1,751,050 |
| Several | 283 | 21,969,991 | 100 | 4 | 15 | 0 | 0 | 0 | 0 | n/a | n/a | 0 |
| Solvents | 55 | 1,887,100 | 100 | 6 | 25 | 1 | 150,000 | 100,171 | 67 | 5 | 24 | 49,829 |
| Sterilant | 1 | 5,000 | 100 | 1 | 9 | 0 | 0 | 0 | 0 | n/a | n/a | 0 |
| Implementation type |  |  |  |  |  |  |  |  |  |  |  |  |
| Agency | 1,329 | 63,280,519 | 100 | 6 | 20 | 74 | 5,066,250 | 1,200,127 | 24 | 11 | 32 | 3,866,123 |
| National | 151 | 10,866,600 | 100 | 10 | 28 | 46 | 3,461,650 | 826,715 | 24 | 9 | 29 | 2,634,935 |
| Disbursement |  |  |  |  |  |  |  |  |  |  |  |  |
| During imp. | 1,474 | 73,247,367 | 100 | 6 | 21 | 119 | 8,327,900 | 1,892,839 | 23 | 10 | 31 | 6,435,061 |
| After imp. | 6 | 899,752 | 100 | 7 | 21 | 0 | 0 | 0 | 0 | n/a | n/a | 0 |
| Retroactive | 0 | 0 | 0 | n/a | n/a | 0 | 0 | 0 | 0 | n/a | n/a | 0 |
| Country to final beneficiaries | 0 | 0 | 0 | n/a | n/a | 1 | 200,000 | 134,003 | 67 | 7 | 24 | 65,997 |

CLOSED AND TRANSFERRED PROJECTS

# Table 6 presents a summary of closed and transferred projects. Of the 250 closed projects, 101 were project preparation activities. The World Bank has the highest number of closed projects (95). Remaining balances for closed projects are the result of possible unpaid commitments against these projects; however, projects should be classified as closed only after the balances have been returned. Bilateral and implementing agencies provide a report on any balances from cancelled projects in the context of the report on balances and availability of resources (UNEP/OzL.Pro/ExCom/77/4). No projects were cancelled and closed in 2015.

# Transferred projects are projects that have been transferred from one agency to another. There are 53 such transferred projects.

Table 6: Closed and transferred projects summary

| Agency | Number of projects | Approved funding (US$) | Adjustments (USS) | Approved funding plus adjustment (US$) | Funds disbursed (US$) | Balances (US$) | Percent of funds disbursed (%) | Consumption ODP to be phased out | Consumption ODP phased out |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Closed projects |  |  |  |  |  |  |  |  |  |
| UNDP | 78 | 16,947,886 | -10,052,770 | 6,895,116 | 6,895,116 | 0 | 100 | 671 | 636 |
| UNEP | 5 | 680,000 | -659,000 | 21,000 | 21,000 | 0 | 100 | 0 | 0 |
| UNIDO | 58 | 11,185,651 | -6,665,913 | 4,519,738 | 4,519,741 | -3 | 100 | 1,123 | 338 |
| World Bank | 95 | 30,924,304 | -29,550,785 | 1,373,519 | 1,373,519 | 0 | 100 | 657 | 581 |
| Bilaterals | 14 | 1,149,323 | -921,422 | 227,901 | 227,901 | 0 | 100 | 221 | 0 |
| Total | 250 | 60,887,164 | -47,849,890 | 13,037,274 | 13,037,277 | -3 | 100 | 2,671 | 1,555 |
| Transferred projects |  |  |  |  |  |  |  |  |  |
| UNDP | 16 | 1,639,859 | -1,407,764 | 232,095 | 232,095 | 0 | 100 | 0 | 0 |
| UNEP | 7 | 242,453 | -242,453 | 0 | 0 | 0 | 0 | 0 | 0 |
| UNIDO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| World Bank | 13 | 5,901,904 | -3,496,997 | 2,404,907 | 2,404,907 | 0 | 100 | 277 | 277 |
| Bilaterals | 17 | 4,120,449 | -3,827,399 | 293,050 | 293,050 | 0 | 100 | 0 | 0 |
| Total | 53 | 11,904,665 | -8,974,613 | 2,930,052 | 2,930,052 | 0 | 100 | 277 | 277 |

Appendix I

PROJECTS WITH IMPLEMENTATION DELAYS

| Agency | Code | Project title | Category of delays |
| --- | --- | --- | --- |
| Germany | JOR/FUM/29/INV/54 | Complete phase-out of the use of methyl bromide in Jordan | 12 months delays |
| UNDP | PAK/ARS/56/INV/71 | Plan for phase-out of CFCs in the manufacture of pharmaceutical MDIs | 12 months delays |
| UNEP | DJI/SEV/74/TAS/22 | Survey of ODS alternatives at the national level | 12 months delays |
| UNEP | GLO/SEV/73/TAS/323 | Compliance Assistance Programme: 2015 budget | 12 months delays |
| UNEP | GUI/SEV/74/TAS/31 | Survey of ODS alternatives at the national level | 12 months delays |
| UNEP | TRI/FUM/65/TAS/28 | Technical assistance to phase out the use of methyl bromide | 12 and 18 months delays |
| UNIDO | BHE/SEV/74/TAS/31 | Survey of ODS alternatives at the national level | 12 months delays |
| UNIDO | CPR/ARS/56/INV/473 | Sector plan for phase-out of CFCs consumption in MDI sector | 12 months delays |
| UNIDO | EGY/ARS/50/INV/92 | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | 12 months delays |
| UNIDO | IRQ/FUM/62/INV/13 | Technical assistance for alternatives to methyl bromide | 12 months delays |
| UNIDO | IRQ/REF/57/INV/07 | Replacement of refrigerant CFC-12 with isobutane and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigerators and chest freezers at Light Industries Company | 12 months delays |
| UNIDO | SUD/FUM/73/TAS/36 | Technical assistance for the final phase-out of methyl bromide in the post-harvest sector | 12 months delays |
| UNIDO | SYR/REF/62/INV/103 | Phase-out of HCFC-22 and HCFC-141b from the manufacture of unitary air-conditioning equipment and rigid polyurethane insulation panels at Al Hafez Group | 12 months delays |
| UNIDO | TUN/FUM/73/TAS/63 | Technical assistance for the final phase-out of methyl bromide in the palm dates sector | 12 months delays |
| UNIDO | ZAM/FUM/56/INV/21 | Technical assistance for the total phase out of methyl bromide in tobacco, cut flowers, horticulture and post-harvest uses | 12 months delays |
| World Bank | THA/SEV/74/TAS/167 | Survey of ODS alternatives at the national level | 12 months delays |

Appendix II

# PROJECTS WITH ADDITIONAL STATUS REPORTS

| Country/Project code | Project title | Reasons | Agency |
| --- | --- | --- | --- |
| Indonesia (IDS/PHA/64/TAS/196) | HCFC phase-out management plan (technical assistance for refrigerant management) (stage I, first tranche) | The disbursement rate of approved funds. | Australia |
| China (CPR/FOA/73/PRP/553) | Preparation for HCFC phase-out investment activities (stage II) (extruded polystyrene foam sector) | The disbursement rate of approved funds. | Germany |
| China (CPR/PHA/74/PRP/557) | Preparation of a HCFC phase-out management plan (stage II) (refrigeration servicing sector and enabling programme) | The disbursement rate of approved funds. | Germany |
| Tunisia (TUN/FUM/73/TAS/62) | Technical assistance for the final phase-out of methyl bromide in the palm dates sector | The disbursement rate of approved funds. | Italy |
| Barbados (BAR/PHA/69/INV/21) | HCFC phase-out management plan (stage I, first tranche) | The signing of the agreement by the Government and UNDP. | UNDP |
| Brazil (BRA/PHA/75/INV/312) | HCFC phase-out management plan (stage II, first tranche) (foam sector) | The signing of the agreement by the Government. | UNDP |
| Brazil (BRA/PHA/75/TAS/313) | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing, regulatory actions and project monitoring) | The signing of the agreement by the Government. | UNDP |
| Chile CHI/PHA/73/INV/184 | HCFC phase-out management plan (stage I, third tranche) | Disbursement rate of approved funds. | UNDP |
| China (CPR/PHA/71/INV/534) | HCFC phase-out management plan (stage I, third tranche) (industrial and commercial refrigeration and air conditioning sector plan) | Disbursement of operating costs. | UNDP |
| Ghana (GHA/PHA/67/INV/34) | HCFC phase-out management plan (stage I, second tranche) | The delivery of the equipment. | UNDP |
| Iran (Islamic Republic of) (IRA/PHA/74/INV/219) | HCFC phase-out management plan (stage I, fourth tranche) (air conditioning sector plan and project management unit) | The activities implemented by the project management unit. | UNDP |
| Nepal (NEP/PHA/66/INV/30) | HCFC phase-out management plan (stage I, first tranche) | The delivery of the equipment. | UNDP |
| Nigeria (NIR/PHA/71/INV/135) | HCFC phase-out management plan (stage I, third tranche) (foam) | Delays in the establishment of the licensing process for the pilot plant. | UNDP |
| Pakistan (PAK/ARS/56/INV/71) | Plan for phase-out of CFCs in the manufacture of pharmaceutical MDIs | Project completion. | UNDP |
| Saint Kitts and Nevis (STK/PHA/64/TAS/16) | HCFC phase-out management plan (stage I, first tranche) | The signing of the agreement by the Government. | UNDP |
| Afghanistan (AFG/PHA/72/TAS/16) | HCFC phase-out management plan (stage I, second tranche) | The appointment of project management unit coordinator. | UNEP |
| Algeria (ALG/SEV/73/INS/81) | Extension of the institutional strengthening project (phase VI: 12/2014-11/2016) | Project implementation progress and the disbursement rate of approved funds | UNEP |
| Antigua and Barbuda (ANT/PHA/66/TAS/14) | HCFC phase-out management plan (stage I, first tranche) | The signing of the endorsement letter from the Ministry. | UNEP |
| Antigua and Barbuda (ANT/SEV/68/INS/15 | Extension of institutional strengthening project (phase IV: 1/2013-12/2014) | Project implementation progress and the disbursement rate of approved funds | UNEP |
| Antigua and Barbuda ANT/SEV/73/INS/16) | Extension of institutional strengthening project (phase V: 1/2015-12/2016) | Project implementation progress and the disbursement rate of approved funds | UNEP |
| Bahamas (the) (BHA/SEV/72/INS/22) | Extension of the institutional strengthening project (phase V: 4/2014-3/2016) | Project implementation progress and the disbursement rate of approved funds | UNEP |
| Bahrain (BAH/PHA/75/TAS/29) | HCFC phase-out management plan (stage I, second tranche) (policy, refrigeration servicing, monitoring and verification) | The signing of the agreement by the Government and UNEP. | UNEP |
| Barbados (BAR/PHA/69/TAS/22) | HCFC phase-out management plan (stage I, first tranche) | Awarding of contracts for the HPMP. | UNEP |
| Benin (BEN/PHA/70/TAS/28) | HCFC phase-out management plan (stage I, second tranche) | Low disbursement rate of approved funds. | UNEP |
| Botswana (BOT/PHA/75/TAS/17) | HCFC phase-out management plan (stage I, first tranche) | The signing of the agreement by the Government and UNEP. | UNEP |
| Brunei Darussalam (BRU/PHA/74/TAS/16) | HCFC phase-out management plan (stage I, second tranche) | The signing of the agreement by the Government. | UNEP |
| Brunei Darussalam (BRU/SEV/73/INS/15) | Renewal of the institutional strengthening project (phase IV: 1/2015-12/2016) | Project implementation progress and the disbursement rate of approved funds | UNEP |
| Burkina Faso (BKF/PHA/70/TAS/33) | HCFC phase-out management plan (stage I, second tranche) | The signing of the second agreement between the Government and UNEP for the release of remaining funds. | UNEP |
| Central African Republic (the) (CAF/PHA/64/TAS/22) | HCFC phase-out management plan (stage I, first tranche) | The resumption of project implementation. | UNEP |
| Central African Republic (the) (CAF/SEV/68/INS/23) | Extension of the institutional strengthening project (phase VI: 1/2013-12/2014) | Project implementation progress and the disbursement rate of approved funds | UNEP |
| Chile (CHI/PHA/71/TAS/180) | HCFC phase-out management plan (stage I, second tranche) | The signing of the agreement by the Government. | UNEP |
| Chile (CHI/PHA/73/TAS/185) | HCFC phase-out management plan (stage I, third tranche) | The signing of the agreement by the Government. | UNEP |
| Colombia (COL/PHA/75/TAS/93) | HCFC phase-out management plan (stage II, first tranche) (technical assistance in policies formulation and implementation) | The signing of the agreement by the Government and UNEP. | UNEP |
| Democratic People’s Republic of Korea (the) (DRK/SEV/68/INS/57) | Extension of institutional strengthening project (phases VI and VII: 1/2010-12/2013) | Project implementation progress and the disbursement rate of approved funds | UNEP |
| Democratic Republic of the Congo (the) (DRC/PHA/70/TAS/38) | HCFC phase-out management plan (stage I, second tranche) | Completion of training for the new national ozone officer. | UNEP |
| Dominican Republic (the) (DOM/PHA/69/TAS/52) | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Completion of the global bidding process. | UNEP |
| El Salvador (ELS/PHA/65/TAS/28) | HCFC phase-out management plan (stage I, first tranche) | The signing of the agreement by the Government and UNEP (original agreement expired). | UNEP |
| El Salvador (ELS/PHA/74/TAS/32) | HCFC phase-out management plan (stage I, second tranche) | The signing of the agreement by the Government and UNEP. | UNEP |
| Eritrea ERI/SEV/68/INS/12) | Institutional strengthening (phase II: 1/2013-12/2014) | Project implementation progress and the disbursement rate of approved funds | UNEP |
| Grenada (GRN/PHA/62/TAS/18) | HCFC phase-out management plan (stage I, first tranche) | Transfer of investment to non-investment activities. | UNEP |
| Haiti (HAI/PHA/68/TAS/18) | HCFC phase-out management plan (stage I, first tranche) | The signing of a new agreement and the appointment of legal assistance to development of regulations. | UNEP |
| Honduras (HON/PHA/63/TAS/35) | HCFC phase-out management plan (stage I, first tranche) | The signing of the agreement by the Government and UNEP. | UNEP |
| Honduras (HON/PHA/70/TAS/38) | HCFC phase-out management plan (stage I, second tranche) | The signing of the agreement by the Government and UNEP. | UNEP |
| India (IND/PHA/71/TAS/450) | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector and enabling activities) | The signing of the amendment to the agreement. | UNEP |
| India (IND/PHA/75/TAS/466) | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector and enabling activities) | The signing of the agreement by the Government and UNEP. | UNEP |
| Iraq (IRQ/PHA/73/PRP/21) | Preparation of a HCFC phase-out management plan (stage II) | The signing of the agreements by the Government and UNEP. | UNEP |
| Iraq (IRQ/PHA/65/TAS/17) | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Submission of required expenditure and progress reports from the Government to UNEP. | UNEP |
| Iraq (IRQ/PHA/74/TAS/22) | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | The signing of the agreement by the Government and UNEP. | UNEP |
| Malawi (MLW/PHA/70/TAS/34) | HCFC phase-out management plan (stage I, second tranche) | Low disbursement rate of approved funds. | UNEP |
| Mali (MLI/PHA/71/TAS/33) | HCFC phase-out management plan (stage I, second tranche) | Low disbursement rate of approved funds. | UNEP |
| Mauritania (MAU/PHA/55/PRP/20) | Preparation of a HCFC phase-out management plan | The submission of the HCFC phase-out management plan. | UNEP |
| Mozambique (MOZ/PHA/73/TAS/25) | HCFC phase-out management plan (stage I, second tranche) | Completion of the procurement of equipment. | UNEP |
| Namibia (NAM/SEV/73/INS/20) | Extension of institutional strengthening project (phase VIII: 12/2014-11/2016) | Project implementation progress and the disbursement rate of approved funds | UNEP |
| Nauru (NAU/PHA/63/TAS/07) | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Nauru) | The appointment of a national ozone officer. | UNEP |
| Nauru (NAU/PHA/74/TAS/10) | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Nauru) | The signing of the agreement by the Government and UNEP. | UNEP |
| Nauru (NAU/SEV/67/INS/08 | Extension of the institutional strengthening project (phase IV: 8/2012-7/2014) | Project implementation progress and the disbursement rate of approved funds | UNEP |
| Nauru NAU/SEV/72/INS/09) | Extension of the institutional strengthening project (phase V: 8/2014-7/2016) | Project implementation progress and the disbursement rate of approved funds | UNEP |
| Nepal (NEP/PHA/66/TAS/29) | HCFC phase-out management plan (stage I, first tranche) | The appointment of a national ozone officer. | UNEP |
| Nepal (NEP/PHA/75/TAS/34) | HCFC phase-out management plan (stage I, second tranche) | The appointment of a national ozone officer. | UNEP |
| Nepal (NEP/SEV/72/INS/32) | Extension of the institutional strengthening project (phase VIII: 12/2014-11/2016) | Project implementation progress and the disbursement rate of approved funds | UNEP |
| Oman (OMA/PHA/65/TAS/22) | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | The adoption and enforcement of the e-licensing system and certification scheme. | UNEP |
| Pakistan (PAK/PHA/70/TAS/84) | HCFC phase-out management plan (stage I, second tranche) | The signing of the memorandum of understanding for technician training. | UNEP |
| Philippines (the) (PHI/PHA/68/TAS/95) | HCFC phase-out management plan (stage I, first tranche) | Submission of technical and financial report. | UNEP |
| Qatar (QAT/PHA/73/PRP/20) | Preparation of a HCFC phase-out management plan (stage II) | The signing of the agreements by the Government and UNEP. | UNEP |
| Qatar (QAT/PHA/65/TAS/17) | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | The signing of the agreement by the Government and UNEP. | UNEP |
| Saint Lucia (STL/SEV/73/INS/23) | Renewal of institutional strengthening project (phase IX: 1/2015-12/2016) | Project implementation progress and the disbursement rate of approved funds | UNEP |
| Saudi Arabia (SAU/PHA/68/TAS/16) | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | The completion of the required expenditures report. | UNEP |
| Saudi Arabia (SAU/PHA/68/TAS/18) | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | The completion of the required expenditures report. | UNEP |
| Serbia (YUG/PHA/71/TAS/43) | HCFC phase-out management plan (stage I, second tranche) | The completion of training for customs officers and environmental inspectors. | UNEP |
| Suriname (SUR/PHA/74/TAS/22) | HCFC phase-out management plan (stage I, second tranche) | The signing of the agreement by the Government and UNEP. | UNEP |
| Swaziland (SWA/SEV/71/INS/21) | Extension of institutional strengthening project (phase V: 12/2013-11/2015) | Project implementation progress and the disbursement rate of approved funds | UNEP |
| Vanuatu (VAN/PHA/63/TAS/09) | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Vanuatu) | The submission of required expenditure and progress reports from the Government to UNEP. | UNEP |
| Viet Nam (VIE/SEV/73/INS/68) | Extension of the institutional strengthening project (phase X: 7/2015-6/2017) | Project implementation progress and the disbursement rate of approved funds | UNEP |
| Yemen (YEM/PHA/73/PRP/44) | Preparation of a HCFC phase-out management plan (stage II) | The resumption of the project. | UNEP |
| Yemen (YEM/PHA/68/TAS/40) | HCFC phase-out management plan (stage I, first tranche) | The resumption of project implementation. | UNEP |
| Region: Europe EUR/DES/69/DEM/13 | Demonstration of a regional strategy for ODS waste management and disposal in the Europe and Central Asia region | Project completion. | UNEP |
| Albania (ALB/PHA/70/INV/25) | HCFC phase-out management plan (stage I, second tranche) | Completion of legislation for a new certification. | UNIDO |
| Algeria (ALG/PHA/66/INV/77) | HCFC phase-out management plan (stage I, first tranche) (activities in the refrigeration servicing sector including phase-out of HCFC-141b used for flushing, and project monitoring) | No response from the national ozone unit on the training plan and verification exercise. | UNIDO |
| Bahrain (BAH/PHA/68/INV/27) | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-22 from the manufacturing of central air conditioning and window air conditioning at Awal Gulf manufacturing company) | Procurement and/or delivery of the equipment. | UNIDO |
| Cameroon (CMR/PHA/64/INV/35) | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector plan) | Procurement and/or delivery of the equipment. | UNIDO |
| Central African Republic (the) (CAF/PHA/64/INV/21) | HCFC phase-out management plan (stage I, first tranche) | Resumption of activities due to security situations. | UNIDO |
| China (CPR/PHA/64/INV/513) | HCFC-22 phase-out management plan for room air-conditioner manufacturing sector (stage I, first tranche) | Completion of the disbursement of incremental operating costs. | UNIDO |
| China CPR/PHA/68/INV/524 | HCFC-22 phase-out management plan for room air-conditioner manufacturing sector (stage I, second tranche) | Completion of the conversion of the compressor line. | UNIDO |
| China (CPR/PHA/73/INV/548) | HCFC phase-out management plan (stage I, fourth tranche) (room air-conditioner manufacturing sector plan) | Procurement and/or delivery of the equipment. | UNIDO |
| Democratic People’s Republic of Korea (the) (DRK/PHA/73/INV/59) | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b in polyurethane foam sector at Pyongyang Sonbong and Puhung Building Materials) | Procurement and/or delivery of equipment. | UNIDO |
| Democratic People’s Republic of Korea (the) (DRK/PHA/73/TAS/60) | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | The resolution of the issue of the funding disbursement mechanism. | UNIDO |
| Egypt (EGY/FUM/74/TAS/123) | Technical assistance on two alternatives to methyl bromide in the palm date sector | Resumption of activities. | UNIDO |
| Iraq (MYA) | National phase-out plan | The installation of the equipment. | UNIDO |
| Iraq (IRQ/PHA/73/PRP/19) | Preparation of a HCFC phase-out management plan (stage II) | Resumption of activities. | UNIDO |
| Iraq (IRQ/REF/73/PRP/20) | Preparation for HCFC phase-out investment activities (stage II) (air-conditioning sector) | Resumption of activities. | UNIDO |
| Kuwait (KUW/PHA/66/INV/18) | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Procurement and/or delivery of the equipment. | UNIDO |
| Kuwait (KUW/PHA/66/INV/20) | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector phase-out: Kuwait polyurethane Industry Co.; Kirby Building Systems, technical assistance to spray foam users and other small users) | Procurement and/or delivery of the equipment. | UNIDO |
| Kuwait (KUW/PHA/66/INV/21) | HCFC phase-out management plan (stage I, first tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Comapny) | Procurement and/or delivery of the equipment. | UNIDO |
| Morocco (MOR/PHA/65/INV/68) | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Completion of the audit. | UNIDO |
| Morocco (MOR/PHA/68/INV/69) | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Completion of the training of custom authorities and the audit of HCFC consumption. | UNIDO |
| Niger (NER/PHA/66/INV/28) | HCFC phase-out management plan (stage I, first tranche) | Completion of the calibration of the equipment. | UNIDO |
| Nigeria (NIR/PHA/71/INV/136) | HCFC phase-out management plan (stage I, third tranche) (refrigeration air-conditioning manufacturing and coordination) | Procurement and/or delivery of the equipment. | UNIDO |
| Saudi Arabia (SAU/PHA/68/INV/17) | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | Ongoing project with 100 per cent of funds disbursed. | UNIDO |
| Saudi Arabia SAU/PHA/72/INV/21 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Completion of the import tax exemption to facilitate the shipment of equipment. | UNIDO |
| Sierra Leone (SIL/PHA/65/INV/24) | HCFC phase-out management plan (stage I, first tranche) | Procurement and/or delivery of the equipment. | UNIDO |
| Suriname (SUR/PHA/65/INV/18) | HCFC phase-out management plan (stage I, first tranche) | Resumption of activities in the first quarter of 2017. | UNIDO |
| Syrian Arabic Republic SYR/PHA/55/PRP/97 | Preparation of a HCFC phase-out management plan | Resumption of activities. | UNIDO |
| Syrian Arabic Republic (SYR/FOA/61/PRP/102) | Preparation for HCFC phase-out investment activities (foam sector) | Resumption of activities. | UNIDO |
| Syrian Arab Republic (SYR/SEV/73/INS/104) | Extension of institutional strengthening (phase V: 1/2015- 12/2016) | Low disbursement rates of approved funds. | UNIDO |
| TUR/PHA/68/INV/102 | HCFC phase-out management plan (stage I, first tranche) (technical assistance for small and medium enterprises in the foam sector) | Completion of training for the project. | UNIDO |
| VEN/PHA/75/INV/131 | HCFC phase-out management plan (stage I, fourth tranche) | Date of completion different from the completion date in tranche request. | UNIDO |
| VEN/PHA/75/TAS/130 | HPMP Stage I - Transfer from UNEP | Date of completion different from the completion date in tranche request. | UNIDO |
| Yemen (MYA) | National phase-out plan | Resumption of activities if the extension to December 2018 is approved, or completion of the project as per decision 75/10(b)(i). | UNIDO |
| Yemen (YEM/PHA/68/TAS/39) | HCFC phase-out management plan (stage I, first tranche) | Resumption of activities due to security situations. | UNIDO |
| Yemen (YEM/PHA/73/PRP/45) | Preparation of a HCFC phase-out management plan (stage II) | Resumption of activities. | UNIDO |
| Yemen (YEM/FOA/73/PRP/46) | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Resumption of activities. | UNIDO |
| Region: Africa (AFR/FUM/54/DEM/40) | Regional demonstration project on alternatives to the use of methyl bromide for treatment of high moisture dates (Algeria and Tunisia) | To monitor project completion by December 2016. | UNIDO |
| Argentina (ARG/PHA/66/TAS/170) | HCFC phase-out management plan (stage I, first tranche) (monitoring and reporting of HCFC-22 production) | Disbursement rates of approved funds. | World Bank |
| China (CPR/FOA/59/DEM/491) | Conversion demonstration from HCFC-141b-based to cyclopentane-based pre-blended polyol in the manufacture of rigid polyurethane foam at Guangdong Wanhua Rongwei Polyurethane Co. Ltd | Project completion. | World Bank |
| China (CPR/PRO/72/INV/540) | HCFC production phase-out management plan (stage I, second tranche) | Ongoing project with 100 per cent of fund disbursement. | World Bank |
| Thailand (THA/PHA/68/TAS/160) | HCFC phase-out management plan (stage I, first tranche) (technical assistance) | Ongoing project with 100 per cent of fund disbursement. | World Bank |
| Thailand (THA/SEV/68/INS/159) | Extension of institutional strengthening project (phase VII: 1/2013-12/2014) | Request additional information on the activities conducted in 2015 and 2016 by the national ozone unit since limited information was provided in the World Bank’s progress report. | World Bank |
| Viet Nam (VIE/PHA/63/TAS/58) | HCFC phase-out management plan (stage I, first tranche) (Technical assistance and project management) | Ongoing project with 100 per cent of fund disbursement. | World Bank |
| Viet Nam (VIE/PHA/63/INV/56) | HCFC phase-out management plan (stage I, first tranche) (foam sector plan) | Ongoing project with 100 per cent of fund disbursement. | World Bank |

Progress reports were submitted by the following agencies: Australia, Germany, Italy, Japan, Spain, UNDP, UNEP, UNIDO and the World Bank. Progress report was not submitted by France. Data from its progress reports for 2014 was included, along with information for projects approved in 2015.

The Executive Committee requested that detailed information on a project-by-project basis be made available to Committee members, with a printout available upon request (decision 19/23). The database for the Consolidated Progress Report is provided on the Executive Committee’s intranet in the spreadsheet programme, Microsoft Excel 1997-2003.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies as well. The cost-effectiveness for HPMP multi-year agreements (MYAs) is US $68.20/kg ODP and for stage I of HCFC production phase-out management plan (HPPMP) is US $23.93/kg ODP.

An additional US $111.75 million has been approved for the meetings of the Executive Committee, the operation of the Secretariat, and the Treasurer fees.

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or annual funding tranche of an MYA of US $1 million is considered one project as is a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively-financed projects.

Ongoing projects are all projects that have been approved by the Executive Committee and were under implementation as of 31 December 2015. Key indicators of progress include: percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year (funds disbursed plus estimated disbursements in 2014) as a percentage of the approved funding; the average length of projected delay in implementation (project completion per proposal and currently planned date of completion); and information provided in the Remarks column in the databases.

The condition of approval indicated that all project activities would be completed no later than 31 December 2018 and the project completion report would be submitted to the Executive Committee no later than the first meeting in 2019.

The planned date of completion was extended to match the completion date of the production sector and submit one project completion report for both sectors. Moreover, US $166,507 of the US $302,742 was disbursed as at 31 December 2015.

One-hundred and thirty surveys had originally been approved but one survey was transferred from one agency to another.

ODS survey reports should be submitted by January 2017 to enable the Secretariat to provide an analysis of the results of the surveys for consideration of the Executive Committee at its 78th meeting (decision 74/53(h)).

These countries include: the Central African Republic, Iraq, and Yemen.

Projects approved over 18 months with disbursement less than one per cent, or projects that are expected to be completed 12 months later than forecast in the last progress report (decision 22/61). Pursuant to decision 36/14, the following types of projects are no longer so classified: institutional strengthening, halon banking, customs training, recovery and recycling, and demonstration projects; however, the Secretariat was requested to continue to monitor these types of projects, as appropriate.

Montreal, 31 August to 1 September 2016.

Completed projects/activities are defined in decisions 17/22 and 19/23 as projects that have been commissioned and where the ODS addressed has been phased out. A further decision (decision 28/2) extends the definition to cover situations where no further use of CFCs in the sectors covered is in evidence, where an alternative product is being produced (and/or production has begun), and where the equipment using CFCs has been destroyed/dismantled/rendered unusable with respect to ODSs. Work programme activities without an ODS phase-out are considered completed when the activity is finished (e.g., for a workshop, when it has been conducted).

Total phased out for the Fund includes 467,077 ODP tonnes from completed investment projects, 14,260 ODP tonnes from completed non-investment projects and 5,549 ODP tonnes from ongoing projects.