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EVALUATION OF THE PERFORMANCE OF THE IMPLEMENTING AGENCIES 
AGAINST THEIR 2017 BUSINESS PLANS[footnoteRef:1] [1:  Also includes qualitative assessment of bilateral agencies.] 


Introduction

This document presents:
(a) The quantitative evaluations of the performance of the implementing agencies with respect to the performance targets set in the 2017 business plans and progress and financial reports submitted to the 82nd meeting[footnoteRef:2]; [2:  Based on the performance indicators adopted in decision 41/93, as modified by decisions 47/51 and 71/28, and the targets that were adopted for the 2017 business plans in Annexes V – VIII to the report of the 77th meeting (UNEP/OzL.Pro/ExCom/77/76).
] 

(b) A trend analysis for each of the eight performance indicators; 
(c) The qualitative assessment of the performance of bilateral and implementing agencies based on input received from national ozone unit (NOU) officers; and
(d) Secretariat’s comments and recommendation. 
This document also includes the following three annexes: 
Annex I: 	Investment project performance by agency
Annex II: 	Non-investment project performance by agency
Annex III: 	Qualitative assessment of the implementing agencies by the national ozone units for 2017
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Analysis of quantitative performance indicators 
Table 1 presents the approved targets, measures of progress towards achieving each target, and the number of targets achieved.
Table 1: 2017 performance indicator targets and achievement 
	Item


	UNDP
	UNEP
	UNIDO
	World Bank

	
	Target
	Agency achievement
	Secretariat assessment
	Met target
	Target
	Agency achievement
	Secretariat assessment
	Met target
	Target
	Agency achievement
	Secretariat assessment
	Met target
	Target
	Agency achievement
	Secretariat assessment
	Met    target

	Tranches approved*
	23
	16
	16
	No
	34
	18
	18
	No
	26
	14
	14
	No
	6
	3
	3
	No

	Projects/activities approved
	15
	11
	11
	No
	64
	88
	39
	No
	11
	9
	9
	No
	1
	4
	1
	Yes

	Funds disbursed (million US $)
	27.84 
	30.45 
	30.71 
	Yes
	13.12 
	16.76

	17.84 
	Yes
	22.35 
	31.08 
	30.9 
	Yes
	31 
	31 
	31 
	Yes

	ODS phase-out*
	186.04
	155.4
	155.4
	No
	37.10
	24.5
	24.5
	No
	472.2
	285
	319.2
	No
	523.2
	117
	279.6
	No

	Project completion for activities
	62
	63
	63
	Yes
	82
	49
	191
	Yes
	60
	64
	64
	Yes
	13
	12
	12
	No

	Speed of financial completion
	70% (36)
	36
	36
	Yes
	14 months
	31 months
	21 months
	No
	12 months after operational completion
	12 months
	12 months
	Yes
	90%
	94%
	94%
	Yes

	Timely submission of project completion reports
	On time (8)
	On time (8)
	On time (8)
	Yes
	On time (47)
	Not on time
	Not on time (26)
	No
	On time
	On time
	On time
	Yes
	On time (21)
	Not on time
	Not on time (7)
	No

	Timely submission of progress reports
	On time
	On time
	On time
	Yes
	On time
	On time
	On time
	Yes
	On time
	On time
	On time
	Yes
	On time
	On time
	On time
	Yes

	Number of targets achieved
	
	
	
	5/8
	
	
	
	3/8
	
	
	
	5/8
	
	
	
	4/8
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* The targets of an agency would be reduced “if it could not submit a tranche owing to another cooperating agency or lead agency” or “if HPMP submitted for consideration by the Executive Committee was not approved as a result of factors beyond the control of the NOU and agency”. 
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Weighted assessment of performance
Table 2 presents the outcome of the 2017 weighted assessment by performance indicator based on the Secretariat’s methodology. 
Table 2: Weighted assessment of implementing agencies performance in 2017
	Item
	Weighting
	UNDP
	UNEP
	UNIDO
	World Bank

	
	
	% of target achieved
	Points
	% of target achieved
	Points
	% of target achieved
	Points
	% of target achieved
	Points

	Tranches approved
	10
	70
	7
	53
	5
	54
	5
	50
	5

	Projects/activities approved
	10
	73
	7
	61
	6
	82
	8
	100
	10

	Funds disbursed
	15
	110
	15
	136
	15
	138
	15
	100
	15

	ODS phase-out
	25
	84
	21
	66
	17
	68
	17
	53
	13

	Project completion for activities
	20
	102
	20
	233
	20
	107
	20
	92
	18

	Speed of financial completion
	10
	100
	10
	50
	5
	100
	10
	104
	10

	Timely submission of project completion reports
	5
	100
	5
	55
	3
	100
	5
	33
	2

	Timely submission of progress reports
	5
	100
	5
	100
	5
	100
	5
	100
	5

	2017 Assessment
	100
	 
	90
	 
	76
	 
	85
	 
	78



Analysis of other quantitative performance indicators
In line with decision 41/93[footnoteRef:3] Annexes I and II present the historical analyses for investment[footnoteRef:4] and non-investment[footnoteRef:5] projects, respectively.  [3:  The Secretariat was requested to continue monitoring the investment and non‑investment performance indicators on the basis of trend analysis in future evaluations of the performance of implementing agencies.]  [4:  Investment projects include multi-year agreements (MYAs) that are so-designated by project code.]  [5:  Only the “funds disbursed”, “speed of first disbursement” and “speed of project completion” indicators are applicable to non-investment projects.] 

These annexes show that agencies have had various levels of success in different years. For investment projects, the target for ODS phased out was achieved by UNIDO and the World Bank in 2017 while UNDP did not achieve this target for that year. The target for the amount of funds disbursed was only achieved by UNIDO while UNDP met 97 per cent and the World Bank met 96 per cent. UNDP and UNIDO reached their targets for project completion reports, and the World Bank met 33 per cent of its target. The speed of delivery and first disbursement for 2017 are similar to previous years reflecting the historical performance for all implementing agencies. The achievement of the target of “value of projects approved” increased for UNIDO and decreased for UNDP and the World Bank. The target for “ODS to be phased out” has not been achieved for all implementing agencies in 2017. The indicators “cost‑effectiveness” and “cost of project preparation” are inconclusive with respect to any trend due to the differences in ODP of CFCs and HCFCs and the approval of MYAs instead of individual projects.
For non-investment projects, the target for the amount of funds disbursed was achieved by all implementing agencies. The speed of delivery and first disbursement for 2017 are similar to previous years for all implementing agencies.
Analysis of qualitative performance indicators 
A total of 66[footnoteRef:6] questionnaires received from the NOUs of 40 Article 5 countries to assess the qualitative performance of the bilateral and implementing agencies were processed.  [6:  Germany (5), UNDP (11), UNEP (29), UNIDO (19) and the World Bank (2).] 

Table 3 presents a summary of the overall ratings provided by the NOUs for the three main categories. It should be noted that several countries did not provide overall ratings for one or more of the categories, although they did send responses to individual questions that have been included in Annex III. Most of the overall ratings were satisfactory or above. 
Table 3: Overall ratings for qualitative performance of bilateral and implementing agencies by category
	Category
	Highly satisfactory
	Satisfactory
	Less satisfactory
	Unsatisfactory

	Impact
	24
	18
	3
	0

	Organization and cooperation
	8
	17
	2
	0

	Technical assistance/training
	18
	19
	2
	0



In addition to the three main categories, the NOUs provide ratings divided into several sub‑categories, and questions by sub-category (Annex III). There were 115 less than satisfactory ratings from the sub‑categories. 
SECRETARIAT’S COMMENTS AND RECOMMENDATIONS
COMMENTS
The implementing agencies have been informed of the results of the quantitative assessment of their performance for 2017, showing that all of them achieved 76 per cent or more of their targets.
The Secretariat sent the assessments received from NOUs to the respective bilateral and implementing agencies for their comments, with an emphasis on the less than satisfactory ratings. Implementing agencies provided comments and, where applicable, reported on the results of their dialogues with the respective NOUs. However, dialogues between NOUs and implementing agencies have not been completed for a number of countries that identified issues in their qualitative assessments (i.e., ratings of “less satisfactory” or “unsatisfactory”).
Implementing agencies have been able to resolve issues in most cases where they have had dialogues with countries that provided less than satisfactory ratings on any qualitative performance indicator. However, at the time of finalizing the present document, the Government of Germany had an ongoing dialogue with the NOU in Zimbabwe, and the following agencies informed the Secretariat that they would finalize their discussions with the respective NOUs during the Thirtieth Meeting of the Parties in November 2018; UNEP (Barbados), and UNIDO (Botswana, Iraq, Mexico, Pakistan, Somalia, Malawi and Rwanda). The outcomes of the discussions are expected to be reported prior to the 82nd meeting, in which case an update will be provided to the Executive Committee at the 82nd meeting. In the event that the outcomes of the discussions are not reported, the Executive Committee may wish to request the Government of Germany, UNEP and UNIDO to have open and constructive discussions with the relevant NOUs to resolve any issues raised in the evaluation of their performance and to report to the 83rd meeting on the outcome of these discussions.
RECOMMENDATIONS
The Executive Committee may wish:
(e) To note:
(i) The evaluation of the performance of implementing agencies against their 2017 business plans, as contained in document UNEP/OzL.Pro/ExCom/82/10; 
(ii) That all implementing agencies had a quantitative assessment of their performance for 2017 of at least 76 on a scale of 100; 
(iii) That the trend analysis indicated that performance of implementing agencies had not improved in some indicators in 2017 in relation to 2016; and
To request the following bilateral and implementing agencies to have open and constructive discussions with the respective national ozone units (NOUs) about the areas in which their services were perceived to be less than satisfactory and to report back to the 83rd meeting on the results of their consultations: UNEP with Barbados; UNIDO with Botswana, Iraq, Mexico, Pakistan, Somalia, Malawi and Rwanda; and the Government of Germany with Zimbabwe.
(f) To encourage NOUs to submit on a yearly basis and in a timely manner, their assessments of the qualitative performance of the bilateral and implementing agencies assisting their Government, noting that only 40 out of 144 countries submitted questionnaires for 2017.
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Annex I
INVESTMENT PROJECT PERFORMANCE BY AGENCY
(1996-2017)

	UNDP
	1996
	1997
	1998
	1999
	2000
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017

	ODS phased out
	24%
	93%
	100%
	76%
	41%
	99%
	92%
	100%
	79%
	91%
	85%
	100%
	86%
	100%
	N/A
	0%
	94%
	100%
	100%
	100%
	0%
	34%

	Funds disbursed
	59%
	100%
	95%
	90%
	100%
	95%
	77%
	64%
	100%
	96%
	66%
	76%
	98%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	97%
	97%

	Project completion reports
	
	
	
	38%
	93%
	86%
	87%
	100%
	97%
	79%
	30%
	82%
	74%
	100%
	54%
	100%
	100%
	100%
	100%
	100%
	100%
	100%

	Distribution among countries
	
	
	
	65%
	61%
	63%
	58%
	38%
	72%
	44%
	75%
	64%
	66%
	83%
	51%
	79%
	94%
	81%
	68%
	85%
	90%
	60%

	Value of projects approved
	100%
	100%
	
	100%
	80%
	100%
	99%
	65%
	73%
	82%
	83%
	77%
	100%
	100%
	38%
	87%
	100%
	87%
	89%
	91%
	100%
	80%

	ODS to be phased out
	74%
	100%
	
	100%
	92%
	96%
	77%
	44%
	89%
	70%
	100%
	100%
	100%
	100%
	100%
	92%
	61%
	100%
	29%
	83%
	84%
	84%

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Cost of project preparation 
(% of approvals)
	
	4.4%
	3%
	2.7%
	2.7%
	1.1%
	2.5%
	1.6%
	3.6%
	1.4%
	0.5%
	3.6%
	1.5%
	14.7%
	14.4%
	3.0%
	2.8%
	1.8%
	0.2%
	4.3%
	2.3%
	2.71%

	Cost-effectiveness ($/kg)
	
	6.1
	6.3
	9.14
	6.74
	8.3
	10.35
	7.1
	6.27
	8.24
	4.99
	5.76
	5.61
	6.09
	59.84
	146.85
	92.53
	56.92
	249.68
	70.89
	108.35
	184.95

	Speed of first disbursement (months)
	
	13
	13
	12
	13
	12.84
	12.8
	12.8
	12.91
	12.9
	13.0
	13.1
	13.2
	13.4
	13.6 
	13.7
	13.7
	13.7
	13.7
	13.7
	13.6
	13.5

	Speed of completion (months)
	24
	29
	29.5
	32
	33
	33.6
	32.7
	32.4
	32.41
	32.9
	33.6
	33.9
	33.8
	33.9
	34.2 
	34.6
	34.9 
	34.9
	35.2
	35.1
	34.4
	35.6

	Net emissions due to delays (ODP tonnes)
	
	
	
	8,995
	11,350
	11,727
	9,023
	6,466
	3,607
	4,538
	6,619
	2,674
	1,312
	92
	113
	101
	520
	538
	248
	238
	-881
	416.3

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	UNIDO
	1996
	1997
	1998
	1999
	2000
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017

	ODS phased out
	73%
	80%
	100%
	57%
	70%
	100%
	100%
	88%
	100%
	99%
	100%
	100%
	84%
	86%
	100%
	100%
	0%
	27%
	42%
	100%
	100%
	100%

	Funds disbursed
	81%
	88%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	91%
	100%
	94%
	100%
	100%
	100%
	97%
	100%
	100%
	100%

	Project completion reports
	
	
	
	83%
	66%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	84%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%

	Distribution among countries
	
	
	
	83%
	74%
	89%
	73%
	78%
	67%
	79%
	69%
	75%
	82%
	61%
	81%
	83%
	100%
	72%
	67%
	100%
	76%
	54%

	Value of projects approved
	99%
	99%
	
	100%
	93%
	99%
	97%
	68%
	82%
	100%
	100%
	92%
	100%
	59%
	78%
	100%
	79%
	88%
	64%
	93%
	71%
	73%

	ODS to be phased out
	42%
	85%
	
	100%
	72%
	100%
	100%
	37%
	89%
	100%
	47%
	91%
	100%
	100%
	100%
	36%
	81%
	21%
	36%
	100%
	82%
	61%

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Cost of project preparation (% of approvals)
	
	2.2%
	4.2%
	2.7%
	3.8%
	2.7%
	3.3%
	3.6%
	2%
	0.9%
	1.8%
	2.1%
	1.3%
	11.9%
	5.7%
	2.7%
	3.9%
	1.1%
	1.3%
	1.8%
	3.6%
	2.6%

	Cost-effectiveness ($/kg)
	
	6.11
	6.27
	7.78
	6.71
	5.67
	7.28
	9.79
	3.58
	3.10
	7.13
	6.51
	9.34
	3.26
	22.58
	187.59
	35.34
	186.02
	79.01
	56.02
	65.50
	53.61

	Speed of first disbursement (months)
	
	10
	9
	8
	9
	9.29
	9.16
	9.2
	9.06
	8.97
	9.0
	8.9
	8.7
	8.7
	8.7 
	8.4
	8.6
	8.5
	8.6
	9.0
	8.9
	9.0

	Speed of completion (months)
	20
	24
	28
	26
	29
	29.85
	30.89
	31.7
	32.35
	32.98
	33.2
	33.5
	33.4
	33.7
	34.1 
	35.0
	35.9
	36.8
	38.3
	39.5
	40.2
	40.9

	Net emissions due to delays (ODP tonnes)
	
	
	
	4,667
	5,899
	5,727
	5,960
	3,503
	13,035
	1,481
	3,864
	4,470
	3,431
	6,970
	8,918
	14,583
	17,144
	8,805
	9,939
	13,389
	6,906
	8,054.8

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	World Bank
	1996
	1997
	1998
	1999
	2000
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017

	ODS phased out
	32%
	94%
	100%
	100%
	100%
	100%
	100%
	84%
	100%
	69%
	31%
	84%
	47%
	100%
	100%
	100%
	20%
	98%
	100%
	100%
	100%
	100%

	Funds disbursed
	64%
	77%
	88%
	97%
	100%
	74%
	100%
	100%
	73%
	100%
	100%
	100%
	100%
	73%
	64%
	43%
	15%
	100%
	100%
	100%
	78%
	96%

	Project completion reports
	
	
	
	61%
	98%
	74%
	100%
	84%
	84%
	100%
	84%
	74%
	69%
	25%
	20%
	85%
	10%
	100%
	24%
	24%
	8%
	33%

	Distribution among countries
	
	
	
	75%
	79%
	67%
	79%
	65%
	71%
	93%
	79%
	92%
	77%
	67%
	50%
	57%
	100%
	67%
	50%
	33%
	100%
	50%

	Value of projects approved
	94%
	87%
	
	100%
	75%
	92%
	100%
	82%
	94%
	83%
	87%
	83%
	93%
	98%
	3%
	93%
	29%
	93%
	72%
	100%
	39%
	29%

	ODS to be phased out
	34%
	100%
	
	100%
	83%
	72%
	91%
	65%
	59%
	100%
	66%
	93%
	35%
	100%
	89%
	11%
	7%
	25%
	11%
	100%
	50%
	74%

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Cost of project preparation (% of approvals)
	
	2.9%
	2.7%
	2.9%
	5.5%
	1.3%
	0.4%
	0.6%
	0.2%
	0.4%
	0.4%
	0.02%
	0.6%
	2.2%
	74.8%
	1.5%
	5.6%
	0.2%
	0.6%
	0.4%
	4.0%
	18.64%

	Cost-effectiveness ($/kg)
	
	3.6
	1.9
	2.83
	2.96
	3.85
	4.57
	6.12
	3.74
	1.04
	3.33
	3.29
	9.36
	1.43
	1.12
	545.23
	69.01
	118.26
	214.04
	19.84
	48.54
	52.66

	Speed of first disbursement (months)
	
	26
	26
	25
	25
	25.33
	26.28
	26
	26.02
	25.7
	25.3
	25.0
	24.8
	24.8
	24.6 
	24.6
	24.7
	24.6
	24.6
	24.6
	24.6 
	24.5

	Speed of completion (months)
	37
	34
	40
	37
	39
	40.09
	41.35
	41
	40.88
	40.7
	40.3
	40.2
	39.8
	39.8
	40.2 
	40.2
	40.2
	40.3
	40.8
	40.8
	40.8
	41.0

	Net emissions due to delays (ODP tonnes)
	
	
	
	7,352
	16,608
	21,539
	22,324
	18,021
	8,338
	4,843
	5,674
	2,316
	1,303
	182
	1,680
	801
	901
	901
	1,002
	275
	455
	249.9
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Annex II

NON-INVESTMENT PROJECT PERFORMANCE BY AGENCY
(1997-2017)

	UNDP
	1997
	1998
	1999
	2000
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017

	Funds disbursed
	100%
	98%
	100%
	100%
	93%
	61%
	100%
	100%
	100%
	92%
	100%
	100%
	100%
	100%
	100%
	84%
	88%
	100%
	47%
	82%
	100%

	Speed until first disbursement (months)
	12
	6
	11
	11.29
	12
	11.4
	11
	11.44
	11.5
	11.8
	11.7
	11.7
	11.8
	12.2
	11.8
	11.9
	11.9
	11.8
	12.0
	11.9
	11.8

	Speed until project completion (months)
	31
	24
	33
	34.16
	36
	34.7
	35
	35.36
	35.4
	36.6
	37.3
	37.1
	37.3
	37.7
	37.1
	37.4
	37.2
	36.7
	36.3
	36.0
	36.8

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	UNEP
	1997
	1998
	1999
	2000
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017

	Funds disbursed
	49%
	100%
	100%
	100%
	93%
	93%
	99%
	54%
	54%
	51%
	49%
	64%
	69%
	60%
	63%
	55%
	47%
	61%
	44%
	91%
	100%

	Speed until first disbursement (months)
	5
	3
	5
	6.33
	6.87
	7.3
	7.6
	8.49
	8.4
	8.4
	8.7
	9.0
	9.0
	9.5 
	9.6
	9.8
	9.8
	9.9
	10.1
	10.5
	10.5

	Speed until project completion (months)
	20
	15
	25
	27.9
	29.66
	30.4
	31
	31.8
	32.4
	32.9
	33.2
	33.6
	32.9
	33.9 
	34.3
	34.4
	34.7
	35.3
	35.3
	36.1
	36.7

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	UNIDO
	1997
	1998
	1999
	2000
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017

	Funds disbursed
	80%
	100%
	49%
	100%
	48%
	89%
	100%
	100%
	90%
	80%
	89%
	69%
	100%
	84%
	95%
	100%
	62%
	82%
	82%
	75%
	100%

	Speed until first disbursement (months)
	7
	6.5
	6
	8
	9.15
	9.85
	9.4
	9.34
	8.9
	9.8
	10.2
	10.6
	10.4
	10.4 
	10.3
	10.3
	10.2
	10.1
	10.0
	10.1
	10.4

	Speed until project completion (months)
	24
	11
	29
	31
	33.66
	33.84
	33.7
	33.89
	31.9
	33.1
	33.0
	32.9
	32.0
	31.9 
	31.4
	32.8
	32.8
	33.7
	32.7
	33.4
	33.5

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	World Bank
	1997
	1998
	1999
	2000
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017

	Funds disbursed
	100%
	49%
	35%
	27%
	12%
	38%
	100%
	79%
	100%
	57%
	59%
	59%
	19%
	47%
	75%
	59%
	49%
	42%
	100%
	88%
	100%

	Speed until first disbursement (months)
	16
	17
	5
	12
	11.95
	12.05
	13.7
	14.58
	13.6
	14.6
	14.3
	14.4
	14.4
	14.9 
	14.6
	15.1
	14.7
	14.0
	14.1
	14.8 
	16.8

	Speed until project completion (months)
	28
	32
	26
	30
	29.24
	28.85
	30
	30.39
	31
	31.5
	31.1
	30.7
	30.7
	30.3 
	30.1
	30.3
	30.2
	30.0
	29.8
	29.8
	29.2
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Annex III
QUALITATIVE ASSESSMENT OF THE IMPLEMENTING AGENCIES 
BY THE NATIONAL OZONE UNITS FOR 2017

	Category
	Sub-category
	Questions
	Values
	Germany
	UNDP
	UNEP
	UNIDO
	World Bank

	IMPACT
	General
	Has cooperation with the implementing agency substantially contributed and added value to your work or organization in managing compliance in your country?
	Highly satisfactory
	2
	6
	19
	9
	1

	
	
	
	Satisfactory
	2
	4
	10
	7
	1

	
	
	
	Less satisfactory
	1
	1
	 
	2
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 

	
	
	IMPACT (Overall Rating)
	Highly satisfactory
	1
	4
	13
	6
	 

	
	
	
	Satisfactory
	1
	5
	6
	6
	 

	
	
	
	Less satisfactory
	1
	 
	 
	2
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 

	
	
	In the design and implementation of the project, has the implementing agency been striving to achieve sustainable results?
	Highly satisfactory
	2
	6
	20
	9
	1

	
	
	
	Satisfactory
	2
	4
	9
	8
	1

	
	
	
	Less satisfactory
	1
	 
	 
	2
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 

	ORGANIZATION AND COOPERATION
	General
	Did cooperation with the staff of the implementing agency take place in an atmosphere of mutual understanding?
	Highly satisfactory
	3
	6
	25
	10
	1

	
	
	
	Satisfactory
	1
	5
	4
	6
	1

	
	
	
	Less satisfactory
	1
	 
	 
	3
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 

	
	
	Did the implementing agency clearly explain its work plan and division of tasks?
	Highly satisfactory
	2
	5
	16
	6
	1

	
	
	
	Satisfactory
	2
	5
	11
	9
	1

	
	
	
	Less satisfactory
	 
	 
	1
	4
	 

	
	
	
	Unsatisfactory
	1
	 
	 
	 
	 

	
	
	Did the implementing agency sufficiently control and monitor the delivery of consultant services?
	Highly satisfactory
	2
	5
	15
	7
	1

	
	
	
	Satisfactory
	2
	5
	11
	9
	1

	
	
	
	Less satisfactory
	1
	 
	 
	1
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	2
	 

	
	
	Did the responsible staff of the implementing agency communicate sufficiently and help to avoid misunderstanding?
	Highly satisfactory
	3
	4
	22
	11
	1

	
	
	
	Satisfactory
	2
	7
	7
	5
	1

	
	
	
	Less satisfactory
	 
	 
	 
	2
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 

	
	
	Has the use of funds been directed effectively to reach the targets and was it agreed between the national ozone unit and the implementing agency?
	Highly satisfactory
	2
	6
	19
	9
	2

	
	
	
	Satisfactory
	2
	3
	10
	7
	 

	
	
	
	Less satisfactory
	 
	 
	 
	2
	 

	
	
	
	Unsatisfactory
	1
	1
	 
	1
	 

	
	
	If there was a lead agency for a multi-agency project, did it coordinate the activities of the other implementing agencies satisfactorily?
	Highly satisfactory
	1
	4
	9
	4
	 

	
	
	
	Satisfactory
	 
	2
	7
	4
	1

	
	
	
	Less satisfactory
	 
	 
	 
	4
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 

	
	
	ORGANIZATION AND COOPERATION (Overall Rating)
	Highly satisfactory
	1
	2
	5
	 
	 

	
	
	
	Satisfactory
	1
	5
	7
	4
	 

	
	
	
	Less satisfactory
	1
	 
	 
	1
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 

	
	
	Was active involvement of the national ozone unit ensured in project Development?
	Highly satisfactory
	2
	6
	20
	6
	1

	
	
	
	Satisfactory
	2
	4
	9
	10
	1

	
	
	
	Less satisfactory
	1
	 
	 
	2
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 

	
	
	Was active involvement of the national ozone unit ensured in project Identification?
	Highly satisfactory
	2
	6
	21
	6
	1

	
	
	
	Satisfactory
	2
	4
	8
	11
	1

	
	
	
	Less satisfactory
	1
	 
	 
	2
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 

	
	
	Was active involvement of the national ozone unit ensured in project Implementation?
	Highly satisfactory
	2
	7
	20
	8
	1

	
	
	
	Satisfactory
	2
	4
	9
	6
	1

	
	
	
	Less satisfactory
	1
	 
	 
	3
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	2
	 

	
	
	Were the required services of the implementing agency delivered in time?
	Highly satisfactory
	2
	2
	15
	4
	1

	
	
	
	Satisfactory
	2
	9
	14
	10
	1

	
	
	
	Less satisfactory
	1
	 
	 
	4
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 

	TECHNICAL ASSISTANCE/TRAINING
	General
	Did project partners receive sufficient technical advice and/or assistance in their decision-making on technology?
	Highly satisfactory
	2
	7
	17
	4
	1

	
	
	
	Satisfactory
	2
	1
	9
	13
	1

	
	
	
	Less satisfactory
	1
	1
	 
	2
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 

	
	
	Did the agency give sufficient consideration to training aspects within funding limits?
	Highly satisfactory
	2
	5
	19
	5
	1

	
	
	
	Satisfactory
	2
	3
	8
	9
	1

	
	
	
	Less satisfactory
	1
	1
	 
	4
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 

	
	
	Do you feel that you have received sufficient support in building capacities for the national implementation of the project (within the funding limitations)?
	Highly satisfactory
	2
	3
	18
	7
	1

	
	
	
	Satisfactory
	2
	6
	10
	8
	1

	
	
	
	Less satisfactory
	1
	 
	 
	2
	 

	
	
	
	Unsatisfactory
	 
	1
	 
	2
	 

	
	
	Has the acquisition of services and equipment been successfully administered, contracted and its delivery monitored?
	Highly satisfactory
	2
	7
	12
	7
	 

	
	
	
	Satisfactory
	2
	2
	11
	9
	1

	
	
	
	Less satisfactory
	1
	1
	 
	1
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	2
	 

	
	
	In case of need, was trouble-shooting by the agency quick and in direct response to your needs?
	Highly satisfactory
	2
	6
	15
	6
	1

	
	
	
	Satisfactory
	2
	2
	10
	6
	1

	
	
	
	Less satisfactory
	1
	1
	 
	3
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 

	
	
	TECHNICAL ASSISTANCE/TRAINING (Overall Rating)
	Highly satisfactory
	1
	4
	8
	4
	1

	
	
	
	Satisfactory
	1
	4
	10
	4
	 

	
	
	
	Less satisfactory
	1
	 
	 
	1
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 

	
	
	Was the selection and competence of consultants provided by the agency satisfactory?
	Highly satisfactory
	2
	5
	16
	8
	 

	
	
	
	Satisfactory
	2
	4
	9
	9
	1

	
	
	
	Less satisfactory
	1
	 
	 
	2
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 

	
	
	Were project partners and stakeholders encouraged by the implementing agency to participate positively in decision-making and design of activities?
	Highly satisfactory
	2
	6
	14
	8
	1

	
	
	
	Satisfactory
	3
	3
	13
	9
	1

	
	
	
	Less satisfactory
	 
	1
	 
	2
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 

	
	Investment projects
	Has the agency been effective and met the expectations of stakeholders in providing technical advice, training and commissioning?
	Highly satisfactory
	1
	7
	9
	7
	1

	
	
	
	Satisfactory
	2
	1
	10
	9
	1

	
	
	
	Less satisfactory
	 
	 
	 
	1
	 

	
	
	
	Unsatisfactory
	1
	 
	 
	1
	 

	
	
	Has the agency been responsive in addressing any technical difficulties that may have been encountered subsequent to the provision of non-ODS technology?
	Highly satisfactory
	1
	5
	8
	5
	1

	
	
	
	Satisfactory
	2
	1
	10
	10
	1

	
	
	
	Less satisfactory
	 
	 
	 
	 
	 

	
	
	
	Unsatisfactory
	1
	 
	 
	1
	 

	
	National phase-out plans
	Has support for the distribution of equipment been adequate?
	Highly satisfactory
	2
	3
	10
	8
	 

	
	
	
	Satisfactory
	1
	5
	10
	7
	1

	
	
	
	Less satisfactory
	1
	 
	 
	 
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	2
	 

	
	
	Has support to identify policy issues related to implementation been adequate?
	Highly satisfactory
	2
	3
	15
	6
	1

	
	
	
	Satisfactory
	1
	5
	9
	9
	1

	
	
	
	Less satisfactory
	1
	 
	 
	3
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 

	
	
	Has technical advice on equipment specifications been adequate?
	Highly satisfactory
	2
	6
	11
	8
	1

	
	
	
	Satisfactory
	1
	2
	11
	7
	1

	
	
	
	Less satisfactory
	1
	 
	 
	1
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 

	
	
	Has the technical advice or training that was provided been effective?
	Highly satisfactory
	2
	6
	18
	9
	1

	
	
	
	Satisfactory
	2
	1
	7
	7
	1

	
	
	
	Less satisfactory
	 
	 
	 
	1
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 

	
	
	Were proposed implementation strategies adequate?
	Highly satisfactory
	2
	5
	15
	8
	1

	
	
	
	Satisfactory
	1
	3
	12
	8
	1

	
	
	
	Less satisfactory
	1
	 
	 
	2
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 

	
	Regulatory assistance projects
	Were the regulations that were proposed by the agency Adapted to local circumstances?
	Highly satisfactory
	1
	4
	14
	3
	1

	
	
	
	Satisfactory
	1
	3
	11
	8
	1

	
	
	
	Less satisfactory
	1
	 
	 
	3
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 

	
	
	Were the regulations that were proposed by the agency Applicable?
	Highly satisfactory
	1
	5
	16
	5
	1

	
	
	
	Satisfactory
	2
	2
	9
	6
	1

	
	
	
	Less satisfactory
	 
	 
	 
	2
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 

	
	
	Were the regulations that were proposed by the agency Enforceable?
	Highly satisfactory
	1
	4
	15
	5
	1

	
	
	
	Satisfactory
	1
	3
	10
	6
	1

	
	
	
	Less satisfactory
	1
	 
	 
	2
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 

	
	Training projects
	Was the quality of the training provided satisfactory?
	Highly satisfactory
	3
	4
	16
	9
	1

	
	
	
	Satisfactory
	1
	3
	9
	5
	1

	
	
	
	Less satisfactory
	 
	 
	 
	1
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 

	
	
	Was the training designed so that those trained would be likely to use the skills taught?
	Highly satisfactory
	3
	4
	19
	7
	1

	
	
	
	Satisfactory
	 
	3
	4
	8
	1

	
	
	
	Less satisfactory
	1
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