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COMPTE RENDU SUR L’ÉTAT DE LA MISE EN OEUVRE DU PLAN D’ACTIVITÉS GÉNÉRAL DE 2024-2026 DU FONDS MULTILATÉRAL

Introduction

À sa 93e réunion, le Comité exécutif a endossé le plan d’activités général de 2024-2026 du Fonds multilatéral. En réponse à la décision 93/28, le Secrétariat a ajusté le plan d’activités général de 2024-2026, tel qu’indiqué dans le tableau 1.
Tableau 1. Affection des ressources du plan général ajusté de 2024-2026 pour les activités du Fonds multilatéral ($ US)*
	Description 
	2024
	2025
	2026
	Total 

	Activités relatives aux HCFC
	 
	 
	 
	 

	Plans de gestion de l’élimination des HCFC (PGEH) approuvés
	48 499 466
	50 384 491
	50 158 180
	149 042 137

	Plans de gestion de l’élimination de la production de HCFC (PGEPH) approuvés
	23 232 000
	0
	0
	23 232 000

	PGEH phase II – préparation 
	134 400
	44 300
	0
	178 700

	PGEH phase II
	4 970 041
	6 870 087
	10 870 876
	22 711 004

	PGEH phase III – préparation 
	522 900
	65 400
	0
	588 300

	PGEH phase III
	15 849 471
	10 765 760
	23 015 282
	49 630 513

	PGEH phase IV – préparation 
	70 000
	0
	0
	70 000

	PGEH phase IV
	0
	0
	3 691 000
	3 691 000

	Vérification du PGEH**
	588 600
	588 600
	588 600
	1 765 800

	PGEH – efficacité énergétique
	3 726 111
	3 305 040
	111 200
	7 142 351

	Total partiel des activités relatives aux HCFC
	97 592 989
	72 023 678
	88 435 138
	258 051 805

	Activités relatives aux HFC
	 
	 
	 
	 

	Plans de mise en œuvre de l’Amendement de Kigali sur les HFC (KIP) approuvés
	0
	10 127 716
	6 590 654
	16 718 370

	Approuvés pour le contrôle des émissions de HFC-23 
	414 238
	626 900
	572 433
	1 613 571

	HFC – activités de facilitation
	53 500
	160 500
	0
	214 000

	HFC – assistance technique
	678 000
	0
	0
	678 000

	HFC-23 
	8 000 000
	0
	0
	8 000 000

	KIP phase I
	11 458 349
	27 565 521
	6 378 667
	45 402 537

	KIP phase I – préparation de l’investissement
	32 100
	0
	0
	32 100

	KIP phase I – Investissement 
	3 712 616
	0
	0
	3 712 616

	KIP phase I – préparation
	2 891 415
	1 167 771
	211 280
	4 270 466

	Total partiel des activités relatives aux HFC
	27 240 219
	39 648 408
	13 753 034
	80 641 660

	Autres activités
	 
	 
	 
	 

	Projet pilote pour l’efficacité énergétique – démonstration 
	1 870 000
	1 000 000
	0
	2 870 000

	Projet pilote pour l’efficacité énergétique – investissement 
	4 789 988
	248 600
	0
	5 038 588

	Projet pilote pour l’efficacité énergétique – préparation 
	85 600
	0
	0
	85 600

	Préparation pour les stocks de SAO
	1 232 150
	310 300
	0
	1 542 450

	Total partiel des activités relatives aux HFC
	7 977 738
	1 558 900
	0
	9 536 638

	Activités standard
	 
	 
	 
	 

	Renforcement institutionnel (RI)
	22 071 008
	1 830 362
	21 294 756
	45 196 125

	Programme d’aide à la conformité (PAC)
	11 765 667
	12 113 777
	12 310 330
	36 189 774

	Unité de base
	6 611 529
	6 653 609
	6 095 985
	19 361 122

	Coûts associés au Secrétariat, au Comité exécutif, et aux activités de surveillance et d’évaluation, moins la contrepartie canadienne
	7 202 023
	6 816 624
	6 964 604
	20 983 251

	Trésorier
	500 000
	500 000
	500 000
	1 500 000

	Total partiel pour les activités standard
	48 150 226
	27 914 372
	47 165 675
	123 230 273

	Total
	180 961 172
	141 145 358
	149 353 846
	471 460 376

	Par agence
	 
	 
	 
	 

	Australie
	0
	615 610
	0
	615 610

	Autriche
	783 667
	0
	0
	783 667

	France
	671 075
	0
	0
	671 075

	Allemagne
	7 500 449
	2 148 339
	5 834 901
	15 483 689

	PNUD
	44 305 827
	38 729 891
	40 741 817
	123 777 535

	PNUE
	47 977 295
	27 975 506
	35 097 810
	111 050 611

	ONUDI
	40 363 268
	49 551 567
	30 746 018
	120 660 853

	Banque mondiale
	31 068 968
	14 219 221
	28 880 096
	74 168 285

	Vérification du PGEH**
	588 600
	588 600
	588 600
	1 765 800

	Coûts associés au Secrétariat, au Comité exécutif, et aux activités de surveillance et d’évaluation, moins la contrepartie canadienne
	7 202 023
	6 816 624
	6 964 604
	20 983 251

	Trésorier
	500 000
	500 000
	500 000
	1 500 000


* Incluant les coûts d’appui à l’agence, le cas échéant.
** Le financement pour la préparation des rapports de vérification des PGEH pour les pays à faible volume de consommation est approuvé par le Comité exécutif sur une base annuelle.

État de la mise en œuvre du plan d’activités de 2024

La valeur totale du plan d’activités pour 2024 s’élève à 180 961 172 $ US. De ce montant, la somme de 61 332 446 $ US a été approuvée à la 94e réunion. De plus, des activités dont le montant s’élève à 124 178 563 $ US seront examinées à la 95e réunion; si les fonds pour toutes les propositions de projets soumises sont approuvés tel que demandé, le budget du plan d’activités de 2024 serait dépassé de 4 549 837 $ US, comme le montre le tableau 2. 
Tableau 2. Plan d’activités général de 2024, approbations à la 94e réunion, projet recommandé à la 95e réunion, et solde ($ US)*
	Postes budgétaires
	Valeur totale dans le plan d’activités
	Approbations à la 94e réunion
	Activités recommandées à la 95e réunion
	Solde (supérieur)/inférieur

	Agences bilatérales
	8 955 191
	7 722 115
	4 501 291
	(3 268 215)

	PNUD
	44 305 827
	16 932 440
	22 592 547
	4 780 840

	PNUE
	47 977 295
	12 910 251
	34 033 332
	1 033 712

	ONUDI
	40 363 268
	23 196 140
	27 767 338
	(10 600 210)

	Banque mondiale
	31 068 968
	0
	27 582 032
	3 486 936

	Vérification du PGEH
	588 600
	571 500
	0
	17 100

	Total partiel (agences)
	173 259 149
	61 332 446
	116 476 540
	(4 549 837)

	Coûts du Secrétariat/Comité exécutif/ Surveillance et évaluation (moins la contrepartie canadienne)
	7 202 023
	0
	7 202 023
	0

	Trésorier
	500 000
	0
	500 000
	0

	Total partiel (coûts standard)
	7 702 023
	0
	7 702 023
	0

	Total
	180 961 172
	61 332 446
	124 178 563
	(4 549 837)


* Incluant les coûts de l’unité de base.

La valeur des propositions de projets recommandées à la 95e réunion de 116 476 540 $ US, soit 25 156 871 $ US au-dessus de la valeur inscrite dans le plan d’activités de 2024, dont 15 899 209 $ US pour des propositions de projets qui ne sont pas incluses dans le plan d’activités de 2024[footnoteRef:2].  [2:  Phase I du PGEH pour le Bhoutan (PNUD et PNUE); phase II des PGEH pour les Îles Cook (PNUE), Kiribati (PNUE), les Îles Marshall (PNUE), Micronésie (États fédérés de) (PNUE), Nauru (PNUE), Nioué (PNUE), Palaos (PNUE), la région des pays insulaires du Pacifique (PIP) (Australie et PNUE), le Samoa (PNUE), les Îles Salomon (PNUE), les Tonga (PNUE), les Tuvalu (PNUE), et le Vanuatu (PNUE); phase III des PGEH pour le Chili (PNUD) et le Mexique (Allemagne); une préparation de projet pour la phase II du PGEH pour la Dominique (ONUDI); trois activités de préparation de projets pour la phase III des PGEH de l’Angola (PNUD) et du Bangladesh (PNUD et PNUE); une préparation de projet pour la phase IV du PGEH du Nigeria (Allemagne); un projet d’investissement du KIP pour l’Argentine (ONUDI); une préparation de projet pour un projet d’investissement du KIP pour l’Indonésie (Banque mondiale); quatre préparations de projets pour la phase I des KIP pour les Bahamas (PNUE et ONUDI), la Barbade (PNUE) et la Chine (PNUD); phase I des KIP pour le Bénin (PNUE et ONUDI), le Tchad (PNUE et ONUDI), le Guatemala (PNUE et ONUDI), Maurice (Allemagne), la région des PIP (Australie et PNUE), le Sénégal (PNUE et ONUDI), et l’Uruguay (PNUD et ONUDI); 16 projets concernant l’efficacité énergétique aux termes de la décision 89/6 pour le Bhoutan (PNUE), les Îles Cook (PNUE), Kiribati (PNUE), les Îles Marshall (PNUE), Micronésie (États fédérés de) (PNUE), Nauru (PNUE), Nioué (PNUE), Palaos (PNUE), la région des PIP (Australie et PNUE), Saint-Vincent-et-les-Grenadines (PNUE), le Samoa (PNUE), les Îles Salomon (PNUE), les Tonga (PNUE), les Tuvalu (PNUE), et le Vanuatu (PNUE); et 28 activités de préparation de projets pour les inventaires nationaux des stocks de substances réglementées indésirables aux termes de la décision 91/66 pour les Bahamas (PNUE), le Bangladesh (ONUDI), le Bhoutan (PNUE), le Brunei Darussalam (PNUE), le Congo (ONUDI), les Îles Cook (PNUE), l’Eswatini (PNUE), les Fidji (PNUE), la Gambie (PNUE), l’Indonésie (PNUD), Kiribati (PNUE), Madagascar (ONUDI), les Îles Marshall (PNUE), Micronésie (États fédérés de) (PNUE), la Mongolie (PNUE), Nauru (PNUE), le Népal (PNUE), Nioué (PNUE), Palaos (PNUE), le Samoa (PNUE), le Sénégal (Allemagne), les Îles Salomon (PNUE), la Thaïlande (Banque mondiale), le Timor-Leste (PNUE), les Tonga (PNUE), les Tuvalu (PNUE), l’Ouganda (PNUE), et le Vanuatu (PNUE).] 

La valeur des activités relatives aux HFC recommandées à la 95e réunion est de19 833 551 $ US, soit 8 720 978 $ US pour des propositions de projets qui ne sont pas incluses dans le plan d’activités de 2024. L’Annexe I au présent document contient la liste des projets relatifs aux HFC soumis par les agences bilatérales et d’exécution à la 95e réunion. 
La valeur des projets recommandés dans le cadre de la fenêtre de financement pour des projets pilotes relatifs à l’efficacité énergétique, conformément à la décision 91/65, est de 4 642 176 $ US. En tenant compte des approbations aux 92e, 93e et 94e réunions, à hauteur de 5 976 489 $U S, et des valeurs recommandées à la 95e réunion, le solde des fonds disponibles dans le cadre de la fenêtre de financement est de 9 381 335 $ US. L’Annexe II au présent document contient la liste des projets pilotes soumis par les agences bilatérales et d’exécution à la 95e réunion, conformément à la décision 91/65. 
La valeur des projets recommandés dans le cadre de la fenêtre de financement pour l’efficacité énergétique, conformément à la décision 94/60, est de 1 170 247 $ US, et le solde des fonds disponibles dans le cadre de cette fenêtre de financement est de 98 829 753 $ US. L’Annexe III au présent document contient la liste des projets soumis par les agences bilatérales et d’exécution à la 95e réunion, conformément à la décision 94/60. 
La valeur des projets recommandés dans le cadre de la fenêtre de financement pour la préparation d’inventaires nationaux des stocks de substances réglementées indésirables, conformément à la décision 91/66, est de 2 638 600 $ US, incluant un montant de 2 446 500 $ US qui n’est pas inclus dans le plan d’activités de 2024. L’Annexe IV au présent document contient la liste des activités de préparation de projets soumises par les agences bilatérales et d’exécution à la 95e réunion, conformément à la décision 91/66.
Engagements à terme
Le montant total des engagements à terme existants pour des accords pluriannuels (APA) pour la période de 2024 à 2031 est de 336,6 M$ US, en supposant que les demandes de financement des APA soumises à la 95e réunion seront approuvées en principe, tel qu’indiqué au Tableau 3.
Tableau 3. Engagements à terme (2024-2031) (000 $ US)
	Description
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	2031
	Total

	Approuvés en principe
	99 643
	50 780
	67 400
	22 538
	20 214
	8 176
	15 120
	57
	283 929

	Soumis la 95e réunion
	22 866
	0
	0
	24 773
	139
	2 367
	2 583
	0
	52 729

	Total 
	122 510
	50 780
	67 400
	47 312
	20 353
	10 543
	17 703
	57
	336 657



Recommandation 

Le Comité exécutif pourrait envisager de prendre note :
Du compte rendu sur l’état de la mise en œuvre du plan d’activités général de 2024-2026 du Fonds multilatéral, figurant dans le document UNEP/OzL.Pro/ExCom/95/23;
Que la valeur totale des activités, comme recommandées à la 95e réunion, s’élève à 116 476 540 $ US (incluant 19 833 551 $ US pour les activités relatives aux HFC; 4 642 176 $ US pour des projets pilotes concernant l’efficacité énergétique conformément à la décision 91/65; 1 170 247 $ US pour les projets concernant l’efficacité énergétique conformément à la décision 94/60; et 2 638 600 $ US pour la préparation d’inventaires nationaux des stocks de substances réglementées indésirables conformément à la décision 91/66), dont 15 899 209 $ US sont associés à des propositions de projets qui ne sont pas incluses dans le plan d’activités de 2024.
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Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 95TH MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Argentina
	UNIDO
	INV
	KIP
	Investment project to phase out R‑410A in domestic air conditioner manufacturing sector in Argentina
	5,697,593
	398,832

	Bahamas (the)
	UNEP
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	91,000
	11,830

	Bahamas (the)
	UNIDO
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	39,000
	2,730

	Barbados
	UNEP
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	130,000
	16,900

	Benin
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	117,500
	15,275

	Benin
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	60,000
	7,800

	Chad
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	141,000
	18,330

	Chad
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	75,000
	9,750

	China
	UNDP
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	250,000
	17,500

	Colombia
	Germany
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	258,825
	33,647

	Colombia
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	1,066,225
	74,636

	Colombia
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (local installation and assembly subsector)
	341,100
	23,877

	Colombia
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (manufacturing sector)
	1,023,513
	71,646

	Colombia
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	124,148
	8,690

	Cook Islands (the)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	23,250
	3,023

	Costa Rica
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first trance)
	356,880
	45,029

	Costa Rica
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first trance) (PMU)
	14,088
	1,778

	Guatemala
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	10,000
	1,300

	Guatemala
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	251,019
	17,571

	Indonesia
	IBRD
	PRP
	KIP
	Preparation of a KIP investment project in the domestic and stand-alone commercial refrigerator manufacturing sector
	80,000
	5,600

	Kiribati
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	15,000
	1,950

	Lesotho
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	64,000
	8,320

	Lesotho
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	18,000
	2,340

	Marshall Islands (the)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	11,750
	1,527

	Mauritius
	Germany
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	103,000
	13,390

	Micronesia (Federated States of)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	63,500
	8,255

	Morocco
	UNIDO
	INV
	KIP
	Conversion of two production lines in one enterprise (MANAR) manufacturing domestic refrigeration equipment from HFC-134a to R-600a
	352,985
	24,709

	Nauru
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	10,500
	1,365

	Nigeria
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	1,902,050
	133,144

	Nigeria
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	130,800
	17,004

	Nigeria
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	705,510
	49,386

	Niue
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	9,250
	1,202

	Oman
	UNEP
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	160,000
	20,800

	Oman
	UNIDO
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	30,000
	2,100

	Palau
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	57,500
	7,475

	Rwanda
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	48,400
	6,292

	Rwanda
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	27,500
	3,575

	Samoa
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	66,000
	8,580

	Senegal
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	168,000
	21,840

	Senegal
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	127,500
	8,925

	Solomon Islands
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	74,125
	9,637

	Togo
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	117,500
	15,275

	Togo
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	70,000
	9,100

	Tonga
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	60,750
	7,898

	Türkiye
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	845,445
	59,181

	Türkiye
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	1,943,985
	136,079

	Tuvalu
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	12,250
	1,592

	Uruguay
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	126,927
	16,500

	Uruguay
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	49,860
	6,482

	Vanuatu
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	31,625
	4,112

	Zimbabwe
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	90,000
	11,700

	Zimbabwe
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	151,500
	19,695

	Region: ASP
	Australia
	INV
	KIP
	Regional Kigali HFC implementation plan for Pacific Island Countries (stage I, first tranche)
	295,000
	38,350

	Region: ASP
	UNEP
	TAS
	KIP
	Regional Kigali HFC implementation plan for Pacific Island Countries (stage I, first tranche)
	247,500
	32,174
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Annex II

PILOT PROJECTS FOR ENERGY EFFICIENCY (DECISION 91/65) 
SUBMITTED TO THE 95TH MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	China
	UNDP
	INV
	EEF
	Pilot project to enhance the energy efficiency of cooling technologies in data centres through the demonstration of single-phase immersion cooling system in a data centre (decision 91/65)
	1,790,800
	125,356

	Colombia
	UNDP
	TAS
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65)
	506,319
	35,442

	Costa Rica
	UNDP
	INV
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65)
	260,000
	18,200

	Honduras
	UNIDO
	INV
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65)
	278,068
	19,465

	Malaysia
	IBRD
	INV
	EEF
	Pilot project to enhance the energy efficiency of stand-alone commercial refrigeration equipment in Malaysia in the context of the HFC phase-down (investment and non-investment activities) (decisions 91/65)
	500,000
	35,000

	Montenegro
	UNIDO
	TAS
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65)
	120,000
	10,800

	Peru
	UNEP
	TAS
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65)
	115,000
	14,950

	Uganda
	United Kingdom of Great Britain and Northern Ireland
	INV
	EEF
	Demonstration of energy-efficient ultra‑low GWP technology in a supermarket (decision 91/65)
	435,200
	56,576

	Uruguay
	UNDP
	INV
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of technologies in the commercial refrigeration and residential AC sectors in the context of HFC phase-down (non-investment activities) (decision 91/65)
	300,000
	21,000
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Annex III

PROJECTS FOR ENERGY EFFICIENCY PURSUANT TO DECISION 94/60
SUBMITTED TO THE 95TH MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Egypt
	UNIDO
	PRP
	EEF
	Preparation of a pilot project on energy efficiency (decision 94/60)
	210,000
	14,700

	Malaysia
	IBRD
	INV
	EEF
	Pilot project to enhance the energy efficiency of stand-alone commercial refrigeration equipment in Malaysia in the context of the HFC phase-down (investment and non‑investment activities) (decisions 94/60)
	415,689
	29,098

	Nigeria
	UNIDO
	PRP
	EEF
	Preparation of a pilot project on energy efficiency (decision 94/60)
	78,000
	5,460

	Thailand
	IBRD
	PRP
	EEF
	Preparation of a project for enhancing energy efficiency in manufacturing of light commercial air-conditioning (AC) systems in the context of HFC phase-down (decision 94/60)
	150,000
	10,500

	Tunisia
	UNIDO
	PRP
	EEF
	Preparation of a pilot project on energy efficiency (decision 94/60)
	20,000
	1,400

	Türkiye
	UNIDO
	PRP
	EEF
	Preparation of a pilot project on energy efficiency (decision 94/60)
	220,000
	15,400
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Annex IV

PROJECT PREPARATION FOR NATIONAL INVENTORIES OF BANKS 
OF WASTE‑CONTROLLED SUBSTANCES (DECISION 91/66) 
SUBMITTED TO THE 95TH MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Bahamas (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Bangladesh
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Bhutan
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Brunei Darussalam
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Congo (the)
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Cook Islands (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Eswatini
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Fiji
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Gambia (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Indonesia
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	7,000

	Kiribati
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Madagascar
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Maldives
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Marshall Islands (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Micronesia (Federated States of)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Mongolia
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Nauru
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Nepal
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Niue
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Palau
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Samoa
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Senegal
	Germany
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Solomon Islands
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Sri Lanka
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Thailand
	IBRD
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	7,000

	Timor-Leste
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Tonga
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Tuvalu
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Uganda
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Vanuatu
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100
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