| NATIONS UNIES |  | EP |
| --- | --- | --- |
|  | Programme des Nations Unies pour l’environnement | Distr. GÉNÉRALE UNEP/OzL.Pro/ExCom/95/23 25 novembre 2024 FRANÇAIS ORIGINAL : ANGLAIS |

COMITÉ EXÉCUTIF 
  DU FONDS MULTILATÉRAL AUX FINS 
  D’APPLICATION DU PROTOCOLE DE MONTRÉAL
Quatre-vingt-quinzième réunion

Montréal, 4-8 décembre 2024

Point 8(a) de l’ordre du jour provisoire

COMPTE RENDU SUR L’ÉTAT DE LA MISE EN OEUVRE DU PLAN D’ACTIVITÉS GÉNÉRAL DE 2024-2026 DU FONDS MULTILATÉRAL

- Introduction

# À sa 93e réunion, le Comité exécutif a endossé le plan d’activités général de 2024-2026 du Fonds multilatéral. En réponse à la décision 93/28, le Secrétariat a ajusté le plan d’activités général de 2024-2026, tel qu’indiqué dans le tableau 1.

Tableau 1. Affection des ressources du plan général ajusté de 2024-2026 pour les activités du Fonds multilatéral ($ US)*

| Description | 2024 | 2025 | 2026 | Total |
| --- | --- | --- | --- | --- |
| Activités relatives aux HCFC |  |  |  |  |
| Plans de gestion de l’élimination des HCFC (PGEH) approuvés | 48 499 466 | 50 384 491 | 50 158 180 | 149 042 137 |
| Plans de gestion de l’élimination de la production de HCFC (PGEPH) approuvés | 23 232 000 | 0 | 0 | 23 232 000 |
| PGEH phase II – préparation | 134 400 | 44 300 | 0 | 178 700 |
| PGEH phase II | 4 970 041 | 6 870 087 | 10 870 876 | 22 711 004 |
| PGEH phase III – préparation | 522 900 | 65 400 | 0 | 588 300 |
| PGEH phase III | 15 849 471 | 10 765 760 | 23 015 282 | 49 630 513 |
| PGEH phase IV – préparation | 70 000 | 0 | 0 | 70 000 |
| PGEH phase IV | 0 | 0 | 3 691 000 | 3 691 000 |
| Vérification du PGEH** | 588 600 | 588 600 | 588 600 | 1 765 800 |
| PGEH – efficacité énergétique | 3 726 111 | 3 305 040 | 111 200 | 7 142 351 |
| Total partiel des activités relatives aux HCFC | 97 592 989 | 72 023 678 | 88 435 138 | 258 051 805 |
| Activités relatives aux HFC |  |  |  |  |
| Plans de mise en œuvre de l’Amendement de Kigali sur les HFC (KIP) approuvés | 0 | 10 127 716 | 6 590 654 | 16 718 370 |
| Approuvés pour le contrôle des émissions de HFC-23 | 414 238 | 626 900 | 572 433 | 1 613 571 |
| HFC – activités de facilitation | 53 500 | 160 500 | 0 | 214 000 |
| HFC – assistance technique | 678 000 | 0 | 0 | 678 000 |
| HFC-23 | 8 000 000 | 0 | 0 | 8 000 000 |
| KIP phase I | 11 458 349 | 27 565 521 | 6 378 667 | 45 402 537 |
| KIP phase I – préparation de l’investissement | 32 100 | 0 | 0 | 32 100 |
| KIP phase I – Investissement | 3 712 616 | 0 | 0 | 3 712 616 |
| KIP phase I – préparation | 2 891 415 | 1 167 771 | 211 280 | 4 270 466 |
| Total partiel des activités relatives aux HFC | 27 240 219 | 39 648 408 | 13 753 034 | 80 641 660 |
| Autres activités |  |  |  |  |
| Projet pilote pour l’efficacité énergétique – démonstration | 1 870 000 | 1 000 000 | 0 | 2 870 000 |
| Projet pilote pour l’efficacité énergétique – investissement | 4 789 988 | 248 600 | 0 | 5 038 588 |
| Projet pilote pour l’efficacité énergétique – préparation | 85 600 | 0 | 0 | 85 600 |
| Préparation pour les stocks de SAO | 1 232 150 | 310 300 | 0 | 1 542 450 |
| Total partiel des activités relatives aux HFC | 7 977 738 | 1 558 900 | 0 | 9 536 638 |
| Activités standard |  |  |  |  |
| Renforcement institutionnel (RI) | 22 071 008 | 1 830 362 | 21 294 756 | 45 196 125 |
| Programme d’aide à la conformité (PAC) | 11 765 667 | 12 113 777 | 12 310 330 | 36 189 774 |
| Unité de base | 6 611 529 | 6 653 609 | 6 095 985 | 19 361 122 |
| Coûts associés au Secrétariat, au Comité exécutif, et aux activités de surveillance et d’évaluation, moins la contrepartie canadienne | 7 202 023 | 6 816 624 | 6 964 604 | 20 983 251 |
| Trésorier | 500 000 | 500 000 | 500 000 | 1 500 000 |
| Total partiel pour les activités standard | 48 150 226 | 27 914 372 | 47 165 675 | 123 230 273 |
| Total | 180 961 172 | 141 145 358 | 149 353 846 | 471 460 376 |
| Par agence |  |  |  |  |
| Australie | 0 | 615 610 | 0 | 615 610 |
| Autriche | 783 667 | 0 | 0 | 783 667 |
| France | 671 075 | 0 | 0 | 671 075 |
| Allemagne | 7 500 449 | 2 148 339 | 5 834 901 | 15 483 689 |
| PNUD | 44 305 827 | 38 729 891 | 40 741 817 | 123 777 535 |
| PNUE | 47 977 295 | 27 975 506 | 35 097 810 | 111 050 611 |
| ONUDI | 40 363 268 | 49 551 567 | 30 746 018 | 120 660 853 |
| Banque mondiale | 31 068 968 | 14 219 221 | 28 880 096 | 74 168 285 |
| Vérification du PGEH** | 588 600 | 588 600 | 588 600 | 1 765 800 |
| Coûts associés au Secrétariat, au Comité exécutif, et aux activités de surveillance et d’évaluation, moins la contrepartie canadienne | 7 202 023 | 6 816 624 | 6 964 604 | 20 983 251 |
| Trésorier | 500 000 | 500 000 | 500 000 | 1 500 000 |

* Incluant les coûts d’appui à l’agence, le cas échéant.

** Le financement pour la préparation des rapports de vérification des PGEH pour les pays à faible volume de consommation est approuvé par le Comité exécutif sur une base annuelle.

État de la mise en œuvre du plan d’activités de 2024

# La valeur totale du plan d’activités pour 2024 s’élève à 180 961 172 $ US. De ce montant, la somme de 61 332 446 $ US a été approuvée à la 94e réunion. De plus, des activités dont le montant s’élève à 124 178 563 $ US seront examinées à la 95e réunion; si les fonds pour toutes les propositions de projets soumises sont approuvés tel que demandé, le budget du plan d’activités de 2024 serait dépassé de 4 549 837 $ US, comme le montre le tableau 2.

Tableau 2. Plan d’activités général de 2024, approbations à la 94e réunion, projet recommandé à la 95e réunion, et solde ($ US)*

| Postes budgétaires | Valeur totale dans le plan d’activités | Approbations à la 94e réunion | Activités recommandées à la 95e réunion | Solde (supérieur)/inférieur |
| --- | --- | --- | --- | --- |
| Agences bilatérales | 8 955 191 | 7 722 115 | 4 501 291 | (3 268 215) |
| PNUD | 44 305 827 | 16 932 440 | 22 592 547 | 4 780 840 |
| PNUE | 47 977 295 | 12 910 251 | 34 033 332 | 1 033 712 |
| ONUDI | 40 363 268 | 23 196 140 | 27 767 338 | (10 600 210) |
| Banque mondiale | 31 068 968 | 0 | 27 582 032 | 3 486 936 |
| Vérification du PGEH | 588 600 | 571 500 | 0 | 17 100 |
| Total partiel (agences) | 173 259 149 | 61 332 446 | 116 476 540 | (4 549 837) |
| Coûts du Secrétariat/Comité exécutif/ Surveillance et évaluation (moins la contrepartie canadienne) | 7 202 023 | 0 | 7 202 023 | 0 |
| Trésorier | 500 000 | 0 | 500 000 | 0 |
| Total partiel (coûts standard) | 7 702 023 | 0 | 7 702 023 | 0 |
| Total | 180 961 172 | 61 332 446 | 124 178 563 | (4 549 837) |

* Incluant les coûts de l’unité de base.

# La valeur des propositions de projets recommandées à la 95e réunion de 116 476 540 $ US, soit 25 156 871 $ US au-dessus de la valeur inscrite dans le plan d’activités de 2024, dont 15 899 209 $ US pour des propositions de projets qui ne sont pas incluses dans le plan d’activités de 2024.

# La valeur des activités relatives aux HFC recommandées à la 95e réunion est de19 833 551 $ US, soit 8 720 978 $ US pour des propositions de projets qui ne sont pas incluses dans le plan d’activités de 2024. L’Annexe I au présent document contient la liste des projets relatifs aux HFC soumis par les agences bilatérales et d’exécution à la 95e réunion.

# La valeur des projets recommandés dans le cadre de la fenêtre de financement pour des projets pilotes relatifs à l’efficacité énergétique, conformément à la décision 91/65, est de 4 642 176 $ US. En tenant compte des approbations aux 92e, 93e et 94e réunions, à hauteur de 5 976 489 $U S, et des valeurs recommandées à la 95e réunion, le solde des fonds disponibles dans le cadre de la fenêtre de financement est de 9 381 335 $ US. L’Annexe II au présent document contient la liste des projets pilotes soumis par les agences bilatérales et d’exécution à la 95e réunion, conformément à la décision 91/65.

# La valeur des projets recommandés dans le cadre de la fenêtre de financement pour l’efficacité énergétique, conformément à la décision 94/60, est de 1 170 247 $ US, et le solde des fonds disponibles dans le cadre de cette fenêtre de financement est de 98 829 753 $ US. L’Annexe III au présent document contient la liste des projets soumis par les agences bilatérales et d’exécution à la 95e réunion, conformément à la décision 94/60.

# La valeur des projets recommandés dans le cadre de la fenêtre de financement pour la préparation d’inventaires nationaux des stocks de substances réglementées indésirables, conformément à la décision 91/66, est de 2 638 600 $ US, incluant un montant de 2 446 500 $ US qui n’est pas inclus dans le plan d’activités de 2024. L’Annexe IV au présent document contient la liste des activités de préparation de projets soumises par les agences bilatérales et d’exécution à la 95e réunion, conformément à la décision 91/66.

# Engagements à terme

# Le montant total des engagements à terme existants pour des accords pluriannuels (APA) pour la période de 2024 à 2031 est de 336,6 M$ US, en supposant que les demandes de financement des APA soumises à la 95e réunion seront approuvées en principe, tel qu’indiqué au Tableau 3.

Tableau 3. Engagements à terme (2024-2031) (000 $ US)

| Description | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approuvés en principe | 99 643 | 50 780 | 67 400 | 22 538 | 20 214 | 8 176 | 15 120 | 57 | 283 929 |
| Soumis la 95e réunion | 22 866 | 0 | 0 | 24 773 | 139 | 2 367 | 2 583 | 0 | 52 729 |
| Total | 122 510 | 50 780 | 67 400 | 47 312 | 20 353 | 10 543 | 17 703 | 57 | 336 657 |

# Recommandation

# Le Comité exécutif pourrait envisager de prendre note :

## Du compte rendu sur l’état de la mise en œuvre du plan d’activités général de 2024-2026 du Fonds multilatéral, figurant dans le document UNEP/OzL.Pro/ExCom/95/23;

## Que la valeur totale des activités, comme recommandées à la 95e réunion, s’élève à 116 476 540 $ US (incluant 19 833 551 $ US pour les activités relatives aux HFC; 4 642 176 $ US pour des projets pilotes concernant l’efficacité énergétique conformément à la décision 91/65; 1 170 247 $ US pour les projets concernant l’efficacité énergétique conformément à la décision 94/60; et 2 638 600 $ US pour la préparation d’inventaires nationaux des stocks de substances réglementées indésirables conformément à la décision 91/66), dont 15 899 209 $ US sont associés à des propositions de projets qui ne sont pas incluses dans le plan d’activités de 2024.

Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 95TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Argentina | UNIDO | INV | KIP | Investment project to phase out R-410A in domestic air conditioner manufacturing sector in Argentina | 5,697,593 | 398,832 |
| Bahamas (the) | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 91,000 | 11,830 |
| Bahamas (the) | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 39,000 | 2,730 |
| Barbados | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 130,000 | 16,900 |
| Benin | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 117,500 | 15,275 |
| Benin | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 60,000 | 7,800 |
| Chad | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 141,000 | 18,330 |
| Chad | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 75,000 | 9,750 |
| China | UNDP | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 250,000 | 17,500 |
| Colombia | Germany | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 258,825 | 33,647 |
| Colombia | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 1,066,225 | 74,636 |
| Colombia | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (local installation and assembly subsector) | 341,100 | 23,877 |
| Colombia | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (manufacturing sector) | 1,023,513 | 71,646 |
| Colombia | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 124,148 | 8,690 |
| Cook Islands (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 23,250 | 3,023 |
| Costa Rica | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first trance) | 356,880 | 45,029 |
| Costa Rica | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first trance) (PMU) | 14,088 | 1,778 |
| Guatemala | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 10,000 | 1,300 |
| Guatemala | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 251,019 | 17,571 |
| Indonesia | IBRD | PRP | KIP | Preparation of a KIP investment project in the domestic and stand-alone commercial refrigerator manufacturing sector | 80,000 | 5,600 |
| Kiribati | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 15,000 | 1,950 |
| Lesotho | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 64,000 | 8,320 |
| Lesotho | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 18,000 | 2,340 |
| Marshall Islands (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 11,750 | 1,527 |
| Mauritius | Germany | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 103,000 | 13,390 |
| Micronesia (Federated States of) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 63,500 | 8,255 |
| Morocco | UNIDO | INV | KIP | Conversion of two production lines in one enterprise (MANAR) manufacturing domestic refrigeration equipment from HFC-134a to R-600a | 352,985 | 24,709 |
| Nauru | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 10,500 | 1,365 |
| Nigeria | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 1,902,050 | 133,144 |
| Nigeria | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 130,800 | 17,004 |
| Nigeria | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 705,510 | 49,386 |
| Niue | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 9,250 | 1,202 |
| Oman | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 160,000 | 20,800 |
| Oman | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 30,000 | 2,100 |
| Palau | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 57,500 | 7,475 |
| Rwanda | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 48,400 | 6,292 |
| Rwanda | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 27,500 | 3,575 |
| Samoa | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 66,000 | 8,580 |
| Senegal | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 168,000 | 21,840 |
| Senegal | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 127,500 | 8,925 |
| Solomon Islands | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 74,125 | 9,637 |
| Togo | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 117,500 | 15,275 |
| Togo | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 70,000 | 9,100 |
| Tonga | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 60,750 | 7,898 |
| Türkiye | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 845,445 | 59,181 |
| Türkiye | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 1,943,985 | 136,079 |
| Tuvalu | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 12,250 | 1,592 |
| Uruguay | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 126,927 | 16,500 |
| Uruguay | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 49,860 | 6,482 |
| Vanuatu | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 31,625 | 4,112 |
| Zimbabwe | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 90,000 | 11,700 |
| Zimbabwe | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 151,500 | 19,695 |
| Region: ASP | Australia | INV | KIP | Regional Kigali HFC implementation plan for Pacific Island Countries (stage I, first tranche) | 295,000 | 38,350 |
| Region: ASP | UNEP | TAS | KIP | Regional Kigali HFC implementation plan for Pacific Island Countries (stage I, first tranche) | 247,500 | 32,174 |

Annex II

Pilot projects for energy efficiency (decision 91/65) 
SUBMITTED TO THE 95TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| China | UNDP | INV | EEF | Pilot project to enhance the energy efficiency of cooling technologies in data centres through the demonstration of single-phase immersion cooling system in a data centre (decision 91/65) | 1,790,800 | 125,356 |
| Colombia | UNDP | TAS | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65) | 506,319 | 35,442 |
| Costa Rica | UNDP | INV | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65) | 260,000 | 18,200 |
| Honduras | UNIDO | INV | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65) | 278,068 | 19,465 |
| Malaysia | IBRD | INV | EEF | Pilot project to enhance the energy efficiency of stand-alone commercial refrigeration equipment in Malaysia in the context of the HFC phase-down (investment and non-investment activities) (decisions 91/65) | 500,000 | 35,000 |
| Montenegro | UNIDO | TAS | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65) | 120,000 | 10,800 |
| Peru | UNEP | TAS | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65) | 115,000 | 14,950 |
| Uganda | United Kingdom of Great Britain and Northern Ireland | INV | EEF | Demonstration of energy-efficient ultra-low GWP technology in a supermarket (decision 91/65) | 435,200 | 56,576 |
| Uruguay | UNDP | INV | EEF | Pilot project to maintain and/or enhance the energy efficiency of technologies in the commercial refrigeration and residential AC sectors in the context of HFC phase-down (non-investment activities) (decision 91/65) | 300,000 | 21,000 |

Annex III

projects for energy efficiency PURSUANT TO decision 94/60
SUBMITTED TO THE 95TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Egypt | UNIDO | PRP | EEF | Preparation of a pilot project on energy efficiency (decision 94/60) | 210,000 | 14,700 |
| Malaysia | IBRD | INV | EEF | Pilot project to enhance the energy efficiency of stand-alone commercial refrigeration equipment in Malaysia in the context of the HFC phase-down (investment and non-investment activities) (decisions 94/60) | 415,689 | 29,098 |
| Nigeria | UNIDO | PRP | EEF | Preparation of a pilot project on energy efficiency (decision 94/60) | 78,000 | 5,460 |
| Thailand | IBRD | PRP | EEF | Preparation of a project for enhancing energy efficiency in manufacturing of light commercial air-conditioning (AC) systems in the context of HFC phase-down (decision 94/60) | 150,000 | 10,500 |
| Tunisia | UNIDO | PRP | EEF | Preparation of a pilot project on energy efficiency (decision 94/60) | 20,000 | 1,400 |
| Türkiye | UNIDO | PRP | EEF | Preparation of a pilot project on energy efficiency (decision 94/60) | 220,000 | 15,400 |

Annex IV

Project preparation for national inventories of banks 
of waste-controlled substances (decision 91/66) 
SUBMITTED TO THE 95TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Bahamas (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Bangladesh | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Bhutan | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Brunei Darussalam | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Congo (the) | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Cook Islands (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Eswatini | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Fiji | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Gambia (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Indonesia | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Kiribati | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Madagascar | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Maldives | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Marshall Islands (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Micronesia (Federated States of) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Mongolia | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Nauru | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Nepal | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Niue | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Palau | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Samoa | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Senegal | Germany | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Solomon Islands | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Sri Lanka | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Thailand | IBRD | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Timor-Leste | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Tonga | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Tuvalu | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Uganda | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Vanuatu | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |

UNEP/OzL.Pro/ExCom/95/1

Phase I du PGEH pour le Bhoutan (PNUD et PNUE); phase II des PGEH pour les Îles Cook (PNUE), Kiribati (PNUE), les Îles Marshall (PNUE), Micronésie (États fédérés de) (PNUE), Nauru (PNUE), Nioué (PNUE), Palaos (PNUE), la région des pays insulaires du Pacifique (PIP) (Australie et PNUE), le Samoa (PNUE), les Îles Salomon (PNUE), les Tonga (PNUE), les Tuvalu (PNUE), et le Vanuatu (PNUE); phase III des PGEH pour le Chili (PNUD) et le Mexique (Allemagne); une préparation de projet pour la phase II du PGEH pour la Dominique (ONUDI); trois activités de préparation de projets pour la phase III des PGEH de l’Angola (PNUD) et du Bangladesh (PNUD et PNUE); une préparation de projet pour la phase IV du PGEH du Nigeria (Allemagne); un projet d’investissement du KIP pour l’Argentine (ONUDI); une préparation de projet pour un projet d’investissement du KIP pour l’Indonésie (Banque mondiale); quatre préparations de projets pour la phase I des KIP pour les Bahamas (PNUE et ONUDI), la Barbade (PNUE) et la Chine (PNUD); phase I des KIP pour le Bénin (PNUE et ONUDI), le Tchad (PNUE et ONUDI), le Guatemala (PNUE et ONUDI), Maurice (Allemagne), la région des PIP (Australie et PNUE), le Sénégal (PNUE et ONUDI), et l’Uruguay (PNUD et ONUDI); 16 projets concernant l’efficacité énergétique aux termes de la décision 89/6 pour le Bhoutan (PNUE), les Îles Cook (PNUE), Kiribati (PNUE), les Îles Marshall (PNUE), Micronésie (États fédérés de) (PNUE), Nauru (PNUE), Nioué (PNUE), Palaos (PNUE), la région des PIP (Australie et PNUE), Saint-Vincent-et-les-Grenadines (PNUE), le Samoa (PNUE), les Îles Salomon (PNUE), les Tonga (PNUE), les Tuvalu (PNUE), et le Vanuatu (PNUE); et 28 activités de préparation de projets pour les inventaires nationaux des stocks de substances réglementées indésirables aux termes de la décision 91/66 pour les Bahamas (PNUE), le Bangladesh (ONUDI), le Bhoutan (PNUE), le Brunei Darussalam (PNUE), le Congo (ONUDI), les Îles Cook (PNUE), l’Eswatini (PNUE), les Fidji (PNUE), la Gambie (PNUE), l’Indonésie (PNUD), Kiribati (PNUE), Madagascar (ONUDI), les Îles Marshall (PNUE), Micronésie (États fédérés de) (PNUE), la Mongolie (PNUE), Nauru (PNUE), le Népal (PNUE), Nioué (PNUE), Palaos (PNUE), le Samoa (PNUE), le Sénégal (Allemagne), les Îles Salomon (PNUE), la Thaïlande (Banque mondiale), le Timor-Leste (PNUE), les Tonga (PNUE), les Tuvalu (PNUE), l’Ouganda (PNUE), et le Vanuatu (PNUE).