| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/91/20 21 November 2022 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-first Meeting

Montreal, 5-9 December 2022

Item 8(a) of the provisional agenda

UPDATE ON THE STATUS OF IMPLEMENTATION OF THE 2022-2024 CONSOLIDATED BUSINESS PLAN OF THE MULTILATERAL FUND AND FINANCIAL PLANNING FOR THE TRIENNIUM 2021-2023

- Introduction

# The present document consists of the following sections:

## I.	An update on the status of the implementation of the 2022–2024 business plans

## II.	Financial planning: Resource allocation for the 2021–2023 triennium

III.	Recommendation

## I.	Update on the status of the implementation of the 2022–2024 business plans

# At its 88th meeting, the Executive Committee endorsed the 2022–2024 consolidated business plan of the Multilateral Fund. In response to decision 88/34, the Secretariat adjusted the consolidated 2022–2024 business plan, as shown in table 1.

Table 1. Resource allocation of the adjusted 2022–2024 consolidated business plan of the Multilateral Fund (US $)*

| Description | 2022 | 2023 | 2024 | Total |
| --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 63,931,709 | 57,389,790 | 36,969,548 | 158,291,047 |
| HPMP project preparation (PRP) – stage II | 150,350 | 128,330 | 33,900 | 312,580 |
| HPMP stage II | 5,933,030 | 5,671,633 | 6,094,891 | 17,699,555 |
| HPMP PRP – stage III | 96,300 | 513,600 | 0 | 609,900 |
| HPMP stage III | 8,391,663 | 41,759,745 | 58,150,643 | 108,302,052 |
| HPMP verification** | 588,600 | 588,600 | 588,600 | 1,765,800 |
| HCFC activities subtotal | 79,091,652 | 106,051,699 | 101,837,582 | 286,980,933 |
| HFC activities |  |  |  |  |
| HFC – enabling activities | 0 | 214,000 | 0 | 214,000 |
| HFC – investment | 530,598 | 0 | 0 | 530,598 |
| Kigali HFC implementation plans (KIPs) – PRP | 7,972,750 | 3,716,543 | 0 | 11,689,293 |
| KIPs | 0 | 36,665,672 | 300,000 | 36,965,672 |
| HFC – technical assistance | 678,000 | 0 | 678,000 | 1,356,000 |
| HFC activities subtotal | 9,181,348 | 40,596,215 | 978,000 | 50,755,563 |
| Standard activities |  |  |  |  |
| Institutional strengthening (IS) | 9,783,324 | 11,572,147 | 9,783,324 | 31,138,795 |
| Compliance Assistance Programme (CAP) | 11,427,930 | 11,770,768 | 12,123,891 | 35,322,589 |
| Core unit | 5,952,617 | 5,994,285 | 6,036,246 | 17,983,148 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 6,260,173 | 5,935,637 | 6,063,422 | 18,259,232 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |
| Standard activities subtotal | 33,924,044 | 35,772,837 | 34,506,883 | 104,203,764 |
| Grand total | 122,197,044 | 182,420,752 | 137,322,465 | 441,940,261 |
| Austria | 0 | 783,667 | 0 | 783,667 |
| France | 0 | 671,075 | 0 | 671,075 |
| Germany | 2,392,607 | 1,599,725 | 483,512 | 4,475,844 |
| Japan | 0 | 67,800 | 0 | 67,800 |
| United Kingdom of Great Britain and Northern Ireland (the) | 192,100 | 0 | 0 | 192,100 |
| UNDP | 24,053,719 | 80,749,797 | 58,911,492 | 163,715,008 |
| UNEP | 30,378,110 | 30,479,401 | 25,103,124 | 85,960,635 |
| UNIDO | 24,629,936 | 39,106,803 | 18,600,937 | 82,337,676 |
| World Bank | 33,201,800 | 21,938,246 | 27,071,378 | 82,211,424 |
| HPMP verification** | 588,600 | 588,600 | 588,600 | 1,765,800 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 6,260,173 | 5,935,637 | 6,063,422 | 18,259,232 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |

* Including agency support costs where applicable.

** Funding for the preparation of HPMP verification reports for low-volume-consuming countries is approved by the Executive Committee on an annual basis.

I.1	Status of implementation of the 2022 business plan

# The total funding available for 2022 amounts to US $122,197,044. Of this amount, US $18,554,871 has been approved at the 90th meeting. In addition, activities amounting to US $89,808,338 would be considered at the 91st meeting; if funding for all project proposals submitted as requested are approved, a balance of US $13,833,835 would be available from the 2022 business plan, as shown in table 2.

Table 2. 2022 consolidated business plan, approvals at the 90th meeting, project submissions to the 91st meeting, and balance (US $)*

| Budget items | Total value in business plan | Approvals at the 90th meeting | Activities as requested to the 91st meeting | Balance (above)/below |
| --- | --- | --- | --- | --- |
| Bilateral agencies | 2,584,707 | 721,388 | 2,283,589 | (420,270) |
| UNDP | 24,053,719 | 5,058,472 | 13,931,040 | 5,064,207 |
| UNEP | 30,378,110 | 5,603,434 | 20,155,815 | 4,618,861 |
| UNIDO | 24,629,936 | 7,138,877 | 19,420,888 | (1,929,829) |
| World Bank | 33,201,800 | 0 | 26,688,933 | 6,512,867 |
| HPMP verification | 588,600 | 32,700 | 567,900 | (12,000) |
| Subtotal (agencies) | 115,436,871 | 18,554,871 | 83,048,165 | 13,833,835 |
| Secretariat/Executive Committee/Monitoring and Evaluation (excluding Canadian counterpart) | 6,260,173 | 0 | 6,260,173 | 0 |
| Treasurer | 500,000 | 0 | 500,000 | 0 |
| Subtotal (standard costs) | 6,760,173 | 0 | 6,760,173 | 0 |
| Total | 122,197,044 | 18,554,871 | 89,808,338 | 13,833,835 |

* Including core unit costs.

# The value of project activities as requested to the 91st meeting is US $83,048,165, of which US $18,297,605 is associated with project proposals not included in the 2022 business plan.

# The value of HFC-related activities submitted to the 91st meeting is US $4,829,989, of which US $2,445,565 is associated with project proposals not included in the 2022 business plan. Annex I to the present document lists HFC-related projects submitted by the bilateral and implementing agencies to the 91st meeting.

# Project proposals with a value of US $33,042,681 that were included in the 2022 business plan, were not submitted to the 91st meeting. These proposals have been included in the consolidated business plan of the Multilateral Fund for 2023–2025.

# I.2	Forward commitments

# The total amount for existing forward commitments for multi-year agreements (MYAs) for the period 2022 to 2031 is US $292.31 million, assuming that the funding requests of MYAs submitted to the 91st meeting will be approved in principle, as shown in table 3.

Table 3. Forward commitments (2022–2031) (US $000)

| Description | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approved in principle | 63,663 | 52,145 | 41,385 | 39,783 | 35,452 | 7,869 | 938 | 1,750 | 6,033 | 57 | 249,075 |
| Submitted to the 91st meeting | 15,578 | 0 | 10,669 | 3,301 | 7,343 | 2,321 | 491 | 2,982 | 543 | 0 | 43,229 |
| Total | 79,241 | 52,145 | 52,054 | 43,084 | 42,796 | 10,190 | 1,429 | 4,732 | 6,576 | 57 | 292,305 |

# II.	Financial planning: Resource allocation for the 2021–2023 triennium

# The Secretariat has prepared the financial planning for the triennium 2021–2023 taking into consideration decision Ex.V/1 of the Fifth Extraordinary Meeting of the Parties on the level of replenishment of the Fund, and the commitments and resource availability in the light of expected cash flow during the triennium.

# The resources approved by the Parties to the Montreal Protocol for the 2021–2023 triennium amount to US $540,000,000. Taking into account the approvals in 2021 and at the 90th meeting of US $123,674,574, the submissions to the 91st meeting including Secretariat/Executive Committee and Treasurer costs of US $89,808,338, the remaining resource allocation for 2023 is US $326,517,088.

Table 4. Resource allocation for the 2021–2023 triennium

| Description | Amount (US $) |
| --- | --- |
| Total budget for the 2021-2023 triennium | 540,000,000 |
| 2021 approvals (87th and 88th meetings) including Secretariat/Executive Committee/Monitoring and Evaluation/Treasurer | (105,119,703) |
| 90th meeting approvals | (18,554,871) |
| 91st meeting submissions | (83,048,165) |
| 2022 Secretariat/Executive Committee/Monitoring and Evaluation/Treasurer | (6,760,173) |
| Resources available for 2023 | 326,517,088 |

II.1	Possible factors impacting financial planning and cash flow during the 2021–2023 triennium

# The cash flow of the Multilateral Fund for the 2021–2023 triennium is influenced by several factors, inter alia: receipt of agreed 2021–2023 pledged contributions; payment of contributions in arrears included in the carry-over; interest to be accrued; the loss/gain due to the fixed-exchange rate mechanism (FERM); and the balances returned from cancelled or completed projects. The following paragraphs provide forecasted information for the 2021–2023 triennium based on actual data from 2021 and 2022.

Receipt of agreed pledged contributions

# Based on the rate of pledges received during the 2018–2020 triennium (i.e., 99.1 per cent), of the US $475 million of pledged contribution, US $470.72 million is expected to be received during the 2021-2023 triennium.

Payment of outstanding contributions in arrears included in the carry-over

# The actual carry-over for the 2021–2023 triennium is US $65 million including US $153,334 of outstanding contributions expected to be collected.

Potential interest accrued during the 2021–2023 triennium

# Based on the cash balance in 2021 and 2022 and using the average interest collected for 2021 and up to 3 November 2022, it might be expected that the interest accrued during the 2021–2023 triennium would amount to US $310,825.

# Gains/losses due to the FERM

# In 2021, the US dollar was weakened against most other currencies and the FERM gain was US $4,820,982; however, in 2022, the US dollar has strengthened against most other currencies and the FERM loss was US $2,958,396, hence net gain of US $1,862,586 as at 3 November 2022. In 2023, the situation might change and a conservative estimate of the 2021–2023 triennium will be a net loss of US $600,000.

# Potential balances returned from cancelled or completed projects

# It is difficult to calculate the potential total funds associated with the return of balances from cancelled or completed projects during the 2021–2023 triennium. The funds and interests returned for 2021 was US $15,796,272 and US $3,480,090 for the 90th meeting. US $12.67 million was expected to be returned for funds and interests at the 91st meeting. Bilateral and implementing agencies are strongly encouraged to immediately return all the balances for those projects which have been operationally completed or cancelled.

# III.	Recommendation

# The Executive Committee may wish to note:

## The update on the status of implementation of the 2022–2024 consolidated business plan of the Multilateral Fund as contained in document UNEP/OzL.Pro/ExCom/91/20; and

## That the total value of activities as requested to the 91st meeting amounts to US $83,048,165 (including US $4,829,989 for HFC-related activities), of which US $18,297,605 is associated with project proposals not included in the 2022 business plan.

Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 91ST MEETING

| Country | Agency | Type | Sector | Project title | Amount requested (US $) | Support costs requested (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Bosnia and Herzegovina | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan | 130,000 | 9,100 |
| Cabo Verde | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan | 130,000 | 16,900 |
| Comoros (the) | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan | 100,000 | 13,000 |
| Congo (the) | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan | 51,000 | 6,630 |
| Congo (the) | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan | 119,000 | 8,330 |
| Cote d’Ivoire | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan | 133,000 | 17,290 |
| Cote d’Ivoire | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan | 57,000 | 3,990 |
| Ecuador | UNIDO | INV | REF | Conversion project for the phase-down of HFC-134a in the manufacturing of domestic and commercial refrigerators at the enterprise INDUGLOB | 328,935 | 24,670 |
| Gabon | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan | 133,000 | 17,290 |
| Gabon | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan | 57,000 | 3,990 |
| Guinea-Bissau | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan | 91,000 | 11,830 |
| Guinea-Bissau | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan | 39,000 | 2,730 |
| Malaysia | IBRD | PRP | KIP | Preparation of HFC investment project in mobile air-conditioning sector | 30,000 | 2,100 |
| Malaysia | IBRD | PRP | KIP | Preparation of HFC investment projects in fire fighting sector | 150,000 | 10,500 |
| Malaysia | IBRD | PRP | KIP | Preparation of HFC investment projects in refrigeration sector | 80,000 | 5,600 |
| Mongolia | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan | 130,000 | 16,900 |
| Morocco | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan | 190,000 | 13,300 |
| Niger (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 84,500 | 10,985 |
| Niger (the) | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 113,500 | 7,945 |
| Philippines (the) | UNDP | PRP | KIP | Preparation of a Kigali HFC implementation plan | 220,000 | 15,400 |
| Saint Lucia | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan | 90,000 | 11,700 |
| Saint Lucia | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan | 40,000 | 2,800 |
| United Republic of Tanzania (the) | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan | 91,000 | 11,830 |
| United Republic of Tanzania (the) | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan | 39,000 | 2,730 |
| Zimbabwe | UNDP | PRP | KIP | Preparation of a Kigali HFC implementation plan | 51,000 | 3,570 |
| Zimbabwe | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan | 119,000 | 15,470 |
| Region: ASP | UNEP | PRP | KIP | Regional Kigali HFC implementation plan for 12 Pacific Island Countries: Cook Islands, Kiribati, Marshall Islands, Federated States of Micronesia, Nauru, Niue, Palau, Samoa, Solomon Islands, Tonga, Tuvalu and Vanuatu (Overarching) | 780,000 | 95,800 |
| Global | UNEP | TAS | SEV | Twinning of Ozone Officers and National Energy Efficiency Policymakers to support Kigali Amendment objectives | 793,400 | 97,274 |

UNEP/OzL.Pro/ExCom/91/1

Project preparation for stage II of the HPMP for Haiti (UNDP) and stage III of the HPMPs for Mexico (UNIDO) and Viet Nam (World Bank); tranches of the HPMPs for Barbados (UNDP), India (Germany, UNDP and UNEP), Morocco (UNIDO) and  Syrian Arab Republic (UNIDO); KIP preparation for investment projects for Malaysia (World Bank); KIP project preparation activities for the Congo (UNEP and UNIDO), Morocco (UNIDO), the Philippines (UNDP), Pacific Island Countries region (UNEP), Saint Lucia (UNIDO) and Zimbabwe (UNDP); KIP for the Niger (UNEP and UNIDO); HFC investment project for Ecuador (UNIDO); energy efficiency project for Maldives (UNEP); and institutional strengthening for Belize (UNEP) and Mexico (UNIDO).

These activities include: 65 HCFC-related activities for 33 countries (US $25.3 million), 38 HFC-related activities for 29 countries (US $4.77 million) and 21 IS activities (US $2.98 million).

UNEP/OzL.Pro/ExCom/91/22