| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/88/24 25 October 2021 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Eighty-eighth Meeting

Montreal, 15-19 November 2021

UNDP BUSINESS PLAN FOR 2022–2024

# This document presents the UNDP business plan for 2022–2024 and includes: the planned activities for the phase-out of controlled substances under the Montreal Protocol (controlled substances) during the 2022–2024 period; the business plan performance indicators; policy issues; and a recommendation for consideration by the Executive Committee. The narrative of UNDP’s business plan for 2022–2024 is attached to the present document.

Planned activities during the 2022–2024 period

# Table 1 sets out, by year, the value of activities included in UNDP’s business plan.

Table 1. Resource allocation in the UNDP business plan for 2022–2024 as submitted (US $000s)*

| Description | 2022 | 2023 | 2024 | Total (2022–2024) | Total after 2024 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 9,598 | 16,945 | 1,682 | 28,225 | 22,592 |
| HPMP project preparation (PRP) – stage II | 10 | 0 | 0 | 10 | 0 |
| HPMP stage II | 278 | 84 | 184 | 547 | 1,034 |
| HPMP stage III | 4,929 | 29,677 | 52,334 | 86,940 | 4,609 |
| HCFC activities subtotal | 14,815 | 46,706 | 54,200 | 115,721 | 28,236 |
| HFC activities |  |  |  |  |  |
| Kigali HFC implementation plan (KIP) – PRP | 938 | 691 | 0 | 1,629 | 0 |
| KIPs | 0 | 26,240 | 0 | 26,240 | 19,577 |
| HFC activities subtotal | 938 | 26,932 | 0 | 27,870 | 19,577 |
| Standard activities |  |  |  |  |  |
| Institutional strengthening (IS) | 2,069 | 4,317 | 2,069 | 8,456 | 0 |
| Core unit | 2,143 | 2,158 | 2,173 | 6,474 | 0 |
| Standard activities subtotal | 4,212 | 6,475 | 4,242 | 14,930 | 0 |
| Total | 19,966 | 80,112 | 58,442 | 158,520 | 47,813 |

* Including agency support costs where applicable.

# Secretariat’s comments

# Stage II of HPMPs

# The total levels of funding for stage II of HPMPs for low-volume-consuming (LVC) countries to meet the 67.5 per cent reduction of the HCFC baseline amount to US $171,461 (including US $84,261 for 2022–2024), and to US $1.41 million (including US $462,557 for 2022–2024) to meet a 100 per cent reduction.

# Stage III of HPMPs

# A total of US $91.55 million is included in the business plan for stage III of the HPMPs for 10 countries (Brazil, Colombia, India, Indonesia, Islamic Republic of Iran, Lebanon, Malaysia, Mexico, Nigeria, and the Republic of Moldova) (including US $86.94 million for 2022–2024).

HFC-related activities

# HFC activities include KIP project preparation activities for 16 countries amounting to US $1.63 million in 2022–2023; and KIPs for 28 countries amounting to US $45.82 million (including US $26.24 million in 2022–2024).

# Eleven of the 16 countries for which KIP project preparation activities have been included have not ratified the Kigali Amendment. Two of the 11 countries have not submitted the required letter from their Government indicating their intent to make best efforts to ratify the Kigali Amendment. One of the 28 countries for which KIPs have been included in the business plan has not ratified the Kigali Amendment.

# Core unit costs

# The core unit costs are expected to increase at an annual rate of 0.7 per cent as agreed.

Proposed adjustments by the Secretariat

# The adjustments to the UNDP business plan for 2022–2024 were based on relevant decisions of the Executive Committee. Further adjustments may be required pending a decision by the Parties on the level of the replenishment of the Multilateral Fund for the 2021–2023 triennium.

# In reviewing the revised UNDP business plan for 2022–2024, the Secretariat noted that the following adjustments were not included:

Table 2. Adjustments to the UNDP business plan for 2022–2024 (US $000)

| Adjustment | 2022–2024 | After 2024 |
| --- | --- | --- |
| HPMP values to reflect the actual amounts approved under the Agreements including tranches of HPMPs that are due but not submitted to the 88th meeting | 2,833 | 0 |
| PRP for KIPs pursuant to decision 84/46(f) or decision 87/50, or that have been submitted to the 88th meeting | (439) | 0 |
| KIPs pursuant to decision 84/46(g) | (275) | (412) |
| IS that have been submitted to the 88th meeting but subsequently withdrawn | 204 | 0 |

# Table 3 presents the results of the Secretariat’s proposed adjustments to the UNDP business plan for 2022–2024, which are also addressed in the context of the Consolidated business plan of the Multilateral Fund for 2022–2024.

Table 3. Resource allocation in UNDP’s adjusted business plan for 2022–2024 (US $000s)*

| Description | 2022 | 2023 | 2024 | Total (2022–2024) | Total after 2024 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 11,027 | 18,349 | 1,682 | 31,058 | 22,592 |
| HPMP project preparation (PRP) – stage II | 10 | 0 | 0 | 10 | 0 |
| HPMP stage II | 278 | 84 | 184 | 547 | 1,034 |
| HPMP stage III | 4,929 | 29,677 | 52,334 | 86,940 | 4,609 |
| HCFC activities subtotal | 16,244 | 48,110 | 54,200 | 118,554 | 28,236 |
| HFC activities |  |  |  |  |  |
| KIP – PRP | 723 | 467 | 0 | 1,190 | 0 |
| KIPs | 0 | 25,966 | 0 | 25,966 | 19,165 |
| HFC activities subtotal | 723 | 26,433 | 0 | 27,156 | 19,165 |
| Standard activities |  |  |  |  |  |
| IS | 2,274 | 4,113 | 2,274 | 8,660 | 0 |
| Core unit | 2,143 | 2,158 | 2,173 | 6,474 | 0 |
| Standard activities subtotal | 4,416 | 6,271 | 4,447 | 15,134 | 0 |
| Total | 21,384 | 80,813 | 58,647 | 160,844 | 47,401 |

* Including agency support costs where applicable.

Performance indicators

# UNDP submitted performance indicators pursuant to decision 71/28 in its business plan narrative. The Secretariat informed UNDP of the targets shown in Table 4.

Table 4. Performance indicators for UNDP for 2022

| Type of indicator | Short title | Calculation | 2022 target |
| --- | --- | --- | --- |
| Planning--Approval | Tranches approved | Number of tranches approved vs. those planned* | 14 |
| Planning--Approval | Projects/activities approved | Number of projects/activities approved vs. those planned (including project preparation activities)** | 20 |
| Implementation | Funds disbursed | Based on estimated disbursement in progress report | US $22,523,448 |
| Implementation | ODS phase-out | ODS phase-out for the tranche when the next tranche is approved vs. those planned per business plans* | 216.0 ODP tonnes |
| Implementation | Project completion for activities | Project completion vs. planned in progress reports for all activities (excluding project preparation) | 40 |
| Administrative | Speed of financial completion | The extent to which projects are financially completed 12 months after project completion | 70% |
| Administrative | Timely submission of project completion reports | Timely submission of project completion reports vs. those agreed | On time (6) |
| Administrative | Timely submission of progress reports | Timely submission of progress reports and business plans and responses unless otherwise agreed | On time |

* The target of an agency would be reduced if it could not submit a tranche owing to another lead or cooperating agency, if agreed by that agency.

** Project preparation should not be assessed if the Executive Committee has not taken a decision on its funding.

RECOMMENDATION

# The Executive Committee may wish:

## To note the UNDP business plan for 2022–2024, contained in document UNEP/OzL.Pro/ExCom/88/24; and

## To approve the performance indicators for UNDP as set out in Table 4 of document UNEP/OzL.Pro/ExCom/88/24.

Online meetings and an intersessional approval process will be held in November and December 2021 due to coronavirus disease (COVID-19).

Given the constraints imposed by the COVID-19 pandemic, the Secretariat’s comments on the initial submission of the UNDP business plan for 2022–2024 were addressed through bilateral discussions and numerous exchanges of electronic messages. All issues were satisfactorily addressed.

Inclusion of stage III of HPMPs in the business plan is allowed only for those countries with an approved stage II of HPMPs with reduction targets below the 2025 compliance targets, in line with decision 84/46(e).

Funding for the preparation of national implementation plans to meet initial reduction obligations for the phase-down of HFCs could be provided, at the earliest, five years prior to those obligations, after a country had ratified the Kigali Amendment and on the basis of guidelines to be approved in the future (decision 79/46(b)(iii)). In addition, HFC phase-down preparation activities could be included in the business plan for countries that had not ratified the Kigali Amendment but had submitted a letter indicating their Government’s intent to make best efforts to ratify the Kigali Amendment (decision 84/46(f)). The guidelines for the preparation of KIPs were approved at the 87th meeting (decision 87/50).

KIPs are allowed inclusion of such plans in the business plan only for countries that had ratified the Kigali Amendment (decision 84/46(g)).

UNDP’s 2022 core unit costs have been submitted to the 88th meeting (UNEP/OzL.Pro/ExCom/88/35).

In the absence of a decision by the Parties on the level of the replenishment of the Multilateral Fund for the 2021-2023 triennium, and in light of decision XXXII/1, the indicative budget for resource allocation of the business plan for 2022–2024 was assumed at the same level of the replenishment of the 2018–2020 triennium. This issue is discussed in the consolidated 2022-2024 business plan of the Multilateral Fund (UNEP/OzL.Pro/ExCom/88/22).

UNEP/OzL.Pro/ExCom/88/22