| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/90/11 2 June 2022 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninetieth Meeting

Montreal, 20-23 June 2022

Item 8(a) of the provisional agenda

UPDATE ON THE STATUS OF IMPLEMENTATION OF

THE 2022–2024 CONSOLIDATED BUSINESS PLAN OF THE MULTILATERAL FUND

- Introduction

# This document consists of:

## Part I:		An update on the status of the implementation of the 2022–2024 business plans

## Part II:		Resource allocation for the 2018–2020 triennium

## Part III:		Reports on dialogues concerning qualitative performance indicators

Recommendation

Annex I:	HFC-related activities submitted to the 90th meeting

## I.	Update on the status of the implementation of the 2022–2024 business plans

# At its 88th meeting, the Executive Committee endorsed the 2022–2024 consolidated business plan of the Multilateral Fund. In response to decision 88/34, the Secretariat adjusted the consolidated 2022–2024 business plan, as shown in Table 1.

Table 1. Resource allocation of the adjusted 2022–2024 consolidated business plans of the Multilateral Fund (US $)

| Description | 2022 | 2023 | 2024 | Total |
| --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 63,931,709 | 57,389,790 | 36,969,548 | 158,291,047 |
| HPMP project preparation (PRP) – stage II | 150,350 | 128,330 | 33,900 | 312,580 |
| HPMP stage II | 5,933,030 | 5,671,633 | 6,094,891 | 17,699,555 |
| HPMP PRP – stage III | 96,300 | 513,600 | 0 | 609,900 |
| HPMP stage III | 8,391,663 | 41,759,745 | 58,150,643 | 108,302,052 |
| HPMP verification* | 588,600 | 588,600 | 588,600 | 1,765,800 |
| HCFC activities subtotal | 79,091,652 | 106,051,699 | 101,837,582 | 286,980,933 |
| HFC activities |  |  |  |  |
| HFC – enabling activities | 0 | 214,000 | 0 | 214,000 |
| HFC – investment | 530,598 | 0 | 0 | 530,598 |
| Kigali HFC implementation plans (KIPs) – PRP | 7,972,750 | 3,716,543 | 0 | 11,689,293 |
| KIPs | 0 | 36,665,672 | 300,000 | 36,965,672 |
| HFC – technical assistance | 678,000 | 0 | 678,000 | 1,356,000 |
| HFC activities subtotal | 9,181,348 | 40,596,215 | 978,000 | 50,755,563 |
| Standard activities |  |  |  |  |
| Institutional strengthening (IS) | 9,783,324 | 11,572,147 | 9,783,324 | 31,138,795 |
| Compliance Assistance Programme (CAP) | 11,427,930 | 11,770,768 | 12,123,891 | 35,322,589 |
| Core unit | 5,952,617 | 5,994,285 | 6,036,246 | 17,983,148 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 6,260,173 | 5,935,637 | 6,063,422 | 18,259,232 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |
| Standard activities subtotal | 33,924,044 | 35,772,837 | 34,506,883 | 104,203,764 |
| Grand total | 122,197,044 | 182,420,752 | 137,322,465 | 441,940,261 |
| Austria | 0 | 783,667 | 0 | 783,667 |
| France | 0 | 671,075 | 0 | 671,075 |
| Germany | 2,392,607 | 1,599,725 | 483,512 | 4,475,844 |
| Japan | 0 | 67,800 | 0 | 67,800 |
| United Kingdom of Great Britain and Northern Ireland (the) | 192,100 | 0 | 0 | 192,100 |
| UNDP | 24,053,719 | 80,749,797 | 58,911,492 | 163,715,008 |
| UNEP | 30,378,110 | 30,479,401 | 25,103,124 | 85,960,635 |
| UNIDO | 24,629,936 | 39,106,803 | 18,600,937 | 82,337,676 |
| World Bank | 33,201,800 | 21,938,246 | 27,071,378 | 82,211,424 |
| HPMP verification* | 588,600 | 588,600 | 588,600 | 1,765,800 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 6,260,173 | 5,935,637 | 6,063,422 | 18,259,232 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |

* Funding for the preparation of HPMP verification reports for low-volume-consuming countries is approved by the Executive Committee on an annual basis.

Status of implementation of the 2022 business plans

# Table 2 sets out the submissions by agency to the 90th meeting (as at 2 June 2022), and the balance of funds from projects in the 2022 business plans.

Table 2. 2022 consolidated business plan, projects recommended to the 90th meeting, and balance (US $)*

| Budget items | Total value in business plan | Activities reviewed/ recommended to the 90h meeting | Balance (above)/below |
| --- | --- | --- | --- |
| Bilateral agencies | 2,584,707 | 721,388 | 1,863,319 |
| UNDP | 24,053,719 | 5,058,472 | 18,995,247 |
| UNEP | 30,378,110 | 5,603,434 | 24,774,676 |
| UNIDO | 24,629,936 | 7,134,286 | 17,495,650 |
| World Bank | 33,201,800 | 0 | 33,201,800 |
| HPMP verification | 588,600 | 32,700 | 555,900 |
| Subtotal (agencies) | 115,436,871 | 18,550,280 | 96,886,591 |
| Secretariat/Executive Committee/Monitoring and Evaluation (excluding Canadian counterpart) | 6,260,173 | 0 | 6,260,173 |
| Treasurer | 500,000 | 0 | 500,000 |
| Subtotal (standard costs) | 6,760,173 | 0 | 6,760,173 |
| Total | 122,197,044 | 18,550,280 | 103,646,764 |

* Including core unit costs.

# The value of project proposals reviewed/recommended to the 90th meeting of US $18,550,280 is US $1,807,866 above its value in the 2022 business plan, including US $1,043,745 associated with project proposals not included in the 2022 business plan.

# The value of HFC-related activities submitted to the 90th meeting is US $2,872,500 of which US $635,540 is associated with project proposals not included in the 2022 business plan. Annex I to the present document lists HFC-related projects submitted by the implementing agencies to the 90th meeting.

# Forward commitments

# The total amount for existing forward commitments for multi-year agreements (MYAs) for the period 2022 to 2031 is US $256.33 million, assuming that the funding requests of MYAs submitted to the 90th meeting will be approved in principle, as shown in Table 3.

Table 3. Forward commitments (2022–2031) (US $000)

| Description | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approved in principle | 63,147 | 56,587 | 38,252 | 36,843 | 33,860 | 5,565 | 784 | 1,750 | 4,308 | 57 | 241,153 |
| Submitted to 90th meeting | 5,192 | 0 | 1,945 | 2,413 | 1,593 | 2,157 | 154 | 824 | 900 | 0 | 15,179 |
| Total | 68,340 | 56,587 | 40,197 | 39,257 | 35,452 | 7,722 | 938 | 2,574 | 5,208 | 57 | 256,332 |

## II. 	Resource allocation for the 2018–2020 triennium

# The resources approved by the Parties to the Montreal Protocol for the 2018–2020 triennium amount to US $540,000,000. Taking into account the total funding approvals in 2018, 2019, 2020 and 2021, balances returned, interest accrued, paid contributions from non-Article 5 Parties, the gain/loss of the fixed exchange rate mechanism, and the Secretariat/Executive Committee/Treasurer expenditures, the cash available as of 5 May 2022 is US $423,783,701.

# In addition, taking into account net funds transferred of US $14,654,407 at the 87th meeting and US $67,647,037 at the 88th meeting and the cash contributions in 2021 and 2022, the carry-over for the 2018–2020 triennium would be US $302,111,760, as shown in Table 4.

Table 4. Resource allocation for the 2018–2020 triennium

| Description |  | Amount (US $) |
| --- | --- | --- |
| Funds available as of 5 May 2022 | a | 423,783,701 |
| Funding of projects approved at the 87th meeting | b | 20,885,937 |
| Balances/interest returned at the 87th meeting | c | 6,231,530 |
| Net funds transferred to bilateral and implementing agencies for the 87th meeting | d=b-c | 14,654,407 |
| Funding of projects approved at the 88th meeting | e | 77,188,892 |
| Balances/interest returned at the 88th meeting | f | 9,541,855 |
| Net funds transferred to bilateral and implementing agencies for the 88th meeting | g=e-f | 67,647,037 |
| Funds available for the 2021–2023 triennium | h=a+d+g | 506,085,145 |
| Cash contributions in 2021 and 2022 | i | 203,011,596 |
| Interest earned 2021–2022 | j | 961,789 |
| Carry-over | k=h-i-j | 302,111,760 |

III.	Reports on dialogues concerning qualitative performance indicators

# At the 88th meeting, UNIDO was requested to inter alia have an open and constructive discussion with the national ozone unit (NOU) in Iraq with respect to the assessment of its qualitative performance and to report to the 90th meeting on the outcome of the discussion (decision 88/8(b)).

# In line with the decision, UNIDO has initiated dialogues and consultations with the Government of Iraq and reported that communication with the NOU has improved and is more frequent. UNIDO has regular contacts with the NOU on the implementation of the projects. This has enabled UNIDO to implement activities even under tight deadlines.

# Recommendation

# The Executive Committee may wish to note:

## The update on the status of implementation of the 2022–2024 consolidated business plan of the Multilateral Fund as contained in document UNEP/OzL.Pro/ExCom/90/11;

## That the total value of activities submitted to the 90th meeting amounts to US $18,550,280 (including US $2,872,500 for HFC-related activities), of which US $1,043,745 is associated with project proposals not included in the 2022 business plan; and

## With appreciation, the report provided by UNIDO on the outcome of its discussion with the Government of Iraq on the issues raised in the assessment of its qualitative performance, in line with decision 88/8(b).

Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 90TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US$) | Support costs recommended (US$) |
| --- | --- | --- | --- | --- | --- | --- |
| Bangladesh | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan | 40,000 | 5,200 |
| Bangladesh | UNDP | PRP | PHA | Preparation of Kigali HFC implementation plan | 150,000 | 10,500 |
| Benin | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan | 133,000 | 17,290 |
| Benin | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan | 57,000 | 3,990 |
| Botswana | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan | 119,000 | 15,470 |
| Botswana | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan | 51,000 | 3,570 |
| Chad | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan | 119,000 | 15,470 |
| Chad | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan | 51,000 | 3,570 |
| Ethiopia | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan | 91,000 | 11,830 |
| Ethiopia | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan | 39,000 | 2,730 |
| Gambia (the) | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan | 91,000 | 11,830 |
| Gambia (the) | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan | 39,000 | 2,730 |
| Guinea (the) | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan | 133,000 | 17,290 |
| Guinea | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan | 57,000 | 3,990 |
| Honduras | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan | 170,000 | 11,900 |
| Mexico | UNDP | PRP | FOA | Preparation for HFC investment projects in the foam sector | 80,000 | 5,600 |
| Mexico | UNDP | PRP | REF | Preparation for replacement of HFC-134a with HC-290 refrigerant in the manufacturing of commercial refrigerators at Friocima | 30,000 | 2,100 |
| Mozambique | UNDP | PRP | PHA | Preparation of a Kigali HFC implementation plan | 51,000 | 3,570 |
| Mozambique | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan | 119,000 | 15,470 |
| Sao Tome and Principe | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan | 130,000 | 16,900 |
| Serbia | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan | 55,000 | 7,150 |
| Serbia | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan | 115,000 | 8,050 |
| Seychelles | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan | 81,000 | 10,530 |
| Seychelles | Germany | PRP | PHA | Preparation of Kigali HFC implementation plan | 49,000 | 6,370 |
| Somalia | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan | 51,000 | 6,630 |
| Somalia | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan | 119,000 | 8,330 |
| Togo | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan | 119,000 | 15,470 |
| Togo | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan | 51,000 | 3,570 |
| Turkey | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan | 120,000 | 8,400 |
| Turkey | UNDP | PRP | PHA | Preparation of Kigali HFC implementation plan | 100,000 | 7,000 |

UNEP/OzL.Pro/ExCom/90/1

Stage II of the HPMP for Grenada (UNIDO); KIP preparation projects for Honduras (UNIDO), Mozambique (UNDP and UNEP) and Seychelles (Germany and UNEP); two HFC investment preparation projects for Mexico (UNDP); and institutional strengthening projects for Haiti (UNDP) and Panama (UNDP).

Decision XXIX/1