UNEP/OzL.Pro/ExCom/84/29
   20 November 2019

UNEP BUSINESS PLAN FOR 2020–2022

# This document presents the UNEP business plan for 2020–2022 and includes: the planned activities for the phase-out of controlled substances under the Montreal Protocol (controlled substances) during the 2020–2022 period; the business plan performance indicators; policy issues; and a recommendation for consideration by the Executive Committee. The narrative of UNEP’s business plan for 2020–2022 is attached to the present document.

Planned activities during 2020–2022

# Table 1 sets out, by year, the value of activities included in UNEP’s business plan.

Table 1. Resource allocation in the UNEP business plan for 2020–2022 as submitted (US $000s)*

|  | 2020 | 2021 | 2022 | Total (2020–2022) | Total after 2022 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 7,915 | 4,481 | 3,947 | 16,343 | 1,024 |
| HPMP stage I | 150 |  | 150 | 300 | 0 |
| HPMP project preparation (PRP) – stage II | 175 | 107 | 0 | 283 | 34 |
| HPMP stage II | 5,596 | 2,729 | 1,002 | 9,327 | 16,582 |
| HPMP PRP – stage III | 268 | 0 | 0 | 268 | 0 |
| HPMP stage III | 51 | 97 | 0 | 149 | 97 |
| HCFC technical assistance | 509 | 0 | 0 | 509 | 0 |
| HCFC activities subtotal | 14,664 | 7,415 | 5,099 | 27,178 | 17,737 |
| HFC activities |  |  |  |  |  |
| HFC – enabling activities | 214 | 262 | 0 | 476 | 0 |
| HFC phase-down – PRP | 2,995 | 198 | 0 | 3,192 | 0 |
| HFC activities subtotal | 3,209 | 460 | 0 | 3,668 | 0 |
| Standard activities |  |  |  |  |  |
| Institutional strengthening (IS) | 6,447 | 5,216 | 6,447 | 18,109 | 0 |
| Compliance Assistance Programme (CAP) | 11,428 | 11,771 | 12,124 | 35,324 | 0 |
| Standard activities subtotal | 17,875 | 16,987 | 18,571 | 53,433 | 0 |
| Grand total | 35,748 | 24,861 | 23,670 | 84,279 | 17,737 |

* Including agency support costs where applicable.

# Secretariat’s comments

Stage I of HPMPs

# A total of US $300,000 is included in UNEP’s 2020–2022 business plan for Syrian Arab Republic. However, its stage I of HPMP has not yet been approved and it has not been submitted to the 84th meeting.

Stage II of HPMPs

# The total levels of funding for stage II of HPMPs in low-volume-consuming (LVC) countries to meet the 67.5 per cent reduction of the HCFC baseline amount to US $9.41 million (including US $3.42 million for 2020–2022), and to meet a 100 per cent reduction amount to US $7.32 million (including US $3.08 million for 2020–2022).

# The total levels of funding for stage II of HPMPs in non-LVC countries amount to US $9.18 million including US $2.84 million for 2020–2022.

# Stage III of HPMPs

# A total of US $245,764 is included in the business plan for stage III of HPMPs for three countries (Armenia, the Dominican Republic and the Republic of Moldova) (including US $148,523 for 2020–2022) in line with decision 82/45(c)(i).

# HCFC technical assistance regional project

# UNEP has included one HCFC technical assistance regional project for “promoting low-global warming potential refrigerants for air-conditioning sectors in high ambient temperature countries (PRAHA-III),” amounting to US $508,500 in 2020. No funding window for such demonstration project is available.

HFC-related activities

# HFC activities include enabling activities amounting to US $476,150 in 2020 for four countries (Antigua and Barbuda, the Central African Republic, Guinea and Haiti) and HFC phase-down preparation activities for 37 countries amounting to US $3.19 million in 2020 and 2021.

# Regarding enabling activities, one of the four countries (Haiti) has this activity submitted to the 84th meeting by another implementing agency. Activities for the remaining three countries were submitted with the required letter from their Government indicating their intent to make best efforts to ratify the Kigali Amendment as early as possible, if they have not done so, in line with decision 79/46(d)(i).

# Regarding the preparation activities, funding for the preparation of national implementation plans to meet initial reduction obligations for the phase-down of HFCs could be provided, at the earliest, five years prior to those obligations, after a country had ratified the Kigali Amendment and on the basis of guidelines to be approved in the future (decision 79/46(b)(iii)). Of the 37 countries, only two countries have not ratified the Kigali Amendment, but have submitted the required letters from their Governments indicating their intent to make best efforts to ratify the Kigali Amendment.

CAP

# The cost for CAP is expected to increase at an annual rate of 3 per cent as agreed. The total level of funding for CAP is US $35.32 million for 2020–2022. UNEP submitted its CAP budget for 2020 for consideration at the 84th meeting.

Proposed adjustments by the Secretariat

# During the IACM, adjustments to the business plans of bilateral and implementing agencies were agreed based on relevant decisions of the Executive Committee. In reviewing the revised UNEP business plan for 2020–2022, the Secretariat noted that the following adjustments were not included:

Table 2. Adjustments to the UNEP business plan for 2020–2022 (US $000)

| Adjustment | 2020–2022 | After 2022 |
| --- | --- | --- |
| HPMP values to reflect the actual amounts approved under the Agreements | (111) | 64 |
| Stage II of HPMPs in non-LVC countries with the refrigeration servicing sector based on a maximum cost-effectiveness of US $4.80/kg | (0.4) | (390) |
| Stage II of HPMPs in LVC countries to the maximum allowable value to meet the 67.5 or 100 per cent reduction in the HCFC baseline based on decision 74/50(c)(xii) | (0.7) | (0.4) |
| HCFC technical assistance | (509) | 0 |
| Enabling activities submitted to the 84th meeting | (102) | 0 |
| PRP for HFC phase-down pursuant to decision 56/16(c) or countries that have not ratified the Kigali Amendment | (202) | 0 |
| IS project for the Democratic People’s Republic of Korea pursuant to decision 80/34(c)(iii)b. | (333) | 0 |

# Table 3 presents the results of the Secretariat’s proposed adjustments to the UNEP business plan for 2020–2022, which are also addressed in the context of the Consolidated business plan of the Multilateral Fund for 2020–2022.

Table 3. Resource allocation in UNEP’s adjusted business plan for 2020–2022 (US $000s)*

|  | 2020 | 2021 | 2022 | Total (2020–2022) | Total after 2022 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HPMPs | 7,729 | 4,481 | 4,021 | 16,232 | 1,088 |
| HPMP stage I | 150 |  | 150 | 300 | 0 |
| HPMP PRP – stage II | 175 | 107 | 0 | 283 | 34 |
| HPMP stage II | 5,595 | 2,729 | 1,002 | 9,326 | 16,191 |
| HPMP PRP – stage III | 268 | 0 | 0 | 268 | 0 |
| HPMP stage III | 51 | 97 | 0 | 149 | 97 |
| HCFC technical assistance | 0 | 0 | 0 | 0 | 0 |
| HCFC activities subtotal | 13,969 | 7,414 | 5,173 | 26,557 | 17,411 |
| HFC activities |  |  |  |  |  |
| HFC – enabling activities | 214 | 161 | 0 | 375 | 0 |
| HFC phase-down – PRP | 2,844 | 147 | 0 | 2,991 | 0 |
| HFC activities subtotal | 3,058 | 308 | 0 | 3,366 | 0 |
| Standard activities |  |  |  |  |  |
| IS | 6,280 | 5,216 | 6,280 | 17,776 | 0 |
| CAP | 11,428 | 11,771 | 12,124 | 35,324 | 0 |
| Standard activities subtotal | 17,709 | 16,987 | 18,405 | 53,100 | 0 |
| Grand total | 34,736 | 24,708 | 23,578 | 83,022 | 17,411 |

* Including agency support cost where applicable.

Performance indicators

# UNEP submitted performance indicators pursuant to decision 71/28 in its business plan narrative. The Secretariat informed UNEP of the targets shown in Table 4.

Table 4. Performance indicators for UNEP for 2020

| Type of indicator | Short title | Calculation | 2020 target |
| --- | --- | --- | --- |
| Planning--Approval | Tranches approved | Number of tranches approved vs. those planned* | 135 |
| Planning--Approval | Projects/activities approved | Number of projects/activities approved vs. those planned (including project preparation activities)** | 99 |
| Implementation | Funds disbursed | Based on estimated disbursement in progress report | US $20,994,167 |
| Implementation | ODS phase-out | ODS phase-out for the tranche when the next tranche is approved vs. those planned per business plans | 198.14 ODP tonnes |
| Implementation | Project completion for activities | Project completion vs. planned in progress reports for all activities (excluding project preparation) | 130 |
| Administrative | Speed of financial completion | The extent to which projects are financially completed 12 months after project completion | 14 months |
| Administrative | Timely submission of project completion reports | Timely submission of project completion reports vs. those agreed | 15 |
| Administrative | Timely submission of progress reports | Timely submission of progress reports and business plans and responses unless otherwise agreed | On time |

* The target of an agency would be reduced if it could not submit a tranche owing to another cooperating or lead agency, if agreed by that agency.

** Project preparation should not be assessed if the Executive Committee has not taken a decision on its funding.

# Table 5 presents UNEP’s performance indicators for its CAP, which were adopted in decision 48/7(e).

Table 5: Performance indicators for UNEP’s CAP for 2020

| Performance Indicator | Data | Assessment | 2020 target |
| --- | --- | --- | --- |
| Efficient follow-up to regional network/ thematic meetings | List of recommendations emanating from 2018-2019 regional network/thematic meetings | Implementation rate of those meeting recommendations that are to be implemented in 2020 | 90% implementation rate |
| Effective support to NOUs in their work, particularly guidance to new NOUs | List of innovative ways/means/products/ services for supporting NOUs in their work, with specification of those destined for new NOUs | Number of innovative ways, means, products, services for supporting NOUs in their work, with specification of those destined for new NOUs | - 7 such ways, means, products, services; -All new NOUs receive capacity building support. |
| Assistance to countries in actual or potential noncompliance (as per MOP decisions and/or as per reported Article 7 data and trend analysis) | List of countries in actual or potential on compliance that received CAP assistance outside the network meetings | Number of countries in actual or potential non-compliance that received CAP assistance outside the network meetings | All such countries |
| Innovations in production and delivery of global and regional information products and services | List of global and regional information products and services destined for new target audiences or that reach existing target audiences in new ways | Number of global and regional information products and services destined for new target audiences or that reach existing target audiences in new ways | 7 such products and services |
| Close cooperation between CAP regional teams and Implementing and bilateral agencies working in the regions | List of joint missions/ undertakings of CAP regional staff with Implementing and bilateral agencies | Number of joint missions/undertakings | 2 in each region |

Policy issues

# UNEP seeks guidance from the Executive Committee about the eligibility and guidelines for the preparation of HFC phase-down national implementation plans.

RECOMMENDATION

# The Executive Committee may wish:

## To note the UNEP business plan for 2020–2022, contained in document UNEP/OzL.Pro/ExCom/84/29; and

## To approve the performance indicators for UNEP as set out in Tables 4 and 5 of document UNEP/OzL.Pro/ExCom/84/29.

A draft business plan for 2020–2022 of UNEP was discussed at the Inter-agency coordination meeting (IACM) held in Montreal from 9 to 11 October 2019. The business plan contained in this document has addressed the issues raised at the meeting.

Funding was approved for the country for the phase-out of 12.9 ODP tonnes of HCFC in the refrigeration and air-conditioning sector as a stand-alone project outside its HPMP, representing 9.6 per cent of the baseline.

UNEP/OzL.Pro/ExCom/84/37

UNEP/OzL.Pro/ExCom/84/26