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CONSOLIDATED PROGRESS REPORT AS AT 31 DECEMBER 2017

The consolidated progress report summarises progress and financial information provided by bilateral and implementing agencies[footnoteRef:1] as of 31 December 2017, in their respective progress reports[footnoteRef:2] submitted to the Secretariat.  [1:  Progress reports were submitted by the following agencies: Australia, France, Germany, Italy, Japan, the Russian Federation, Spain, UNDP, UNEP, UNIDO and the World Bank.]  [2:  The Executive Committee requested that detailed information on a project-by-project basis be made available to Committee members, with a printout available upon request (decision 19/23). The database for the Consolidated Progress Report is provided on the Executive Committee’s intranet in the spreadsheet programme, Microsoft Excel.] 

Scope of the document

This document consists of the following parts:
Part I:	Projects approved under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2017 and cumulative since 1991; it contains a review on the status of implementation of each ongoing[footnoteRef:3] project at the country level; and it identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee. [3:  Ongoing projects are all projects that were under implementation as at 31 December 2017. Key indicators of progress include: percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.
] 

Part II:	Projects approved under the additional voluntary contributions for HFC activities and the status of implementation.
General recommendation.

This document also contains the following annex:
Annex I: 	An analysis of the consolidated progress report.

PART I: 	PROJECTS APPROVED UNDER THE REGULAR CONTRIBUTIONS TO THE     MULTILATERAL FUND

The Secretariat reviewed each of the annual progress reports submitted by bilateral and implementing agencies separately. The review was based on the milestones established for investment and non-investment projects including, inter alia, signing of agreements; date of release of first disbursement; status of procurement and installation of equipment; status on services provided, including training of refrigeration technicians and customs officers; level of disbursement of approved funds; the operational and financial completion of the project; and the return of funds balances. 
During the review process, potential issues were identified, inter alia, cases where agreements had not been signed; national ozone officer not in place; lack of financial progress reports; delayed procurement process; lack of availability of alternative technologies in local markets; security related issues at the country level. All projects with issues had low disbursement rates of approved funds and/or required an extension of planned completion dates. 
To further understand the issues identified, the Secretariat had bilateral exchanges with bilateral and implementing agencies, and resolved several of them satisfactorily. For those projects where the issues could not be resolved, recommendations for consideration by the Executive Committee were proposed. The lists of projects with issues are contained in Annex I of each progress report of bilateral and implementing agencies, which includes a description on the status of implementation; the outstanding issues; and recommendations, which were discussed and agreed with the relevant bilateral or implementing agencies. The recommendations included in each of the progress reports submitted by bilateral and implementing agencies will be considered during the discussions of each agency progress report at the 82nd meeting.
The progress reports of bilateral or implementing agencies did not include any policy issue for consideration by the Executive Committee. Also, no policy issues were identified during the review process of the progress reports by the Secretariat. 
Summary of progress in implementation of projects for 2017 and cumulative

Implementation of projects and activities by bilateral and implementing agencies for 2017 and cumulative since 1991 up to 31 December 2017 is summarized as follows: 
Phase-out: In 2017, 1,455.1 ODP tonnes of consumption were phased out and an additional 261.6 ODP tonnes of consumption were approved for phase-out. Since 1991, 286,176 ODP tonnes of consumption and 204,189 ODP tonnes of production had been phased out of an expected total of 465,791 ODP tonnes from projects approved (excluding cancelled and transferred projects);
(a) Disbursements/approvals: In 2017, US $115.82 million was disbursed and US $110.51 million was planned for disbursement based on the 2016 progress report representing a rate of disbursement of 105 per cent of that planned. Cumulatively, US $2.91 billion had been disbursed out of the total US $3.16 billion approved for disbursement (excluding agency support costs). This represents a rate of disbursement of 92 per cent. In 2017, US $68.37 million was approved for implementation;
(b) Cost-effectiveness (in ODP): Since 1991, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $9.67/kg. The cost-effectiveness for the production sector was US $4.42/kg. The average cost‑effectiveness of investment projects per ODP tonne was US $4.23/kg for completed projects and US $71.30/kg for ongoing projects;[footnoteRef:4] [4:  The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies. The cost-effectiveness for multi-year agreements (MYAs of HCFC phase-out management plan (HPMP)) is US $92.71/kg ODP and for stage I of HCFC production phase-out management plan (HPPMP) is US $23.93/kg ODP. ] 

Number of projects completed: In 2017, 396 projects were completed. Since 1991, 7,197projects of the 7,930 projects (excluding closed or transferred projects) financed by the Multilateral Fund were completed. This represents a completion rate of 91 per cent;
(c) Speed of delivery – investment projects: Projects that were completed in 2017 were completed on average 49 months after their approval. Since 1991, the average time for completion of investment projects has been 36 months after their approval. First disbursements under these projects occurred, on average, 14 months after they had been approved;
(d) Speed of delivery – non-investment projects: Projects that were completed in 2017 were completed on average 39 months after their approval. Since 1991, the average time for completion of non-investment projects has been 37 months after their approval. First disbursements under these projects occurred, on average, 11 months after they had been approved; 
(e) Project preparation: Of the 1,610 project preparation activities approved by the end of 2017, 1,569 have been completed. In 2017, two project preparation activities were approved and 41 were completed, leaving 41 ongoing;
(f) Implementation delays: There were a total of 269 ongoing investment projects under implementation at the end of 2017. These projects, on average, are experiencing a delay of 26 months. However, projects classified as “projects with implementation delays” that are subject to the procedures of project cancellation amount to four (as project preparation, multi‑year agreements (MYAs) and institutional strengthening (IS) are not subject to those procedures); and
(g) MYAs: In 2017, bilateral and implementing agencies were implementing two MYAs for ODS phase-out plans, two MYAs for methyl bromide (MB) consumption, one MYA for MB production, 174 MYAs for HPMPs and one MYA for the HPPMP in China. Since 1991, 364 MYAs have been approved and 184 MYAs have been completed. 
Project implementation progress in 2017

Based on planned completion dates reported in the 2016 progress report, and the results reported in the 2017 progress reports, bilateral and implementing agencies completed 59 per cent of the projects they had planned to complete in 2017 and achieve 33 per cent of the total phase-out target. Given that 294 of the 525 ongoing projects (excluding IS and project preparation) have been delayed since the 2016 progress report, additional status reports have been requested to address all impediments that caused the delays. 
Bilateral and implementing agencies achieved an overall rate of disbursement of 105 per cent in 2017. On a country/region basis, 97 countries (including regions) had a disbursement rate of over 85 per while 24 countries (including regions) had a disbursement rate of below 50 per cent. 
In total, bilateral and implementing agencies are requested to report to the 83rd meeting on 100 ongoing projects or tranches with outstanding issues.
Appendix I to Annex I provides information on project implementation on a country basis in 2017, and Appendix II to Annex I summarizes the total funding approved and disbursed for HPMP activities at the country level.
SECRETARIAT COMMENTS
The Secretariat noted that in some of the HPMPs, activities are implemented beyond the project completion dates contained in the Agreement between the government concerned and the Executive Committee and/or as decided by the Executive Committee; in such cases, the Secretariat reminded bilateral and implementing agencies that in line with decision 77/8(l), any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments should be made before the extension is approved.
The Secretariat also noted that in certain cases where two phases of IS projects are ongoing (decision 77/8(i)), the previous phase was ongoing for more than two years after the approval of the current phase; in light of this, the previous phase should be closed within two years after the approval of the current phase. Further, given the importance of continued operations of IS project for smooth and effective implementation of Montreal Protocol at national level, information on IS projects not submitted for two years or more should be submitted to the Executive Committee. These measures will ensure need-based and sustainable funding.
PART II:	PROJECTS APPROVED UNDER THE ADDITIONAL VOLUNTARY CONTRIBUTIONS FOR HFC ACTIVITIES
In 2017, the Executive Committee had approved 79 HFC-related projects under the additional voluntary contributions amounting to US $11.67 million (excluding agency support costs). A summary of the status of these projects is presented in Table 1. 
Table 1. HFC-related projects approved in 2017
	Type
	Number of projects
	Funding (US $)*

	
	Approved
	Completed
	% completed
	Approved
	Disbursed
	Balance
	% disbursed

	Investment
	1
	0
	0
	3,131,610
	0
	3,131,610
	0

	Project preparation
	9
	0
	0
	270,000
	9,800
	260,200
	4

	Technical assistance - Enabling activities
	69
	0
	0
	8,270,000
	30,000
	8,240,000
	0

	Total
	79
	0
	0
	11,671,610
	39,800
	11,631,810
	0


*Excludes agency support costs. 

General recommendation

The Executive Committee may wish: 
To note:
The consolidated progress report of the Multilateral Fund as at 31 December 2017 contained in document UNEP/OzL.Pro/ExCom/82/14; 
With appreciation, the efforts undertaken by bilateral and implementing agencies in reporting the 2017 activities; and
That the bilateral and implementing agencies would report to the 83rd meeting on four projects with implementation delays and 100 ongoing projects or tranches recommended for additional status reports, as contained in Annex I of each individual progress report of bilateral and implementing agencies;
To remind bilateral and implementing agencies that in line with decision 77/8(l), any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments should be made before the extension is approved;
To request bilateral and implementing agencies:
To return balances of the previous phase of institutional strengthening (IS) projects where two phases are ongoing, no later than two years from the approval of the current phase, in line with decision 77/8(i); and
To provide an update on all countries where renewal of IS projects was not submitted for two years prior to the last meeting of every year.
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Pre-session documents of the Executive Committee of the Multilateral Fund for the Implementation of the Montreal Protocol are without prejudice to any decision that the Executive Committee might take following issuance of the document.
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Annex I

ANALYSIS OF THE CONSOLIDATED PROGRESS REPORT OF THE MULTILATERAL FUND AS AT 31 DECEMBER 2017

1. This Annex consists of the following two parts:
Part I:	Projects approved under the regular contributions to the Multilateral Fund.
Part II:	Projects approved under the additional voluntary contributions for HFC activities.
PART I: 	PROJECTS APPROVED UNDER THE REGULAR CONTRIBUTIONS TO THE     MULTILATERAL FUND

1. As of 31 December 2017, the Executive Committee had approved US $3.52 billion[footnoteRef:5] to bilateral and implementing agencies as shown in Table 1. In 2017, 127 new projects and activities were approved. This level of funding is expected to result in the phase-out of 465,791 ODP tonnes of ODS consumption and production. [5:  An additional US $122.68 million has been approved for the meetings of the Executive Committee, the operation of the Secretariat, and the Treasurer fees.] 

Table 1. Approved funding by sector and agency as at 31 December 2017
	Sector
	Approved funding (US $)

	
	UNDP
	UNEP
	UNIDO
	World Bank
	Bilateral
	Total

	Aerosol
	26,054,838
	882,689
	34,413,700
	22,984,030
	2,051,914
	86,387,171

	Destruction
	3,607,085
	232,200
	5,005,764
	400,000
	1,789,410
	11,034,459

	Fire fighting
	50,000
	0
	0
	0
	0
	50,000

	Foam
	173,568,025
	0
	88,967,004
	136,426,742
	8,095,338
	407,057,109

	Halon
	4,996,975
	767,640
	1,780,369
	70,221,038
	6,147,361
	83,913,384

	Fumigants
	20,081,243
	2,614,366
	78,092,525
	5,837,887
	18,230,946
	124,856,966

	Multiple sectors
	0
	0
	139,440
	2,341,168
	0
	2,480,608

	Other
	0
	0
	11,317,246
	5,059,360
	0
	16,376,606

	Phase-out plan
	292,035,855
	47,941,392
	300,110,322
	200,033,936
	57,531,878
	897,653,384

	Process agent
	1,286,923
	0
	6,337,359
	114,342,497
	0
	121,966,779

	Production
	1,056,000
	0
	50,515,326
	359,729,770
	10,000,000
	421,301,096

	Refrigeration
	137,487,947
	13,926,555
	180,640,788
	180,543,076
	40,243,785
	552,842,151

	Several
	58,007,316
	228,035,168
	15,932,021
	28,337,410
	4,469,718
	334,781,633

	Solvents
	63,699,998
	198,860
	23,247,443
	10,237,394
	2,512,738
	99,896,433

	Sterilant
	417,628
	0
	0
	661,227
	0
	1,078,855

	Sub-total
	782,349,834
	294,598,870
	796,499,307
	1,137,155,535
	151,073,088
	3,161,676,633

	Agency support costs
	105,664,706
	24,792,253
	102,606,340
	113,849,560
	14,218,639
	361,131,499

	Total
	888,014,540
	319,391,123
	899,105,647
	1,251,005,095
	165,291,727
	3,522,808,132



A summary of the status of projects, by category, is presented in Table 2. 
Table 2. Status of project implementation by category
	Type
	Number of projects*
	Funding (US $)**

	
	Approved
	Completed
	% completed
	Approved
	Disbursed
	Balance
	% disbursed

	Country programme
	165
	165
	100
	7,266,559
	7,266,559
	0
	100

	Demonstration
	136
	113
	83
	64,094,165
	53,675,333
	10,418,832
	84

	Institutional strengthening
	1,138
	971
	85
	130,101,798
	110,079,177
	20,022,620
	85

	Investment
	2,957
	2,688
	91
	2,542,200,184
	2,365,374,325
	176,825,859
	93

	Project preparation
	1,610
	1,569
	97
	83,583,997
	81,569,882
	2,014,114
	98

	Technical assistance
	1,600
	1,367
	85
	308,623,168
	262,373,361
	46,249,807
	85

	Training projects
	324
	324
	100
	25,806,764
	25,806,763
	1
	100

	Total
	7,930
	7,197
	91
	3,161,676,633
	2,906,145,400
	255,531,233
	92


*Excludes closed and transferred projects.
** Excludes agency support costs. 

Table 3 presents an overview of status of project implementation by year.[footnoteRef:6] Of the US $3.16 billion approved, US $2.91 billion has been disbursed (including US $115.82 million disbursed in 2017). All projects and activities approved between 1991 and the end of 2005 have now been completed. Approved projects (investment and non-investment) have resulted in the phase-out of 490,365 ODP[footnoteRef:7] tonnes of consumption and production. As of 31 December 2017, investment projects representing around US $1.98 billion have been completed, resulting in the permanent phase-out of 468,128 ODP tonnes with an overall cost‑effectiveness of US $4.23/kg ODP phased out.  [6:  The data is presented according to the year when a project was approved. It treats all approvals (investment and non‑investment projects) equally (i.e., an investment project or annual funding tranche of an MYA of US $1 million is considered one project as is a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP phased out, and percentage of funds disbursed. ]  [7:  Total phased out for the Fund includes 468,128 ODP tonnes from completed investment projects, 14,286 ODP tonnes from completed non-investment projects and 7,951 ODP tonnes from ongoing projects.] 

Table 3. Status of project implementation by year
	Year
	Number of projects*
	Funding (US$)**

	
	Approved
	Completed
	% completed
	Approved
	Disbursed
	Balance
	% disbursed

	1991
	68
	68
	100
	7,950,771
	7,950,771
	0
	100

	1992
	176
	176
	100
	41,261,376
	41,261,376
	0
	100

	1993
	217
	217
	100
	73,198,586
	73,198,586
	0
	100

	1994
	379
	379
	100
	128,630,289
	128,630,290
	-1
	100

	1995
	355
	355
	100
	111,188,308
	111,188,308
	0
	100

	1996
	257
	257
	100
	83,813,027
	83,813,027
	0
	100

	1997
	532
	532
	100
	154,314,938
	154,314,940
	-2
	100

	1998
	422
	422
	100
	99,680,368
	99,680,367
	1
	100

	1999
	546
	546
	100
	152,710,735
	152,710,736
	-1
	100

	2000
	426
	426
	100
	109,540,524
	109,540,522
	2
	100

	2001
	427
	427
	100
	130,139,751
	130,139,751
	0
	100

	2002
	358
	358
	100
	162,045,816
	162,045,815
	1
	100

	2003
	247
	247
	100
	157,043,468
	157,043,468
	0
	100

	2004
	271
	271
	100
	162,388,009
	162,388,008
	1
	100

	2005
	255
	255
	100
	181,090,090
	180,276,022
	814,068
	100

	2006
	261
	260
	100
	120,946,659
	120,470,506
	476,153
	100

	2007
	213
	213
	100
	120,179,787
	119,849,798
	329,989
	100

	2008
	355
	351
	99
	121,942,254
	121,470,731
	471,524
	100

	2009
	321
	316
	98
	73,885,449
	72,770,238
	1,115,210
	98

	2010
	229
	215
	94
	85,288,120
	81,495,990
	3,792,130
	96

	2011
	265
	240
	91
	202,661,299
	193,592,453
	9,068,846
	96

	2012
	184
	132
	72
	102,808,443
	86,902,836
	15,905,607
	85

	2013
	185
	145
	78
	126,185,691
	116,607,611
	9,578,080
	92

	2014
	228
	156
	68
	95,863,653
	81,130,707
	14,732,946
	85

	2015
	381
	214
	56
	168,650,695
	118,748,475
	49,902,221
	70

	2016
	245
	15
	6
	119,897,363
	37,387,391
	82,509,972
	31

	2017
	127
	4
	3
	68,371,165
	1,536,677
	66,834,488
	2

	Total
	7,930
	7,197
	91
	3,161,676,633
	2,906,145,400
	255,531,233
	92


*Excludes closed and transferred projects.
** Excludes agency support costs. 

COMPLETED PROJECTS[footnoteRef:8] [8:  Completed projects/activities are defined in decisions 17/22 and 19/23 as projects that have been commissioned and where the ODS addressed has been phased out. A further decision (decision 28/2) extends the definition to cover situations where no further use of CFCs in the sectors covered is in evidence, where an alternative product is being produced (and/or production has begun), and where the equipment using CFCs has been destroyed/dismantled/rendered unusable with respect to ODSs. Work programme activities without an ODS phase‑out are considered completed when the activity is finished (e.g., for a workshop, when it has been conducted). This definition has been applied for HCFC-related projects. ] 


Overall, 99.8 per cent of the funds approved for completed investment projects have been disbursed.[footnoteRef:9]  [9:  The reason that 100 per cent of funds have not been disbursed for completed projects is that it may take from six months to one year to finalise accounting records.] 

Completed investment projects

Table 4 presents information on investment projects that have been completed since 1991. The table presents the data in total, followed by data according to region, sector, implementation characteristics, and disbursement method.
Table 4. Cumulative completed investment projects
	Item
	Number 
of 
projects
	Approved funds plus adjustment
(US $)
	Per cent of funds disbursed
	Consumption (ODP phased out*)
	Production (ODP phased out*)
	Average 
number
 of months from approval to 
first 
disbursement
	Average number of months from approval to completion
	Overall cost-effectiveness
to the Fund (US $/kg)

	TOTAL
	2,688
	1,978,781,653
	100
	266,852
	201,277
	14
	36
	4.23 

	Region
	
	
	
	
	
	
	
	 

	Africa
	446
	146,500,609
	99
	17,931
	0
	12
	37
	8.17 

	Asia & Pacific
	1,451
	1,396,424,561
	100
	207,396
	181,327
	16
	36
	3.59 

	Europe
	138
	62,708,914
	100
	7,744
	175
	11
	33
	7.92 

	Latin America and Caribbean
	653
	373,147,570
	100
	33,780
	19,775
	14
	36
	6.97 

	Global
	n/a
	0
	0
	0
	0
	n/a
	n/a
	n/a

	Sector
	
	
	
	
	
	
	
	 

	Aerosol
	125
	63,118,299
	100
	26,967
	0
	16
	41
	2.34 

	Destruction
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a

	Fire fighting
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a

	Foam
	1,001
	368,732,332
	100
	69,207
	0
	15
	34
	5.33 

	Fumigants
	120
	98,487,872
	100
	7,721
	0
	10
	48
	12.76 

	Halon
	39
	71,476,177
	100
	42,111
	41,958
	17
	30
	0.85 

	Multiple sectors
	4
	2,287,376
	100
	419
	0
	28
	78
	5.46 

	Other
	8
	16,059,360
	100
	1,574
	0
	12
	20
	10.20 

	Phase-out plan
	561
	360,210,712
	99
	47,778
	10,988
	12
	38
	6.13 

	Process agent
	30
	120,252,627
	100
	19,573
	52,162
	10
	27
	1.68 

	Production
	58
	347,142,580
	100
	0
	96,169
	9
	18
	3.61 

	Refrigeration
	611
	435,588,659
	100
	44,156
	0
	16
	40
	9.86 

	Solvents
	128
	94,351,804
	100
	7,285
	0
	19
	32
	12.95 

	Sterilant
	3
	1,073,855
	100
	60
	0
	15
	34
	17.78 

	Implementation characteristics

	Agency implementation
	1,692
	732,057,590
	100
	92,515
	17,381
	11
	34
	6.66 

	National implementation
	996
	1,246,724,063
	100
	174,337
	183,896
	21
	40
	3.48 

	Disbursement method 

	During implementation
	2,595
	1,885,696,458
	100
	262,136
	199,719
	14
	37
	4.08 

	After implementation
	50
	17,166,608
	100
	2,512
	0
	23
	25
	6.83 

	Retroactive funding
	37
	14,638,587
	100
	2,100
	500
	15
	11
	5.63 

	Country to final beneficiaries
	6
	61,280,000
	100
	103
	1,058
	9
	31
	52.76 


*Excludes closed and transferred projects.

Completed non-investment projects

Table 5 presents data on cumulative completed non-investment projects. Since 1991, 2,940 non‑investment projects have been completed at a total value of US $436.10 million. 
Table 5. Cumulative completed non-investment projects
	Item
	Number of projects
	Approved funds plus adjustment (US $)
	Per cent of funds disbursed
	Average number of months from approval to first disbursement
	Average number
of months from approval to completion

	TOTAL
	2,940
	436,101,261
	98
	11
	37

	Region
	
	
	
	
	 

	Africa
	855
	75,089,049
	98
	11
	38

	Asia & Pacific
	885
	126,742,145
	98
	13
	39

	Europe
	198
	19,269,193
	95
	9
	34

	Latin America and Caribbean
	708
	82,609,062
	98
	13
	40

	Global
	294
	132,391,812
	98
	6
	23

	Sector
	
	
	
	
	 

	Aerosol
	31
	2,461,265
	100
	11
	36

	Destruction
	13
	6,231,383
	84
	11
	60

	Fire fighting
	0
	0
	0
	n/a
	n/a

	Foam
	28
	9,322,219
	100
	14
	36

	Fumigants
	135
	20,782,526
	100
	9
	39

	Halon
	82
	11,238,157
	100
	17
	44

	Multiple sectors
	1
	53,792
	100
	56
	58

	Other
	1
	76,499
	100
	7
	38

	Phase-out plan
	368
	34,677,174
	95
	12
	39

	Process agent
	0
	0
	0
	n/a
	n/a

	Production
	1
	40,000
	100
	4
	4

	Refrigeration
	624
	86,187,825
	100
	16
	50

	Several
	1,622
	261,631,641
	98
	9
	31

	Solvents
	34
	3,398,781
	100
	11
	27

	Sterilant
	0
	0
	0
	n/a
	n/a

	Implementation characteristics
	
	
	
	
	 

	Agency implementation
	2,395
	328,310,076
	98
	11
	36

	National implementation
	545
	107,791,185
	99
	15
	42

	Disbursement method
	
	
	
	
	 

	During implementation
	2,908
	425,719,966
	98
	11
	37

	After implementation
	26
	2,325,462
	100
	14
	21

	Retroactive funding
	1
	146,698
	100
	3
	83

	Country to final beneficiaries
	5
	7,909,135
	100
	6
	44



The average time from approval to first disbursement for non-investment projects is 11 months. Non-investment projects have been completed, on average, 37 months after they were approved. This figure is influenced by the large number of projects (1,622 of 2,940) in the sector called “several”, which had an average time from approval to completion of 31 months. Non‑investment projects in the other sectors were completed between 4 and 60 months after they had been approved.
Almost all projects were implemented by the agency concerned rather than through national implementation. Agency implementation of non-investment projects normally does not require legal agreements, which may explain the shorter period of time (36 months) compared with nationally‑implemented non-investment projects (42 months). 
ONGOING PROJECTS

Ongoing investment projects

Table 6 presents information on the status of investment projects under implementation by region, sector, and implementation characteristics.
Table 6. Cumulative ongoing investment projects
	Item
	Number 
of 
projects
	Approved funds plus adjustment (US $)
	Per cent of funds disbursed
	Number of projects disbursing
	Per cent of projects disbursing
	Average number of months from approval to first disbursement
	Average number of months from approval to planned completion
	Average length of delay in project planned completion
	Overall cost-effective-ness to the Fund (US$/kg.)*

	TOTAL
	269
	548,703,077
	69
	193
	72
	10
	54
	26
	71.30 

	Region
	
	
	
	
	
	
	
	
	 

	Africa
	78
	34,532,328
	40
	51
	65
	9
	55
	20
	60.39 

	Asia & Pacific
	116
	466,451,571
	73
	90
	78
	12
	59
	37
	77.98 

	Europe
	15
	11,852,691
	66
	11
	73
	10
	47
	24
	32.70 

	Latin America and Caribbean
	60
	35,866,487
	38
	41
	68
	8
	45
	14
	45.98 

	Global
	0
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a

	Sector
	
	
	
	
	
	
	
	
	 

	Aerosol
	2
	19,399,000
	97
	2
	100
	7
	135
	86
	40.25 

	Destruction
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a
	n/a

	Fire fighting
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a
	n/a

	Foam
	5
	11,392,615
	85
	5
	100
	33
	95
	72
	39.57 

	Fumigants
	3
	1,457,759
	81
	3
	100
	8
	71
	47
	5.38 

	Halon
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a
	n/a

	Multiple sectors
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a
	n/a

	Other
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a
	n/a

	Phase-out plan
	253
	440,036,761
	62
	177
	70
	10
	52
	23
	68.24 

	Process agent
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a
	n/a

	Production
	4
	72,790,000
	100
	4
	100
	5
	46
	31
	n/a

	Refrigeration
	2
	3,626,942
	64
	2
	100
	7
	115
	88
	17.56 

	Solvents
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a
	n/a

	Sterilant
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a
	n/a

	Implementation characteristics 

	Agency implementation
	173
	261,241,321
	63
	130
	75
	9
	58
	27
	50.72 

	National implementation
	96
	287,461,756
	73
	63
	66
	11
	48
	26
	112.92 

	Disbursement method

	During implementation
	242
	198,178,786
	43
	168
	69
	10
	54
	25
	36.28 

	After implementation
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a
	n/a

	Country to final beneficiaries
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a
	n/a

	During implementation
	27
	350,524,291
	83
	25
	93
	9
	55
	34
	156.88 


*Based on the ODS to be phased out according to the proposal.

There are currently 269 investment projects under implementation at a total value of over US $548.70 million. Around 69 per cent of the funds have already been disbursed. The overall average cost-effectiveness of ongoing investment projects is US $71.30/kg ODP to be phased out. The average number of months from approval to first disbursement is 10 months. The average duration of an ongoing investment project is 54 months. Typically, ongoing investment projects are completed 26 months later than originally planned, which could be considered the average delay.
Ongoing non-investment projects

Table 7 presents information on the status of non-investment projects under implementation by region, sector, and implementation characteristic.
Table 7. Cumulative ongoing non-investment projects
	Item
	Number
of
projects
	Approved funds plus adjustment (US $)
	Per cent
of funds disbursed
	Number of projects disbursing
	Per cent
of projects disbursing
	Average number of months from approval to first disbursement
	Average number of months from approval to planned completion
	Average length of
delay in project planned completion

	TOTAL
	423
	98,506,222
	32
	236
	56
	13
	42
	14

	Region
	
	
	
	
	
	
	 
	 

	Africa
	146
	14,005,154
	23
	75
	51
	11
	38
	12

	Asia & Pacific
	147
	36,852,567
	20
	85
	58
	14
	47
	16

	Europe
	18
	2,554,152
	32
	13
	72
	9
	34
	4

	Latin America and Caribbean
	102
	15,337,371
	29
	58
	57
	14
	45
	16

	Global
	10
	29,756,978
	51
	5
	50
	5
	28
	11

	Sector
	
	
	
	
	
	
	 
	 

	Aerosol
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a

	Destruction
	4
	3,720,799
	39
	4
	100
	11
	77
	45

	Fire fighting
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a

	Foam
	6
	1,494,880
	20
	5
	83
	10
	29
	13

	Fumigants
	2
	464,090
	58
	2
	100
	10
	37
	9

	Halon
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a

	Multiple sectors
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a

	Other
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a

	Phase-out plan
	216
	34,291,054
	22
	129
	60
	14
	48
	16

	Process agent
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a

	Production
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a

	Refrigeration
	17
	7,580,041
	27
	12
	71
	9
	33
	10

	Several
	178
	50,955,358
	38
	84
	47
	11
	35
	11

	Solvents
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a

	Sterilant
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a

	Implementation characteristics 

	Agency implementation
	348
	70,940,426
	32
	187
	54
	13
	43
	14

	National implementation
	75
	27,565,796
	30
	49
	65
	12
	39
	11

	Disbursement method

	During implementation
	421
	96,980,207
	31
	234
	56
	13
	42
	14

	After implementation
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a

	Retroactive funding
	0
	0
	0
	0
	0
	n/a
	n/a
	n/a

	Country to final beneficiaries
	2
	1,526,015
	70
	2
	100
	8
	25
	4



There are currently 423 non-investment projects under implementation at a total value of US $98.51 million, with 32 per cent of the funds already disbursed. The average number of months from approval to first disbursement is 13 months. On average, ongoing non-investment projects are completed 42 months from the date of approval, which represents a delay of 14 months. 
CLOSED PROJECTS

Table 8 presents a summary of closed projects. 
Table 8. Closed projects summary
	Agency
	Number of projects
	Approved funding (US $)
	Adjustments (US S)
	Approved funding plus adjustment (US $)
	Funds disbursed (US $)
	Consumption ODP to be phased out
	Consumption ODP phased out 

	UNDP
	79
	17,127,886
	-10,226,042
	6,901,844
	6,895,392
	671
	636

	UNEP
	7
	824,500
	-803,500
	21,000
	21,000
	0
	0

	UNIDO
	59
	11,560,710
	-7,027,415
	4,533,295
	4,533,295
	1,123
	338

	World Bank
	95
	31,176,550
	-29,803,031
	1,373,519
	1,373,519
	657
	581

	Bilateral
	15
	1,399,323
	-921,422
	477,901
	227,901
	221
	0

	Total
	255
	62,088,969
	-48,781,410
	13,307,559
	13,051,107
	2,671
	1,555


PART II:	PROJECTS APPROVED UNDER THE ADDITIONAL VOLUNTARY CONTRIBUTIONS FOR HFC ACTIVITIES
In 2017, the Executive Committee had approved 79 HFC-related projects under the additional voluntary contributions amounting to US $11.67 million (excluding agency support costs). A summary of the status of these projects is presented in Table 9. 
Table 9. HFC-related projects approved in 2017
	Type
	Number of projects
	Funding (US $)*

	
	Approved
	Completed
	% completed
	Approved
	Disbursed
	Balance
	% disbursed

	Investment
	1
	0
	0
	3,131,610
	0
	3,131,610
	0

	Project preparation
	9
	0
	0
	270,000
	9,800
	260,200
	4

	Technical assistance - Enabling activities
	69
	0
	0
	8,270,000
	30,000
	8,240,000
	0

	Total
	79
	0
	0
	11,671,610
	39,800
	11,631,810
	0


*Excludes agency support costs. 
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Appendix I

PROJECT IMPLEMENTATION IN 2017 BY COUNTRY

	Country
	Phased out in 2017
	Percentage of planned phase-out achieved in 2017
	Estimated funds disbursed in 2017 (US$)
	Funds disbursed in 2017 (US$)
	Percentage of funds disbursed over estimation in 2017
	Percentage of planned projects completed in 2017

	Afghanistan
	0.0
	0
	96,154
	315,435
	328
	75

	Albania
	0.0
	 
	54,135
	103,642
	191
	100

	Algeria
	13.5
	100
	876,422
	16,494
	2
	40

	Angola
	1.6
	 
	89,735
	252,779
	282
	100

	Antigua and Barbuda
	0.0
	 
	14,881
	2,626
	18
	25

	Argentina
	0.0
	 
	546,646
	1,739,960
	318
	83

	Armenia
	0.0
	 
	96,919
	117,766
	122
	80

	Bahamas (the)
	0.0
	0
	24,328
	121,383
	499
	100

	Bahrain
	0.0
	0
	305,600
	413,119
	135
	50

	Bangladesh
	0.6
	100
	161,766
	194,754
	120
	33

	Barbados
	0.0
	[bookmark: _GoBack] 
	41,985
	58,438
	139
	75

	Belize
	0.2
	 
	12,140
	69,936
	576
	100

	Benin
	0.0
	0
	46,039
	212,481
	462
	100

	Bhutan
	0.0
	0
	37,193
	91,222
	245
	67

	Bolivia (Plurinational State of)
	0.0
	 
	46,898
	98,975
	211
	100

	Bosnia and Herzegovina
	0.0
	 
	94,682
	64,019
	68
	100

	Botswana
	0.0
	 
	38,853
	17,409
	45
	50

	Brazil
	44.7
	23
	6,089,142
	4,819,527
	79
	30

	Brunei Darussalam
	0.0
	0
	34,625
	7,100
	21
	20

	Burkina Faso
	0.0
	 
	15,278
	146,744
	960
	100

	Burundi
	0.4
	 
	63,501
	184,500
	291
	20

	Cabo Verde
	0.0
	 
	25,776
	62,730
	243
	75

	Cambodia
	0.6
	100
	60,861
	175,110
	288
	75

	Cameroon
	2.0
	100
	222,626
	362,926
	163
	100

	Central African Republic (the)
	0.0
	 
	12,001
	0
	0
	0

	Chad
	2.4
	 
	81,126
	288,155
	355
	100

	Chile
	2.6
	11
	875,519
	994,755
	114
	67

	China
	293.5
	30
	43,355,694
	56,569,915
	130
	42

	Colombia
	0.0
	0
	1,617,021
	1,126,867
	70
	17

	Comoros (the)
	0.0
	 
	55,497
	209,833
	378
	100

	Congo (the)
	0.0
	0
	66,895
	142,483
	213
	67

	Cook Islands (the)
	0.0
	 
	18,054
	14,628
	81
	100

	Costa Rica
	1.4
	100
	330,780
	646,322
	195
	67

	Cote d’Ivoire
	0.0
	0
	190,158
	499,275
	263
	75

	Croatia
	0.0
	 
	2
	0
	0
	 

	Cuba
	0.0
	 
	313,826
	221,030
	70
	29

	Democratic People’s Republic of Korea (the)
	0.0
	 
	138,775
	64,038
	46
	0

	Democratic Republic of the Congo (the)
	1.8
	38
	43,267
	185,792
	429
	100

	Djibouti
	0.0
	 
	37,938
	69,489
	183
	50

	Dominica
	0.0
	 
	16,222
	12,625
	78
	0

	Dominican Republic (the)
	0.0
	 
	275,294
	480,548
	175
	67

	Ecuador
	0.0
	0
	78,631
	88,761
	113
	50

	Egypt
	29.0
	57
	1,629,349
	1,381,173
	85
	62

	El Salvador
	0.0
	0
	87,093
	95,007
	109
	50

	Equatorial Guinea
	0.0
	 
	28,364
	268,621
	947
	75

	Eritrea
	0.2
	 
	69,244
	68,749
	99
	50

	Eswatini 
	0.0
	0
	57,848
	69,973
	121
	33

	Ethiopia
	0.2
	40
	100,696
	111,029
	110
	80

	Fiji
	0.0
	0
	48,955
	49,036
	100
	60

	Gabon
	0.0
	 
	97,167
	99,894
	103
	33

	Gambia (the)
	0.2
	0
	27,189
	16,248
	60
	50

	Georgia
	0.0
	0
	71,473
	85,426
	120
	75

	Ghana
	9.1
	100
	247,138
	309,049
	125
	60

	Grenada
	0.1
	 
	28,693
	58,144
	203
	100

	Guatemala
	0.0
	0
	194,004
	152,288
	78
	0

	Guinea
	0.0
	 
	56,135
	153,773
	274
	50

	Guinea-Bissau
	0.3
	 
	66,613
	63,758
	96
	50

	Guyana
	0.0
	0
	72,220
	27,070
	37
	50

	Haiti
	0.0
	0
	59,603
	31,069
	52
	25

	Honduras
	0.4
	 
	107,762
	149,534
	139
	100

	India
	99.4
	34
	6,429,478
	2,643,412
	41
	48

	Indonesia
	44.1
	67
	2,740,813
	1,767,858
	65
	46

	Iran (Islamic Republic of)
	90.6
	77
	1,847,684
	850,271
	46
	42

	Iraq
	3.5
	0
	1,134,901
	594,400
	52
	38

	Jamaica
	3.8
	0
	83,994
	58,236
	69
	50

	Jordan
	0.0
	0
	638,252
	345,392
	54
	83

	Kenya
	0.0
	 
	208,457
	349,154
	167
	50

	Kiribati
	0.0
	 
	13,000
	24,953
	192
	100

	Kuwait
	0.0
	0
	1,026,305
	107,067
	10
	44

	Kyrgyzstan
	0.0
	0
	93,437
	196,249
	210
	75

	Lao People’s Democratic Republic (the)
	0.0
	 
	60,024
	134,156
	224
	100

	Lebanon
	12.4
	0
	965,684
	1,657,656
	172
	33

	Lesotho
	0.0
	 
	134,250
	115,112
	86
	50

	Liberia
	0.0
	 
	90,611
	121,161
	134
	100

	Libya
	24.1
	0
	619,363
	117,695
	19
	67

	Madagascar
	1.0
	 
	79,273
	53,430
	67
	67

	Malawi
	1.3
	0
	34,350
	123,508
	360
	100

	Malaysia
	16.5
	16
	2,174,854
	1,323,868
	61
	38

	Maldives
	0.0
	
	155,244
	21,448
	14
	67

	Mali
	0.0
	0
	75,726
	129,966
	172
	50

	Marshall Islands (the)
	0.0
	 
	10,789
	68,126
	631
	100

	Mauritania
	0.0
	 
	12,000
	90,000
	750
	100

	Mauritius
	0.0
	 
	96,723
	89,777
	93
	75

	Mexico
	129.4
	58
	4,330,406
	4,200,656
	97
	60

	Micronesia (Federated States of)
	0.0
	 
	19,964
	21,338
	107
	100

	Mongolia
	0.0
	 
	20,381
	62,144
	305
	100

	Montenegro
	0.0
	 
	31,001
	40,483
	131
	 

	Morocco
	0.0
	 
	50,001
	27,738
	55
	 

	Mozambique
	0.0
	 
	75,163
	86,768
	115
	67

	Myanmar
	0.0
	0
	27,443
	64,587
	235
	75

	Namibia
	0.0
	0
	185,780
	139,528
	75
	50

	Nauru
	0.0
	 
	14,328
	25,305
	177
	100

	Nepal
	0.0
	0
	54,002
	112,024
	207
	67

	Nicaragua
	0.0
	 
	110,492
	97,149
	88
	100

	Niger (the)
	0.0
	 
	222,851
	199,535
	90
	100

	Nigeria
	38.0
	14
	1,127,784
	594,602
	53
	30

	Niue
	0.0
	 
	9,647
	22,928
	238
	100

	Oman
	0.0
	 
	152,308
	211,886
	139
	67

	Pakistan
	31.2
	0
	482,468
	303,146
	63
	67

	Palau
	0.0
	 
	15,885
	117,322
	739
	100

	Panama
	0.0
	0
	251,626
	163,130
	65
	17

	Papua New Guinea
	0.0
	 
	123,800
	56,306
	45
	100

	Paraguay
	0.0
	0
	135,966
	141,492
	104
	75

	Peru
	2.2
	100
	93,431
	253,755
	272
	100

	Philippines (the)
	0.0
	 
	383,352
	429,024
	112
	100

	Qatar
	0.0
	0
	167,264
	75,099
	45
	25

	Republic of Moldova (the)
	0.0
	0
	62,285
	31,925
	51
	83

	Rwanda
	0.0
	0
	26,379
	64,976
	246
	100

	Saint Kitts and Nevis
	0.0
	0
	62,920
	0
	0
	0

	Saint Lucia
	0.1
	 
	25,062
	40,675
	162
	100

	Saint Vincent and the Grenadines
	0.0
	 
	20,011
	704
	4
	0

	Samoa
	0.0
	 
	19,236
	118,314
	615
	100

	Sao Tome and Principe
	0.0
	 
	47,943
	117,589
	245
	100

	Saudi Arabia
	173.7
	96
	1,668,606
	407,185
	24
	25

	Senegal
	0.0
	 
	164,556
	211,852
	129
	33

	Serbia
	2.6
	0
	259,561
	78,972
	30
	67

	Seychelles
	0.0
	0
	66,991
	80,214
	120
	50

	Sierra Leone
	0.1
	0
	49,550
	115,100
	232
	67

	Solomon Islands
	0.0
	 
	12,525
	30,400
	243
	100

	Somalia
	1.3
	 
	56,550
	99,301
	176
	100

	South Africa
	69.3
	100
	1,025,001
	272,306
	27
	0

	South Sudan
	0.0
	 
	13,996
	0
	0
	50

	Sri Lanka
	1.4
	56
	141,358
	172,776
	122
	50

	Sudan (the)
	9.1
	 
	352,675
	206,776
	59
	100

	Suriname
	0.0
	 
	27,642
	52,573
	190
	50

	Syrian Arab Republic
	0.0
	 
	10,002
	6,337
	63
	 

	Thailand
	113.6
	0
	4,973,820
	7,843,822
	158
	67

	The former Yugoslav Republic of Macedonia
	0.2
	100%
	105,002
	111,031
	106
	67

	Timor-Leste
	0.0
	 
	38,704
	94,815
	245
	71

	Togo
	0.0
	 
	44,245
	64,569
	146
	67

	Tonga
	0.0
	 
	13,010
	65,840
	506
	100

	Trinidad and Tobago
	4.2
	0
	239,557
	284,247
	119
	80

	Tunisia
	6.9
	78
	463,489
	364,519
	79
	100

	Turkey
	144.0
	0
	1,143,839
	539,598
	47
	50

	Turkmenistan
	1.7
	 
	31,999
	74,054
	231
	100

	Tuvalu
	0.0
	 
	16,395
	86,674
	529
	100

	Uganda
	0.0
	 
	42,405
	21,447
	51
	67

	United Republic of Tanzania (the)
	0.2
	0
	35,300
	50,582
	143
	25

	Uruguay
	1.9
	0
	249,281
	269,910
	108
	50

	Vanuatu
	0.0
	 
	18,388
	58,358
	317
	50

	Venezuela (Bolivarian Republic of)
	22.5
	11
	490,587
	597,034
	122
	60

	Viet Nam
	0.0
	 
	1,761,621
	1,173,085
	67
	100

	Yemen
	0.0
	0
	5
	0
	0
	0

	Zambia
	0.0
	 
	46,852
	170,238
	363
	100

	Zimbabwe
	0.0
	 
	102,712
	254,784
	248
	33

	Region: AFR
	0.0
	 
	275,465
	15,009
	5
	100

	Region: ASP
	0.0
	 
	151,362
	227,311
	150
	67

	Region: EUR
	0.0
	 
	54,417
	276,170
	508
	100

	Global
	0.0
	 
	9,631,903
	8,182,494
	85
	67

	Grand Total
	1,455.1
	33
	110,506,193
	115,815,835
	105
	59
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Appendix II

HCFC PHASE-OUT MANAGEMENT PLAN BY COUNTRY 
AS AT 31 DECEMBER 2017

	Country
	Approved phase-out (ODP tonnes)
	Funds approved (US$)
	Funds disbursed (US$)
	Balance (US$)
	Funds disbursed (%)

	Afghanistan
	8.4
	572,938
	171,491
	401,447
	30

	Albania
	0.6
	243,965
	185,099
	58,866
	76

	Algeria
	13.5
	1,809,240
	97,396
	1,711,844
	5

	Angola
	5.6
	626,000
	175,726
	450,274
	28

	Antigua and Barbuda
	0.0
	45,850
	27,235
	18,615
	59

	Argentina
	104.0
	12,077,789
	9,619,689
	2,458,100
	80

	Armenia
	2.2
	649,359
	465,228
	184,131
	72

	Bahamas (the)
	1.0
	277,050
	183,047
	94,003
	66

	Bahrain
	6.4
	814,455
	309,420
	505,035
	38

	Bangladesh
	20.8
	1,551,311
	1,438,311
	113,000
	93

	Barbados
	0.4
	210,000
	38,573
	171,427
	18

	Belize
	1.0
	242,500
	140,000
	102,500
	58

	Benin
	4.8
	501,224
	305,574
	195,650
	61

	Bhutan
	0.3
	423,000
	303,182
	119,818
	72

	Bolivia (Plurinational State of)
	0.5
	253,500
	236,114
	17,386
	93

	Bosnia and Herzegovina
	6.0
	877,645
	678,187
	199,458
	77

	Botswana
	1.1
	275,000
	5,870
	269,130
	2

	Brazil
	295.6
	29,311,109
	17,338,954
	11,972,155
	59

	Brunei Darussalam
	0.6
	242,900
	163,164
	79,736
	67

	Burkina Faso
	2.0
	565,630
	382,594
	183,036
	68

	Burundi
	0.4
	153,044
	116,860
	36,184
	76

	Cabo Verde
	0.0
	110,290
	53,034
	57,256
	48

	Cambodia
	1.5
	900,000
	767,501
	132,499
	85

	Cameroon
	24.1
	1,182,725
	986,513
	196,212
	83

	Central African Republic (the)
	0.5
	200,000
	64,001
	135,999
	32

	Chad
	4.0
	444,542
	423,329
	21,213
	95

	Chile
	35.0
	2,854,044
	1,525,605
	1,328,439
	53

	China
	2,546.5
	352,765,903
	263,291,771
	89,474,132
	75

	Colombia
	135.9
	9,539,617
	7,572,747
	1,966,870
	79

	Comoros (the)
	0.0
	114,000
	79,029
	34,971
	69

	Congo (the)
	2.2
	288,626
	173,626
	115,000
	60

	Cook Islands (the)
	0.0
	89,100
	49,250
	39,850
	55

	Costa Rica
	15.4
	1,097,522
	980,966
	116,556
	89

	Cote d’Ivoire
	6.4
	900,000
	410,403
	489,597
	46

	Croatia
	6.1
	801,942
	801,942
	0
	100

	Cuba
	15.1
	1,591,527
	1,294,450
	297,077
	81

	Democratic People’s Republic of Korea (the)
	19.4
	798,247
	116,914
	681,333
	15

	Democratic Republic of the Congo (the)
	5.8
	475,000
	373,225
	101,775
	79

	Djibouti
	0.0
	99,500
	60,177
	39,323
	60

	Dominica
	0.0
	82,250
	10,026
	72,224
	12

	Dominican Republic (the)
	12.5
	2,349,986
	1,991,476
	358,510
	85

	Ecuador
	17.2
	1,783,786
	1,691,954
	91,832
	95

	Egypt
	223.3
	12,200,361
	5,522,744
	6,677,617
	45

	El Salvador
	8.8
	1,039,277
	736,518
	302,759
	71

	Equatorial Guinea
	0.6
	144,962
	140,012
	4,950
	97

	Eritrea
	0.4
	189,000
	78,479
	110,521
	42

	Eswatini 
	7.9
	847,920
	717,102
	130,818
	85

	Ethiopia
	1.9
	280,000
	126,079
	153,921
	45

	Fiji
	2.0
	283,500
	168,111
	115,389
	59

	Gabon
	4.9
	431,000
	171,824
	259,176
	40

	Gambia (the)
	0.4
	167,497
	76,790
	90,707
	46

	Georgia
	1.2
	350,000
	290,745
	59,255
	83

	Ghana
	5.8
	1,050,000
	957,583
	92,417
	91

	Grenada
	0.3
	189,000
	90,216
	98,784
	48

	Guatemala
	2.9
	327,269
	251,409
	75,860
	77

	Guinea
	1.2
	303,981
	238,053
	65,928
	78

	Guinea-Bissau
	1.0
	251,138
	120,199
	130,939
	48

	Guyana
	0.3
	281,180
	93,111
	188,069
	33

	Haiti
	0.4
	167,119
	70,000
	97,119
	42

	Honduras
	2.0
	448,623
	280,723
	167,900
	63

	India
	488.2
	31,195,490
	19,311,982
	11,883,508
	62

	Indonesia
	155.5
	13,830,125
	8,495,239
	5,334,886
	61

	Iran (Islamic Republic of)
	217.2
	12,923,042
	9,479,578
	3,443,464
	73

	Iraq
	9.5
	750,000
	203,040
	546,960
	27

	Jamaica
	8.9
	589,450
	448,372
	141,078
	76

	Jordan
	32.2
	4,282,588
	3,154,216
	1,128,372
	74

	Kenya
	14.1
	1,356,500
	757,254
	599,246
	56

	Kiribati
	0.0
	98,100
	64,995
	33,105
	66

	Kuwait
	209.9
	7,500,378
	271,445
	7,228,933
	4

	Kyrgyzstan
	2.6
	407,992
	250,470
	157,522
	61

	Lao People's Democratic Republic (the)
	0.8
	252,000
	142,993
	109,007
	57

	Lebanon
	54.3
	4,905,109
	4,240,366
	664,743
	86

	Lesotho
	0.0
	252,000
	155,918
	96,082
	62

	Liberia
	2.0
	283,500
	186,460
	97,040
	66

	Libya
	24.1
	1,717,950
	23,164
	1,694,786
	1

	Madagascar
	3.7
	460,000
	244,383
	215,617
	53

	Malawi
	2.0
	273,750
	173,795
	99,955
	63

	Malaysia
	186.6
	13,095,408
	9,232,700
	3,862,708
	71

	Maldives
	0.6
	1,100,000
	766,695
	333,305
	70

	Mali
	3.4
	448,830
	260,462
	188,368
	58

	Marshall Islands (the)
	0.1
	101,700
	76,616
	25,084
	75

	Mauritania
	0.0
	255,000
	0
	255,000
	0

	Mauritius
	3.1
	621,200
	309,500
	311,700
	50

	Mexico
	509.4
	23,840,188
	19,537,715
	4,302,473
	82

	Micronesia (Federated States of)
	0.1
	100,800
	60,132
	40,668
	60

	Mongolia
	1.0
	329,000
	284,000
	45,000
	86

	Montenegro
	0.1
	353,500
	302,324
	51,176
	86

	Morocco
	11.0
	1,249,159
	985,436
	263,723
	79

	Mozambique
	0.3
	150,000
	13,025
	136,975
	9

	Myanmar
	0.4
	251,000
	46,994
	204,006
	19

	Namibia
	8.2
	810,000
	437,807
	372,193
	54

	Nauru
	0.0
	66,600
	44,915
	21,685
	67

	Nepal
	0.6
	189,000
	48,801
	140,199
	26

	Nicaragua
	0.7
	212,777
	179,335
	33,442
	84

	Niger (the)
	2.7
	274,090
	186,141
	87,949
	68

	Nigeria
	90.1
	4,938,830
	3,617,253
	1,321,577
	73

	Niue
	0.0
	65,700
	57,255
	8,445
	87

	Oman
	5.3
	731,391
	488,705
	242,686
	67

	Pakistan
	136.3
	7,994,265
	5,447,471
	2,546,794
	68

	Palau
	0.1
	108,000
	82,875
	25,125
	77

	Panama
	5.0
	600,645
	317,287
	283,358
	53

	Papua New Guinea
	2.0
	991,000
	499,500
	491,500
	50

	Paraguay
	6.3
	567,000
	375,836
	191,164
	66

	Peru
	3.8
	695,171
	231,952
	463,219
	33

	Philippines (the)
	40.0
	3,402,237
	2,392,050
	1,010,187
	70

	Qatar
	22.4
	1,150,907
	928,249
	222,658
	81

	Republic of Moldova (the)
	0.2
	218,002
	86,999
	131,003
	40

	Rwanda
	0.6
	222,000
	123,161
	98,839
	55

	Saint Kitts and Nevis
	0.3
	147,600
	58,400
	89,200
	40

	Saint Lucia
	0.2
	175,219
	131,076
	44,143
	75

	Saint Vincent and the Grenadines
	0.2
	318,951
	178,951
	140,000
	56

	Samoa
	0.1
	133,650
	106,250
	27,400
	79

	Sao Tome and Principe
	0.0
	109,012
	88,592
	20,420
	81

	Saudi Arabia
	353.5
	10,579,575
	4,734,585
	5,844,990
	45

	Senegal
	3.6
	454,023
	227,617
	226,406
	50

	Serbia
	5.2
	939,040
	471,537
	467,503
	50

	Seychelles
	1.4
	540,000
	325,550
	214,450
	60

	Sierra Leone
	0.4
	168,000
	83,352
	84,648
	50

	Solomon Islands
	0.7
	175,500
	129,650
	45,850
	74

	Somalia
	1.8
	360,374
	201,068
	159,306
	56

	South Africa
	94.2
	5,855,184
	3,453,559
	2,401,625
	59

	South Sudan
	0.0
	20,000
	0
	20,000
	0

	Sri Lanka
	4.7
	591,866
	440,098
	151,768
	74

	Sudan (the)
	43.3
	3,839,883
	1,526,959
	2,312,924
	40

	Suriname
	0.2
	123,500
	84,178
	39,322
	68

	Thailand
	234.6
	18,108,630
	12,687,573
	5,421,057
	70

	The former Yugoslav Republic of Macedonia
	2.0
	796,131
	684,897
	111,234
	86

	Timor-Leste
	0.0
	409,700
	197,126
	212,574
	48

	Togo
	4.8
	527,000
	277,894
	249,106
	53

	Tonga
	0.0
	114,300
	85,276
	29,024
	75

	Trinidad and Tobago
	6.7
	1,229,733
	917,606
	312,127
	75

	Tunisia
	9.4
	1,606,868
	335,738
	1,271,130
	21

	Turkey
	384.5
	11,123,085
	8,318,459
	2,804,626
	75

	Turkmenistan
	2.4
	618,800
	431,092
	187,708
	70

	Tuvalu
	0.0
	82,800
	65,472
	17,328
	79

	Uganda
	0.0
	143,977
	54,584
	89,393
	38

	United Republic of Tanzania (the)
	0.6
	187,875
	95,493
	92,382
	51

	Uruguay
	5.2
	694,004
	428,422
	265,582
	62

	Vanuatu
	0.1
	133,650
	83,591
	50,059
	63

	Venezuela (Bolivarian Republic of)
	28.9
	2,569,145
	2,012,467
	556,678
	78

	Viet Nam
	148.6
	8,644,947
	8,205,602
	439,345
	95

	Yemen
	11.6
	625,000
	176,907
	448,093
	28

	Zambia
	1.1
	252,956
	147,956
	105,000
	58

	Zimbabwe
	12.3
	982,818
	795,818
	187,000
	81

	Region: ASP
	0.0
	240,000
	159,166
	80,834
	66

	Grand Total
	7,216.1
	668,978,113
	468,656,774
	200,321,340
	70
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