| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/82/16 2 November 2018 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Eighty-second Meeting

Montreal, 3-7 December 2018

PROGRESS REPORT OF UNDP AS AT 31 DECEMBER 2017

# This document presents the progress report of UNDP as of 31 December 2017.

Scope of the document

# This document consists of the following parts:

## Part I:	Projects approved under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2017 and cumulative since 1991; it contains a review on the status of implementation of each ongoing project at the country level; and it identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee.

## Part II:	Projects approved under the additional voluntary contributions for HFC activities and the status of implementation.

General recommendation.

# This document also contains the following annexes:

Annex I: 	A summary status and a recommendation for each ongoing project with outstanding issues for consideration by the Executive Committee.

Annex II: 	An analysis of the progress report.

Part I: 	Projects approved under the regular contributions to the Multilateral Fund

Summary of progress in implementation of projects for 2017 and cumulative

# Implementation of projects and activities by UNDP for 2017 and cumulative since 1991 up to 31 December 2017 is summarized as follows:

## Phase-out: In 2017, 325.3 ODP tonnes of consumption of HCFCs were phased out and an additional 88.7 ODP tonnes of consumption of HCFCs were approved for phase-out. Since 1991, 66,765 ODP tonnes of consumption of ODS had been phased out, of an expected total of 67,526 ODP tonnes from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2017, US $30.71 million was disbursed and US $31.3 million was planned for disbursement based on the 2016 progress report, representing a rate of disbursement of 98 per cent of that planned. Cumulatively, US $704.29 million had been disbursed out of the total US $782.35 million approved for disbursement (excluding agency support costs). This represents a rate of disbursement of 90 per cent. In 2017, US $30.73 million was approved for implementation;

## Cost-effectiveness (in ODP): Since 1991, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $10.20/kg. The average cost-effectiveness of investment projects per ODP tonne was US $8.49/kg for completed projects and US $96.77/kg for ongoing projects;

## Number of projects completed: In 2017, 85 projects were completed. Since 1991, 2,231 projects of the 2,377 projects approved (excluding closed or transferred projects) were completed. This represents a completion rate of 94 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2017 were completed on average 39 months after their approval. Since 1991, the average time for completion of investment projects has been 33 months after their approval. First disbursements under these projects occurred, on average, 13 months after they had been approved;

## Speed of delivery – non investment projects: Projects that were completed in 2017 were completed on average 36 months after their approval. Since 1991, the average time for completion of non-investment projects has been 40 months after their approval. First disbursements under these projects occurred, on average, 13 months after they had been approved;

## Project preparation: Of the 520 project preparation activities approved by the end of 2017, 505 have been completed. In 2017, 22 projects were completed, leaving 15 ongoing;

## Implementation delays: There were a total of 74 ongoing investment projects under implementation at the end of 2017. These projects, on average, are experiencing a delay of 20 months. However, there are no projects classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as project preparation, multi-year agreements (MYAs) and institutional strengthening (IS) are not subject to those procedures); and

## MYAs: In 2017, UNDP was implementing 54 MYAs for HCFC phase-out management plans (HPMPs). Since 1991, 134 MYAs have been approved and 80 MYAs have been completed.

Project implementation progress in 2017

# The Secretariat reviewed the status of project implementation on a country-by-country basis taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2017, the potential impact of these delays on phase-out and the rate of planned disbursements.

# Of the 106 ongoing projects, excluding IS and project preparation, 84 projects have extended planned dates of completion since the 2016 progress report.

# During the review of the progress report, the Secretariat had several exchanges with UNDP, where a number of issues on ongoing projects were satisfactorily resolved. However, issues could not be resolved for those projects or tranches of MYAs for HCFCs, project preparation and renewal of IS projects shown in Annex I to the present document. For each ongoing project, a brief description on the status of implementation and the outstanding issues are presented and a recommendation is proposed for consideration by the Executive Committee.

# The issues identified with regard to the following projects are discussed under relevant sections of the reports on projects with specific reporting requirements: stage I of the HPMP for Bangladesh (first tranche) (BGD/PHA/65/INV/40), the demonstration project for HCFC-free low-global warming potential technology performance in air-conditioning applications (capacity above 8TR) in Kuwait (KUW/REF/76/DEM/32), and stage II of the HPMP for Venezuela (Bolivarian Republic of) (stage II, first tranche) (foam sector) (VEN/PHA/76/INV/33).

Part II: Projects approved under the additional voluntary contributions for HFC activities

# In 2017, the Executive Committee had approved 16 HFC-related projects under the additional voluntary contributions amounting to US $4,729,610 (excluding agency support costs). A summary of the status of these projects is presented in Table 1.

# Table 1. HFC-related projects approved in 2017

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment | 1 | 0 | 0 | 3,131,610 | 0 | 3,131,610 | 0 |
| Project preparation | 5 | 0 | 0 | 150,000 | 0 | 150,000 | 0 |
| Technical assistance - Enabling activities | 10 | 0 | 0 | 1,448,000 | 0 | 1,448,000 | 0 |
| Total | 16 | 0 | 0 | 4,729,610 | 0 | 4,729,610 | 0 |

* Excludes agency support costs.

General recommendation

# The Executive Committee may wish:

## To note the progress report of UNDP as at 31 to December 2017 contained in document UNEP/OzL.Pro/ExCom/82/16; and

## To approve the recommendations related to ongoing projects with specific issues contained in Annex I to the present document.

Annex I

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR UNDP

| Country/project code | Project title | Disbursement rate (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- |
| Armenia ARM/PHA/77/INV/18 | HCFC phase-out management plan (stage II, first tranche) | 2 | Low disbursement; the procurement process for equipment is at contracting stage and this is expected to increase the disbursement rate | To request a status report to the 83rd meeting on the level of funds disbursement |
| Chile CHI/PHA/73/INV/184 | HCFC phase-out management plan (stage I, third tranche) | 3 | Project completion date by decision is December 2017 | To request cancellation of the project and return of remaining balances to the 82nd meeting |
| Cuba CUB/REF/58/PRP/42 | Preparation for HCFC phase-out investment activities (manufacturing sector) | 0 | The enterprise indicated that it would not adopt low-global warming potential technologies | To request cancellation of the project and return of remaining balances to the 82nd meeting |
| Democratic Republic of the Congo (the) DRC/PHA/79/PRP/42 | Preparation of a HCFC phase-out management plan (stage II) | 0 | Low disbursement and slow progress in project preparation; currently, in coordination with UNEP, stage II is proposed to be submitted to the 83rd meeting | To request a status report to the 83rd meeting on the level of funds disbursement, noting that stage II is proposed to be submitted to the 83rd meeting |
| Haiti HAI/PHA/76/INV/22 | HCFC phase-out management plan (stage I, second tranche) | 0 | Low disbursement rate due to delay in finalisation of agreement | To request: (a) a status report to the 83rd meeting on the level of funds disbursement and finalization of agreement; and (b) UNEP CAP to provide assistance for expedited implementation of project activities |
| India IND/SEV/76/INS/467 | Extension of institutional strengthening project (phase X: 4/2016-3/2018) | 0 | Low disbursement rate of approved funds due to delays in signing of project document | To request a status report to the 83rd meeting on the level of funds disbursement and signing of project document |
| Iran (Islamic Republic of) IRA/PHA/77/INV/226 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | 0 | Low disbursement rate due to political and economic situation on technology transfer and funds transfer | To request a status report to the 83rd meeting on the level of funds disbursement |
| Nigeria NIR/PHA/75/INV/143 | HCFC phase-out management plan (stage I, fifth tranche) (foam sector and refrigeration servicing) | 0 | Low disbursement and slow progress in implementation; extension of project to December 2018 approved at the 80th meeting | To request a status report to the 83rd meeting on the level of funds disbursement, noting that the project would be completed by December 2018 |
| Saint Kitts and Nevis STK/PHA/64/TAS/16 | HCFC phase-out management plan (stage I, first tranche) | 0 | Low disbursement and slow progress in approval of activities; specification of equipment has been approved by ozone office | ###### To request: (a) a status report to the 83rd meeting on low disbursement rate of approved funds, noting that procurement of equipment has been initiated; and (b) UNEP CAP to provide assistance for expedited implementation of project activities |

Annex II

ANALYSIS OF THE PROGRESS REPORT OF UNDP AS AT 31 DECEMBER 2017

# This Annex consists of the following two parts:

## Part I:	Projects approved under the regular contributions to the Multilateral Fund.

## Part II:	Projects approved under the additional voluntary contributions for HFC activities.

Part I: 	Projects approved under the regular contributions to the Multilateral Fund

# As of 31 December 2017, the Executive Committee had approved US $888.01 million consisting of US $782.35 million for the implementation of investment and non-investment projects and US $105.66 million for agency support costs, as shown in Table 1. In 2017, 28 new projects and activities were approved. This level of funding is expected to result in the phase-out of 67,526 ODP tonnes of ODS consumption.

# Table 1: Approved funding by sector for UNDP as at 31 December 2017

| Sector | Funding (US $) |
| --- | --- |
| Sector |  |
| Aerosol | 26,054,838 |
| Destruction | 3,607,085 |
| Fire fighting | 50,000 |
| Foam | 173,568,025 |
| Halon | 4,996,975 |
| Fumigants | 20,081,243 |
| Phase-out plan | 292,035,855 |
| Process agent | 1,286,923 |
| Production | 1,056,000 |
| Refrigeration | 137,487,947 |
| Several | 58,007,316 |
| Solvents | 63,699,998 |
| Sterilant | 417,628 |
| Sub-total | 782,349,834 |
| Agency support costs | 105,664,706 |
| Total | 888,014,540 |

# A summary of the status of projects implemented by category is presented in Table 2.

Table 2: Status of project implementation by category

| Type | Number of projects* |  |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved |  | Disbursed | Balance | % disbursed |
| Country programme | 22 | 22 | 100 | 1,628,797 |  | 1,628,797 | 0 | 100 |
| Demonstration | 43 | 35 | 81 | 22,205,198 |  | 19,544,729 | 2,660,470 | 88 |
| Institutional strengthening | 228 | 203 | 89 | 48,234,446 |  | 42,415,092 | 5,819,355 | 88 |
| Investment | 1,243 | 1,169 | 94 | 644,723,109 |  | 582,576,205 | 62,146,903 | 90 |
| Project preparation | 520 | 505 | 97 | 21,891,173 |  | 21,171,761 | 719,413 | 97 |
| Technical assistance | 293 | 269 | 92 | 42,076,621 |  | 35,363,830 | 6,712,791 | 84 |
| Training | 28 | 28 | 100 | 1,590,489 |  | 1,590,489 | 0 | 100 |
| Total | 2,377 | 2,231 | 94 | 782,349,834 |  | 704,290,902 | 78,058,931 | 90 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

# Table 3 presents an overview of status of project implementation by year. All projects and activities approved between 1991 and 2008, have now been completed.

Table 3: Status of project implementation by year

| Year | Number of projects* |  |  |  | Funding (US $)** |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved |  | Disbursed | Balance | % disbursed |
| 1991 | 15 | 15 | 100 | 1,149,032 |  | 1,149,032 | 0 | 100 |
| 1992 | 67 | 67 | 100 | 8,619,002 |  | 8,619,002 | 0 | 100 |
| 1993 | 57 | 57 | 100 | 13,204,712 |  | 13,204,712 | 0 | 100 |
| 1994 | 148 | 148 | 100 | 49,481,580 |  | 49,481,581 | -1 | 100 |
| 1995 | 117 | 117 | 100 | 29,599,445 |  | 29,599,446 | -1 | 100 |
| 1996 | 83 | 83 | 100 | 27,838,805 |  | 27,838,805 | 0 | 100 |
| 1997 | 188 | 188 | 100 | 44,056,257 |  | 44,056,257 | 0 | 100 |
| 1998 | 172 | 172 | 100 | 31,305,010 |  | 31,305,010 | 0 | 100 |
| 1999 | 204 | 204 | 100 | 35,896,883 |  | 35,896,884 | -1 | 100 |
| 2000 | 149 | 149 | 100 | 31,268,362 |  | 31,268,361 | 1 | 100 |
| 2001 | 179 | 179 | 100 | 35,292,272 |  | 35,292,271 | 1 | 100 |
| 2002 | 117 | 117 | 100 | 44,316,424 |  | 44,316,422 | 2 | 100 |
| 2003 | 64 | 64 | 100 | 36,336,530 |  | 36,336,530 | 0 | 100 |
| 2004 | 69 | 69 | 100 | 24,802,715 |  | 24,802,714 | 1 | 100 |
| 2005 | 53 | 53 | 100 | 29,125,258 |  | 29,124,834 | 425 | 100 |
| 2006 | 62 | 62 | 100 | 15,753,458 |  | 15,753,461 | -3 | 100 |
| 2007 | 54 | 54 | 100 | 12,142,488 |  | 12,142,486 | 2 | 100 |
| 2008 | 84 | 84 | 100 | 22,873,866 |  | 22,873,865 | 0 | 100 |
| 2009 | 93 | 91 | 98 | 13,283,556 |  | 13,188,578 | 94,978 | 99 |
| 2010 | 43 | 42 | 98 | 19,735,825 |  | 19,597,909 | 137,915 | 99 |
| 2011 | 63 | 59 | 94 | 57,454,510 |  | 56,404,467 | 1,050,043 | 98 |
| 2012 | 29 | 25 | 86 | 33,933,810 |  | 32,282,762 | 1,651,048 | 95 |
| 2013 | 43 | 34 | 79 | 34,573,667 |  | 31,538,959 | 3,034,708 | 91 |
| 2014 | 67 | 52 | 78 | 22,987,400 |  | 20,215,699 | 2,771,701 | 88 |
| 2015 | 75 | 39 | 52 | 33,705,450 |  | 20,955,060 | 12,750,390 | 62 |
| 2016 | 54 | 4 | 7 | 42,878,670 |  | 16,899,307 | 25,979,363 | 39 |
| 2017 | 28 | 3 | 11 | 30,734,847 |  | 146,488 | 30,588,359 | 0 |
| Total | 2,377 | 2,231 | 94 | 782,349,834 |  | 704,290,902 | 78,058,931 | 90 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

# Table 4 presents project implementation by country for 2017.

Table 4. Summary of project implementation by UNDP for 2017

| Country | Phased out in 2017 | Percentage of planned phase-out achieved in 2017 | Estimated funds disbursed in 2017 (US$) | Funds disbursed in 2017 (US$) | Percentage of funds disbursed over estimation in 2017 | Percentage of planned projects completed in 2017 |
| --- | --- | --- | --- | --- | --- | --- |
| Angola | 1.6 |  | 35,896 | 123,112 | 343 | 100 |
| Argentina | 0.0 |  | 176,343 | 136,116 | 77 | 50 |
| Armenia | 0.0 |  | 60,810 | 2,590 | 4 | 67 |
| Bangladesh | 0.6 | 100 | 146,850 | 94,780 | 65 | 33 |
| Barbados | 0.0 |  | 20,000 | 3,198 | 16 | 100 |
| Belize | 0.2 |  | 0 | 0 |  |  |
| Bhutan | 0.0 | 0 | 23,430 | 21,895 | 93 | 0 |
| Brazil | 34.5 | 23 | 4,353,639 | 3,272,502 | 75 | 25 |
| Brunei Darussalam | 0.0 |  | 9,840 | 0 | 0 | 0 |
| Cambodia | 0.6 | 100 | 40,000 | 50,000 | 125 | 50 |
| Chile | 2.6 | 13 | 750,643 | 809,216 | 108 | 40 |
| China | 82.2 | 53 | 7,228,303 | 13,986,970 | 194 | 50 |
| Colombia | 0.0 | 0 | 1,387,429 | 1,101,004 | 79 | 0 |
| Democratic Republic of the Congo (the) | 1.8 | 100 | 8,665 | 21,651 | 250 | 100 |
| Costa Rica | 1.4 | 100 | 330,780 | 646,322 | 195 | 67 |
| Cuba | 0.0 |  | 313,826 | 221,030 | 70 | 29 |
| Dominican Republic (the) | 0.0 |  | 241,797 | 405,468 | 168 | 75 |
| Egypt | 23.0 | 57 | 1,293,623 | 932,133 | 72 | 40 |
| El Salvador | 0.0 | 0 | 57,408 | 72,207 | 126 | 50 |
| Fiji | 0.0 | 0 | 27,350 | 7,036 | 26 | 50 |
| Georgia | 0.0 | 0 | 51,473 | 69,426 | 135 | 67 |
| Ghana | 7.7 | 100 | 172,205 | 247,208 | 144 | 33 |
| Guyana | 0.0 | 0 | 59,720 | 23,730 | 40 | 0 |
| Haiti | 0.0 | 0 | 38,848 | 0 | 0 | 0 |
| India | 75.0 | 35 | 5,536,497 | 2,380,888 | 43 | 41 |
| Indonesia | 18.9 | 68 | 1,430,078 | 552,597 | 39 | 56 |
| Iran (Islamic Republic of) | 0.0 | 0 | 735,507 | 472,600 | 64 | 14 |
| Jamaica | 3.8 |  | 64,527 | 53,261 | 83 | 0 |
| Kuwait | 0.0 |  | 125,200 | 0 | 0 | 100 |
| Kyrgyzstan | 0.0 | 0 | 65,983 | 94,299 | 143 | 50 |
| Lebanon | 12.4 | 0 | 935,684 | 1,598,644 | 171 | 33 |
| Malaysia | 16.5 | 16 | 2,174,854 | 1,323,868 | 61 | 38 |
| Maldives | 0.0 |  | 126,505 | 21,448 | 17 | 50 |
| Mali | 0.0 | 0 | 42,243 | 0 | 0 | 0 |
| Mexico | 24.8 | 35 | 1,092,219 | 294,138 | 27 | 0 |
| Republic of Moldova (the) | 0.0 | 0 | 46,632 | 1 | 0 | 80 |
| Nepal | 0.0 | 0 | 27,040 | 10,000 | 37 | 0 |
| Nigeria | 8.0 | 14 | 495,827 | 408,503 | 82 | 14 |
| Pakistan | 0.0 |  | 300,869 | 104,731 | 35 | 33 |
| Panama | 0.0 | 0 | 232,693 | 163,130 | 70 | 25 |
| Paraguay | 0.0 | 0 | 66,931 | 66,786 | 100 | 50 |
| Peru | 2.2 | 100 | 75,899 | 131,663 | 173 | 100 |
| Saint Kitts and Nevis | 0.0 | 0 | 16,000 | 0 | 0 | 0 |
| Sri Lanka | 1.4 | 56 | 131,232 | 116,937 | 89 | 40 |
| Timor-Leste | 0.0 |  | 16,000 | 0 | 0 | 50 |
| Trinidad and Tobago | 4.2 |  | 230,665 | 261,196 | 113 | 67 |
| Uruguay | 1.9 | 0 | 199,281 | 197,617 | 99 | 40 |
| Venezuela (Bolivarian Republic of) | 0.0 | 0 | 298,439 | 209,561 | 70 | 33 |
| Global | 0.0 |  | 0 | 0 |  | 100 |
| Grand Total | 325.3 | 31 | 31,295,683 | 30,709,461 | 98 | 42 |

Part II: Projects approved under the additional voluntary contributions for HFC activities

# In 2017, the Executive Committee had approved 16 HFC-related projects under the additional voluntary contributions amounting to US $4,729,610 (excluding agency support costs). A summary of the status of these projects is presented in Table 5.

# Table 5. HFC-related projects approved in 2017

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment | 1 | 0 | 0 | 3,131,610 | 0 | 3,131,610 | 0 |
| Project preparation | 5 | 0 | 0 | 150,000 | 0 | 150,000 | 0 |
| Technical assistance - Enabling activities | 10 | 0 | 0 | 1,448,000 | 0 | 1,448,000 | 0 |
| Total | 16 | 0 | 0 | 4,729,610 | 0 | 4,729,610 | 0 |

* Excludes agency support costs.

The progress report is attached to this document. The data has been included in the Consolidated Progress Report database that is available upon request.

Ongoing projects are all projects that were under implementation as at 31 December 2017. Key indicators of progress include: percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies.

UNEP/OzL.Pro/ExCom/82/20

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively-financed projects.