| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/98/9 30 May 2026 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-eighth Meeting

Montreal, 22–26 June 2026

Item 7(b) of the provisional agenda

TRANCHE SUBMISSION DELAYS

Introduction

# Pursuant to decision 47/50(d), the Secretariat has prepared the present document. It presents actions taken in response to the status of submissions on tranche submission delays under multi-year agreements (MYAs) at the 97th meeting and an analysis of each of the MYA tranches that were due but were not submitted to the 98th meeting. It also provides an overview of the reasons for the delays and the impact on compliance with the countries’ obligations under the Montreal Protocol, and the Secretariat’s recommendation. In accordance with decision 95/91(c), the present document is the first tranche submission delays document presented on an annual basis at the first meeting of 2026.

- Tranche submission delays at the 97th meeting

# At the 97th meeting, 21 out of the 41 countries (33 out of 69 activities) scheduled to submit MYA tranche requests did not do so on time, representing a non-submission rate of 51 per cent. These tranches were rescheduled for submission to the 98th meeting.

- Analysis of tranches not submitted to the 98th meeting

# Forty-one activities associated with tranches of HPMPs or Kigali HFC implementation plans for 25 countries, at a total value of US $23,855,238 (including agency support costs), due for submission to the 98th meeting, were not submitted, as shown in annex I to the present document.

# In addition, the third tranche of stage II of the HPMP for Qatar amounting to US $142,170 (including agency support costs) was submitted to the 98th meeting but subsequently withdrawn by the relevant implementing agencies during the project review process. This tranche is also included in annex I.

- Reasons for delays and impact on compliance

# The reasons for delays in the submission of MYA tranches include: Government decisions, and/or endorsements, and/or changes in the national ozone unit, and/or structural change (21); disbursement below the 20 per cent threshold of approved funds for the previous tranche (16); sufficient funds from previous tranche approved (4); internal or external difficulties (4); submission of progress and financial reports (3);  lack of verification report (2); Executive Committee approval conditions (2); enterprise delays (1); signing of agreement or project document (1); investment component (1); lead or cooperating agency not ready for submission (1); operational delays (1); and procurement delays (1). For the delays in the submissions, more than one reason may apply.

# As reported by the relevant bilateral and implementing agencies, delays in the submission of MYA tranches that were past due would have no impact on compliance with the countries’ obligations under the Montreal Protocol. However, one country reported 2025 HCFC consumption data under Article 7 that is greater than its 67.5 per cent reduction levels for that year. This issue is addressed in the Country programme data and prospects for compliance.

# All outstanding tranches are expected to be submitted to the 99th meeting, except for Afghanistan and Thailand, whose remaining tranches of stage II of their HPMPs will not be submitted/requested, and for the Sudan and Viet Nam, whose outstanding tranches are expected to be submitted to the 100th meeting.

- Recommendation

# The Executive Committee may wish:

## To note:

### The report on tranche submission delays contained in document UNEP/OzL.Pro/ExCom/98/9;

### The information on tranche submission delays under multi-year agreements (MYAs) submitted by the Governments of France and Germany, UNDP, UNEP, UNIDO and the World Bank;

### That 31 out of 72 activities (18 out of 43 countries) related to MYA tranches due for submission at the 98th meeting had been submitted on time;

### That relevant bilateral and implementing agencies had indicated that the late submission of the tranches of HCFC phase-out management plans and Kigali HFC implementation plans due for submission at the first meeting in 2026 would have no impact on countries’ compliance with the Montreal Protocol, and that there was no indication that any of the countries concerned were in non-compliance with the Montreal Protocol control measures, except for one country; and

## To request the Secretariat to send letters to the relevant Governments regarding the decisions on tranche submission delays contained in annex I to the present report.

Annex I

TRANCHES NOT SUBMITTED TO THE 98TH MEETING

| Country | Agency | Tranche | Amount (with support costs) (US $) | Reason for delay/withdrawal | Recommendations |
| --- | --- | --- | --- | --- | --- |
| Afghanistan (HCFC phase-out management plan (HPMP) stage II) | UNIDO | 2025 | 300,135 | Internal or external difficulties | Cancellation of stage II of the HPMP for Afghanistan is being requested at the present meeting. |
| Barbados (HPMP stage II) | UNDP | 2026 | 102,559 | 20 per cent disbursement threshold | Noting that the overall disbursement rate of the first (2022) tranche of stage II of the HPMP was below the 20 per cent disbursement threshold, that the mandatory verification on HCFC consumption targets had not been completed, and urging the Government of Barbados to work with UNEP to complete the verification, and with UNEP and UNDP so that the second (2026) tranche of stage II of the HPMP could be submitted to the 99th meeting, on the understanding that the 20 per cent disbursement threshold for funding of the previous tranche had been achieved. |
|  | UNEP | 2026 | 59,325 | Lack of verification report |  |
| Cameroon (Kigali HFC implementation plan (KIP) stage I) | UNIDO | 2026 | 434,420 | Government decisions/endorsements/ changes in the national ozone unit (NOU) | Noting the delays due to the heavy national administrative procedures and urging the Government of Cameroon to work with UNIDO so that the second (2026) tranche of stage I of the KIP could be submitted to the 99th meeting. |
| Comoros (the) (HPMP stage II) | UNEP | 2026 | 266,115 | Government decisions/endorsements/ changes in the NOU | Noting the delays due to structural changes within the Government and urging the Government of the Comoros to work with UNEP so that the second (2026) tranche of stage II of the HPMP could be submitted to the 99th meeting. |
| Ethiopia (HPMP stage II) | UNEP | 2026 | 110,740 | Government decisions/endorsements/ changes in the NOU | Noting the delays due to the change of NOU and urging the Government of Ethiopia to work with UNEP and UNIDO so that the third (2026) tranche of stage II of the HPMP could be submitted to the 99th meeting. |
|  | UNIDO | 2026 | 40,330 | Government decisions/endorsements/ changes in the NOU/20 per cent disbursement threshold |  |
| Gabon (HPMP stage II) | UNEP | 2026 | 357,910 | Government decisions/endorsements/ changes in the NOU/submission of progress and financial reports | Noting the non-submission of the progress and financial reports and urging the Government of Gabon to work with UNEP to submit the required progress and financial reports, and with UNEP and UNIDO so that the second (2026) tranche of stage II of the HPMP could be submitted to the 99th meeting. |
|  | UNIDO | 2026 | 123,050 | 20 per cent disbursement threshold |  |
| Grenada (HPMP stage II) | UNEP | 2025 | 44,861 | Lack of verification report | Noting that the mandatory verification on HCFC consumption targets had not been completed and urging the Government of Grenada to work with UNEP to complete the verification, and with UNEP and UNIDO so that the second (2025) tranche of stage II of the HPMP could be submitted to the 99th meeting with a revised plan of action to take into account the reallocation of the 2025 and subsequent tranches where necessary. |
|  | UNIDO | 2025 | 13,161 | Government decisions/endorsements/ changes in the NOU |  |
| Guinea (HPMP stage II) | UNEP | 2026 | 134,470 | Government decisions/endorsements/ changes in the NOU/submission of progress and financial reports | Noting the non-submission of the progress and financial reports and urging the Government of Guinea to work with UNEP to submit the required progress and financial reports, and with UNEP and UNIDO so that the second (2026) tranche of stage II of the HPMP could be submitted to the 99th meeting with a revised agreement in accordance with decision XXXVII/9 on the change of the baseline. |
|  | UNIDO | 2026 | 112,270 | 20 per cent disbursement threshold |  |
| Iraq (HPMP stage II) | UNEP | 2023 | 730,610 | Government decisions/endorsements/ changes in the NOU/internal or external difficulties/investment component/20 per cent disbursement threshold | Noting that the overall disbursement rate of the second (2022) tranche of stage II of the HPMP (UNEP component) was below the 20 per cent disbursement threshold and the recent completion of the delayed conversion investment projects under the national phase-out plan (NPP), and urging the Government of Iraq to work with UNIDO to submit the project completion reports for the conversion investment projects prior to the 99th meeting so that the third (2023) tranche of stage II of the HPMP for UNEP and the second and third (2022 and 2023) tranches of stage II of the HPMP for UNIDO could be submitted to the 99th meeting with a revised plan of action to take into account the reallocation of the 2022, 2023 and subsequent tranches where necessary, on the understanding that the 20 per cent disbursement threshold for funding of the previous tranche had been achieved. |
|  | UNIDO | 2022 and 2023 | 722,250 | Enterprise delays |  |
| Kenya (HPMP stage II) | France | 2023 | 671,075 | Government decisions/endorsements/ changes in the NOU | Noting the delays due to changes in the national regulatory framework and urging the Government of Kenya to work with the Government of France so that the third (2023) tranche of stage II of the HPMP could be submitted to the 99th meeting with a revised plan of action to take into account the reallocation of the 2023 and subsequent tranches where necessary. |
| Kuwait (HPMP stage II) | UNEP | 2025 | 299,298 | Government decisions/endorsements/ changes in the NOU/submission of progress and financial reports/20 per cent disbursement threshold | Noting that the overall disbursement rate of the second (2023) tranche of stage II of the HPMP was below the 20 per cent disbursement threshold, and the non-submission of the progress and financial reports, and urging the Government of Kuwait to work with UNEP to submit the required progress and financial reports, and with UNEP and UNIDO so that the third (2025) tranche of stage II of the HPMP could be submitted to the 99th meeting with a revised plan of action to take into account the reallocation of the 2025 tranche where necessary, on the understanding that the 20 per cent disbursement threshold for funding of the previous tranche had been achieved. |
|  | UNIDO | 2025 | 64,200 | Lead or cooperating agency not ready |  |
| Malaysia (KIP stage I) | World Bank | 2025 | 3,473,530 | 20 per cent disbursement threshold | Noting that the overall disbursement rate of the first (2023) tranche of stage I of the KIP was below the 20 per cent disbursement threshold, and urging the Government of Malaysia to work with the World Bank so that the second (2025) tranche of stage I of the KIP could be submitted to the 99th meeting with a revised plan of action to take into account the reallocation of the 2025 and subsequent tranches where necessary, on the understanding that the 20 per cent disbursement threshold for funding of the previous tranche had been achieved. |
| Mauritius (HPMP) | Germany | 2023 | 75,343 | Government decisions/endorsements/ changes in the NOU/20 per cent disbursement threshold | Noting that the overall disbursement rate of the fourth (2020) tranche of the HPMP was below the 20 per cent disbursement threshold, and urging the Government of Mauritius to work with the Government of Germany so that the fifth (2023) tranche of the HPMP could be submitted to the 99th meeting with a revised plan of action to take into account the reallocation of the 2023 and subsequent tranches where necessary, on the understanding that the 20 per cent disbursement threshold for funding of the previous tranche had been achieved. |
| Mozambique (HPMP stage II) | UNDP | 2026 | 110,363 | 20 per cent disbursement threshold | Noting the delays due to political situation and successive changes in the government and urging the Government of Mozambique to work with UNDP and UNEP so that the second (2026) tranche of stage II of the HPMP could be submitted to the 99th meeting. |
|  | UNEP | 2026 | 180,353 | Government decisions/endorsements/ changes in the NOU |  |
| Mozambique (KIP stage I) | UNDP | 2026 | 6,780 | 20 per cent disbursement threshold | Noting the delays due to political situation and successive changes in the Government and urging the Government of Mozambique to work with UNDP and UNEP so that the second (2026) tranche of stage I of the KIP could be submitted to the 99th meeting. |
|  | UNEP | 2026 | 92,095 | Government decisions/endorsements/ changes in the (NOU |  |
| Pakistan (HPMP stage III) | UNEP | 2026 | 664,514 | Government decisions/endorsements/ changes in the NOU/sufficient funds from previous tranche approved/20 per cent disbursement threshold | Noting the delays due to the structural changes within the Government and urging the Government of Pakistan to work with UNEP and UNIDO so that the third (2026) tranche of stage III of the HPMP could be submitted to the 99th meeting. |
|  | UNIDO | 2026 | 928,118 | Government decisions/endorsements/ changes in the NOU |  |
| Qatar (HPMP stage II) | UNEP | 2025 | 77,970 | Executive Committee (ExCom) approval conditions | Noting that the third (2025) tranche of stage II of the HPMP submitted to the 98th meeting had been withdrawn, as not all the conditions specified in decision 88/54(e)(i), (ii) and (iii) had been met, and urging the Government of Qatar to work with UNEP and UNIDO so that the third (2025) tranche of stage II of the HPMP could be submitted to the 99th meeting with a revised plan of action to take into account the reallocation of the 2025 tranche where necessary. |
|  | UNIDO | 2025 | 64,200 | ExCom approval conditions |  |
| Saudi Arabia (HPMP stage II) | UNEP | 2026 | 2,044,327 | Internal or external difficulties/signing of agreement/project document | Noting the delays due to non-compliance with the ExCom approval conditions and that the overall disbursement rate of the first (2024) tranche of stage II of the HPMP was below the 20 per cent disbursement threshold and urging the Government of Saudi Arabia to work with UNEP and UNIDO so that the second (2026) tranche of stage II of the HPMP could be submitted to the 99th meeting, on the understanding that the 20 per cent disbursement threshold for funding of the previous tranche had been achieved. |
|  | UNIDO | 2026 | 3,843,800 | 20 per cent disbursement threshold/ ExCom approval conditions |  |
| Sierra Leone (HPMP stage II) | UNEP | 2026 | 79,100 | Government decisions/endorsements/ changes in the NOU | Noting the delays due to the change in ministers within the Government and urging the Government of Sierra Leone to work with UNEP so that the third (2026) tranche of stage II of the HPMP could be submitted to the 99th meeting. |
| Sudan (the) (HPMP stage III) | UNIDO | 2026 | 120,375 | 20 per cent disbursement threshold/ExCom approval conditions | Noting the delays due to non-compliance with the ExCom approval conditions and that the overall disbursement rate of the first (2021) tranche of stage III of the HPMP was below the 20 per cent disbursement threshold and urging the Government of the Sudan to work with UNIDO so that the second (2026) tranche of stage III of the HPMP could be submitted to the 100th meeting with a revised plan of action to take into account the reallocation of the 2026 and subsequent tranches, on the understanding that the 20 per cent disbursement threshold for funding of the previous tranche had been achieved. |
| Syrian Arab Republic (HPMP stage I) | UNEP | 2024 | 445,295 | Government decisions/endorsements/ changes in the NOU/sufficient funds from previous tranche approved/20 per cent disbursement threshold | Noting the delays due to change of ministry and NOU and that the overall disbursement rate of the second (2022) tranche of stage I of the HPMP was below the 20 per cent disbursement threshold and urging the Government of Syrian Arab Republic to work with UNEP and UNIDO so that the third (2024) tranche of stage I of the HPMP could be submitted to the 99th meeting with a revised plan of action to take into account the reallocation of the 2024 and subsequent tranches where necessary, on the understanding that the 20 per cent disbursement threshold for funding of the previous tranche had been achieved. |
|  | UNIDO | 2024 | 924,965 | Government decisions/endorsements/ changes in the NOU/20 per cent disbursement threshold |  |
| Thailand (HPMP stage II) | World Bank | 2022 | 186,763 | Sufficient funds from previous tranche approved | Noting that sufficient funds remain available from the previously approved tranche; that stage II of the HPMP was completed at the end of 2025 and its project completion report was submitted to the 98th meeting; and that the third and final (2022) tranche of stage II of the HPMP will not be requested in the future. |
| Timor-Leste (HPMP stage II) | UNDP | 2025 | 15,173 | Operational delays | Noting that sufficient funds remain available from the previously approved tranche and urging the Government of Timor-Leste to work with UNDP and UNEP so that the fourth (2025) tranche of stage II of the HPMP could be submitted to the 99th meeting with a revised plan of action to take into account the reallocation of the 2025 tranche where necessary. |
|  | UNEP | 2025 | 23,594 | Sufficient funds from previous tranche approved |  |
| United Republic of Tanzania (the) (HPMP stage II) | UNEP | 2026 | 138,425 | Government decisions/endorsements/ changes in the NOU | Noting the delays due to the political unrest and urging the Government of the United Republic of Tanzania to work with UNEP and UNIDO so that the second (2026) tranche of stage II of the HPMP could be submitted to the 99th meeting. |
|  | UNIDO | 2026 | 76,300 | Government decisions/endorsements/ changes in the NOU |  |
| Uruguay (HPMP stage III) | UNDP | 2026 | 349,483 | Procurement delays | Noting the delays due to the procurement of tools and equipment and urging the Government of Uruguay to work with UNDP and UNIDO so that the third (2026) tranche of stage III of the HPMP could be submitted to the 99th meeting. |
|  | UNIDO | 2026 | 30,215 | Government decisions/endorsements/ changes in the NOU |  |
| Venezuela (Bolivarian Republic of) (HPMP stage II) | UNIDO | 2025 | 526,654 | Internal or external difficulties | Noting the delays due to external factors that affected the implementation of the project and urging the Government of the Bolivarian Republic of Venezuela to work with UNIDO so that the fourth (2025) tranche of stage II of the HPMP could be submitted to the 99th meeting with a revised plan of action to take into account the reallocation of the 2025 and subsequent tranches where necessary. |
| Viet Nam (HPMP stage III) | World Bank | 2026 | 4,932,894 | 20 per cent disbursement threshold | Noting that the overall disbursement rate of the first (2023) tranche of stage III of the HPMP was below the 20 per cent disbursement threshold, and urging the Government of Viet Nam to work with the World Bank so that the second (2026) tranche of stage III of the HPMP could be submitted to the 100th meeting with a revised plan of action to take into account the reallocation of the 2026 and subsequent tranches, on the understanding that the 20 per cent disbursement threshold for funding of the previous tranche had been achieved. |
| Total |  |  | 23,997,408 |  |  |

UNEP/OzL.Pro/ExCom/98/1

The Executive Committee decided that a separate sub-agenda item on delays in the submission of annual tranches and disbursement of funds for tranches and obligations should be included for future meetings.

UNEP/OzL.Pro/ExCom/97/19, paragraph 10 and annex I.

The document on tranche submission delays would only be submitted at the first Executive Committee meeting of the year.

Including tranches of HCFC phase-out management plans (HPMPs) for two countries which were submitted but subsequently withdrawn.

UNEP/OzL.Pro/ExCom/98/5

See document UNEP/OzL.Pro/ExCom/98/6, section I on “Projects with implementation delays and for which special status reports were requested”.

See document UNEP/OzL.Pro/ExCom/98/6

See document UNEP/OzL.Pro/ExCom/98/6

See document UNEP/OzL.Pro/ExCom/98/49