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PROGRESS REPORT OF BILATERAL COOPERATION AS AT 31 DECEMBER 2022

Introduction

The following non-Article 5 countries currently involved in bilateral cooperation activities submitted progress report[footnoteRef:2] databases: Australia, Canada, France, Germany, Italy, Japan, and Spain. Additional data from earlier progress reports for other non-Article 5 countries previously involved in bilateral cooperation,[footnoteRef:3] covering data for the projects already reported as financially completed, are included in the consolidated progress report.[footnoteRef:4] [2:  Progress reports are the only means for indicating the final closure of all funding accounts associated with projects approved by the Executive Committee for bilateral cooperation.]  [3:  Austria, Belgium, the Czech Republic, Denmark, Finland, Hungary, Israel, Poland, Portugal, the Russian Federation, Singapore, the Slovak Republic, South Africa, Sweden, Switzerland, the United Kingdom of Great Britain and Northern Ireland, and the United States of America.]  [4:  UNEP/OzL.Pro/ExCom/93/14] 

The progress report of the bilateral cooperation includes the implementation status of projects, including seven HFC-related projects funded under the additional voluntary contributions by 17 non‑Article 5 Parties to provide fast-start support for the implementation of the Kigali Amendment.
The Secretariat reviewed the status of implementation of each ongoing project on a country‑by‑country basis, taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2022, the potential impact of these delays on the phase‑out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs, which are measured in CO2-eq tonnes.[footnoteRef:5] [5:  In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 93rd meeting.] 

This document consists of the following sections:
[bookmark: _Hlk115854077]I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2022 and cumulative since 1992 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs). It also contains a review on the status of implementation of each ongoing[footnoteRef:6] project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee. [6:  Ongoing projects are all projects that were under implementation as at 31 December 2022. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.] 

II.	Projects approved for Annex F substances (HFCs) under the additional voluntary contributions for fast‑start support for HFC phase-down.[footnoteRef:7] [7:  In line with decision 84/12(b), a detailed progress report providing an overview of the objectives, status of implementation, key findings and lessons learned, the amounts of HFC phased out where applicable, the level of funds approved and disbursed and potential challenges in completing the projects and activities, is presented in the consolidated progress report (UNEP/OzL.Pro/ExCom/93/14).] 

III.	Recommendation.

I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund

I.1	Progress in implementation of projects for 2022 and cumulative since 1992

As of 31 December 2022, the Executive Committee had approved US $187.5 million in projects for the bilateral agencies, consisting of US $170.95 million for the implementation of investment and non‑investment projects and US $16.56 million for agency support costs, as shown in table 1. 
Table 1: Approved funding by sector for bilateral agencies as at 31 December 2022
	Sector
	Funding (US $)

	Aerosol
	2,051,914

	Destruction
	1,526,282

	Foam
	8,093,731

	Halon
	6,147,361

	HFC phase-down plan
	609,000

	Fumigants
	18,226,925

	Phase-out plan
	76,107,711

	Production
	10,000,000

	Refrigeration
	40,910,116

	Several
	4,759,718

	Solvents
	2,512,738

	Sub-total
	170,945,495

	Agency support costs
	16,559,425

	Total
	187,504,921



In 2022, six new projects and activities were approved. This level of funding is expected to result in the phase-out of 10,538 ODP tonnes and 70,104 CO2-eq tonnes of consumption of controlled substances. Annex I shows the status of project implementation per country in 2022.
Table 2 shows the status of project implementation including fund disbursement per project type as at 31 December 2022. Annex II presents analytical information per year since 1992.
Table 2. Status of project implementation by type as at 31 December 2022
	Type
	Number of projects*
	Funding (US $)**

	
	Approved
	Completed
	% completed
	Approved
	Disbursed
	Balance
	% disbursed

	Country programme
	9
	9
	100
	340,787
	340,787
	0
	100

	Demonstration
	38
	38
	100
	9,409,431
	9,409,431
	0
	100

	Institutional strengthening (IS)
	7
	7
	100
	883,376
	883,376
	0
	100

	Investment
	256
	212
	83
	117,744,581
	105,492,446
	12,252,136
	90

	Project preparation
	132
	123
	93
	6,160,111
	5,491,245
	668,866
	89

	Technical assistance
	214
	208
	97
	27,985,793
	26,329,635
	1,656,158
	94

	Training 
	73
	73
	100
	8,421,416
	8,421,416
	0
	100

	Total
	729
	[bookmark: RANGE!C24]670
	92
	170,945,495
	156,368,336
	14,577,159
	91


* Excludes closed and transferred projects.
** Excludes agency support costs.

Implementation of projects and activities by the bilateral agencies for 2022 and cumulative since 1992 up to 31 December 2022 is summarized as follows and in table 3:
Phase-out:[footnoteRef:8] In 2022, 43.2 ODP tonnes of consumption of controlled substances were phased out[footnoteRef:9] and an additional 51.6 ODP tonnes of consumption of controlled substances were approved for phase-out. Since 1992, 9,256 ODP tonnes and 65,242 CO2-eq tonnes of consumption of controlled substances had been phased out, of an expected total of 10,538 ODP tonnes and 70,104 CO2-eq tonnes from projects approved (excluding cancelled and transferred projects); [8:  Phase-out of ODS is expressed in ODP tonnes and of HFCs in CO2-eq tonnes.]  [9:  No phase-out for HFC-related projects in 2022.] 

Disbursements/approvals: In 2022, US $3.6 million was disbursed and US $3.55 million was planned for disbursement based on the 2021 progress report, representing a rate of disbursement of 101 per cent of that planned. Cumulatively, US $156.37 million had been disbursed out of the total US $170.95 million approved for disbursement (excluding agency support costs), representing a rate of disbursement of 91 per cent. In 2022, US $3.82 million was approved for implementation;
Number of projects completed: In 2022, seven projects were completed. Since 1992, 670 projects of the 729 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 92 per cent;
Speed of delivery – investment projects: Projects that were completed in 2022 were completed on average 56 months after their approval. Since 1992, the average time for completion of investment projects has been 42 months after their approval. First disbursements under these projects occurred, on average, 11 months after they had been approved;
Speed of delivery – non-investment projects: Projects that were completed in 2022 were completed 43 months after their approval. Since 1992, the average time for completion of non-investment projects has been 44 months after their approval. First disbursements under these projects occurred, on average, 13 months after they had been approved;
Project preparation: Of the 132 project preparation activities approved by the end of 2022, 123 have been completed, leaving nine ongoing activities. In 2022, no preparation activities were completed;
Implementation delays: A total of 59 projects were under implementation at the end of 2022, experiencing, on average, a delay of 17 months. Fourteen of these projects are classified as “projects with implementation delays”[footnoteRef:10] that are subject to the procedures of project cancellation (as demonstration projects, project preparation and IS are not subject to those procedures); and [10:  Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61). ] 

Multi-year agreements (MYAs): In 2022, 26 MYAs for HCFC phase-out management plans (HPMPs) were under implementation. Since 1992, 87 MYAs have been approved and 61 MYAs have been completed, representing a completion rate of 70 per cent.
Table 3 summarized progress made by the bilateral agencies since 1992. 
Table 3. Progress made by bilateral agencies since 1992 
	Phase out achieved
	Disbursement (US $)
	Number 
of projects
	Speed of delivery for completion (months)
	Average project delays (months)
	Number of MYAs

	ODP tonnes
	CO2-eq tonnes
	
	Approved
	Completed
	Investment
	Non- investment
	
	Approved
	Completed

	9,256
	65,242
	156,368,336
	729
	670
	42
	44
	17
	87
	61



HFC-related projects

As of 31 December 2022, the Executive Committee had approved 13 HFC-related projects (including three investment projects, five project preparation and five enabling activities) under regular contributions amounting to US $1,663,988 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 5 to 9. 
Table 4. HFC-related projects approved under regular contributions
	Type
	Number of projects
	Funding (US $)*

	
	Approved
	Completed
	% completed
	Approved
	Disbursed
	Balance
	% disbursed

	Investment**
	3
	2
	67
	764,988
	664,988
	100,000
	87

	Project preparation
	5
	0
	0
	609,000
	8,337
	600,663
	1

	Technical assistance - Enabling activities
	5
	5
	100
	290,000
	290,000
	0
	100

	Total
	13
	7
	54
	1,663,988
	963,325
	700,663
	58


* Excludes agency support costs. 
** 45.5 mt (65,242 CO2-eq tonnes) of 48.9 mt (70,104 CO2-eq tonnes) of HFCs had been phased out.

As of the end of 2022, of the 13 projects approved, two investment projects and five enabling activities had been completed, leaving six ongoing. 
The five ongoing project preparation activities are for the preparation of Kigali HFC implementation plans and are expected to be completed in 2023 and 2024. The remaining ongoing investment project, approved at the 82nd meeting, with no funds disbursed, is expected to be completed in 2023. Extension of the completion date of this project was approved.
Of the total cumulative funding approved of US $1,663,988, US $963,325 had been disbursed, representing a disbursement rate of 58 per cent.
I.2	Issues identified in project implementation in 2022

Further to the review process, several issues were discussed with relevant bilateral agencies and satisfactorily addressed, except for issues on 14 projects classified as projects with implementation delays (including 13 projects related to components of MYAs that are subject to procedures for project cancellation, in line with decision 84/45(c); and one HFC investment project). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 94th meeting.
In addition, issues have been identified regarding tranches of MYAs for the phase-out of HCFCs. These issues are also presented in annex III. For each of these projects, a brief description on the status of implementation and the outstanding issues are presented and a recommendation is proposed for consideration by the Executive Committee.
Details of progress in implementation of projects associated with the HPMPs for China (servicing sector plan)[footnoteRef:11] and Colombia[footnoteRef:12] (both implemented by Germany), and Nigeria[footnoteRef:13] (implemented by Italy) have been submitted to the 93rd meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. The issues relating to the HPMPs for Kenya (implemented by France) and Mauritius (implemented by Germany), tranches of which were due at the 93rd meeting but were not submitted, and for China (room air‑conditioner manufacturing sector plan) (implemented by Austria), the tranche of which was submitted but later withdrawn, are addressed in the document on tranche submission delays.[footnoteRef:14] Outstanding issues for the remaining ongoing projects not included in annex III to the present document, and requests for extension of dates of completion, are addressed below. [11:  UNEP/OzL.Pro/ExCom/93/47]  [12:  UNEP/OzL.Pro/ExCom/93/48]  [13:  UNEP/OzL.Pro/ExCom/93/77]  [14:  UNEP/OzL.Pro/ExCom/93/24] 

Of the 50 ongoing projects, excluding project preparation, 19 projects have revised planned dates of completion since the 2021 progress report. 
In line with decision 82/11(b),[footnoteRef:15] the Government of Germany has requested the extension of the duration of one project as shown in table 5. [15:  Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.] 

 Table 5. Project for which an extension of the completion date has been requested
	Country/project code
	Project title
	Disburse-ment (%)
	Status/issues
	Original date of completion
	Date of completion requested

	Egypt
EGY/PHA/84/INV/142
	HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector)
	10
	Additional time required to complete the remaining training activities with equipment delivered at end of 2023
	Dec-23
	Jun-24



II.	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down

As of 31 December 2022, the Executive Committee had approved seven HFC-related projects for two bilateral agencies (Germany and Italy) under the additional voluntary contributions amounting to US $480,000 (excluding agency support costs). A summary of the status of these projects is presented in table 6. 
Table 6. Status of approved HFC-related projects as of the end of 2022
	Type
	Number of projects
	Funding (US $)*

	
	Approved
	Completed
	% completed
	Approved
	Disbursed
	Balance
	% disbursed

	Technical assistance – Enabling activities
	7
	7
	100
	480,000
	[bookmark: RANGE!F12]479,080
	920
	99.8


* Excludes agency support costs.
As of the end of 2022, all of the seven enabling activities approved had been completed.
Of the total cumulative funding approved of US $480,000, US $479,080 had been disbursed, representing a disbursement rate of 99.8 per cent. 
III.	Recommendation

The Executive Committee may wish:
To note, with appreciation, the progress reports submitted by the Governments of Australia, Canada, France, Germany, Italy, Japan and Spain contained in document UNEP/OzL.Pro/ExCom/93/15; 
To approve the extension, to 30 June 2024, of the completion date of stage II of the HCFC phase‑out management plan for Egypt (second tranche (refrigeration servicing sector) (EGY/PHA/84/INV/142)), to allow for completion of the remaining ongoing activities as reflected in table 5 of document UNEP/OzL.Pro/ExCom/93/15; and
(a) To approve the recommendations related to ongoing projects with specific issues contained in annex III to the present document. 

UNEP/OzL.Pro/ExCom/93/15


UNEP/OzL.Pro/ExCom/93/15



Pre-session documents of the Executive Committee of the Multilateral Fund for the Implementation of the Montreal Protocol are without prejudice to any decision that the Executive Committee might take following issuance of the document.

2

3
Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR BILATERAL AGENCIES PER COUNTRY FOR 2022

1. Table 1 of annex I presents the status of project implementation by country for 2022 in achieved phased out, planned and achieved disbursements and project completion. 
[bookmark: _Hlk115855444]Table 1. Status of project implementation for 2022
	Country
	Phased out in 2022 (ODP tonnes)
	Phased out in 2022 (CO2-eq tonnes)*
	Estimated funds disbursed in 2022 (US$)
	Funds disbursed in 2022 (US$)
	Percentage of funds disbursed over estimation in 2022
	Percentage of planned projects completed in 2022**

	Argentina
	1.3
	0
	20,000
	0
	0
	 

	Bangladesh
	0.0
	0
	 
	 
	 
	100

	Belize
	0.0
	0
	 
	 
	 
	100

	Brazil
	17.0
	0
	940,000
	1,569,834
	167
	 

	Burkina Faso
	0.0
	0
	10,000
	112
	1
	 

	China
	0.0
	0
	238,000
	259,995
	109
	 

	Colombia
	0.0
	0
	47,800
	46,652
	98
	0

	Cuba
	0.0
	0
	 
	 
	 
	100

	Egypt
	0.0
	0
	30,000
	15,307
	51
	 

	India
	0.0
	0
	363,484
	449,000
	124
	100

	Iran (Islamic Republic of)
	1.2
	0
	197,558
	88,683
	45
	0

	Kenya
	0.0
	0
	89,861
	76,697
	85
	 

	Lao People's Democratic Republic (the)
	0.0
	0
	45,000
	0
	0
	0

	Lesotho
	0.0
	0
	45,732
	5,732
	13
	 

	Liberia
	3.2
	0
	20,850
	17,977
	86
	100

	Mauritius
	3.1
	0
	85,000
	57,134
	67
	 

	Mexico
	4.9
	0
	622,000
	450,500
	72
	33

	Mongolia
	0.0
	0
	3,000
	1,522
	51
	 

	Namibia
	0.0
	0
	39,323
	20,517
	52
	 

	Nigeria
	3.5
	0
	294,113
	252,366
	86
	0

	Papua New Guinea
	0.0
	0
	135,665
	68,860
	51
	0

	Seychelles
	1.0
	0
	12,555
	12,561
	100
	0

	Tunisia
	0.0
	0
	1
	0
	0
	 

	Viet Nam
	0.0
	0
	175,592
	98,090
	56
	0

	Zimbabwe
	8.0
	0
	61,057
	64,384
	105
	100

	Region: ASP
	0.0
	0
	70,000
	43,000
	61
	 

	Grand total
	43.2
	0
	3,546,591
	3,598,923
	101
	37


* No phase-out in 2022 for HFC-related projects.
** For projects that were planned to be completed in 2022.
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Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR BILATERAL AGENCIES PER YEAR AS AT 31 DECEMBER 2022

1. Table 1 of annex II presents an overview of the status of project implementation by year.[footnoteRef:16] All projects and activities approved between 1992 and 2012 and 2014, have now been completed.  [16:  The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.] 

Table 1. Status of project implementation by year
	Year
	Number of projects*
	Funding (US $)**

	
	Approved
	Completed
	% completed
	Approved
	Disbursed
	Balance
	% disbursed

	1992
	18
	18
	100
	2,883,669
	2,883,669
	0
	100

	1993
	10
	10
	100
	1,445,586
	1,445,586
	0
	100

	1994
	30
	30
	100
	3,190,374
	3,190,374
	0
	100

	1995
	17
	17
	100
	4,654,902
	4,654,902
	0
	100

	1996
	26
	26
	100
	3,468,211
	3,468,211
	0
	100

	1997
	32
	32
	100
	4,040,251
	4,040,251
	0
	100

	1998
	39
	39
	100
	4,108,525
	4,108,525
	0
	100

	1999
	59
	59
	100
	12,131,407
	12,131,407
	0
	100

	2000
	29
	29
	100
	4,808,878
	4,808,878
	0
	100

	2001
	41
	41
	100
	7,523,213
	7,523,213
	0
	100

	2002
	61
	61
	100
	7,910,174
	7,910,174
	0
	100

	2003
	32
	32
	100
	6,810,120
	6,810,120
	0
	100

	2004
	30
	30
	100
	15,005,412
	15,005,412
	0
	100

	2005
	28
	28
	100
	18,183,034
	18,183,034
	0
	100

	2006
	25
	25
	100
	7,128,808
	7,128,808
	0
	100

	2007
	13
	13
	100
	3,138,440
	3,138,440
	0
	100

	2008
	33
	33
	100
	7,531,037
	7,531,037
	-1
	100

	2009
	21
	21
	100
	2,347,228
	2,347,228
	0
	100

	2010
	20
	20
	100
	3,278,389
	3,278,389
	-1
	100

	2011
	20
	20
	100
	6,821,798
	6,821,798
	0
	100

	2012
	11
	11
	100
	6,594,959
	6,594,959
	0
	100

	2013
	7
	6
	86
	2,276,412
	2,270,857
	5,555
	100

	2014
	14
	14
	100
	1,365,834
	1,365,618
	216
	100

	2015
	26
	25
	96
	4,921,949
	4,712,010
	209,939
	96

	2016
	16
	10
	63
	5,129,894
	3,644,955
	1,484,939
	71

	2017
	9
	4
	44
	2,605,614
	2,112,727
	492,887
	81

	2018
	16
	10
	63
	7,050,550
	5,387,717
	1,662,833
	76

	2019
	6
	2
	33
	1,922,831
	1,091,160
	831,671
	57

	2020
	13
	4
	31
	4,136,467
	1,859,795
	2,276,672
	45

	2021
	21
	0
	0
	4,708,887
	919,082
	3,789,805
	20

	2022
	6
	0
	0
	3,822,643
	0
	3,822,643
	0

	Total
	729
	670
	92
	170,945,495
	156,368,336
	14,577,159
	91


* Excludes closed and transferred projects.
** Excludes agency support costs. 
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Annex III

ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR BILATERAL AGENCIES
	Country/project code
	Agency
	Project title
	Disbursement (%)
	Status/Issues
	Recommendation

	Kenya
KEN/PHA/80/INV/62
	France
	HCFC phase-out management plan (stage II, first tranche)
	71
	12 months delays
	To request the Government of France to report to the 94th meeting on this project with implementation delays

	Kenya
KEN/PHA/86/INV/65
	France
	HCFC phase-out management plan (stage II, second tranche)
	0
	18 months delays
	To request the Government of France to report to the 94th meeting on this project with implementation delays

	Zimbabwe
ZIM/REF/82/INV/56
	France
	Conversion from HFC-134a to isobutane in the manufacture of domestic refrigerators at Capri (SME Harare)
	0
	18 months delays
	To request the Government of France to report to the 94th meeting on this project with implementation delays

	Brazil
BRA/PHA/82/TAS/321
	Germany
	HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector)
	77
	12 months delays
	To request the Government of Germany to report to the 94th meeting on this project with implementation delays

	Iran (Islamic Republic of)
IRA/PHA/86/INV/250
	Germany
	HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration sector)
	0
	18 months delays
	To request the Government of Germany to report to the 94th meeting on this project with implementation delays

	Mauritius
MAR/PHA/79/INV/27
	Germany
	HCFC phase-out management plan (third tranche)
	55
	Implementation of activities delayed
	To request the Government of Germany to report to the 94th meeting on the status of implementation of activities 

	Mauritius
MAR/PHA/86/INV/30
	Germany
	HCFC phase-out management plan (stage I, fourth tranche)
	0
	(i) 18 months delays 
(ii) Implementation of activities delayed
	(i) To request the Government of Germany to report to the 94th meeting on this project with implementation delays
(ii) To request the Government of Germany to report to the 94th meeting on the status of implementation of activities 

	Mexico
MEX/PHA/77/INV/179
	Germany
	HCFC phase-out management plan (stage II, second tranche) (HC demonstration and training)
	23
	12 months delays
	To request the Government of Germany to report to the 94th meeting on this project with implementation delays

	Namibia
NAM/PHA/79/INV/23
	Germany
	HCFC phase-out management plan (third tranche)
	37
	Implementation of activities delayed
	To request the Government of Germany to report to the 94th meeting on the status of implementation of activities

	Papua New Guinea
PNG/PHA/77/INV/15
	Germany
	HCFC phase-out management plan (third tranche)
	94
	12 months delays
	To request the Government of Germany to report to the 94th meeting on this project with implementation delays

	Seychelles
SEY/PHA/70/INV/19
	Germany
	HCFC phase-out management plan (second tranche)
	97
	(i) 12 months delays
(ii) Implementation of activities delayed
	(i) To request the Government of Germany to report to the 94th meeting on this project with implementation delays
(ii) To request the Government of Germany to report to the 94th meeting on the status of implementation of activities 

	Seychelles
SEY/PHA/75/INV/23
	Germany
	HCFC phase-out management plan (stage I, third tranche)
	6
	Implementation of activities delayed
	To request the Government of Germany to report on the status of implementation of activities to the 94th meeting

	Iran (Islamic Republic of)
IRA/PHA/77/INV/224
	Italy
	HCFC phase-out management plan (stage II, first tranche) (foam sector)
	16
	12 months delays
	To request the Government of Italy to report to the 94th meeting on this project with implementation delays

	Iran (Islamic Republic of)
IRA/PHA/84/INV/237
	Italy
	HCFC phase-out management plan (stage II, second tranche) (foam sector)
	0
	12 and 18 months delays
	To request the Government of Italy to report to the 94th meeting on this project with implementation delays

	Mexico
MEX/PHA/77/INV/180
	Spain
	HCFC phase-out management plan (stage II, second tranche) (cleaning agent phase-out in refrigeration servicing sector)
	100
	12 months delays
	Noting decision 77/8(j), to request the Government of Spain to report to the 94th meeting on this project with implementation delays

	Mexico
MEX/PHA/77/INV/185
	Spain
	HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector)
	100
	12 months delays
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