| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/97/24 4 November 2025 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-seventh Meeting

Montreal, 1-5 December 2025

Item 8(c)(iv) of the provisional agenda

UNIDO BUSINESS PLAN FOR 2026–2028

# Introduction

# This document presents the UNIDO business plan for 2026–2028 and includes the planned activities for the reduction of controlled substances and other activities under the Montreal Protocol during the period 2026–2028. The narrative of UNIDO’s business plan for 2026–2028 is attached to the present document.

# This document consists of the following sections:

- Planned activities during the period 2026–2028

- Secretariat’s comments

- Proposed adjustments by the Secretariat

- Performance indicators

- Recommendation

I.	Planned activities during the period 2026–2028

# Table 1 sets out, by year, the value of activities included in UNIDO’s business plan.

Table 1. Resource allocation in the UNIDO business plan for 2026–2028 (US $)* – as submitted

| Description | 2026 | 2027 | 2028 | Total (2026–2028) | Total after 2028 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 24,622,419 | 16,694,368 | 6,067,594 | 47,384,381 | 7,436,020 |
| HPMP stage II | 209,241 | 893,108 | 537,636 | 1,639,986 | 397,933 |
| HPMP stage III – project preparation (PRP) | 0 | 42,800 | 0 | 42,800 | 0 |
| HPMP stage III | 2,502,788 | 9,682,722 | 6,771,140 | 18,956,651 | 3,202,825 |
| HPMP – energy efficiency (decision 89/6) | 70,620 | 38,520 | 0 | 109,140 | 0 |
| HCFC activities subtotal | 27,405,068 | 27,351,519 | 13,376,370 | 68,132,958 | 11,036,778 |
| HFC activities |  |  |  |  |  |
| Approved Kigali HFC implementation plans (KIPs) | 1,405,039 | 18,125,130 | 342,650 | 19,872,819 | 6,025,296 |
| Approved HFC-23 emission control | 584,100 | 552,371 | 509,571 | 1,646,042 | 1,170,921 |
| KIP stage I – PRP | 1,143,303 | 413,377 | 0 | 1,556,680 | 0 |
| KIP stage I | 1,574,047 | 2,486,979 | 3,929,546 | 7,990,571 | 2,102,819 |
| KIP stage I – investment | 0 | 339,000 | 0 | 339,000 | 0 |
| HFC activities subtotal | 4,706,489 | 21,916,856 | 4,781,767 | 31,405,112 | 9,299,036 |
| Other activities |  |  |  |  |  |
| Pilot projects for energy efficiency – preparation (decision 91/65) | 53,500 | 0 | 0 | 53,500 | 0 |
| Pilot projects for energy efficiency (decision 91/65) | 2,407,500 | 3,210,000 | 0 | 5,617,500 | 0 |
| Energy efficiency (decision 94/60) – preparation | 53,500 | 0 | 0 | 53,500 | 0 |
| Energy efficiency (decision 94/60) | 6,420,000 | 0 | 0 | 6,420,000 | 0 |
| Other activities subtotal | 8,934,500 | 3,210,000 | 0 | 12,144,500 | 0 |
| Standard activities |  |  |  |  |  |
| Institutional strengthening (IS) | 2,637,276 | 3,312,748 | 1,505,539 | 7,455,563 | 0 |
| Core unit | 2,108,424 | 2,123,183 | 2,138,045 | 6,369,652 | 0 |
| Standard activities subtotal | 4,745,700 | 5,435,931 | 3,643,584 | 13,825,215 | 0 |
| Total | 45,791,757 | 57,914,307 | 21,801,721 | 125,507,785 | 20,335,815 |

* Including agency support costs where applicable.

# II.	Secretariat’s comments

II.1	HCFC activities

# Stage II of HPMPs

# The total level of funding for stage II of HPMPs for four low-volume-consuming (LVC) countries to meet the 100 per cent reduction of the HCFC baseline amounts to US $930,899 (including US $639,419 for 2026–2028 and US $291,480 for the period after 2028).

# The total level of funding for stage II of HPMPs for two non-LVC countries amounts to US $1.11 million (including US $1 million for 2026–2028 and US $106,453 for the period after 2028).

# Stage III of HPMPs

# The total level of funding for stage III of HPMPs for three LVC countries to meet the 100 per cent reduction of the HCFC baseline amounts to US $788,852 (including US $742,950 for 2026–2028 and US $45,901 for the period after 2028).

# The total level of funding for stage III of HPMPs for 11 non-LVC countries amounts to US $21.37 million (including US $18.21 million for 2026–2028 and US $3.16 million for the period after 2028).

# A total of US $42,800 is included in the business plan for the preparation of stage III of the HPMP for one country for 2027.

# Energy efficiency for LVC countries (decision 89/6)

# A total of US $109,140 is included in the business plan for energy efficiency activities for three LVC countries for 2026–2027.

II.2	HFC-related activities

# KIP project preparation

# A total of US $1.56 million is included in the business plan for the preparation of stage I of the KIPs for 15 countries in 2026–2027.

# Of the 15 countries for which KIP project preparation activities have been included, 11 have not yet ratified the Kigali Amendment, but have submitted the required letter from their respective Government indicating their intent to make best efforts to ratify the Kigali Amendment in line with decision 84/46(f).

# Stage I of KIPs

# A total of US $10.09 million is included in the business plan for stage I of the KIPs for 20 countries (including US $7.99 million for 2026–2028 and US $2.1 million for the period after 2028). In addition, UNIDO also included a KIP investment project for one country amounting to US $339,000 in 2027. All these countries have ratified the Kigali Amendment.

II.3	Other activities

Pilot projects for energy efficiency (decision 91/65)

# A total of US $5.62 million is included in the business plan under the funding window for pilot projects for energy efficiency for 2026–2027 for six countries. A total of US $53,500 is included in the business plan for project preparation for one country for 2026.

Energy efficiency (decision 94/60)

# A total of US $6.42 million is included in the business plan for projects under the funding window for energy efficiency per decision 94/60 for three countries in 2026. A total of US $53,500 is included in the business plan for project preparation for one country for 2026.

# II.4	Core unit costs

# The core unit costs are expected to increase at an annual rate of 0.7 per cent as agreed.

III.	Proposed adjustments by the Secretariat

# The adjustments to the UNIDO business plan for 2026–2028 were based on relevant decisions of the Executive Committee. In reviewing the revised UNIDO business plan for 2026–2028, the Secretariat noted that the following adjustments were not included:

Table 2. Adjustments to the UNIDO business plan for 2026–2028 (US $)* – as proposed by the Secretariat

| Adjustment | 2026–2028 | After 2028 |
| --- | --- | --- |
| MYA values to reflect the actual amounts approved under the Agreements, including MYA tranches: (i) that have been submitted to the 97th meeting but have subsequently been withdrawn; (ii) that are due but have not been submitted to the 97th meeting; and (iii) that are removed because they have been submitted to the 97th meeting | 533,277 | (108,983) |
| PRP for stage I of KIPs submitted to the 97th meeting | (278,600) | 0 |
| Servicing sector for stage I of KIPs pursuant to decision 92/37 | (343,894) | (152,262) |

* Including agency support costs where applicable.

# Table 3 presents the results of the Secretariat’s proposed adjustments to the UNIDO business plan for 2026–2028, which are also addressed in the context of the consolidated business plan of the Multilateral Fund for 2026–2028.

# Table 3. Resource allocation in UNIDO’s adjusted business plan for 2026–2028 (US $)*

| Description | 2026 | 2027 | 2028 | Total (2026–2028) | Total after 2028 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HPMPs | 25,326,693 | 16,694,368 | 6,067,594 | 48,088,655 | 7,436,020 |
| HPMP stage II | 209,241 | 893,108 | 537,636 | 1,639,986 | 397,933 |
| HPMP stage III – PRP | 0 | 42,800 | 0 | 42,800 | 0 |
| HPMP stage III | 2,502,788 | 9,682,722 | 6,771,140 | 18,956,651 | 3,202,825 |
| HPMP – energy efficiency (decision 89/6) | 70,620 | 38,520 | 0 | 109,140 | 0 |
| HCFC activities subtotal | 28,109,342 | 27,351,519 | 13,376,370 | 68,837,232 | 11,036,778 |
| HFC activities |  |  |  |  |  |
| Approved KIPs | 1,245,709 | 18,125,130 | 342,650 | 19,713,489 | 6,025,296 |
| Approved HFC-23 emission control | 572,433 | 552,371 | 509,571 | 1,634,375 | 1,061,938 |
| KIP stage I – PRP | 864,703 | 413,377 | 0 | 1,278,079 | 0 |
| KIP stage I | 1,574,047 | 2,143,085 | 3,929,546 | 7,646,678 | 1,950,558 |
| KIP stage I – investment | 0 | 339,000 | 0 | 339,000 | 0 |
| HFC activities subtotal | 4,256,891 | 21,572,963 | 4,781,767 | 30,611,621 | 9,037,792 |
| Other activities |  |  |  |  |  |
| Pilot projects for energy efficiency – preparation (decision 91/65) | 53,500 | 0 | 0 | 53,500 | 0 |
| Pilot projects for energy efficiency (decision 91/65) | 2,407,500 | 3,210,000 | 0 | 5,617,500 | 0 |
| Energy efficiency (decision 94/60) – preparation | 53,500 | 0 | 0 | 53,500 | 0 |
| Energy efficiency (decision 94/60) | 6,420,000 | 0 | 0 | 6,420,000 | 0 |
| Other activities subtotal | 8,934,500 | 3,210,000 | 0 | 12,144,500 | 0 |
| Standard activities |  |  |  |  |  |
| IS | 2,637,276 | 3,312,748 | 1,505,539 | 7,455,563 | 0 |
| Core unit | 2,108,424 | 2,123,183 | 2,138,045 | 6,369,652 | 0 |
| Standard activities subtotal | 4,745,700 | 5,435,931 | 3,643,584 | 13,825,215 | 0 |
| Total | 46,046,433 | 57,570,413 | 21,801,721 | 125,418,568 | 20,074,570 |

*Including agency support costs where applicable.

IV.	Performance indicators

# UNIDO submitted performance indicators pursuant to decision 93/8(d) in its business plan narrative. The Secretariat informed UNIDO of the targets shown in table 4.

Table 4. Performance indicators for UNIDO for 2026

| Type of indicator | Short title | Calculation | 2026 target |
| --- | --- | --- | --- |
| Planning-Approval | Tranches approved | Number of tranches approved vs. those planned* | 51 |
| Planning-Approval | Individual projects/ activities approved | Number of projects/activities approved vs. those planned (including project preparation activities) | 26 |
| Implementation | Funds disbursed | Based on estimated disbursement in progress reports | 18,778,560 |
| Implementation | ODS phase-out for HCFC-related projects | ODS phase-out for HCFC-related projects in ODP tonnes vs. those planned per progress reports | 152.7 ODP tonnes |
| Implementation | HFC phase-down for HFC-related projects | HFC phase-down for HFC-related projects in CO2-eq tonnes vs. those planned per progress reports | 449,139 CO2-eq tonnes |
| Implementation | Project operational completion | Project operational completion vs. planned in progress reports for all activities (excluding project preparation)** | 57 |
| Implementation | Gender mainstreaming | Operational policy on gender mainstreaming applied to all approved projects | 100% |
| Administrative | Speed of financial completion | The extent to which projects are financially completed within 12 months after project operational completion | 12 months after operational completion |
| Administrative | Timely submission of project completion reports | Timely submission of project completion reports based on the progress report | 3 |
| Administrative | Timely submission of progress reports and business plans | Timely submission of progress reports and business plans and responses unless otherwise agreed | On time |

- * The targets of an agency will be reduced if it cannot submit a tranche owing to another cooperating agency or lead agency or if the HCFC phase-out management plan or Kigali HFC implementation plan submitted for consideration by the Executive Committee is not approved as a result of factors beyond the control of the national ozone unit and agency.

- ** The targets of an agency will be reduced if an extension of the completion date has been approved by the Executive Committee.

V.	Recommendation

# The Executive Committee may wish:

## To note the UNIDO business plan for 2026–2028 contained in document UNEP/OzL.Pro/ExCom/97/24; and

## To approve the performance indicators for UNIDO set out in table 4 of document UNEP/OzL.Pro/ExCom/97/24.

UNEP/OzL.Pro/ExCom/97/1

Decision 89/6 allowed bilateral and implementing agencies, when submitting existing and future stages of HPMPs for LVC countries, to include the funding associated with the need for the introduction of alternatives to HCFCs with low- or zero-global-warming potential and for maintaining energy efficiency in the refrigeration servicing sector.

The Executive Committee established a funding window and criteria for pilot projects to maintain and/or enhance energy efficiency of replacement technologies and equipment in the context of HFC phase-down. The duration of the window for the proposal of projects under decision 91/65 only for the servicing activities was extended to the 100th meeting, inclusive (decision 95/87(d)).

The Executive Committee established a funding window for projects developed and implemented under the operational framework to support maintaining and/or enhancing energy efficiency while phasing down HFCs.

UNIDO’s 2026 core unit costs will be considered at the 97th meeting (UNEP/OzL.Pro/ExCom/97/84).

UNEP/OzL.Pro/ExCom/97/20