| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/82/25 1 November 2018 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Eighty-second Meeting

Montreal, 3-7 December 2018

CONSOLIDATED BUSINESS PLAN OF THE MULTILATERAL FUND for 2019–2021

# Introduction

# The Secretariat and the bilateral and implementing agencies began their collaborative efforts on business planning of the Multilateral Fund for 2019–2021 with the submission of the initial business plan tables on 17 August 2018. The total value of the 2019–2021 business plan tables as submitted is summarized in Table 1.

Table 1: Total initial business plan values for 2019–2021 (U$ $000)

| Item | 2019 | 2020 | 2021 | Total (2019–2021) | Total after 2021 |
| --- | --- | --- | --- | --- | --- |
| Grand total | 190,040 | 219,850 | 168,475 | 578,364 | 774,978 |
| Indicative budget | 174,600 | 171,000 | 180,000* | 525,600 |  |
| Difference | 15,440 | 48,850 | (11,525) | 52,764 |  |

* Assumed the same level of the 2018–2020 replenishment of the Multilateral Fund.

# The Secretariat reviewed new activities, in particular stage II of HCFC phase-out management plans (HPMPs) in the light of stage I of HPMPs, remaining funding eligibility and costs, and sent comments to bilateral and implementing agencies. During the Inter-agency coordination meeting (IACM), the Secretariat discussed the issues arising from the review of the initial business plan tables including, inter alia: over-programming, HPMP-related activities, projects in the 2018 business plans but not submitted to the 82nd meeting, the production sector including tranches associated with the HCFC production phase-out management plan (HPPMP) for China, and HFC-related activities.

# Further to the discussion at the IACM, bilateral and implementing agencies revised their business plan tables and resubmitted them with the narrative sections. The total value of the business plan for 2019-2021 is summarized in Table 2.

Table 2: Total revised business plan values for 2019–2021 as submitted (US $000)

| Item | 2019 | 2020 | 2021 | Total (2019–2021) | Total after 2021 |
| --- | --- | --- | --- | --- | --- |
| Grand total | 208,189 | 214,938 | 168,713 | 591,839 | 612,805 |
| Indicative budget | 174,600 | 171,000 | 180,000* | 525,600 |  |
| Difference | 33,589 | 43,938 | (11,287) | 66,239 |  |

* Assumed the same level of the 2018–2020 replenishment of the Multilateral Fund.

Content

# This document presents the consolidated business plans of the Multilateral Fund for 2019–2021 and comprises the business plans for 2019–2021 of bilateral agencies, and UNDP, UNEP, UNIDO and the World Bank submitted to the 82nd meeting.

# This document consists of the following sections:

- Resource allocation in the business plan for 2019–2021

- Secretariat’s comments on activities required for compliance

- Adjustments to the consolidated business plan of the Multilateral Fund for 2019–2021

- Other policy issues

- Recommendation

Resource allocation in the business plan for 2019–2021

# Table 3 presents, by year, the value of activities included in the business plan for 2019–2021. The values exceed the indicative budget by US $66.24 million.

Table 3: Resource allocation in the business plan for 2019–2021 as submitted (US $000)*

| Item | 2019 | 2020 | 2021 | Total (2019–2021) | Total after 2021 |
| --- | --- | --- | --- | --- | --- |
| Required for compliance |  |  |  |  |  |
| Approved HPMPs | 112,573 | 122,081 | 96,856 | 331,509 | 171,697 |
| HPMP stage I | 0 | 354 | 0 | 354 | 500 |
| HPMP stage I – additional funding | 0 | 659 | 0 | 659 | 0 |
| HPMP project preparation (PRP) – stage II | 1,717 | 471 | 131 | 2,318 | 68 |
| HPMP stage II | 1,761 | 17,686 | 5,581 | 25,028 | 71,230 |
| HCFC production – stage II | 29,145 | 29,145 | 29,145 | 87,434 | 142,059 |
| HPMP PRP – stage III | 599 | 701 | 161 | 1,461 | 503 |
| HPMP stage III | 0 | 7,313 | 112 | 7,425 | 226,072 |
| HPMP verification | 589 | 589 | 589 | 1,766 | 0 |
| Required for compliance subtotal | 146,383 | 178,999 | 132,573 | 457,955 | 612,128 |
| HFC activities |  |  |  |  |  |
| HFC – demonstration | 10,180 | 0 | 0 | 10,180 | 0 |
| HFC – enabling activities | 940 | 0 | 0 | 940 | 0 |
| HFC – investment | 15,512 | 0 | 0 | 15,512 | 0 |
| HFC – investment PRP | 180 | 0 | 0 | 180 | 0 |
| HFC activities subtotal | 26,813 | 0 | 0 | 26,813 | 0 |
| Standard activities |  |  |  |  |  |
| Compliance Assistance Programme (CAP) | 11,301 | 11,640 | 11,989 | 34,929 | 0 |
| Core unit | 5,932 | 5,961 | 5,991 | 17,884 | 0 |
| Institutional strengthening (IS) | 10,461 | 10,883 | 10,546 | 31,891 | 677 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 6,799 | 6,954 | 7,114 | 20,868 | 0 |
| Treasurer | 500 | 500 | 500 | 1,500 | 0 |
| Standard activities subtotal | 34,993 | 35,939 | 36,140 | 107,072 | 677 |
| Grand total | 208,189 | 214,938 | 168,713 | 591,839 | 612,805 |
| Indicative budget | 174,600 | 171,000 | 180,000** | 525,600 |  |
| Difference | 33,589 | 43,938 | (11,287) | 66,239 |  |

* Including agency support costs where applicable.

** Assumed the same level of the 2018–2020 replenishment of the Multilateral Fund.

# Secretariat’s comments on activities required for compliance

Production sector

# A total of US $229.49 million is included for the HPPMP for China. This amount includes US $87.43 million for the period 2019–2021 for stage II and US $142.06 million for after 2021. At the 81st meeting, the Executive Committee approved, on an exceptional basis, US $24.29 million (including agency support costs) that would be deducted from the funding of stage II of the HPPMP. Taking into account approvals at the 81st meeting, the average annual level of funding after stage I of the HPPMP starting in 2019 should be US $23.50 million (or US $70.49 million for the period 2019–2021) assuming the maximum amount of funding (US $406.56 million including agency support costs) per decision 69/28(e). Therefore, the proposed level of funding for 2019–2021 would exceed the average annual amount by approximately 24 per cent.

# Stage I of HPMPs and additional projects

# There is one country (Syrian Arab Republic) for which stage I of the HPMP has not yet been approved. The business plan includes US $853,978 for activities, of which US $353,978 is programmed for 2019–2021.

# Implementing agencies included additional funding for projects outside stage I of the HPMPs for two countries (Bahrain and Costa Rica), amounting to US $659,364 for 2019–2021. These requests fall under different decisions of the Executive Committee that allow those countries to submit additional projects during the implementation of stage I of their HPMPs.

# Stage II of HPMPs

# The total level of funding for stage II of HPMPs for low-volume-consuming (LVC) countries is US $25.66 million, of which US $10.18 million is for 2019–2021 to meet the 67.5 per cent reduction of the HCFC baseline in 2025. The value of projects for LVC countries required to meet a 35 per cent reduction in 2020 is US $267,441 including US $194,342 for 2019–2021.

# The total level of funding for stage II of HPMPs in non-LVC countries is US $70.33 million with an associated phase-out of 758.2 ODP tonnes of HCFCs, including US $14.65 million for 2019–2021 with a phase-out of 273.6 ODP tonnes of HCFCs. The funding distribution by sector is provided in Table 4.

Table 4: Funding distribution of stage II of HPMPs in non-LVC countries by sector (US $000)

| Sector | 2019–2021 | After 2021 | Total | Per cent of total (%) |
| --- | --- | --- | --- | --- |
| Rigid foam | 1,092 | 514 | 1,606 | 2.3 |
| Rigid foam and refrigeration servicing | 2,635 | 0 | 2,635 | 3.7 |
| Refrigeration air-conditioning | 853 | 0 | 853 | 1.2 |
| Refrigeration assembly | 178 | 467 | 645 | 0.9 |
| Refrigeration manufacturing | 1,303 | 30,413 | 31,716 | 45.1 |
| Refrigeration servicing | 8,592 | 24,285 | 32,877 | 46.7 |
| Grand total | 14,652 | 55,679 | 70,332 | 100.0 |

HPMP verification

# The Secretariat has included an amount of US $588,600 per year for verification reports, assuming that 18 reports, each at a cost of US $32,700, will be prepared (US $1.77 million for 2019–2021).

HFC-related activities

# One of the pre-requisites for including an HFC activity in a business plan is a letter of intention/endorsement from the government concerned indicating its intent to make best efforts to ratify the Kigali Amendment as early as possible, if it has not done so, in line with decision 79/46(d)(i). All of these activities, with the exception of India and the Democratic People’s Republic of Korea, were submitted with the required letter.

# HFC activities submitted in the business plan include enabling, demonstration projects, investment projects and preparation projects.

# The total level of funding for HFC enabling activities is US $940,300 in 2019 for seven countries.

# The total level of funding for technology demonstration of HFC-23 by-product conversion is US $10.18 million in 2019 for two countries (China and India).

# The total level of funding for HFC investment activities amounts to US $15.51 million in 2019 for five countries (Argentina, Brazil, China, Islamic Republic of Iran and Pakistan). The total level of funding for preparation projects amounts to US $179,800 in 2019 for three countries (the Democratic People’s Republic of Korea, Mexico and Pakistan).

Adjustments to the consolidated business plan of the Multilateral Fund for 2019–2021

# During the IACM, adjustments to the business plans of bilateral and implementing agencies were agreed based on relevant decisions of the Executive Committee. However, in reviewing the revised business plans submitted after the IACM, it was noted that the adjustments listed in Table 5 below were not considered:

Table 5: Further adjustments to the consolidated business plan of the Multilateral Fund for 2019-2021 (US $000)

| Adjustment | 2019–2021 | After 2021 |
| --- | --- | --- |
| HPMP values to reflect the actual amounts approved under the agreements, including tranches of HPMPs that are due but not submitted to the 82nd meeting | 3,659 | 981 |
| HPMP values to reflect the revised agreement submitted to the 82nd meeting | 0 | 15,008 |
| Additional project outside of stage I of HPMPs with the foam sector based on a maximum cost-effectiveness of US $7.00/kg | (14) | 0 |
| PRP for stage II of HPMPs pursuant to decision 71/42 | (302) | (34) |
| Stage II of HPMPs in LVC countries to the maximum allowable value to meet 35 or 67.5 per cent reductions of the HCFC baseline based on decision 74/50(c)(xii) | (71) | (150) |
| Stage II of HPPMP starting in 2019 as per decision 69/28(e) | (16,946) | 69,405 |
| Stage III of HPMPs and PRP pursuant to decision 80/34(c)(iii)a. | (8,886) | (226,575) |
| IS pursuant to decision 74/51(c) or values after 2021 have been removed | 3 | (677) |
| Activities related to the Democratic People’s Republic of Korea pursuant to decision 80/34(c)(iii)b. (stage I, stage II and PRP, HFC investment PRP and IS) | (193) | (1,751) |
| HFC investment PRP | (43) | 0 |
| Technology demonstration of HFC-23 by-product conversion activities have been removed in line with decision 79/47(g) | (10,180) | 0 |
| HFC enabling activities as per decision 79/46(c) | 7 | 0 |

# Table 6 presents the results of the proposed adjustments to the consolidated business plan for 2019-2021. The values exceed the indicative budget by US $33.27 million.

Table 6: Adjusted resource allocation for the business plan for 2019–2021 (US $000)*

| Item | 2019 | 2020 | 2021 | Total (2019–2021) | Total after 2021 |
| --- | --- | --- | --- | --- | --- |
| Required for compliance |  |  |  |  |  |
| Approved HPMPs | 116,126 | 122,992 | 96,008 | 335,126 | 187,685 |
| HPMP stage I | 0 | 354 | 0 | 354 | 500 |
| HPMP stage I – additional funding | 0 | 646 | 0 | 646 | 0 |
| HPMP PRP – stage II | 1,415 | 396 | 131 | 1,941 | 34 |
| HPMP stage II | 1,761 | 17,655 | 5,541 | 24,957 | 69,328 |
| HCFC production – stage II | 23,496 | 23,496 | 23,496 | 70,488 | 211,464 |
| HPMP PRP – stage III | 0 | 0 | 0 | 0 | 0 |
| HPMP stage III | 0 | 0 | 0 | 0 | 0 |
| HPMP verification | 589 | 589 | 589 | 1,766 |  |
| Required for compliance subtotal | 143,386 | 166,127 | 125,765 | 435,278 | 469,012 |
| HFC activities |  |  |  |  |  |
| HFC – demonstration | 0 | 0 | 0 | 0 | 0 |
| HFC – enabling activities | 947 | 0 | 0 | 947 | 0 |
| HFC – investment | 15,512 | 0 | 0 | 15,512 | 0 |
| HFC – investment PRP | 62 | 0 | 0 | 62 | 0 |
| HFC activities subtotal | 16,522 | 0 | 0 | 16,522 | 0 |
| Standard activities |  |  |  |  |  |
| CAP | 11,301 | 11,640 | 11,989 | 34,929 | 0 |
| Core unit | 5,932 | 5,961 | 5,991 | 17,884 | 0 |
| IS | 10,461 | 10,886 | 10,546 | 31,894 | 0 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 6,799 | 6,954 | 7,114 | 20,868 | 0 |
| Treasurer | 500 | 500 | 500 | 1,500 | 0 |
| Standard activities subtotal | 34,993 | 35,942 | 36,140 | 107,075 | 0 |
| Grand total | 194,901 | 202,069 | 161,905 | 558,874 | 469,012 |
| Indicative budget | 174,600 | 171,000 | 180,000** | 525,600 |  |
| Difference | 20,301 | 31,069 | (18,095) | 33,274 |  |
| By agency |  |  |  |  |  |
| France | 79 | 693 | 0 | 772 | 771 |
| Germany | 1,916 | 1,989 | 2,855 | 6,759 | 5,447 |
| Italy | 565 | 265 | 0 | 830 | 0 |
| Japan | 306 | 90 | 0 | 396 | 0 |
| UNDP | 39,149 | 54,517 | 30,001 | 123,667 | 30,295 |
| UNEP | 27,918 | 28,567 | 25,123 | 81,607 | 16,051 |
| UNIDO | 61,115 | 50,301 | 45,870 | 157,286 | 125,990 |
| World Bank | 55,966 | 57,604 | 49,854 | 163,423 | 290,458 |
| HPMP verification | 589 | 589 | 589 | 1,766 | 0 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 6,799 | 6,954 | 7,114 | 20,868 |  |
| Treasurer | 500 | 500 | 500 | 1,500 |  |

* Including agency support costs where applicable.

** Assumed the same level of the 2018-2020 replenishment of the Multilateral Fund.

Other policy issues

Activities in the 2018 business plan not approved at the 82nd meeting

# Activities included in the 2018 business plans of bilateral and implementing agencies but not submitted to the 82nd meeting have already been included in the business plan for 2019–2021. Any project submitted to the 82nd meeting but subsequently deferred would be included in the business plan for 2019-2021.

# Stage III of HPMPs

# In line with decision 80/34(c)(iii)a., the Secretariat removed all activities related to stage III of HPMPs including project preparation from the 2019–2021 business plan.  However, taking into account that some countries have already been implementing stage II of HPMPs, the Secretariat would like to seek guidance from the Executive Committee on the timing for which activities related to stage III of HPMPs could be included in the future business plan.

# Over-budgeting

# Following adjustments, the values of activities in the business plan exceed the overall indicative budget by US $33.27 million for the 2019–2021 triennium, assuming an annual budget of US $180 million for 2021, i.e., at the same level as the 2018–2020 replenishment. The amounts in excess of the indicative budget per year are: US $20.30 million in 2019, of which US $16.52 million is related to HFC activities, and US $31.07 million in 2020.

# The business plan value of US $194.90 million for 2019 includes US $19,560,120 associated with funding tranches that were not submitted in 2018 and, therefore, are included in 2019.

Further adjustment post the 82nd meeting

# The 2019–2021 business plan could be further adjusted based on the funding levels of HPMPs that will be approved in principle at the 82nd meeting. The Executive Committee may wish to adjust the 2019-2021 business plan based on the level of funds for the HPMPs approved in principle at the 82nd meeting.

RECOMMENDATION

# The Executive Committee may wish:

## To note the consolidated business plan of the Multilateral Fund for 2019–2021 contained in document UNEP/OzL.Pro/ExCom/82/25;

## To decide whether:

### To adjust the business plan as proposed by the Secretariat in document UNEP/OzL.Pro/ExCom/82/25;

### To further adjust the business plan as proposed at the 82nd meeting during the discussions and/or during the presentation of the business plans by bilateral and implementing agencies:

By adding to the 2019 business plan HCFC phase-out management plans (HPMPs) and institutional strengthening activities from the 2018 business plan that had been deferred at the 82nd meeting;

By taking into account the values approved in principle for new HPMPs at the 82nd meeting;

## To consider when activities related to stage III of HPMPs could be submitted; and

## To endorse the consolidated business plan of the Multilateral Fund for 2019–2021, as adjusted by the Secretariat [and the Executive Committee], while noting that endorsement denoted neither approval of the projects identified therein nor their funding or tonnage levels.

Montreal, 4 to 6 September 2018.

UNEP/OzL.Pro/ExCom/82/26

UNEP/OzL.Pro/ExCom/82/27

UNEP/OzL.Pro/ExCom/82/28

UNEP/OzL.Pro/ExCom/82/29

UNEP/OzL.Pro/ExCom/82/30

Decision 61/46(c) requires verification reports for a sample of 20 per cent of the LVC countries with approved HPMPs.

As agreed at the IACM.