| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/99/15 29 October 2026 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-ninth Meeting

Montreal, 7–11 December 2026

Item 7(a)(iii) of the provisional agenda

PROGRESS REPORT OF UNDP AS AT 31 DECEMBER 2025

Introduction

# This document presents the progress report of UNDP as at 31 December 2025.

# The progress report of UNDP includes the status of implementation of each ongoing project, reviewed by the Secretariat on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates reported in 2025, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs, which are measured in metric tonnes (mt) and CO2-eq tonnes.

# This document presents a summary of progress in implementation of projects for 2025 and cumulative since 1991 addressing all controlled substances, including Annex F substances (HFCs), under the Montreal Protocol for all projects approved under regular funding and additional voluntary contributions. It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee. As all projects approved under the additional voluntary contributions have been completed and the remaining balances will be returned to the Fund, the Secretariat no longer reports on these projects separately.

Progress in implementation of projects for 2025 and cumulative since 1991

# As of 31 December 2025, the Executive Committee had approved US $1.11 billion in projects for UNDP, consisting of US $977.4 million for the implementation of investment and non-investment projects, and US $136.8 million for agency support costs (excluding cancelled and transferred projects). Table 1 provides a summary of project implementation since inception through the end of 2025.

# Table 1. Project summary for UNDP since the inception of the Multilateral Fund

| Items | Cumulative since 1991* |
| --- | --- |
| Number of approvals | 2,860 |
| Number of projects completed | 2,670 |
| Total funds approved (excluding support costs) (US $) | 977,401,193 |
| Total funds disbursed (excluding support costs) (US $) | 901,900,455 |
| Total approved phase-out (ODP tonnes)** | 70,620.2 |
| Total actual phase-out (ODP tonnes)** | 69,527.2 |
| Total approved phase-out (mt)*** | 3,794.8 |
| Total actual phase-out (mt)*** | 751.5 |
| Total approved phase-out (CO2-eq tonnes)*** | 6,270,276 |
| Total actual phase-out (CO2-eq tonnes)*** | 992,086 |

* Excluding cancelled and transferred projects.

** Including only consumption.

*** For HFC-related projects only (including only consumption).

# In 2025, 53 new projects and activities were approved. This level of funding is expected to result in the phase-out of 70,620 ODP tonnes of consumption of ODS and 3,795 mt (6,270,276 CO2-eq tonnes) of consumption of HFCs. Annex I shows the status of project implementation per country in 2025.

# Table 2 shows the status of project implementation including fund disbursement per project cluster as at 31 December 2025. Annex II presents analytical information per year since 1991.

Table 2. Status of project implementation by cluster as at 31 December 2025*

| Clusters | Number of projects |  |  | Funding (US$)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Agency programme | 25 | 24 | 96 | 596,500 | 596,500 | 0 | 100 |
| CFC individual | 1,437 | 1,437 | 100 | 301,302,827 | 301,302,829 | -2 | 100 |
| CFC phase-out plans | 118 | 118 | 100 | 58,120,483 | 58,120,483 | 0 | 100 |
| CFC production phase-out plans | 1 | 1 | 100 | 1,056,000 | 1,056,000 | 0 | 100 |
| Disposal | 10 | 10 | 100 | 3,086,833 | 3,086,833 | 0 | 100 |
| Energy efficiency | 16 | 4 | 25 | 3,771,519 | 422,516 | 3,349,003 | 11 |
| Government support | 295 | 273 | 93 | 70,936,154 | 62,659,465 | 8,276,689 | 88 |
| HCFC individual | 230 | 222 | 97 | 25,280,775 | 24,943,225 | 337,550 | 99 |
| HCFC phase-out management plan (HPMP) stage I | 184 | 181 | 98 | 164,132,892 | 164,013,892 | 119,000 | 100 |
| HPMP stage II | 179 | 130 | 73 | 184,185,445 | 164,518,167 | 19,667,278 | 89 |
| HPMP stage III | 34 | 10 | 29 | 33,211,908 | 6,624,347 | 26,587,561 | 20 |
| HFC individual | 102 | 82 | 80 | 16,648,883 | 13,859,747 | 2,789,136 | 83 |
| Kigali HFC implementation plan (KIP) stage I | 55 | 4 | 7 | 15,288,509 | 913,990 | 14,374,519 | 6 |
| Other ODS individual | 112 | 112 | 100 | 13,870,732 | 13,870,729 | 3 | 100 |
| Other ODS sector plans | 62 | 62 | 100 | 85,911,732 | 85,911,732 | 0 | 100 |
| Total | 2,860 | 2,670 | 93 | 977,401,193 | 901,900,455 | 75,500,738 | 92 |

* Excluding cancelled and transferred projects.

** Excluding agency support costs.

# Implementation of projects and activities by UNDP for 2025 and cumulative since 1991 up to 31 December 2025 is summarized as follows:

## Phase-out: In 2025, 560.3 ODP tonnes of consumption of ODS were phased out and 114.2 mt (180,564 CO2-eq tonnes) of consumption of HFCs were phased out and an additional 92.3 ODP tonnes of consumption of ODS and 676.4 mt (909,793 CO2-eq tonnes) of consumption of HFCs were approved for phase-out. Since 1991, 69,527 ODP tonnes had been phased out, of an expected total of 70,620 ODP tonnes of consumption of ODS and 751.5 mt (992,086 CO2-eq tonnes) had been phased out, of an expected total of 3,795 mt (6,270,276 CO2-eq tonnes) of consumption of HFCs from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2025, US $20.35 million was disbursed, and US $21.01 million was planned for disbursement based on the 2024 progress report, representing a rate of disbursement of 97 per cent of that planned. Cumulatively, US $901.9 million had been disbursed out of the total US $977.4 million approved for disbursement (excluding agency support costs), representing a rate of disbursement of 92 per cent. In 2025, US $20.15 million was approved for implementation;

## Cost-effectiveness (in ODP): Since 1991, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $11.44/kg. The average cost-effectiveness of investment projects per ODP tonne was US $11.17/kg for completed projects and US $15.83/kg for ongoing projects;

## Number of projects completed: In 2025, 50 projects were completed. Since 1991, 2,670 projects of the 2,860 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 93 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2025 were completed on average 37 months after their approval. Since 1991, the average time for completion of investment projects has been 34 months after their approval. First disbursements under these projects occurred, on average, 13 months after they had been approved;

## Speed of delivery – non-investment projects: Projects that were completed in 2025 were completed on average 29 months after their approval. Since 1991, the average time for completion of non-investment projects has been 39 months after their approval. First disbursements under these projects occurred, on average, 13 months after they had been approved;

## Project preparation: Of the 653 project preparation activities approved by the end of 2025, 629 have been completed, leaving 24 ongoing activities. In 2025, 21 project preparation activities were completed;

## Implementation delays: A total of 190 projects were under implementation at the end of 2025, experiencing, on average, a delay of four months. Thirty-five of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation, and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2025, 46 MYAs for HPMPs and 27 MYAs for KIPs were under implementation. Since 1991, 197 MYAs have been approved and 124 MYAs have been completed, representing a completion rate of 63 per cent.

# Table 3 summarizes progress made by UNDP since 1991.

## Table 3. Progress made by UNDP since 1991

| Phase-out achieved |  | Disbursement (US $) | Average CE (US$/kg) | Number of projects |  | Speed of delivery for completion (months) |  | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes | CO2-eq tonnes* |  |  | Approved | Completed | Investment | Non- investment |  | Approved | Completed |
| 69,527 | 992,086 | 901,900,455 | 11.44 | 2,860 | 2,670 | 34 | 39 | 4 | 197 | 124 |

* HFC-related projects.

HFC-related projects

# As of 31 December 2025, the Executive Committee had approved 157 HFC-related projects (including seven investment projects, 63 preparation activities, 32 technical assistance projects and 55 projects related to stage I of KIPs) amounting to US $31,937,392 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 4 to 8.

Table 4. HFC-related projects approved*

| Clusters | Number of projects |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| HFC individual – investment | 7 | 7 | 100 | 7,548,979 | 6,912,157 | 636,822 | 92 |
| HFC individual – preparation projects | 63 | 45 | 71 | 6,115,923 | 4,031,778 | 2,084,145 | 66 |
| HFC individual – technical assistance | 32 | 30 | 94 | 2,983,981 | 2,915,812 | 68,169 | 98 |
| KIP stage I | 55 | 4 | 7 | 15,288,509 | 913,990 | 14,374,519 | 6 |
| Total | 157 | 86 | 55 | 31,937,392 | 14,773,737 | 17,163,655 | 46 |

* Excluding cancelled and transferred projects.

** Excluding agency support costs.

Note: 3,795 mt (6,270,276 CO2-eq tonnes) of HFCs was approved for phase-out.

# As of the end of 2025, of the 157 projects, seven investment projects, 45 preparation activities, 30 technical assistance projects and four projects related to stage I of KIPs have been completed, leaving 71 ongoing. The ongoing projects are at various stages of implementation.

# Of the total cumulative funding approved of US $31,937,392 (excluding agency support costs), US $14,773,737 has been disbursed, representing a disbursement rate of 46 per cent.

Energy-efficiency projects

# As of 31 December 2025, the Executive Committee had approved 16 energy-efficiency projects (including four preparation activities and 11 technical assistance pilot projects under the funding window pursuant to decision 91/65 and one preparation activity for an energy-efficiency revolving-fund end-user project pursuant to decision 95/87) amounting to US $3,771,519 (excluding agency support costs). A summary of the status of these projects is presented in table 5 and the respective data has already been included in paragraphs 4 to 8.

Table 5. Energy-efficiency projects approved*

| Type | Number of projects |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Pilot projects (decision 91/65) – project preparation | 4 | 3 | 75 | 165,000 | 88,788 | 76,212 | 54 |
| Pilot projects (decision 91/65) – technical assistance | 11 | 1 | 9 | 3,406,519 | 281,394 | 3,125,125 | 8 |
| Energy-efficiency revolving-fund end-user projects (decision 95/87) – project preparation | 1 | 0 | 0 | 200,000 | 52,334 | 147,666 | 26 |
| Total | 16 | 4 | 25 | 3,771,519 | 422,516 | 3,349,003 | 11 |

* Excluding cancelled projects.

** Excluding agency support costs.

# As of the end of 2025, of the 16 projects, three preparation activities and one technical assistance project pursuant to decision 91/65 have been completed, leaving 12 ongoing. The ongoing projects are at various stages of implementation.

# Of the total cumulative funding approved of US $3,771,519 (excluding agency support costs), US $422,516 has been disbursed, representing a disbursement rate of 11 per cent.

Issues identified in project implementation in 2025

# Further to the review process, several issues were discussed and satisfactorily addressed, except for issues on 35 projects classified as projects with implementation delays (including 34 projects related to components of MYAs that are subject to procedures for project cancellation, in line with decision 84/45(c); and one technical assistance project). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 100th meeting.

# In addition, issues have been identified regarding projects or tranches of MYAs for the phase-out of HCFCs; renewal of IS projects; and preparation of HPMPs. These issues are also presented in annex III. For each of these projects, a brief description on the status of implementation and the outstanding issues are presented and a recommendation is proposed for consideration by the Executive Committee.

# Details of progress in implementation of projects associated with the HPMPs for Barbados, China (overarching, industrial and commercial refrigeration and air-conditioning, and solvent), El Salvador, India, Lebanon, Mozambique, Sri Lanka, and Timor-Leste, with the KIPs for Cambodia, Cuba, the Dominican Republic, Kyrgyzstan, and Panama, and a report on a project with specific reporting requirements associated with Bangladesh (HPMP) have been submitted to the 99th meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. Outstanding issues for the remaining ongoing projects not included in annex III to the present document and requests for extension of dates of completion are addressed below.

# Of the 144 ongoing projects, excluding IS and project preparation, 19 projects have revised planned dates of completion since the 2024 progress report.

# In line with decision 95/12(b), the Secretariat noted that a renewal request of the IS project for China had not been submitted for the last three years.

# In line with decision 82/11(b), UNDP has requested the extension of the duration of three projects pursuant to decision 91/66, as shown in table 6.

Table 6. Projects pursuant to decision 91/66 for which an extension of the completion date has been requested

| Country/project code | Disburse-ment (%) | Activities requiring additional time | Original date of completion (mm-yy) | Date of completion requested (mm-yy) |
| --- | --- | --- | --- | --- |
| Preparation of a national inventory of banks of waste controlled substances and development of a national plan for the management of those substances (decision 91/66) |  |  |  |  |
| Indonesia IDN/HFCIND/224/UNDP/PRP/DES/95 | 0 | Completion of data collection and survey by the recruited consultants and suppliers of services | Dec-26 | Dec-27 |
| Peru PER/HFCIND/66/UNDP/PRP/DES/93 | 0 | Development of action plan and completion of remaining activities, including the inventory and national plan | Dec-25* | May-27 |
| Uruguay URY/HFCIND/86/UNDP/PRP/DES/93 | 2 | Completion of survey and remaining activities | Dec-25* | Jun-27 |

* Date of completion had already been revised to December 2026 (decision 97/11(b)(ii)a.).

Gender mainstreaming

# Relevant considerations are integrated throughout project implementation through stakeholder consultations, engagement with women’s associations, the collection of disaggregated data, and recruitment measures that encourage women’s application. Women’s participation in training activities and consultations has increased over time with greater emphasis on implementing the Multilateral Fund’s policy in this area. New global tools are being developed, including a train-the-trainer manual on integrating the needs and roles of women in Montreal Protocol projects and a portfolio review of good practices. UNDP has identified two structural constraints: entrenched perceptions of the refrigeration and air-conditioning (RAC) sector as male-dominated and the lack of dedicated resources, which limit targeted measures. A notable country-level example is the HPMP for Sri Lanka, where staff of the national ozone unit (NOU) received training from a gender expert and launched the “Ozone Friends Badge” developed in collaboration with the Girl Guides Association.

Risk management

# Some of the measures include front-loading project readiness activities, such as the early preparation of project documents, work plans, terms of references, procurement plans, and stakeholder consultations. UNDP also promotes early engagement with approval authorities and applies adaptive procurement approaches, including the establishment of long-term agreements with major RAC equipment suppliers, broader supplier outreach, bundling, and re-tendering. In conflict-affected countries, implementation schedules are adjusted and priority is given to activities that can be delivered under existing operational conditions. Risks are continuously monitored through follow-up with NOUs, stakeholders and beneficiaries. UNDP reports that the majority of projects remain on track despite activity-level delays, many of which are beyond the control of implementing agencies and project partners. Where required, UNDP leverages country office presence and resources to elevate issues to senior government officials, helping to facilitate resolution.

Recommendation

# The Executive Committee may wish:

## To note the progress report of UNDP as at 31 December 2025 contained in document UNEP/OzL.Pro/ExCom/99/15;

## To approve the extension of the completion dates of the preparation of a national inventory of banks of waste controlled substances and development of a national plan for the management of those substances (decision 91/66) for the countries listed below to allow completion of the remaining ongoing activities, as reflected in table 6 of document UNEP/OzL.Pro/ExCom/99/15:

### Indonesia (IDN/HFCIND/224/UNDP/PRP/DES/95), to December 2027;

### Peru (PER/HFCIND/66/UNDP/PRP/DES/93), to May 2027;

### Uruguay (URY/HFCIND/86/UNDP/PRP/DES/93), to June 2027; and

## To approve also the recommendations related to ongoing projects with specific issues contained in annex III to the present document.

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNDP

PER COUNTRY FOR 2025

# Table 1 of annex I presents the status of project implementation by country for 2025 in achieved phase-out, planned and achieved disbursements and project completion.

Table 1. Status of project implementation by UNDP for 2025

| Country | Phased out in 2025 (ODP tonnes) | Phased out in 2025 (CO2-eq tonnes)* | Estimated funds disbursed in 2025 (US$) | Funds disbursed in 2025 (US$) | Percentage of funds disbursed over estimation in 2025 | Percentage of planned projects completed in 2025** |
| --- | --- | --- | --- | --- | --- | --- |
| Angola | 5.2 | 0 | 227,568 | 26,710 | 12 | 100 |
| Argentina |  |  | 163,753 | 75,381 | 46 |  |
| Bangladesh | 0.0 | 0 | 566,113 | 681,690 | 120 | 75 |
| Barbados |  |  | 28,750 | 0 | 0 | 0 |
| Belize | 0.0 | 0 | 111,457 | 73,079 | 66 |  |
| Bhutan |  |  | 29,370 | 0 | 0 | 0 |
| Brazil | 0.0 | 0 | 1,934,103 | 579,669 | 30 | 100 |
| Cambodia | 0.0 | 38,652 | 43,130 | 87,584 | 203 |  |
| Chile | 0.0 | 0 | 452,156 | 225,977 | 50 | 50 |
| China | 506.5 | 0 | 1,250,146 | 5,319,670 | 426 | 100 |
| Colombia | 0.0 | 0 | 1,124,534 | 729,701 | 65 | 100 |
| Costa Rica |  |  | 367,203 | 202,348 | 55 |  |
| Cuba | 0.0 | 0 | 299,307 | 315,429 | 105 | 0 |
| Democratic Republic of the Congo (the) |  |  | 50,140 | 0 | 0 | 0 |
| Dominican Republic (the) |  |  | 303,675 | 183,007 | 60 |  |
| Egypt | 0.0 | 0 | 449,713 | 94,966 | 21 | 33 |
| El Salvador | 0.0 | 0 | 214,064 | 127,242 | 59 | 100 |
| Eswatini | 0.4 | 0 | 90,200 | 138,906 | 154 |  |
| Fiji | 0.0 | 0 | 99,601 | 32,047 | 32 | 50 |
| Georgia | 0.0 | 0 | 93,875 | 108,122 | 115 |  |
| Ghana |  |  | 221,725 | 185,734 | 84 |  |
| Grenada |  |  | 36,187 | 0 | 0 |  |
| Guyana |  |  | 64,055 | 0 | 0 | 0 |
| Haiti |  |  | 94,246 | 30,893 | 33 |  |
| India | 13.8 | 126,039 | 3,253,778 | 3,004,592 | 92 | 56 |
| Indonesia |  |  | 1,776,285 | 2,200,114 | 124 |  |
| Iran (Islamic Republic of) | 5.2 | 0 | 520,240 | 471,081 | 91 | 25 |
| Jamaica |  |  | 176,292 | 33,501 | 19 | 0 |
| Kyrgyzstan |  |  | 52,040 | 43,078 | 83 |  |
| Lao People's Democratic Republic (the) |  |  | 47,129 | 18,733 | 40 |  |
| Lebanon | 0.6 | 0 | 278,534 | 377,151 | 135 | 100 |
| Malaysia | 0.0 | 0 | 1,432,886 | 657,432 | 46 |  |
| Maldives |  |  | 12,974 | 0 | 0 |  |
| Mali | 0.0 | 0 | 51,440 | 44,708 | 87 | 100 |
| Mexico |  |  | 414,917 | 68,276 | 16 |  |
| Mozambique | 0.0 | 0 | 74,921 | 17,126 | 23 | 67 |
| Nepal |  |  | 62,882 | 29,044 | 46 |  |
| Nigeria | 27.8 | 0 | 1,053,508 | 2,206,622 | 209 | 100 |
| Pakistan |  |  | 136,792 | 269,132 | 197 |  |
| Panama | 0.0 | 0 | 396,044 | 325,491 | 82 |  |
| Paraguay |  |  | 163,932 | 72,848 | 44 |  |
| Peru |  |  | 341,099 | 108,854 | 32 | 0 |
| Philippines (the) |  |  | 125,433 | 80,347 | 64 | 0 |
| Republic of Moldova (the) |  |  | 47,873 | 0 | 0 |  |
| South Sudan | 0.0 | 0 | 21,500 | 0 | 0 | 100 |
| Sri Lanka | 0.8 | 0 | 314,363 | 274,572 | 87 | 67 |
| Timor-Leste |  |  | 10,709 | 10,041 | 94 |  |
| Trinidad and Tobago | 0.0 | 0 | 550,268 | 226,593 | 41 |  |
| Türkiye |  |  | 209,857 | 2,865 | 1 |  |
| Uruguay |  |  | 832,653 | 280,567 | 34 |  |
| Venezuela (Bolivarian Republic of) |  |  | 152,485 | 154,465 | 101 |  |
| Zimbabwe | 0.0 | 15,873 | 104,618 | 59,976 | 57 |  |
| Global | 0.0 | 0 | 80,000 | 90,535 | 113 | 100 |
| Grand total | 560.3 | 180,564 | 21,010,523 | 20,345,899 | 97 | 57 |

* 114.2 mt (180,564 CO2-eq tonnes) in 2025 for HFC-related projects.

** For projects that were planned to be completed in 2025.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNDP

PER YEAR AS AT 31 DECEMBER 2025

# Table 1 of annex II presents an overview of the status of project implementation by year. All projects and activities approved between 1991 and 2018, have now been completed.

Table 1. Status of project implementation by year*

| Year | Number of projects |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1991 | 15 | 15 | 100 | 1,133,980 | 1,133,980 | 0 | 100 |
| 1992 | 67 | 67 | 100 | 8,619,002 | 8,619,002 | 0 | 100 |
| 1993 | 57 | 57 | 100 | 13,204,712 | 13,204,712 | 0 | 100 |
| 1994 | 148 | 148 | 100 | 49,079,193 | 49,079,194 | -1 | 100 |
| 1995 | 117 | 117 | 100 | 29,405,010 | 29,405,011 | -1 | 100 |
| 1996 | 83 | 83 | 100 | 27,598,240 | 27,598,240 | 0 | 100 |
| 1997 | 188 | 188 | 100 | 39,952,014 | 39,952,015 | -1 | 100 |
| 1998 | 172 | 172 | 100 | 30,584,240 | 30,584,240 | 0 | 100 |
| 1999 | 204 | 204 | 100 | 35,531,985 | 35,531,986 | -1 | 100 |
| 2000 | 149 | 149 | 100 | 31,195,871 | 31,195,870 | 1 | 100 |
| 2001 | 179 | 179 | 100 | 35,258,983 | 35,258,982 | 1 | 100 |
| 2002 | 117 | 117 | 100 | 43,593,818 | 43,593,817 | 1 | 100 |
| 2003 | 64 | 64 | 100 | 36,316,530 | 36,316,530 | 0 | 100 |
| 2004 | 69 | 69 | 100 | 24,651,834 | 24,651,833 | 1 | 100 |
| 2005 | 53 | 53 | 100 | 29,102,341 | 29,102,340 | 1 | 100 |
| 2006 | 62 | 62 | 100 | 15,753,456 | 15,753,459 | -3 | 100 |
| 2007 | 54 | 54 | 100 | 12,142,488 | 12,142,486 | 2 | 100 |
| 2008 | 84 | 84 | 100 | 22,821,772 | 22,821,773 | -1 | 100 |
| 2009 | 92 | 92 | 100 | 13,206,893 | 13,206,893 | 0 | 100 |
| 2010 | 43 | 43 | 100 | 19,567,971 | 19,567,970 | 1 | 100 |
| 2011 | 63 | 63 | 100 | 57,415,930 | 57,415,931 | -1 | 100 |
| 2012 | 29 | 29 | 100 | 33,818,923 | 33,818,922 | 1 | 100 |
| 2013 | 43 | 43 | 100 | 33,958,973 | 33,958,972 | 1 | 100 |
| 2014 | 67 | 67 | 100 | 22,561,029 | 22,561,030 | -1 | 100 |
| 2015 | 75 | 75 | 100 | 30,256,294 | 30,274,629 | -18,335 | 100 |
| 2016 | 52 | 52 | 100 | 41,536,980 | 41,536,980 | 0 | 100 |
| 2017 | 43 | 43 | 100 | 35,237,535 | 35,152,753 | 84,782 | 100 |
| 2018 | 62 | 62 | 100 | 39,877,040 | 39,710,817 | 166,223 | 100 |
| 2019 | 41 | 39 | 95 | 10,027,998 | 9,876,209 | 151,789 | 98 |
| 2020 | 50 | 49 | 98 | 29,104,536 | 28,046,598 | 1,057,938 | 96 |
| 2021 | 66 | 62 | 94 | 23,381,994 | 21,667,009 | 1,714,985 | 93 |
| 2022 | 38 | 30 | 79 | 13,705,517 | 9,854,117 | 3,851,400 | 72 |
| 2023 | 85 | 29 | 34 | 34,974,872 | 16,845,849 | 18,129,023 | 48 |
| 2024 | 76 | 10 | 13 | 32,674,861 | 2,379,486 | 30,295,375 | 7 |
| 2025 | 53 | 0 | 0 | 20,148,376 | 80,820 | 20,067,556 | 0 |
| Total | 2,860 | 2,670 | 93 | 977,401,193 | 901,900,455 | 75,500,738 | 92 |

* Excluding closed and transferred projects.

** Excluding agency support costs.

Annex III

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR UNDP

| Country | Project code | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- | --- |
| Belize | BLZ/HPMP2/45/UNDP/INV/SRV/94 | HCFC phase-out management plan (stage II, second tranche) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Brazil | BRA/HPMP3/336/UNDP/INV/SRV/94 | HCFC phase-out management plan (stage III, first tranche) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Chile | CHL/KIP1/116/UNDP/INV/SRV/93 | Kigali HFC implementation plan (stage I, first tranche) | 3 | 12 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Chile | CHL/KIP1/121/UNDP/TAS/PMU/93 | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 0 | 12 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Cuba | CUB/HPMP2/68/UNDP/INV/SRV/92 | HCFC phase-out management plan (stage II, second tranche) | 38 | 12 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Democratic Republic of the Congo (the) | COD/HPMP2/50/UNDP/INV/SRV/88 | HCFC phase-out management plan (stage II, first tranche) | 0 | 12 and 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Egypt | EGY/HPMP2/143/UNDP/TAS/PMU/84 | HCFC phase-out management plan (stage II, second tranche) (project management and monitoring) | 0 | 12 and 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Egypt | EGY/HPMP2/152/UNDP/INV/FOA/88 | HCFC phase-out management plan (stage II, third tranche) (extruded polystyrene foam sector) | 38 | 12 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| El Salvador | SLV/KIP1/49/UNDP/INV/SRV/94 | Kigali HFC implementation plan (stage I, first tranche) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Ghana | GHA/KIP1/58/UNDP/TAS/SRV/93 | Kigali HFC implementation plan (stage I, first tranche) (Project monitoring) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Grenada | GRD/KIP1/35/UNDP/INV/SRV/93 | Kigali HFC implementation plan (stage I, first tranche) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Guyana | GUY/HPMP2/33/UNDP/INV/SRV/83 | HCFC phase-out management plan (stage II, second tranche) | 20 | 12 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Guyana | GUY/HPMP2/38/UNDP/INV/SRV/92 | HCFC phase-out management plan (stage II, third tranche) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Guyana | GUY/HPMP2/40/UNDP/TAS/SRVEE/93 | HCFC phase-out management plan (stage II) (Additional activities to maintain energy efficiency for the servicing sector under decision 89/6(b)) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Iran (Islamic Republic of) | IRN/GOV/261/UNDP/INS/NOU/91 | Extension of the institutional strengthening project (phase XIV: 4/2023-3/2025) | 87 | Slow progress in implementation | To request UNDP to submit a status report to the 100th meeting on implementation progress |
| Iran (Islamic Republic of) | IRN/HCFCIND/267/UNDP/PRP/SRV/92 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | 0 | Slow progress in implementation | To request UNDP to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Iran (Islamic Republic of) | IRN/HCFCIND/268/UNDP/PRP/AC/92 | Preparation of HCFC phase-out management plan (stage III) (industrial refrigeration and industrial air-conditioning) | 0 | Slow progress in implementation | To request UNDP to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Iran (Islamic Republic of) | IRN/HPMP2/265/UNDP/INV/REF/92 | HCFC phase-out management plan (stage II, fourth tranche) (commercial refrigeration sector) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Iran (Islamic Republic of) | IRN/HPMP2/266/UNDP/INV/FOA/92 | HCFC phase-out management plan (stage II, fourth tranche) (foam sector) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Iran (Islamic Republic of) | IRN/HPMP2/269/UNDP/INV/REF/94 | HCFC phase-out management plan (stage II, fifth tranche) (commercial refrigeration sector) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Iran (Islamic Republic of) | IRN/HPMP2/270/UNDP/INV/SRV/94 | HCFC phase-out management plan (stage II, fifth tranche) (refrigeration servicing sector and project monitoring unit) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Iran (Islamic Republic of) | IRN/HPMP2/271/UNDP/INV/FOA/94 | HCFC phase-out management plan (stage II, fifth tranche) (foam sector) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Iran (Islamic Republic of) | IRN/GOV/274/UNDP/INS/NOU/95 | Extension of the institutional strengthening project (phase XV: 4/2025-3/2028) | 0 | Slow progress in implementation | To request UNDP to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Iran (Islamic Republic of) | IRN/HPMP3/277/UNDP/INV/SRV/96 | HCFC phase-out management plan (stage III, first tranche) | 0 | Slow progress in implementation | To request UNDP to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Iran (Islamic Republic of) | IRN/HPMP3/278/UNDP/TAS/PMU/96 | HCFC phase-out management plan (stage III, first tranche) (PMU) | 0 | Slow progress in implementation | To request UNDP to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Jamaica | JAM/HPMP2/44/UNDP/INV/SRV/86 | HCFC phase-out management plan (stage II, first tranche) | 49 | 12 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Lao People's Democratic Republic (the) | LAO/KIP1/50/UNDP/INV/SRV/94 | Kigali HFC implementation plan (stage I, first tranche) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Malaysia | MYS/HPMP3/206/UNDP/INV/SRV/94 | HCFC phase-out management plan (stage III, first tranche) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Mexico | MEX/KIP1/214/UNDP/INV/FOA/93 | Kigali HFC implementation plan (stage I, first tranche) (foam sector plan) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Mexico | MEX/KIP1/216/UNDP/INV/SRV/93 | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Mexico | MEX/KIP1/217/UNDP/TAS/PMU/93 | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Mozambique | MOZ/KIP1/48/UNDP/INV/SRV/94 | Kigali HFC implementation plan (stage I, first tranche) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Nepal | NPL/HPMP2/48/UNDP/INV/SRV/95 | HCFC phase-out management plan (stage II, second tranche) | 2 | Slow progress in implementation | To request UNDP to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Nigeria | NGA/HPMP2/168/UNDP/TAS/PMU/93 | HCFC phase-out management plan (stage II, third tranche) (PMU) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Paraguay | PRY/HPMP2/54/UNDP/TAS/SRVEE/94 | HCFC phase-out management plan (stage II) (Additional activities to maintain energy efficiency in the refrigeration servicing sector (decision 89/6)) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Paraguay | PRY/KIP1/55/UNDP/INV/SRV/94 | Kigali HFC implementation plan (stage I, first tranche) | 1 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Paraguay | PRY/KIP1/56/UNDP/TAS/PMU/94 | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Peru | PER/KIP1/67/UNDP/INV/SRV/93 | Kigali HFC implementation plan (stage I, first tranche) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Peru | PER/KIP1/70/UNDP/TAS/PMU/93 | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Republic of Moldova (the) | MDA/HPMP3/50/UNDP/INV/SRV/94 | HCFC phase-out management plan (stage III, second tranche) | 0 | 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| South Sudan | SSD/HPMP1/7/UNDP/INV/SRV/91 | HCFC phase-out management plan (stage I, second tranche) | 0 | 12 and 18 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |
| Sri Lanka | LKA/HCFCIND/64/UNDP/TAS/VER/94 | Verification report on the implementation of stage II of the HCFC phase-out management plan | 5 | 12 months delays | To request UNDP to report to the 100th meeting on this project with implementation delays |

UNEP/OzL.Pro/ExCom/99/1

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database, which is provided on the 99th meeting portal on the Multilateral Fund’s website, in the spreadsheet programme, Microsoft Excel.

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 99th meeting.

Funded by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment.

Ongoing projects are all projects that were under implementation as at 31 December 2025. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

Phase-out of ODS is expressed in ODP tonnes and of HFCs in mt and CO2-eq tonnes.

Including 3,795 mt of HFC-related projects. Cost-effectiveness in CO2-eq is not included due to the limited number of projects approved.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61).

UNEP/OzL.Pro/ExCom/99/39

UNEP/OzL.Pro/ExCom/99/45

UNEP/OzL.Pro/ExCom/99/51

UNEP/OzL.Pro/ExCom/99/56

UNEP/OzL.Pro/ExCom/99/59

UNEP/OzL.Pro/ExCom/99/62

UNEP/OzL.Pro/ExCom/99/73

UNEP/OzL.Pro/ExCom/99/74

UNEP/OzL.Pro/ExCom/99/43

UNEP/OzL.Pro/ExCom/99/48

UNEP/OzL.Pro/ExCom/99/50

UNEP/OzL.Pro/ExCom/99/58

UNEP/OzL.Pro/ExCom/99/66

UNEP/OzL.Pro/ExCom/99/19

Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.

The Executive Committee requested bilateral and implementing agencies to provide a brief report on key gender mainstreaming results achieved as part of their annual progress reports, as of 2023, on the basis of the information available to them (decision 90/48(d)).

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.