| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/99/18 29 October 2026 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-ninth Meeting

Montreal, 7–11 December 2026

Item 7(a)(vi) of the provisional agenda

PROGRESS REPORT OF THE WORLD BANK AS AT 31 DECEMBER 2025

Introduction

# This document presents the progress report of the World Bank as at 31 December 2025.

# The progress report of the World Bank includes the status of implementation of each ongoing project, reviewed by the Secretariat on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates reported in 2025, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs, which are measured in metric tonnes (mt) and CO2-eq tonnes.

# This document presents a summary of progress in implementation of projects for 2025 and cumulative since 1991 addressing all controlled substances, including Annex F substances (HFCs), under the Montreal Protocol for all projects approved under regular funding and additional voluntary contributions. It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee. As all projects approved under the additional voluntary contributions have been completed and the remaining balances will be returned to the Secretariat, the Secretariat will no longer report on these projects separately.

Progress in implementation of projects for 2025 and cumulative since 1991

# As of 31 December 2025, the Executive Committee had approved US $1.37 billion in projects for the World Bank, consisting of US $1.24 billion for the implementation of investment and non-investment projects and US $133.37 million for agency support costs (excluding cancelled and transferred projects). Table 1 provides a summary of project implementation since inception through the end of 2025.

# Table 1. Project summary for the World Bank since the inception of the Multilateral Fund

| Items | Cumulative since 1991* |
| --- | --- |
| Number of approvals | 1,165 |
| Number of projects completed | 1,133 |
| Total funds approved (excluding support costs) (US $) | 1,237,103,129 |
| Total funds disbursed (excluding support costs) (US $) | 1,212,608,500 |
| Total approved phase-out (ODP tonnes)** | 319,215.8 |
| Total actual phase-out (ODP tonnes)** | 344,314.4 |
| Total approved phase-out (mt)*** | 1,390.3 |
| Total actual phase-out (mt)*** | 8.8 |
| Total approved phase-out (CO2-eq tonnes)*** | 2,375,388 |
| Total actual phase-out (CO2-eq tonnes)*** | 12,555 |

* Excluding cancelled and transferred projects.

** Including consumption and production.

*** For HFC-related projects only (including consumption and production).

# In 2025, 11 new projects and activities were approved. This level of funding is expected to result in the phase-out of 319,216 ODP tonnes of consumption and production of ODS and 1,390 mt (2,375,388 CO2-eq tonnes) of consumption of HFCs. Annex I shows the status of project implementation per country in 2025.

# Table 2 shows the status of project implementation including fund disbursement per project cluster as at 31 December 2025. Annex II presents analytical information per year since 1991.

Table 2. Status of project implementation by cluster as at 31 December 2025*

| Clusters | Number of projects |  |  | Funding (US$)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Agency programme | 31 | 30 | 97 | 185,000 | 185,000 | 0 | 100 |
| CFC individual | 717 | 717 | 100 | 307,224,816 | 307,224,817 | -1 | 100 |
| CFC phase-out plans | 34 | 34 | 100 | 73,523,850 | 73,523,850 | 0 | 100 |
| CFC production phase-out plans | 37 | 37 | 100 | 261,179,093 | 261,179,093 | 0 | 100 |
| Disposal | 4 | 4 | 100 | 400,000 | 400,000 | 0 | 100 |
| Energy efficiency | 8 | 1 | 12 | 1,430,689 | 135,099 | 1,295,590 | 9 |
| Government support | 51 | 50 | 98 | 10,743,662 | 10,051,955 | 691,707 | 94 |
| HCFC individual | 46 | 44 | 96 | 7,987,990 | 7,838,881 | 149,109 | 98 |
| HCFC phase-out management plan (HPMP) stage I | 24 | 24 | 100 | 99,298,659 | 99,298,660 | -1 | 100 |
| HPMP stage II | 21 | 19 | 90 | 39,651,104 | 33,032,504 | 6,618,600 | 83 |
| HPMP stage III | 2 | 0 | 0 | 3,227,127 | 0 | 3,227,127 | 0 |
| HCFC production phase-out management plan (HPPMP) stage I | 4 | 4 | 100 | 91,256,301 | 91,256,301 | 0 | 100 |
| HPPMP stage II | 3 | 2 | 67 | 66,997,213 | 62,597,213 | 4,400,000 | 93 |
| HFC individual | 20 | 15 | 75 | 2,672,594 | 2,281,209 | 391,385 | 85 |
| Kigali HFC implementation plan (KIP) stage I | 11 | 0 | 0 | 7,721,113 | 0 | 7,721,113 | 0 |
| Other ODS individual | 64 | 64 | 100 | 15,981,112 | 15,981,111 | 1 | 100 |
| Other ODS individual production | 1 | 1 | 100 | 951,653 | 951,653 | 0 | 100 |
| Other ODS production phase-out plans | 15 | 15 | 100 | 37,499,577 | 37,499,578 | -1 | 100 |
| Other ODS sector plans | 72 | 72 | 100 | 209,171,575 | 209,171,576 | -1 | 100 |
| Total | 1,165 | 1,133 | 97 | 1,237,103,129 | 1,212,608,500 | 24,494,629 | 98 |

* Excluding closed and transferred projects.

** Excluding agency support costs.

# Implementation of projects and activities by the World Bank for 2025 and cumulative since 1991 up to 31 December 2025 is summarized as follows:

## Phase-out: In 2025, 7,184.9 ODP tonnes of consumption and production of ODS were phased out and an additional 330 ODP tonnes of consumption of ODS and 615.8 mt (943,064 CO2-eq tonnes) of consumption of HFCs were approved for phase-out. Since 1991, 150,371 ODP tonnes of consumption of ODS and 193,943 ODP tonnes of production of ODS had been phased out, of an expected total of 319,216 ODP tonnes of consumption and production of ODS, and 8.8 mt (12,555 CO2-eq tonnes) had been phased out, of an expected total of 1,390 mt (2,375,388 CO2-eq tonnes) of consumption of HFCs from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2025, US $22.1 million was disbursed, and US $23.15 million was planned for disbursement based on the 2024 progress report, representing a rate of disbursement of 95 per cent of that planned. Cumulatively, US $1.21 billion had been disbursed out of the total US $1.24 billion approved for disbursement (excluding agency support costs), representing a rate of disbursement of 98 per cent. In 2025, US $9.47 million was approved for implementation;

## Cost-effectiveness (in ODP):  Since 1991, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $5.50/kg and for the production sector was US $2.34/kg. The average cost-effectiveness of investment projects per ODP tonne was US $3.32/kg for completed projects and US $5.35/kg for ongoing projects;

## Number of projects completed: In 2025, 12 projects were completed. Since 1991, 1,133 projects of the 1,165 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 97 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2025 were completed on average 47 months after their approval. Since 1991, the average time for completion of investment projects has been 40 months after their approval. First disbursements under these projects occurred, on average, 23 months after they had been approved;

## Speed of delivery – non-investment projects: Projects that were completed in 2025 were completed on average 34 months after their approval. Since 1991, the average time for completion of non-investment projects has been 39 months after their approval. First disbursements under these projects occurred, on average, 22 months after they had been approved;

## Project preparation: Of the 342 project preparation activities approved by the end of 2025, 330 have been completed, leaving 12 ongoing activities. In 2025, one project preparation activity was completed;

## Implementation delays: A total of 32 projects were under implementation at the end of 2025, experiencing, on average, a delay of three months. Ten of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation, and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2025, two MYAs for HPMPs, one HPPMP and three MYAs for KIPs were under implementation. Since 1991, 44 MYAs have been approved and 38 MYAs have been completed, representing a completion rate of 86 per cent.

# Table 3 summarizes progress made by the World Bank since 1991.

## Table 3. Progress made by the World Bank since 1991

| Phase-out achieved |  | Disbursement (US $) | Average CE (US$/kg) |  | Number of projects |  | Speed of delivery for completion (months) |  | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes* | CO2-eq tonnes** |  | Consump- tion | Produc- tion | Approved | Completed | Investment | Non- investment |  | Approved | Completed |
| 344,314 | 12,555 | 1,212,608,500 | 5.50 | 2.34 | 1,165 | 1,133 | 40 | 39 | 3 | 44 | 38 |

* Consumption and production of ODS.

** HFC-related projects.

HFC-related projects

# As of 31 December 2025, the Executive Committee had approved 31 HFC-related projects (including one investment project, 12 preparation activities, seven technical assistance projects and 11 projects related to stage I of KIPs) amounting to US $10,393,707 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 4 to 8.

Table 4. HFC-related projects approved*

| Clusters | Number of projects |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| HFC individual – investment | 1 | 1 | 100 | 183,514 | 183,514 | 0 | 100 |
| HFC individual – preparation projects | 12 | 7 | 58 | 1,395,000 | 1,003,615 | 391,385 | 72 |
| HFC individual – technical assistance | 7 | 7 | 100 | 1,094,080 | 1,094,080 | 0 | 100 |
| KIP stage I | 11 | 0 | 0 | 7,721,113 | 0 | 7,721,113 | 0 |
| Total | 31 | 15 | 48 | 10,393,707 | 2,281,209 | 8,112,498 | 22 |

* Excluding cancelled and transferred projects.

** Excluding agency support costs.

Note: 1,390 mt (2,375,388 CO2-eq tonnes) of HFCs was approved for phase-out.

# As of the end of 2025, of the 31 projects, one investment project, seven preparation activities and seven technical assistance projects have been completed, leaving 16 ongoing. The ongoing projects are at various stages of implementation.

# Of the total cumulative funding approved of US $10,393,707 (excluding agency support costs), US $2,281,209 has been disbursed, representing a disbursement rate of 22 per cent.

Energy-efficiency projects

# As of 31 December 2025, the Executive Committee had approved eight energy-efficiency projects (including one preparation activity and one technical assistance pilot project under the funding window pursuant to decision 91/65; one preparation activity and one investment project under the funding window pursuant to decision 94/60; three preparation activities for energy-efficiency revolving-fund end-user projects pursuant to decision 95/87; and one preparation activity for a conversion project pursuant to decision 87/50) amounting to US $1,430,689 (excluding agency support costs). A summary of the status of these projects is presented in table 5 and the respective data has already been included in paragraphs 4 to 8.

Table 5. Energy-efficiency projects approved*

| Type | Number of projects |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Pilot projects (decision 91/65) – project preparation | 1 | 1 | 100 | 30,000 | 30,000 | 0 | 100 |
| Pilot projects (decision 91/65) – technical assistance | 1 | 0 | 0 | 500,000 | 0 | 500,000 | 0 |
| Manufacturing (decision 94/60) – project preparation | 1 | 0 | 0 | 35,000 | 35,000 | 0 | 100 |
| Manufacturing (decision 94/60) – investment | 1 | 0 | 0 | 415,689 | 0 | 415,689 | 0 |
| Energy-efficiency revolving-fund end-user projects (decision 95/87) – project preparation | 3 | 0 | 0 | 300,000 | 51,330 | 248,670 | 17 |
| Others – project preparation | 1 | 0 | 0 | 150,000 | 18,769 | 131,231 | 13 |
| Total | 8 | 1 | 13 | 1,430,689 | 135,099 | 1,295,590 | 9 |

* Excluding cancelled projects.

** Excluding agency support costs.

# As of the end of 2025, of the eight projects, one preparation activity pursuant to decision 91/65 has been completed, leaving seven ongoing. The ongoing projects are at various stages of implementation.

# Of the total cumulative funding approved of US $1,430,689 (excluding agency support costs), US $135,099 has been disbursed, representing a disbursement rate of 9 per cent.

Issues identified in project implementation in 2025

# Further to the review process, several issues were discussed and satisfactorily addressed, except for issues on 10 projects classified as projects with implementation delays that are related to components of MYAs that are subject to procedures for project cancellation, in line with decision 84/45(c). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 100th meeting.

# Details of progress in implementation of the project associated with the HPMP for China (polyurethane foam sector plan) and a report on a project with specific reporting requirements associated with Viet Nam (KIP) have been submitted to the 99th meeting. Recommendations for outstanding issues for this project, including approval of extension requests, if any, are addressed in the relevant sections of this document. Outstanding issues for the remaining ongoing projects not included in annex III to the present document, and requests for extension of dates of completion are addressed below.

# Of the 19 ongoing projects, excluding IS and project preparation, five projects have revised planned dates of completion since the 2024 progress report.

# In line with decision 82/11(b), the World Bank has requested the extension of the duration of two projects pursuant to decision 91/66, as shown in table 6.

Table 6. Projects pursuant to decision 91/66 for which an extension of the completion date has been requested

| Country/project code | Disburse-ment (%) | Activities requiring additional time | Original date of completion (mm-yy) | Date of completion requested (mm-yy) |
| --- | --- | --- | --- | --- |
| Preparation of a national inventory of banks of waste controlled substances and development of a national plan for the management of those substances (decision 91/66) |  |  |  |  |
| Thailand THA/HFCIND/190/WB/PRP/DES/95 | 41 | Finalization of the methodology and approach for future inventory updates by the national ozone unit using artificial intelligence tools, and finalization and Government endorsement of the final report | Dec-26 | Jun-27 |
| Viet Nam VNM/HFCIND/95/WB/PRP/DES/93 | 21 | Finalization of the report through stakeholder consultations and Government endorsement | Dec-25* | Jun-27 |

* Date of completion had already been revised to December 2026 (decision 97/14(b)).

# Additionally, in line with decision 82/11(b), the World Bank has requested the extension of the duration of six projects related to the HPMP and KIP for Viet Nam, as shown in table 7.

Table 7. Projects related to the HPMP and KIP for Viet Nam for which an extension of the completion date has been requested

| Project code | Disburse-ment (%) | Activities requiring additional time | Original date of completion (mm-yy) | Date of completion requested (mm-yy) |
| --- | --- | --- | --- | --- |
| HPMP (stage III, first tranche) (PMU) VNM/HPMP3/93/WB/TAS/PMU/93 | 0 | Completion of the remaining planned activities, which were delayed due to constraints during project initiation | Dec-26 | Dec-27 |
| HPMP (stage III, first tranche) (servicing sector) VNM/HPMP3/94/WB/INV/SRV/93 |  |  |  |  |
| KIP (stage I, first tranche) (PMU) VNM/KIP1/97/WB/TAS/PMU/93 |  |  |  |  |
| KIP (stage I, first tranche) (servicing sector) VNM/KIP1/96/WB/INV/SRV/93 |  |  |  |  |
| KIP (stage I, first tranche) (rail mobile air-conditioning conversion) VNM/KIP1/92/WB/INV/AC/93 |  |  |  |  |
| KIP (stage I, first tranche) (industrial refrigeration sector) VNM/KIP1/91/WB/INV/AC/93* |  |  |  |  |

* A request for a transfer of agency has been submitted to the present meeting.

Gender mainstreaming

# The World Bank continues to implement the Multilateral Fund’s policy in this area across projects, alongside the World Bank Group’s Gender Strategy 2024-2030. All projects are reviewed internally by a specialist. Relevant considerations are incorporated into project results frameworks, as well as indicators to track women’s participation in technical training programmes. Participating enterprises (e.g., in Malaysia) have committed to reporting female/male employment ratios. In addition, countries are encouraged to recruit women into newly established project management units from 2026 onward. Efforts to promote women’s participation across project activities remain ongoing, including continuous stakeholder sensitization on the implementation of the policy.

Risk management

# The World Bank closely monitors implementation risks and delays and takes measures to ensure the timely implementation of projects. Certain implementation risks arise from changes in government policies or regulatory requirements that are beyond the control of the implementing agency. In such instances, the World Bank works closely with national partners and relevant government agencies to identify and implement appropriate mitigation measures. For example, appraisal for stage III of the HPMP and stage I of the KIP for Viet Nam was delayed until August 2025 due to government concerns regarding consistency of private-sector financing arrangements with the State Budget and Public Property laws. This issue was resolved by removing direct sub-project disbursements from the overall project.  The World Bank continues to tailor risk mitigation measures to specific national circumstances and to address implementation delays accordingly.

Recommendation

# The Executive Committee may wish:

## To note the progress report of the World Bank as at 31 December 2025 contained in document UNEP/OzL.Pro/ExCom/99/18;

## To approve the extension, to June 2027, of the completion dates of the preparation of a national inventory of banks of waste controlled substances and development of a national plan for the management of those substances (decision 91/66) for Thailand (THA/HFCIND/190/WB/PRP/DES/95) and Viet Nam (VNM/HFCIND/95/WB/PRP/DES/93) to allow completion of the remaining ongoing activities, as reflected in table 6 of document UNEP/OzL.Pro/ExCom/99/18;

## To approve also the extension, to December 2027, of the completion dates of the projects related to the HCFC phase-out management plan (HPMP) and the Kigali HFC implementation plan (KIP) for Viet Nam listed below to allow completion of the remaining ongoing activities, as reflected in table 7 of document UNEP/OzL.Pro/ExCom/99/18:

### HPMP (stage III, first tranche) (PMU) (VNM/HPMP3/93/WB/TAS/PMU/93);

### HPMP (stage III, first tranche) (servicing sector) (VNM/HPMP3/94/WB/INV/SRV/93);

### KIP (stage I, first tranche) (PMU) (VNM/KIP1/97/WB/TAS/PMU/93);

### KIP (stage I, first tranche) (servicing sector) (VNM/KIP1/96/WB/INV/SRV/93);

### KIP (stage I, first tranche) (rail mobile air-conditioning conversion) (VNM/KIP1/92/WB/INV/AC/93);

### KIP (stage I, first tranche) (industrial refrigeration sector) (VNM/KIP1/91/WB/INV/AC/93); and

## To approve also the recommendations related to ongoing projects with specific issues contained in annex III to the present document.

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR THE WORLD BANK

PER COUNTRY FOR 2025

# Table 1 of annex I presents the status of project implementation by country for 2025 in achieved phase-out, planned and achieved disbursements and project completion.

Table 1. Status of project implementation by the World Bank for 2025

| Country | Phased out in 2025 (ODP tonnes)* | Phased out in 2025 (CO2-eq tonnes)** | Estimated funds disbursed in 2025 (US$) | Funds disbursed in 2025 (US$) | Percentage of funds disbursed over estimation in 2025 | Percentage of planned projects completed in 2025*** |
| --- | --- | --- | --- | --- | --- | --- |
| China | 7,135.0 | 0 | 20,930,000 | 20,630,000 | 99 | 75 |
| Grenada |  |  | 0 | 43,872 | Over |  |
| Indonesia | 0.0 | 0 | 159,081 | 194,081 | 122 | 100 |
| Malaysia |  |  | 499,806 | 38,000 | 8 |  |
| Thailand | 49.9 | 0 | 1,492,307 | 1,173,944 | 79 | 33 |
| Viet Nam |  |  | 64,000 | 16,300 | 25 | 0 |
| Global**** |  |  |  |  |  | 100 |
| Grand total | 7,184.9 | 0 | 23,145,194 | 22,096,197 | 95 | 60 |

* Including 49.9 ODP tonnes of consumption and 7,135 ODP tonnes of production of ODS.

** No phase-out in 2025 for HFC-related projects.

*** For projects that were planned to be completed in 2025.

**** 2025 core unit.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR THE WORLD BANK

PER YEAR AS AT 31 DECEMBER 2025

# Table 1 of annex II presents an overview of the status of project implementation by year. All projects and activities approved between 1991 and 2022, have now been completed.

Table 1. Status of project implementation by year*

| Year | Number of projects |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1991 | 42 | 42 | 100 | 5,429,404 | 5,429,404 | 0 | 100 |
| 1992 | 76 | 76 | 100 | 28,027,284 | 28,027,284 | 0 | 100 |
| 1993 | 79 | 79 | 100 | 42,538,405 | 42,538,405 | 0 | 100 |
| 1994 | 91 | 91 | 100 | 40,023,192 | 40,023,192 | 0 | 100 |
| 1995 | 112 | 112 | 100 | 47,007,389 | 47,007,389 | 0 | 100 |
| 1996 | 55 | 55 | 100 | 29,252,692 | 29,252,692 | 0 | 100 |
| 1997 | 95 | 95 | 100 | 56,173,102 | 56,173,103 | -1 | 100 |
| 1998 | 60 | 60 | 100 | 35,959,418 | 35,959,417 | 1 | 100 |
| 1999 | 74 | 74 | 100 | 64,173,138 | 64,173,138 | 0 | 100 |
| 2000 | 68 | 68 | 100 | 36,982,134 | 36,982,133 | 1 | 100 |
| 2001 | 31 | 31 | 100 | 55,212,853 | 55,212,854 | -1 | 100 |
| 2002 | 33 | 33 | 100 | 64,357,778 | 64,357,778 | 0 | 100 |
| 2003 | 24 | 24 | 100 | 72,734,119 | 72,734,119 | 0 | 100 |
| 2004 | 29 | 29 | 100 | 77,111,770 | 77,111,770 | 0 | 100 |
| 2005 | 31 | 31 | 100 | 68,592,865 | 68,592,865 | 0 | 100 |
| 2006 | 23 | 23 | 100 | 64,473,260 | 64,473,261 | -1 | 100 |
| 2007 | 26 | 26 | 100 | 66,005,270 | 66,005,270 | 0 | 100 |
| 2008 | 30 | 30 | 100 | 39,934,666 | 39,934,667 | -1 | 100 |
| 2009 | 23 | 23 | 100 | 23,124,647 | 23,124,647 | 0 | 100 |
| 2010 | 16 | 16 | 100 | 1,148,623 | 1,148,623 | 0 | 100 |
| 2011 | 10 | 10 | 100 | 44,190,517 | 44,324,558 | -134,041 | 100 |
| 2012 | 10 | 10 | 100 | 11,698,145 | 11,698,145 | 0 | 100 |
| 2013 | 7 | 7 | 100 | 43,736,999 | 43,602,958 | 134,041 | 100 |
| 2014 | 13 | 13 | 100 | 28,336,509 | 28,336,509 | 0 | 100 |
| 2015 | 13 | 13 | 100 | 62,990,648 | 62,990,648 | 0 | 100 |
| 2016 | 18 | 18 | 100 | 12,601,632 | 12,601,632 | 0 | 100 |
| 2017 | 6 | 6 | 100 | 2,178,705 | 2,178,705 | 0 | 100 |
| 2018 | 8 | 8 | 100 | 26,650,464 | 26,650,464 | 0 | 100 |
| 2019 | 3 | 3 | 100 | 2,579,179 | 2,579,179 | 0 | 100 |
| 2020 | 2 | 2 | 100 | 2,067,012 | 2,067,012 | 0 | 100 |
| 2021 | 7 | 7 | 100 | 9,608,235 | 9,608,235 | 0 | 100 |
| 2022 | 7 | 7 | 100 | 22,689,082 | 22,686,781 | 2,301 | 100 |
| 2023 | 23 | 9 | 39 | 15,764,363 | 6,438,419 | 9,325,944 | 41 |
| 2024 | 9 | 2 | 22 | 24,275,689 | 18,270,089 | 6,005,600 | 75 |
| 2025 | 11 | 0 | 0 | 9,473,941 | 313,155 | 9,160,786 | 3 |
| Total | 1,165 | 1,133 | 97 | 1,237,103,129 | 1,212,608,500 | 24,494,629 | 98 |

* Excluding closed and transferred projects.

** Excluding agency support costs.

Annex III

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR THE WORLD BANK

| Country | Project code | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- | --- |
| Malaysia | MYS/KIP1/199/WB/INV/AC/93 | Kigali HFC implementation plan (stage I, first tranche) (mobile air-conditioning) | 0 | 18 months delays | To request the World Bank to report to the 100th meeting on this project with implementation delays |
| Malaysia | MYS/KIP1/202/WB/INV/REF/93 | Kigali HFC implementation plan (stage I, first tranche) (commercial refrigeration) | 0 | 18 months delays | To request the World Bank to report to the 100th meeting on this project with implementation delays |
| Malaysia | MYS/KIP1/203/WB/INV/SRV/93 | Kigali HFC implementation plan (stage I, first tranche) (servicing and technical assistance) | 0 | 18 months delays | To request the World Bank to report to the 100th meeting on this project with implementation delays |
| Malaysia | MYS/KIP1/204/WB/TAS/PMU/93 | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 0 | 18 months delays | To request the World Bank to report to the 100th meeting on this project with implementation delays |
| Viet Nam | VNM/HPMP3/93/WB/TAS/PMU/93 | HCFC phase-out management plan (stage III, first tranche) (PMU) | 0 | 18 months delays | To request the World Bank to report to the 100th meeting on this project with implementation delays |
| Viet Nam | VNM/HPMP3/94/WB/INV/SRV/93 | HCFC phase-out management plan (stage III, first tranche) (servicing sector) | 0 | 18 months delays | To request the World Bank to report to the 100th meeting on this project with implementation delays |
| Viet Nam | VNM/KIP1/91/WB/INV/AC/93* | Kigali HFC implementation plan (stage I, first tranche) (industrial refrigeration sector) | 0 | 18 months delays | To request the World Bank to report to the 100th meeting on this project with implementation delays |
| Viet Nam | VNM/KIP1/92/WB/INV/AC/93 | Kigali HFC implementation plan (stage I, first tranche) (rail mobile air-conditioning conversion) | 0 | 18 months delays | To request the World Bank to report to the 100th meeting on this project with implementation delays |
| Viet Nam | VNM/KIP1/96/WB/INV/SRV/93 | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 0 | 18 months delays | To request the World Bank to report to the 100th meeting on this project with implementation delays |
| Viet Nam | VNM/KIP1/97/WB/TAS/PMU/93 | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 0 | 18 months delays | To request the World Bank to report to the 100th meeting on this project with implementation delays |

* A request for a transfer of agency has been submitted to the present meeting.

UNEP/OzL.Pro/ExCom/99/1

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database, which is provided on the 99th meeting portal on the Multilateral Fund’s website, in the spreadsheet programme, Microsoft Excel.

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 99th meeting.

Funded by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment.

Ongoing projects are all projects that were under implementation as at 31 December 2025. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

Phase-out of ODS is expressed in ODP tonnes and of HFCs in mt and CO2-eq tonnes.

Including 49.9 ODP tonnes of consumption and 7,135 ODP tonnes of production of ODS. No phase-out in 2025 for HFC-related projects.

Including 1,390 mt of HFC-related projects. Cost-effectiveness in CO2-eq is not included due to the limited number of projects approved.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61).

UNEP/OzL.Pro/ExCom/99/45

UNEP/OzL.Pro/ExCom/99/19 or UNEP/OzL.Pro/ExCom/99/20

Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.

The Executive Committee requested bilateral and implementing agencies to provide a brief report on key gender mainstreaming results achieved as part of their annual progress reports, as of 2023, on the basis of the information available to them (decision 90/48(d)).

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.