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Corrigendum

PROGRESS REPORT OF UNEP AS AT 31 DECEMBER 2017
This corrigendum is being issued to provide clarification on projects recommended for cancellation in accordance with relevant Executive Committee policies and decisions as follows:
· Add paragraph 8(bis) as follows:
[bookmark: _GoBack]8(bis).	In addition, the Secretariat noted that no progress had been made for nine projects in five countries due to different issues and circumstances noted in the table below. The Executive Committee may wish to consider cancellation of these projects and request remaining balances to be returned.

	Country/
Project code
	Project title

	Disburse-ment rate (%)
	Status/Issues

	Antigua and Barbuda 
ANT/PHA/66/TAS/14
	HCFC phase-out management plan (stage I, first tranche)
	59
	Project completion date of stage I by the Agreement with the Executive Committee is December 2016

	Antigua and Barbuda 
ANT/SEV/68/INS/15
	Extension of institutional strengthening project (phase IV: 1/2013-12/2014)
	50
	Delayed; phase V of IS was approved at the 73rd meeting

	Central African Republic (the)
CAF/PHA/64/TAS/22
	HCFC phase-out management plan (stage I, first tranche)
	60
	Delayed due to security situation in the country; difficulty in continuing project implementation

	Central African Republic (the)
CAF/PHA/71/TAS/24
	Verification report on the implementation of the HCFC phase-out management plan
	0
	

	Ethiopia 
ETH/SEV/73/INS/23
	Extension of the institutional strengthening project (phase VI: 1/2015-12/2016)
	0
	Delayed; phase VII approved at the 77th meeting

	Guyana
GUY/PHA/74/TAS/24
	HCFC phase-out management plan (stage I, second tranche)
	0
	Project completion date of stage I by the Agreement with the Executive Committee is December 2016

	Yemen 
YEM/PHA/68/TAS/40
	HCFC phase-out management plan (stage I, first tranche)
	0
	Delayed due to security situation in the country; difficulty in continuing project implementation

	Yemen 
YEM/PHA/55/TAS/31
	National ODS phase-out plan (first tranche)
	100
	

	Yemen 
YEM/PHA/73/PRP/44
	Preparation of a HCFC phase-out management plan (stage II)
	0
	



· Add sub-paragraph (c) to the recommendation in paragraph 10 as follows:
(c)	To cancel the following projects at the 82nd meeting and to request UNEP to return the remaining balances to the 83rd meeting:
HCFC phase-out management plan for Antigua and Barbuda (stage I, first tranche) (ANT/PHA/66/TAS/14);
Extension of institutional strengthening project for Antigua and Barbuda (phase IV: 1/2013-12/2014) (ANT/SEV/68/INS/15);
HCFC phase-out management plan for the Central African Republic (stage I, first tranche) (CAF/PHA/64/TAS/22);
Verification report on the implementation of the HCFC phase-out management plan for the Central African Republic (CAF/PHA/71/TAS/24);
Extension of the institutional strengthening project for Ethiopia (phase VI: 1/2015‑12/2016) (ETH/SEV/73/INS/23);
HCFC phase-out management plan for Guyana (stage I, second tranche) (GUY/PHA/74/TAS/24);
HCFC phase-out management plan for Yemen (stage I, first tranche) (YEM/PHA/68/TAS/40);
National ODS phase-out plan for Yemen (first tranche) (YEM/PHA/55/TAS/31); and
Preparation of a HCFC phase-out management plan for Yemen (stage II) (YEM/PHA/73/PRP/44).
· Delete the rows for Antigua and Barbuda, the Central African Republic, Ethiopia, Guyana and Yemen in the table contained in Annex I for the projects mentioned in paragraph 8(bis). 
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