| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/95/19 30 October 2024 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-fifth Meeting

Montreal, 4-8 December 2024

Item 7(a)(vi) of the provisional agenda

PROGRESS REPORT OF THE WORLD BANK AS AT 31 DECEMBER 2023

Introduction

# This document presents the progress report of the World Bank as at 31 December 2023.

# The progress report of the World Bank includes the status of implementation of projects, including five HFC-related projects that have been funded under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast start support for implementation of the Kigali Amendment.

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2023, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs, which are measured in metric tonnes (mt) and CO2-eq tonnes.

# This document consists of the following sections:

## I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2023 and cumulative since 1991 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs). It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee.

## II.	Projects approved for Annex F substances (HFCs) under the additional voluntary contributions for fast-start support for HFC phase-down.

III.	Recommendation.

I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund

I.1	Progress in implementation of projects for 2023 and cumulative since 1991

# As of 31 December 2023, the Executive Committee had approved US $1.33 billion in projects for the World Bank, consisting of US $1.21 billion for the implementation of investment and non-investment projects and US $127.72 million for agency support costs, as shown in table 1.

# Table 1. Approved funding by sector for the World Bank as at 31 December 2023

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 22,984,030 |
| Destruction | 500,000 |
| Energy efficiency | 60,000 |
| Foam | 136,059,064 |
| Halon | 70,221,038 |
| HFC phase-down plan | 5,585,704 |
| Fumigants | 5,837,887 |
| Multiple sectors | 2,341,168 |
| Other | 5,059,360 |
| Phase-out plan | 222,655,585 |
| Process agent | 114,342,497 |
| Production | 400,943,496 |
| Refrigeration | 180,259,970 |
| Several | 29,413,466 |
| Solvents | 10,237,394 |
| Sterilant | 661,227 |
| Sub-total | 1,207,161,885 |
| Agency support costs | 127,723,299 |
| Total | 1,334,885,184 |

# In 2023, 24 new projects and activities were approved. This level of funding is expected to result in the phase-out of 313,447 ODP tonnes of consumption and production of ODS and 750.4 mt (1,388,279 CO2-eq tonnes) of consumption of HFCs. Annex I shows the status of project implementation per country in 2023.

# Table 2 shows the status of project implementation including fund disbursement per project type as at 31 December 2023. Annex II presents analytical information per year since 1991.

Table 2. Status of project implementation by type as at 31 December 2023

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance *** | % disbursed |
| Country programme | 29 | 29 | 100 | 1,627,732 | 1,627,732 | 0 | 100 |
| Demonstration | 8 | 8 | 100 | 6,172,901 | 6,172,901 | 0 | 100 |
| Institutional strengthening (IS) | 51 | 49 | 96 | 10,013,716 | 9,710,320 | 303,396 | 97 |
| Investment | 654 | 633 | 97 | 1,147,306,108 | 1,106,559,426 | 40,746,682 | 96 |
| Project preparation | 304 | 297 | 98 | 28,028,320 | 27,201,415 | 826,905 | 97 |
| Technical assistance | 78 | 75 | 96 | 13,707,342 | 15,505,735 | -1,798,393 | 113 |
| Training | 4 | 4 | 100 | 305,766 | 305,766 | 0 | 100 |
| Total | 1,128 | 1,095 | 97 | 1,207,161,885 | 1,167,083,295 | 40,078,590 | 97 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

***Negative balances are due to the distribution of funds balances among different tranches of the same HPMP.

# Implementation of projects and activities by the World Bank for 2023 and cumulative since 1991 up to 31 December 2023, is summarized as follows:

## Phase-out: In 2023, 129.1 ODP tonnes of consumption of ODS were phased out  and an additional 66.4 ODP tonnes of consumption of ODS and 750.4 mt (1,388,279 CO2-eq tonnes) of consumption of HFCs were approved for phase-out. Since 1991, 148,359 ODP tonnes of consumption of ODS and 187,996 ODP tonnes of production of ODS had been phased out, of an expected total of 313,447 ODP tonnes of consumption and production of ODS from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2023, US $8.44 million was disbursed and US $18.16 million was planned for disbursement based on the 2022 progress report, representing a rate of disbursement of 46 per cent of that planned. Cumulatively, US $1.17 billion had been disbursed out of the total US $1.21 billion approved for disbursement (excluding agency support costs), representing a rate of disbursement of 97 per cent. In 2023, US $15.79 million was approved for implementation;

## Cost-effectiveness (in ODP):  Since 1991, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $5.53/kg and for the production sector was US $4.78/kg. The average cost-effectiveness of investment projects per ODP tonne was US $3.24/kg for completed projects and US $7.67/kg for ongoing projects;

## Number of projects completed: In 2023, 14 projects were completed. Since 1991, 1,095 projects of the 1,128 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 97 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2023 were completed on average 37 months after their approval. Since 1991, the average time for completion of investment projects has been 40 months after their approval. First disbursements under these projects occurred, on average, 24 months after they had been approved;

## Speed of delivery – non-investment projects: Projects that were completed in 2023 were completed on average 36 months after their approval. Since 1991, the average time for completion of non-investment projects has been 35 months after their approval. First disbursements under these projects occurred, on average, 22 months after they had been approved;

## Project preparation: Of the 304 project preparation activities approved by the end of 2023, 297 have been completed, leaving seven ongoing activities. In 2023, six preparation activities have been completed;

## Implementation delays: A total of 33 projects were under implementation at the end of 2023, experiencing, on average, a delay of 10 months. Five of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation, and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2023, four MYAs for HCFC phase-out management plans (HPMPs), one HCFC production phase-out management plan (HPPMP) and two Kigali HFC implementation plans (KIPs) were under implementation. Since 1991, 43 MYAs have been approved and 36 MYAs have been completed, representing a completion rate of 84 per cent.

# Table 3 summarizes progress made by the World Bank since 1991.

## Table 3. Progress made by the World Bank since 1991

| Phase out achieved |  | Disbursement (US $) | Average CE (US$/kg) |  | Number of projects |  | Speed of delivery for completion (months) |  | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes* | CO2-eq tonnes |  | Consump- tion | Produc- tion | Approved | Completed | Investment | Non- investment |  | Approved | Completed |
| 336,355 | 0 | 1,167,083,295 | 5.53 | 4.78 | 1,128 | 1,095 | 40 | 35 | 10 | 43 | 36 |

*Consumption and production of ODS.

HFC-related projects

# As of 31 December 2023, the Executive Committee had approved 17 HFC-related projects under regular contributions amounting to US $5,645,704 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 5 to 9.

Table 4. HFC-related projects approved under regular contributions

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment – KIP stage I** | 8 | 0 | 0 | 4,600,704 | 0 | 4,600,704 | 0 |
| Preparation | 9 | 5 | 56 | 1,045,000 | 488,095 | 556,905 | 47 |
| Total | 17 | 5 | 29 | 5,645,704 | 488,095 | 5,157,609 | 9 |

* Excludes agency support costs.

** 750.4 mt (1,388,279 CO2-eq tonnes) of HFCs was approved for phase-out.

# Of the total cumulative funding approved of US $5,645,704, US $488,095 had been disbursed, representing a disbursement rate of 9 per cent. Five of the nine preparation activities were completed in 2023. The remaining four are expected to be completed in 2025. All the eight investment projects for stage I of KIPs were approved in 2023 and are expected to be completed in 2026.

I.2	Issues identified in project implementation in 2023

# Further to the review process, several issues were discussed and satisfactorily addressed, except for issues on five projects related to components of MYAs, classified as projects with implementation delays that are subject to procedures for project cancellation, in line with decision 84/45(c). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 96th meeting.

# Details of progress in implementation of projects associated with the HPMPs for China (polyurethane foam sector plan) and Jordan and the HPPMP for China, and a report on a project with specific reporting requirements associated with the HPMP of Viet Nam has been submitted to the 95th meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. The issues relating to the HPMP for Thailand, the tranche of which was due at the 95th meeting but was not submitted, are addressed in the document on tranche submission delays. Outstanding issues for the remaining ongoing projects not included in annex III to the present document, and requests for extension of dates of completion, are addressed below.

# Of the 24 ongoing projects, excluding IS and project preparation, six projects have revised planned dates of completion since the 2022 progress report.

# In line with decision 82/11(c)(ii), the Secretariat noted that renewal of the IS project for Thailand had not been submitted for the last two years. The World Bank indicated that there remain sufficient funds available for implementation and is planning to submit the renewal request to the 96th meeting.

# In line with decision 82/11(b), the World Bank has requested the extension of the duration of five projects, as shown in table 5.

Table 5. Projects for which an extension of the completion dates has been requested

| Country/ project code | Project title | Disburse-ment (%) | Status/issues | Original date of completion | Date of completion requested |
| --- | --- | --- | --- | --- | --- |
| Thailand THA/PHA/82/INV/179 | HCFC phase-out management plan (stage II, first tranche) (spray foam sector) | 53 | Additional time required to provide support to small spray foam companies and to implement the remaining training activities for technicians in the servicing sector. | Dec-24 | Jun-25 |
| Thailand THA/PHA/82/TAS/177 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector and project management unit) | 69 |  |  |  |
| Thailand THA/PHA/92/INV/181 | HCFC phase-out management plan (stage II, second tranche) (PMU) | 94 |  |  |  |
| Thailand THA/PHA/92/INV/182 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 0 |  |  |  |
| Thailand THA/PHA/92/INV/183 | HCFC phase-out management plan (stage II, second tranche) (spray foam manufacturing sector) | 0 |  |  |  |

Gender mainstreaming

# The World Bank reported that in 2023, two countries were reporting on gender mainstreaming: Malaysia (preparation of the KIP and KIP (stage I, first tranche)); and Viet Nam (preparation of HPMP (stage III), HPMP (stage III, first tranche), preparation of the KIP, and KIP (stage I, first tranche)).

# In both countries, the consultations held included gender mainstreaming and gender aspects related to project implementation. Further, the relevant departments (the Department of Environment in Malaysia and the Department of Climate Change in Viet Nam) agreed to pay continued attention to gender mainstreaming and to seek out opportunities to help foster gender mainstreaming in project activities under their direct control. Gender actions will be reflected in the overarching project under the relevant project agreements.

II.	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down

# As of 31 December 2023, the Executive Committee had approved five HFC-related projects under the additional voluntary contributions amounting to US $957,594 (excluding agency support costs). A summary of the status of these projects is presented in table 6.

# Table 6. Status of approved HFC-related projects as of the end of 2023

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment*** | 1 | 1 | 100 | 183,514 | 183,514 | 0 | 100 |
| Project preparation | 1 | 1 | 100 | 30,000 | 30,000 | 0 | 100 |
| Enabling activities | 3 | 3 | 100 | 744,080 | 744,080 | 0 | 100 |
| Total | 5 | 5 | 100 | 957,594 | 957,594 | 0 | 100 |

* Excludes transferred projects.

** Excludes agency support costs.

*** 8.8 mt (12,555 CO2-eq tonnes) of HFCs was approved and phased out.

# As of the end of 2023, all the five activities approved had been completed.

# The total cumulative funding approved of US $957,594 had been disbursed, representing a disbursement rate of 100 per cent.

III.	Recommendation

# The Executive Committee may wish:

## To note the progress report of the World Bank as at 31 December 2023 contained in document UNEP/OzL.Pro/ExCom/95/19;

## To approve the extension, to 30 June 2025, of the completion date of stage II of the HCFC phase-out management plan for Thailand (first tranche (spray foam sector) (THA/PHA/82/INV/179) and (refrigeration servicing sector and project management unit) (THA/PHA/82/TAS/177); and second tranche (PMU) (THA/PHA/92/INV/181), (refrigeration servicing sector) (THA/PHA/92/INV/182) and (spray foam manufacturing sector) (THA/PHA/92/INV/183)) to allow completion of the remaining ongoing activities, as reflected in table 5 of document UNEP/OzL.Pro/ExCom/95/19; and

## To approve the recommendations related to ongoing projects with specific issues contained in annex III to the present document.

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR THE WORLD BANK

PER COUNTRY FOR 2023

# Table 1 of annex I presents the status of project implementation by country for 2023 in achieved phased out, planned and achieved disbursements and project completion.

Table 1. Status of project implementation by the World Bank for 2023

| Country | Phased out in 2023 (ODP tonnes) | Phased out in 2023 (CO2-eq tonnes)* | Estimated funds disbursed in 2023 (US$) | Funds disbursed in 2023 (US$) | Percentage of funds disbursed over estimation in 2023 | Percentage of planned projects completed in 2023** |
| --- | --- | --- | --- | --- | --- | --- |
| China | 0.0 | 0 | 12,000,000 | 2,000,000 | 17 | 50 |
| Indonesia | 0.0 | 0 | 995,010 | 988,382 | 99 | 100 |
| Jordan | 0.0 | 0 | 1,388,425 | 413,120 | 30 | 0 |
| Malaysia | 0.0 | 0 | 217,000 | 164,199 | 76 | 100 |
| Thailand | 0.0 | 0 | 867,004 | 1,070,787 | 124 | 25 |
| Vietnam | 129.1 | 0 | 2,696,687 | 3,804,714 | 141 | 100 |
| Global*** | 0.0 | 0 | 0 | 0 |  | 100 |
| Grand total | 129.1 | 0 | 18,164,126 | 8,441,202 | 46 | 50 |

* No phase-out in 2023 for HFC-related projects.

** For projects that were planned to be completed in 2023.

*** 2023 core unit.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR THE WORLD BANK

PER YEAR AS AT 31 DECEMBER 2023

# Table 1 of annex II presents an overview of the status of project implementation by year. All projects and activities approved between 1991 and 2015, 2017 and 2020, have now been completed.

Table 1. Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1991 | 42 | 42 | 100 | 5,429,404 | 5,429,404 | 0 | 100 |
| 1992 | 76 | 76 | 100 | 28,047,705 | 28,047,705 | 0 | 100 |
| 1993 | 79 | 79 | 100 | 42,538,405 | 42,538,405 | 0 | 100 |
| 1994 | 91 | 91 | 100 | 41,081,267 | 41,081,267 | 0 | 100 |
| 1995 | 112 | 112 | 100 | 47,224,186 | 47,224,186 | 0 | 100 |
| 1996 | 55 | 55 | 100 | 29,319,479 | 29,319,479 | 0 | 100 |
| 1997 | 95 | 95 | 100 | 56,173,102 | 56,173,103 | -1 | 100 |
| 1998 | 59 | 59 | 100 | 35,959,418 | 35,959,417 | 1 | 100 |
| 1999 | 73 | 73 | 100 | 64,173,138 | 64,173,138 | 0 | 100 |
| 2000 | 67 | 67 | 100 | 36,982,134 | 36,982,133 | 1 | 100 |
| 2001 | 29 | 29 | 100 | 55,212,853 | 55,212,854 | -1 | 100 |
| 2002 | 32 | 32 | 100 | 64,357,778 | 64,357,778 | 0 | 100 |
| 2003 | 24 | 24 | 100 | 72,734,119 | 72,734,119 | 0 | 100 |
| 2004 | 29 | 29 | 100 | 77,111,770 | 77,111,770 | 0 | 100 |
| 2005 | 28 | 28 | 100 | 68,592,865 | 68,592,865 | 0 | 100 |
| 2006 | 22 | 22 | 100 | 64,473,260 | 64,473,260 | 0 | 100 |
| 2007 | 25 | 25 | 100 | 66,005,270 | 66,005,270 | 0 | 100 |
| 2008 | 28 | 28 | 100 | 39,934,666 | 39,934,666 | 0 | 100 |
| 2009 | 22 | 22 | 100 | 25,529,554 | 25,529,554 | 0 | 100 |
| 2010 | 16 | 16 | 100 | 1,148,623 | 1,148,623 | 0 | 100 |
| 2011 | 10 | 10 | 100 | 44,201,956 | 44,335,997 | -134,041 | 100 |
| 2012 | 10 | 10 | 100 | 11,698,145 | 11,698,145 | 0 | 100 |
| 2013 | 7 | 7 | 100 | 43,736,999 | 43,602,958 | 134,041 | 100 |
| 2014 | 13 | 13 | 100 | 28,336,509 | 28,336,509 | 0 | 100 |
| 2015 | 13 | 13 | 100 | 62,990,648 | 62,990,648 | 0 | 100 |
| 2016 | 18 | 17 | 94 | 12,601,632 | 12,601,632 | 0 | 100 |
| 2017 | 3 | 3 | 100 | 1,651,291 | 1,651,291 | 0 | 100 |
| 2018 | 7 | 3 | 43 | 26,408,870 | 25,786,875 | 621,995 | 98 |
| 2019 | 3 | 2 | 67 | 2,579,179 | 2,141,404 | 437,775 | 83 |
| 2020 | 2 | 2 | 100 | 2,067,012 | 2,067,012 | 0 | 100 |
| 2021 | 7 | 5 | 71 | 9,622,863 | 9,348,173 | 274,690 | 97 |
| 2022 | 7 | 5 | 71 | 23,443,422 | 308,710 | 23,134,712 | 1 |
| 2023 | 24 | 1 | 4 | 15,794,363 | 184,945 | 15,609,418 | 1 |
| Total | 1,128 | 1,095 | 97 | 1,207,161,885 | 1,167,083,295 | 40,078,590 | 97 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

Annex III

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR THE WORLD BANK

| Country/project code | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- |
| China CPR/PRO/81/INV/593 | HCFC production phase-out management plan (stage II, first tranche) | 100 | 12 months delays | Noting decision 77/8(j), to request the World Bank to report to the 96th meeting on this project with implementation delays |
| Jordan JOR/PHA/77/INV/99 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | 100 | 12 months delays | Noting decision 77/8(j), to request the World Bank to report to the 96th meeting on this project with implementation delays |
| Jordan JOR/PHA/84/INV/108 | HCFC phase-out management plan (stage II, second tranche) (polyurethane foam sector, project management and coordination) | 57 | 12 months delays | To request the World Bank to report to the 96th meeting on this project with implementation delays |
| Thailand THA/PHA/82/INV/179 | HCFC phase-out management plan (stage II, first tranche) (spray foam sector) | 53 | 12 months delays | To request the World Bank to report to the 96th meeting on this project with implementation delays |
| Thailand THA/PHA/82/TAS/177 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector and project management unit) | 69 | 12 months delays | To request the World Bank to report to the 96th meeting on this project with implementation delays |

UNEP/OzL.Pro/ExCom/95/1

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database, which is provided on the 95th meeting portal on the Multilateral Fund’s website, in the spreadsheet programme, Microsoft Excel.

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 95th meeting.

Ongoing projects are all projects that were under implementation as at 31 December 2023. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

Phase-out of ODS is expressed in ODP tonnes and of HFCs in mt and CO2-eq tonnes.

No phase-out for HFC-related projects in 2023.

No phase-out so far for HFC-related projects.

Including 750.4 mt of HFC-related projects. Cost-effectiveness in CO2-eq. is not included due to the limited number of projects approved.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61).

UNEP/OzL.Pro/ExCom/95/47

UNEP/OzL.Pro/ExCom/95/61

UNEP/OzL.Pro/ExCom/95/SGP/3

UNEP/OzL.Pro/ExCom/95/20 or UNEP/OzL.Pro/ExCom/95/21

UNEP/OzL.Pro/ExCom/95/24

Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.

The Executive Committee requested bilateral and implementing agencies to provide a brief report on key gender mainstreaming results achieved as part of their annual progress reports, as of 2023, on the basis of the information available to them (decision 90/48(d)).

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.