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اللجنــة التنفيـذيــــة للصنــدوق المــتعــدد الأطـــراف
لتنفيـــذ بروتوكـول مونتريــال 
الاجتماع الرابع والتسعون
مونتريال، 27 - 31 مايو/أيار 2024
البند 9 (ب) من جدول الأعمال المؤقت[footnoteRef:1] [1:  UNEP/OzL.Pro/ExCom/94/1] 


تقرير عن الأرصدة وتوافر الموارد

المقدمة
1. تقدم هذه الوثيقة ملخصاً للتعديلات المالية التي أشارت إليها الوكالات المنفذة والوكالات الثنائية حسبما وافقت عليه الأمانة. وهي تتضمن بيانات إحصائية[footnoteRef:2] من جميع المشاريع التي لديها أرصدة احتُفظ بها لأكثر من 12 شهراً بعد إنجاز المشروع، على النحو المطلوب بموجب المقررين 28/7 و56/2(ج). وتتناول الوثيقة الأرصدة التي يتعين إعادتها مقابل المشاريع على سبيل المتابعة للمقررات ذات الصلة (المشار إليها باسم مشاريع "صادر بشأنها مقررات" في هذه الوثيقة). كما تشير إلى مستوى الموارد المتاحة للجنة التنفيذية نقداً على النحو المسجل في وثيقة حالة الاشتراكات والمدفوعات،[footnoteRef:3] على النحو المطلوب في المقرر 41/92(ب)، وتقدم توصية في هذا الصدد. وترد المبالغ التي تحتفظ بها الوكالات المنفذة للمشاريع المنجزة والمشاريع الصادر بشأنها مقررات ومشاريع المساهمات الطوعية الإضافية في المرفق الأول والمرفق الثاني والمرفق الثالث. ويعرض المرفق الرابع الأموال التي أعادتها الوكالات المنفذة من المشاريع المنجزة والصادر بشأنها مقررات ومشاريع المساهمات الطوعية الإضافية. [2:  تستند البيانات المعروضة إلى قالب الإبلاغ الذي أعِدَّ عملاً بالمقرر 31/2.]  [3:  UNEP/OzL.Pro/ExCom/94/3] 

الأموال المقرر إعادتها إلى الاجتماع الرابع والتسعين
يصل إجمالي الأموال التي ستعيدها الوكالات المنفذة إلى 1,362,594 دولاراً أمريكياً من المشاريع المنجزة والمشاريع الصادر بشأنها مقررات ومشاريع المساهمات الطوعية الإضافية  كما هو موضح في الجدول 1.
الجدول 1: الأموال التي ستعيدها الوكالات المنفذة إلى الاجتماع الرابع والتسعين (بالدولار الأمريكي)
	الوكالة
	تكلفة المشروع
	تكلفة دعم الوكالة
	مجموع التكاليف

	البرنامج الإنمائي
	239,606
	17,619
	257,225

	اليونيب
	469,599
	44,402
	514,001

	اليونيدو
	551,985
	39,383
	591,368

	المجموع
	1,261,190
	101,404
	1,362,594



المبالغ التي تحتفظ بها الوكالات المنفّذة 

ترد في الجدول 2 معلومات عن أرصدة المشاريع المنجزة والمشاريع الصادر بشأنها مقررات ومشاريع المساهمات الطوعية الإضافية التي تحتفظ بها الوكالات المنفذة. 
الجدول 2: أرصدة المشاريع المنجزة ومشاريع المساهمات الطوعية  الإضافية التي تحتفظ بها الوكالات المنفذة (بما في ذلك تكاليف دعم الوكالة)
	سنة الإنجاز
	البرنامج الإنمائي
	اليونيدو
	المجموع

	
	العدد
	(بالدولار الأمريكي)
	العدد
	(بالدولار الأمريكي)
	العدد
	(بالدولار الأمريكي)

	المشاريع المنجزة منذ أكثر من سنتين

	2020
	1
	40,434 
	0
	0
	1
	40,434

	2021
	6
	31,261
	5
	72,926
	11
	104,187

	من 1 يناير/كانون الثاني إلى
30 أبريل/نيسان 2022
	0
	0
	0
	0
	0
	0

	المجموع الفرعي
	7
	71,695
	5
	72,926
	12
	144,621

	المشاريع التي مضى على إنجازها أقل من سنتين

	من 1 مايو/أيار إلى 
31 ديسمبر/كانون الأول 2022
	7
	55,953
	15
	3,404,125

	22
	3,460,078

	المجموع الفرعي
	7
	55,953
	15
	3,404,125
	22
	3,460,078

	المجموع 
	14
	127,648
	20
	3,477,052
	34
	3,604,700

	المشاريع الصادر بشأنها مقررات

	
	0
	0
	3
	823,615
	3
	823,615

	مشاريع التبرعات الإضافية

	
	0
	0
	4
	116,758
	4
	116,758

	المجموع الكلي
	14
	127,648
	27
	4,417,425
	41
	4,545,073


توافر الموارد
تشير وثيقة حالة المساهمات والمصروفات إلى رصيد متاح قدره 541,327,510 دولارات أمريكية حتى 25 أبريل/نيسان 2024. ووصل إجمالي الرصيد الذي أعادته الوكالات المنفذة إلى الاجتماع الرابع والتسعين إلى 1,362,594 دولاراً أمريكياً. ولذلك، فإن المستوى الإجمالي للموارد المتاحة للموافقات في الاجتماع الرابع والتسعين هو 542,690,104 دولارات أمريكية. 
تعليقات الأمانة
ذكّرت الأمانة الوكالات المنفذة بأن أرصدة المشاريع المنجزة منذ عام مضى أو والمشاريع المنفذة بموجب مقررات ‑ومشاريع المساهمات الطوعية الإضافية ينبغي إعادتها إلى الصندوق المتعدد الأطراف في أسرع وقت ممكن. 
وبالنظر إلى أن المستوى الإجمالي لتمويل المشاريع والأنشطة بالصيغة  المقدم بها إلى الاجتماع الرابع والتسعين حتى  1 أبريل/نيسان 2024 يبلغ 67,918,167 دولاراً أمريكياً، فإن هناك موارد كافية متاحة للموافقات في الاجتماع الرابع والتسعين. 
التوصية

قد ترغب اللجنة التنفيذية في الآتي:
(1) أن تحيط علماً بما يلي:

’1‘ التقرير المتعلق بالأرصدة وتوافر الموارد الوارد في الوثيقة UNEP/OzL.Pro/ExCom/94/4؛
’2‘ أن المستوى الصافي للأموال المقرر أن تعيدها الوكالات المنفذة في 
الاجتماع الرابع والتسعين يبلغ 1,362,594 دولاراً أمريكياً، يتكون من 239,606 دولاراً أمريكياً بالإضافة إلى تكاليف دعم الوكالة البالغة 17,619 دولاراً أمريكياً من برنامج الأمم المتحدة الإنمائي (البرنامج الإنمائي)؛ و 469,599 دولاراً أمريكياً، بالإضافة إلى تكاليف دعم الوكالة البالغة 44,402 دولاراً أمريكياً من برنامج الأمم المتحدة للبيئة (برنامج البيئة)؛ و551,985 دولاراً أمريكياً، بالإضافة إلى تكاليف دعم الوكالة البالغة 39,383 دولاراً أمريكياً من منظمة الأمم المتحدة للتنمية الصناعية (اليونيدو)؛
’3‘ أن  البرنامج الإنمائي  يحتفظ بأرصدة قدرها 71,695 دولاراً أمريكياً، بما في ذلك تكاليف دعم الوكالة، لسبعة مشاريع أنجزت على مدى عامين سابقين؛
’4‘ أن  اليونيدو تحتفظ بأرصدة قدرها 72,926 دولاراً أمريكياً، بما في ذلك تكاليف دعم الوكالة، لخمسة مشاريع أنجزت على مدى عامين سابقين، و823,615 دولاراً أمريكياً، بما في ذلك تكاليف دعم الوكالة، لثلاثة مشاريع أنجزت "بموجب مقرر صادر عن اللجنة التنفيذية" و116,758 دولاراً أمريكياً بما في ذلك تكاليف دعم الوكالة، لأربعة مشاريع أنجزت بتمويل من  المساهمات الطوعية الإضافية التي قدمتها مجموعة من البلدان المانحة لتمويل أنشطة البداية السريعة لتنفيذ التخفيض التدريجي للهيدروفلوروكربون؛
أن تطلب من البرنامج الإنمائي واليونيدو ما يلي:
’1‘ المضي قدما في صرف أو إلغاء الأموال الملتزم بها وغير الملتزم بها والتي لم تكن هناك حاجة إليها للمشاريع المنجزة، وإعادة الأرصدة المرتبطة بها في الاجتماع الخامس والتسعين؛ 
’2‘ المضي قدما في صرف أو إلغاء الالتزامات الخاصة بالمشاريع التي أنجزت خلال العامين الماضيين وإعادة الأرصدة في الاجتماع الخامس والتسعين؛
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أن تطلب كذلك من اليونيدو المضي قدماً في عملية الصرف أو إعادة أرصدة المشاريع المنجزة "المشاريع الصادر بشأنها مقررات" والمشاريع المنجزة الممولة من المساهمات الطوعية الإضافية في الاجتماع الخامس والتسعين .
إن وثائق ما قبل دورات اللجنة التنفيذية للصندوق المتعدد الأطراف لتنفيذ بروتوكول مونتريال 
قد تصدر دون إخلال بأي قرار تتخذه اللجنة التنفيذية بعد صدورها. 
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Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR COMPLETED PROJECTS

	Code
	Project title
	Date completed (Actual)
	Approved funding plus adjustments as of 
31 Dec 2022
(US $)
	Funds disbursed as of 
94th meeting (US $)
	Balances committed as per 
94th meeting (US $)
	Balances not-committed as per 
94th meeting (US $)
	Support cost on balances committed and not committed as per
94th meeting (US $)
	Why any balances could not be returned?
	When they could be returned?
	Project subject to decision

	UNDP

	ANG/PHA/79/INV/19
	HCFC phase-out management plan (stage II, first tranche)
	Aug-22
	450,000
	443,189
	6,811
	
	477
	
	
	

	ANG/PHA/84/TAS/22
	Verification report on the implementation of the HCFC phase-out management plan
	Dec-21
	30,000
	22,149
	7,851
	
	707
	
	
	

	BGD/SEV/81/TAS/52
	Enabling activities for HFC phase-down
	Jun-22
	14,000
	3,249
	10,751
	
	753
	
	
	

	BZE/SEV/85/TAS/37
	Enabling activities for HFC phase-down
	Oct-22
	55,000
	49,576
	5,424
	
	380
	
	
	

	CUB/PHA/82/PRP/61
	Preparation of a HCFC phase-out management plan (stage II)
	Oct-21
	60,000
	56,531
	3,469
	
	243
	
	
	

	DOM/PHA/83/PRP/68
	Preparation of a HCFC phase-out management plan (stage III)
	Jun-21
	60,000
	56,710
	3,290
	
	230
	
	
	

	EGY/PHA/79/TAS/132
	HCFC phase-out management plan (stage II, first tranche) (project management and monitoring)
	Dec-22
	75,000
	67,871
	7,129
	
	499
	
	
	

	FIJ/PHA/86/INV/38
	HCFC phase-out management plan (stage I, fourth tranche)
	Dec-22
	19,950
	15,186
	4,764
	
	429
	
	
	

	HAI/SEV/84/TAS/23
	Enabling activities for HFC phase-down
	Dec-21
	95,000
	90,311
	4,689
	
	328
	
	
	

	IDS/PHA/76/INV/211
	HCFC phase-out management plan (stage II, first tranche) (fire fighting sector)
	Dec-22
	30,000
	15,078
	14,922
	
	1,045
	
	
	

	JAM/PHA/81/PRP/38
	Preparation of a HCFC phase-out management plan (stage II)
	Jul-21
	40,000
	33,501
	6,499
	
	455
	
	
	

	PAN/PHA/83/PRP/49
	Preparation of a HCFC phase-out management plan (stage III)
	Jun-21
	60,000
	56,728
	3,272
	
	229
	
	
	

	SRL/SEV/86/INS/57
	Extension of the institutional strengthening project (phase XIII: 1/2021-12/2022)
	Dec-22
	171,592
	169,190
	2,402
	
	168
	
	
	

	URU/PHA/77/INV/67
	HCFC phase-out management plan (stage II, first tranche) (foam sector)
	Dec-20
	100,000
	62,211
	37,789
	
	2,645
	
	
	

	TOTAL UNDP
	
	
	
	
	119,062
	
	8,586
	
	
	

	UNIDO[footnoteRef:4] [4:  1: Outstanding obligations to be paid, funds will be returned with next balance list.

] 


	AFG/PHA/77/INV/20
	HCFC phase-out management plan (stage I, second tranche)
	Sep-21
	131,938
	131,427
	512
	
	46
	1
	95
	

	ALG/SEV/84/TAS/83
	Enabling activities for HFC phase-down
	Jun-22
	150,000
	145,939
	4,061
	
	284
	1
	95
	

	ARG/PHA/79/INV/180
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector)
	Jun-22
	645,746
	642,431
	3,315
	
	232
	1
	95
	

	BOT/PHA/75/INV/18
	HCFC phase-out management plan (stage I, first tranche)
	Dec-22
	140,000
	125,670
	14,330
	
	1,003
	1
	95
	

	GAB/PHA/79/INV/34
	HCFC phase-out management plan (stage I, third tranche)
	Dec-22
	119,900
	108,729
	11,171
	
	1,005
	1
	95
	

	GLO/REF/80/DEM/344
	Global chiller replacement project (Argentina)
	Dec-22
	808,438
	554,670
	253,768
	
	19,033
	1
	95
	82/21(d),  86/17(h) and 88/15(b)(ii)

	IRQ/PHA/58/INV/09
	National phase-out plan (first tranche)
	Jun-21
	4,353,530
	4,290,497
	63,033
	
	4,728
	1
	95
	71/11(b), 73/8(c), 75/10(b)(i) and 79/7(c)

	IRQ/PHA/74/INV/23
	HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector)
	Dec-21
	230,000
	229,936
	64
	
	5
	1
	95
	

	IVC/PHA/84/INV/45
	HCFC phase-out management plan (stage I, third tranche)
	Dec-22
	460,000
	452,223
	7,777
	
	544
	1
	95
	90/32(a)

	KUW/PHA/66/INV/21
	HCFC phase-out management plan (stage I, first tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Company)
	Jun-22
	3,510,450
	3,450,649
	59,801
	
	4,485
	1
	95
	

	KUW/PHA/74/INV/24
	HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector phase-out: Kuwait polyurethane Industry Co.; Kirby Building Systems, technical assistance to spray foam users and other small users)
	Jun-22
	643,382
	402,478
	240,904
	
	16,864
	1
	95
	

	KUW/PHA/74/INV/25
	HCFC phase-out management plan (stage I, second tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Company)
	Jun-22
	2,706,000
	134,165
	2,571,835
	
	180,028
	1
	95
	

	MAG/PHA/84/PRP/33
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-22
	20,000
	19,019
	981
	
	69
	1
	95
	

	MOZ/PHA/66/INV/23
	HCFC phase-out management plan (stage I, first tranche)
	Dec-22
	75,000
	72,751
	2,249
	
	202
	1
	95
	

	SEN/PHA/85/INV/41
	HCFC phase-out management plan (stage I, third tranche)
	Dec-21
	50,000
	48,582
	1,418
	
	106
	1
	95
	

	SEN/PHA/85/PRP/43
	Preparation of a HCFC phase-out management plan (stage II)
	Jun-22
	20,000
	13,145
	6,855
	
	480
	1
	95
	

	SOA/PHA/76/INV/10
	HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector plan)
	Dec-22
	622,437
	620,458
	1,979
	
	139
	1
	95
	

	SOA/PHA/76/TAS/11
	HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing, custom training and monitoring)
	Dec-22
	679,898
	679,823
	75
	
	5
	1
	95
	

	SOM/PHA/77/INV/12
	HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector)
	Dec-22
	141,500
	140,891
	609
	
	43
	1
	95
	88/40(a)

	SYR/REF/62/INV/103
	Phase-out of HCFC-22 and HCFC-141b from the manufacture of unitary air-conditioning equipment and rigid polyurethane insulation panels at Al Hafez Group
	Dec-21
	1,465,361
	1,462,556
	2,805
	
	210
	1
	95
	

	TOTAL UNIDO
	
	
	
	
	3,247,540
	
	229,512
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Annex II
COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR BY-DECISIONS PROJECTS
	CODE
	Project title
	Approved funding plus adjustments as of 
31 December 2022 (US $) 
	Funds disbursed as of 
94th  meeting (US $)
	Balances committed as per 
94th meeting (US $)
	Balances not- committed as per 
94th meeting (US $)
	Support cost on balances committed and not-committed as per 
94th meeting (US $) 
	Why any balances could not be returned?
	When they could be returned?

	UNIDO[footnoteRef:5] [5:  2: Outstanding obligations to be paid, funds will be returned with next balance list.


] 


	LIB/PHA/75/INV/36
	HCFC phase-out management plan (stage I, first tranche) (foam sector)
	943,094
	198,681
	744,413
	
	52,109
	2
	95

	LIB/PHA/75/INV/37
	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector)
	27,323
	7,930
	19,394
	
	1,358
	2
	95

	SOM/PHA/88/INV/16
	HCFC phase-out management plan (stage I, third tranche)
	40,000
	34,074
	5,926
	
	415
	2
	95

	TOTAL UNIDO
	
	
	
	769,733

	
	53,882
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Annex III
COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS
	CODE
	Project title
	Approved funding plus adjustments as of 
31 December 2022 (US $) 
	Funds disbursed as of 
94th meeting (US $)
	Balances committed as per 
94th meeting (US $)
	Balances not- committed as per 
94th meeting (US $)
	Support cost on balances committed and not-committed as per 
94th meeting (US $) 
	Why any balances could not be returned?
	When they could be returned?

	UNIDO[footnoteRef:6] [6:  1: Outstanding obligations to be paid, funds will be returned with next balance list.

   


] 


	ARG/REF/81/INV/01+
	Conversion project for replacement of HFC-134a with isobutane 
(R-600a)/propane (R-290)-based refrigerant in the manufacture of domestic and commercial refrigeration equipment at Briket, Bambi and Mabe-Kronen
	1,840,755
	1,838,230
	2,525
	
	177
	1
	95

	ARG/SEV/81/TAS/02+
	Enabling activities for HFC phase-down
	250,000
	199,189
	50,811
	
	3,557
	1
	95

	MOR/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	150,000
	95,506
	54,494
	
	3,815
	1
	95

	VEN/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	250,000
	248,711
	1,289
	
	90
	1
	95

	TOTAL UNIDO
	
	
	
	109,119
	
	7,639
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Annex IV

DETAILS ON COMPLETED, BY DECISIONS AND ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES
	Code
	Project title
	Project costs returned (US $)
	Agency support costs (US $)
	Total (US $)

	UNDP
	
	
	
	

	ARG/SEV/82/INS/188
	Extension for institutional strengthening project (phase X: 1/2019-12/2020)
	1,053
	74
	1,127

	BRA/DES/72/DEM/305
	Pilot demonstration project on ODS waste management and disposal
	242
	17
	259

	BRU/PHA/85/INV/26
	HCFC phase-out management plan (stage I, fourth tranche)
	6,451
	581
	7,032

	CHI/PHA/81/INV/197
	HCFC phase-out management plan (stage II, second tranche) (foam sector)
	128,961
	9,027
	137,988

	COL/PHA/84/TAS/108
	HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector, project management and monitoring)
	21,640
	1,515
	23,155

	COL/PHA/85/PRP/109
	Preparation of a HCFC phase-out management plan (stage III)
	9
	1
	10

	CUB/SEV/81/TAS/57
	Enabling activities for HFC phase-down
	3,592
	251
	3,844

	CUB/SEV/83/INS/62
	Extension of institutional strengthening project (phase XI: 7/2019-6/2021)
	362
	25
	387

	DRC/PHA/79/PRP/42
	Preparation of a HCFC phase-out management plan (stage II)
	847
	59
	906

	ELS/SEV/81/TAS/37
	Enabling activities for HFC phase-down
	522
	37
	559

	FIJ/PHA/82/PRP/34
	Preparation of a HCFC phase-out management plan (stage II)
	3,558
	249
	3,807

	GEO/PHA/85/INV/42
	HCFC phase-out management plan (stage I, fourth tranche)
	5,923
	444
	6,367

	GHA/SEV/86/INS/49
	Extension of the institutional strengthening project (phase XIV: 1/2021-12/2022)
	175
	12
	187

	IRA/SEV/82/TAS/232
	Enabling activities for HFC phase-down
	1,263
	88
	1,352

	MOL/PHA/86/INV/43
	HCFC phase-out management plan (stage II, third tranche)
	17,450
	1,570
	19,020

	MOL/PHA/86/TAS/42
	Verification report for implementation of stage II of the HCFC phase-out management plan
	8,541
	769
	9,310

	MOL/SEV/85/TAS/41
	Enabling activities for HFC phase-down
	11,284
	790
	12,074

	NEP/PHA/86/INV/44
	HCFC phase-out management plan (stage I, third tranche)
	8,400
	756
	9,156

	NIR/PHA/83/PRP/154
	Preparation of a HCFC phase-out management plan (stage III)
	10,783
	755
	11,538

	PAN/SEV/81/TAS/46
	Enabling activities for HFC phase-down
	175
	12
	188

	SWA/PHA/83/PRP/27
	Preparation of a HCFC phase-out management plan (stage II)
	941
	66
	1,007

	Total completed projects
	
	232,173
	17,099
	249,272

	CHI/SEV/80/TAS/03+
	Enabling activities for HFC phase-down
	5,942
	416
	6,358

	URU/SEV/80/TAS/02+
	Enabling activities for HFC phase-down
	1,491
	104
	1,595

	Total “additional voluntary contributions” projects
	
	7,433
	520
	7,953

	TOTAL UNDP
	
	239,606
	17,619
	257,225

	UNEP
	
	
	
	

	BOT/PHA/82/TAS/22
	HCFC phase-out management plan (stage I, second tranche)
	      19,284 
	        2,507 
	      21,791 

	GLO/SEV/88/TAS/357
	Compliance Assistance Programme: 2022 budget
	    249,871 
	      19,990 
	    269,861 

	MAS/SEV/84/INS/15
	Extension of institutional strengthening project (phase VII: 7/2020-6/2022)
	      10,000 
	                - 
	      10,000 

	MOZ/PHA/83/TAS/30
	HCFC phase-out management plan (stage I, third and fourth tranches)
	           217 
	             28 
	           245 

	STL/PHA/82/TAS/29
	HCFC phase-out management plan (stage I, fourth tranche)
	             25 
	               3 
	             28 

	Total completed projects
	
	    279,397 
	      22,528 
	    301,925 

	BHA/PHA/88/TAS/31
	HCFC phase-out management plan (stage I, fourth tranche)
	8,975
	1,167
	10,142

	MYA/PHA/68/TAS/14
	HCFC phase-out management plan (stage I, first tranche)
	51,373
	6,678
	58,051

	MYA/PHA/80/TAS/18
	HCFC phase-out management plan (stage I, second tranche)
	19,465
	2,530
	21,995

	MYA/PHA/86/TAS/23
	HCFC phase-out management plan (stage I, third tranche)
	29,000
	3,770
	32,770

	MYA/PHA/83/PRP/21
	Preparation of a HCFC phase-out management plan (stage II)
	3,855
	501
	4,356

	MYA/PHA/86/TAS/24
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Total “by-decision” projects
	
	142,668
	18,547
	161,215

	ANG/SEV/80/TAS/01+
	Enabling activities for HFC phase-down
	         9,353 
	            655 
	       10,008 

	NEP/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	       38,181 
	         2,673 
	       40,854 

	Total “additional voluntary contributions” projects
	
	       47,534 
	         3,327 
	       50,861 

	TOTAL UNEP
	
	469,599
	44,402
	514,001

	UNIDO
	
	
	
	

	ALB/PHA/88/TAS/46
	Verification report on the implementation of stage II of the HCFC phase-out management plan
	21,036
	1,893
	22,929

	BHE/PHA/72/INV/29
	HCFC phase-out management plan (stage I, second tranche) (activities in the refrigeration servicing sector including policy actions)
	2,023
	142
	2,166

	BHE/PHA/76/INV/33
	HCFC phase-out management plan (stage I, third tranche) (activities in the refrigeration servicing sector including policy actions)
	100
	7
	107

	BHE/PHA/82/INV/36
	HCFC phase-out management plan (stage I, fourth tranche) (activities in the refrigeration servicing sector including policy actions)
	659
	46
	705

	DRK/PHA/77/INV/64
	HCFC phase-out management plan (stage I, third tranche) (policy, refrigeration servicing and monitoring)
	166,050
	11,624
	177,674

	ECU/PHA/87/TAS/79
	HCFC phase-out management plan (stage II, first tranche)
	551
	39
	590

	GUA/PHA/86/INV/57
	HCFC phase-out management plan (stage II, first tranche)
	85
	6
	90

	GUI/PHA/85/INV/34
	HCFC phase-out management plan (stage I, third tranche)
	4,906
	343
	5,250

	HON/PHA/88/TAS/54
	Verification report on the implementation of stage II of the HCFC phase-out management plan
	1,060
	95
	1,156

	IRA/PHA/86/INV/246
	HCFC phase-out management plan (stage II, third tranche) (foam sector)

	50,600

	3,542
	54,142

	IRQ/PHA/84/INV/29
	HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector)
	32,775
	2,458
	35,234

	JOR/PHA/77/INV/100
	HCFC phase-out management plan (stage II, first tranche) (polyurethane spray foam sector)
	92
	6
	98

	JOR/PHA/84/INV/106
	HCFC phase-out management plan (stage II, second tranche) (polyurethane spray foam sector)
	7,469
	523
	7,991

	KUW/PHA/83/TAS/37
	HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector)
	191,906
	13,433
	205,340

	MDN/PHA/88/INV/47
	HCFC phase-out management plan (stage I, eleventh tranche)
	3,099
	232
	3,332

	MEX/SEV/86/INS/193
	Extension of institutional strengthening project (phase XV: 7/2021-6/2023)
	21,140
	1,479
	22,619

	MYA/PHA/80/INV/19
	HCFC phase-out management plan (stage I, second tranche)
	6,122
	551
	6,673

	SOA/PHA/71/INV/06
	HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing, custom training and monitoring)
	20,916
	1,464
	22,380

	TUN/SEV/74/INS/64
	Extension of institutional strengthening project (phase VIII: 4/2015-4/2017)
	7,446
	521
	7,967

	Total completed projects
	
	538,035
	38,406
	576,441

	MYA/PHA/83/PRP/20

	Preparation of a HCFC phase-out management plan (stage II)

	10,000

	700

	10,700

	Total “by-decision” projects
	
	10,000

	700

	10,700

	EGY/SEV/81/TAS/02+
	Enabling activities for HFC phase-down

	3,950

	277

	4,227

	Total “additional voluntary contributions” projects
	
	3,950

	277

	4,227

	TOTAL UNIDO
	
	551,985
	39,383
	591,368




	
	
	
	
	






إن وثائق ما قبل دورات اللجنة التنفيذية للصندوق المتعدد الأطراف لتنفيذ بروتوكول مونتريال تصدر دون إخلال بأي قرار قد تتخذه اللجنة التنفيذية بعد صدورها.
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