| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/79/8 13 June 2017 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
 THE MULTILATERAL FUND FOR THE
 IMPLEMENTATION OF THE MONTREAL PROTOCOL
Seventy-ninth Meeting

Bangkok, 3-7 July 2017

CONSOLIDATED PROGRESS REPORT AS AT 31 DECEMBER 2016

# The consolidated progress report summarises progress and financial information provided by bilateral and implementing agencies as of 31 December 2016, in their respective progress reports submitted to the Secretariat.

Scope of the document

# The Secretariat reviewed each of the annual progress reports submitted by bilateral and implementing agencies separately. The review was based on the milestones established for investment and non-investment projects including, inter alia, signing of agreements; date of release of first disbursement; status of procurement and installation of equipment; status on services provided, including training of refrigeration technicians and customs officers; level of disbursement of approved funds; the operational and financial completion of the project; and the return of funds balances.

# During the review process, potential issues were identified, inter alia, cases where agreements had not been signed; national ozone officer not in place; lack of financial progress reports; delayed procurement process; lack of availability of alternative technologies in local markets; security related issues at the country level. All projects with issues had low disbursement rates of approved funds and/or required an extension of planned completion dates.

# To further understand the issues identified, the Secretariat had bilateral discussions with bilateral and implementing agencies, and resolved several of them satisfactorily. For those projects where the issues could not be resolved, recommendations for consideration by the Executive Committee were proposed. The lists of projects with issues are contained in Annex I of each progress report of bilateral and implementing agencies. Each project listed in Annex I, includes a description on the status of implementation and the outstanding issues, and proposes a recommendation. Most of the recommendations have been discussed and agreed with the relevant bilateral or implementing agencies.

# Based on the process followed for the review of the 2016 progress reports as described above, the present document contains a summary of progress in implementation of projects for 2016 and cumulative (which includes all projects funded under the Multilateral Fund), and a summary on project implementation progress in 2016. The recommendations included in each of the progress reports submitted by bilateral and implementing agencies will be considered during the discussions of each agency progress report at the 79th meeting.

# The progress reports of bilateral or implementing agencies did not include any policy issue for consideration by the Executive Committee. Also, no policy issues were identified during the review process of the progress reports by the Secretariat. Therefore, no policies issues are presented for consideration by the Executive Committee.

Summary of progress in implementation of projects for 2016 and cumulative

# Implementation of projects and activities by bilateral and implementing agencies/supported by the Multilateral Fund for 2016 and cumulative since 1991 up to 31 December 2016 is summarized as follows:

## Phase-out: In 2016, 2,023.3 ODP tonnes of consumption were phased out and an additional 1,405.1 ODP tonnes of consumption were approved for phase-out. Since 1991, 284,720 ODP tonnes of consumption and 204,189 ODP tonnes of production had been phased out of an expected total of 469,614 ODP tonnes from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2016, US $111.64 million was disbursed and US $122.4 million was planned for disbursement based on the 2015 progress report representing a rate of disbursement of 91 per cent of that planned. Cumulatively, US $2.79 billion had been disbursed out of the total US $3.1 billion approved for disbursement (excluding agency fees). This represents a rate of disbursement of 90 per cent. In 2016, US $120.3 million was approved for implementation;

## Cost-effectiveness (in ODP): Since 1991, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $7.90/kg. The cost-effectiveness for the production sector was US $4.24/kg. The average cost-effectiveness of investment projects per ODP tonne was US $4.12/kg for completed projects and US $49.37/kg for ongoing projects;

## Number of projects completed: In 2016, 172 projects were completed. Since 1991, 6,812 projects of the 7,807 projects (excluding closed or transferred projects) financed by the Multilateral Fund were completed. This represents a completion rate of 87 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2016 were completed on average 48 months after their approval. Since 1991, the average time for completion of investment projects has been 36 months after their approval. First disbursements under these projects occurred, on average, 15 months after they had been approved;

## Speed of delivery – non-investment projects: Projects that were completed in 2016 were completed on average 44 months after their approval. Since 1991, the average time for completion of non-investment projects has been 37 months after their approval. First disbursements under these projects occurred, on average, 11 months after they had been approved;

## Project preparation: Of the 1,608 project preparation activities approved by the end of 2016, 1,528 have been completed. In 2016, eight project preparation activities were approved and 48 were completed leaving 80 ongoing;

## Implementation delays: There were a total of 289 ongoing investment projects under implementation at the end of 2016. These projects, on average, are experiencing a delay of 18 months. However, projects classified as “projects with implementation delays” that are subject to the procedures of project cancellation amount to 12 projects (as multi-year agreements (MYAs) are not subject to those procedures); and

## MYAs: In 2016, bilateral and implementing agencies were implementing two MYAs for CFC or ODS phase-out plans, one MYA for CTC phase-out plan, three MYAs for methyl bromide (MB) consumption, one MYA for accelerated CFC production, one MYA for MB production, 172 MYAs for HCFC phase-out management plans and one MYA for the HPPMP in China. Since 1991, 352 MYAs have been approved and 171 MYAs have been completed.

Project implementation progress in 2016

# Based on planned completion dates reported in the 2015 progress report, and the results reported in the 2016 progress reports, bilateral and implementing agencies completed 32 per cent of the projects they had planned to complete in 2016 and achieve 88 per cent of the total phase-out target. Given that 357 of the 715 ongoing projects (excluding institutional strengthening and project preparation) have been delayed since the 2015 progress report, additional status reports have been requested to address all impediments that caused the delays.

# Bilateral and implementing agencies achieved an overall rate of disbursement of 91 per cent in 2016. On a country/region basis, 56 countries (including regions) had a disbursement rate of over 85 per while 44 countries (including regions) had a disbursement rate of below 50 per cent.

# In total, bilateral and implementing agencies are requested to report to the 80th meeting on 112 ongoing projects or tranches, including 12 listed with implementation delays.

# Annex I to the present document presents an analysis of the consolidated progress report of the Multilateral Fund as of 31 December 2016. Appendix I to Annex I provides information on project implementation by country basis in 2016, and Appendix II to Annex I summarizes the total funding approved and disbursed for HPMP phase-out activities at the country level.

Recommendation

# The Executive Committee may wish to note:

## The consolidated progress report of the Multilateral Fund as at 31 December 2016 contained in document UNEP/OzL.Pro/ExCom/79/8;

## With appreciation, the efforts undertaken by bilateral and implementing agencies in reporting the 2016 activities; and

## That the bilateral and implementing agencies would report to the 80th meeting on 112 ongoing projects or tranches, including 12 projects with implementation delays and 100 recommended for additional status reports, as contained in Annex I of each individual progress report of bilateral and implementing agencies.

Annex I

ANALYSIS OF THE CONSOLIDATED PROGRESS REPORT OF THE MULTILATERAL FUND AS OF 31 DECEMBER 2016

# As of 31 December 2016, the Executive Committee had approved approximately US $3.45 billion to bilateral and implementing agencies as shown in Table 1. In 2016, 244 new projects and activities were approved. This level of funding is expected to result in the phase-out of 469,614 ODP tonnes of ODS consumption and production.

Table 1. Approved funding by sector and agency as at 31 December 2016

| Sector | Approved funding (US $) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | UNDP | UN Environment | UNIDO | World Bank | Bilateral | Total |
| Aerosol | 26,432,885 | 882,689 | 34,413,700 | 22,984,030 | 2,051,914 | 86,765,218 |
| Destruction | 3,622,896 | 232,200 | 5,367,342 | 400,000 | 1,789,410 | 11,411,848 |
| Fire fighting | 50,000 | 0 | 0 | 0 | 0 | 50,000 |
| Foam | 173,581,768 | 0 | 89,018,632 | 136,426,743 | 8,095,338 | 407,122,481 |
| Halon | 4,996,975 | 767,640 | 1,810,064 | 70,221,038 | 6,147,361 | 83,943,079 |
| Fumigants | 20,081,243 | 2,614,366 | 78,189,630 | 5,837,887 | 18,295,227 | 125,018,351 |
| Multiple sectors | 0 | 0 | 139,440 | 2,341,168 | 0 | 2,480,608 |
| Other | 0 | 0 | 11,317,246 | 5,059,360 | 0 | 16,376,606 |
| Phase-out plan | 263,071,815 | 48,417,525 | 285,543,305 | 197,274,594 | 54,929,671 | 849,236,910 |
| Process agent | 1,286,923 | 0 | 6,337,359 | 114,342,497 | 0 | 121,966,779 |
| Production | 1,056,900 | 0 | 50,520,740 | 359,729,770 | 10,000,000 | 421,307,410 |
| Refrigeration | 137,489,662 | 13,926,555 | 180,251,568 | 181,574,107 | 40,412,768 | 553,654,660 |
| Several | 56,234,942 | 216,575,428 | 15,004,529 | 28,337,410 | 4,511,975 | 320,664,284 |
| Solvents | 63,699,998 | 198,860 | 23,247,443 | 10,237,394 | 2,512,738 | 99,896,434 |
| Sterilant | 417,628 | 0 | 0 | 661,227 | 0 | 1,078,855 |
| Sub-total | 752,023,635 | 283,615,263 | 781,160,997 | 1,135,427,225 | 148,746,402 | 3,100,973,522 |
| Support cost | 101,591,175 | 24,176,516 | 99,496,665 | 112,066,165 | 13,958,227 | 351,288,748 |
| Total | 853,614,810 | 307,791,778 | 880,657,662 | 1,247,493,391 | 162,704,629 | 3,452,262,270 |

# A summary of the status of projects, by category, is presented in Table 2.

Table 2. Status of project implementation by category

| Type | Number of projects* |  |  | Funding (US $) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 165 | 165 | 100 | 7,266,559 | 7,266,559 | 0 | 100 |
| Demonstration | 137 | 98 | 72 | 64,833,353 | 49,377,059 | 15,456,294 | 76 |
| Institutional strengthening | 1,096 | 896 | 82 | 123,895,822 | 102,897,597 | 20,998,225 | 83 |
| Investment | 2,914 | 2,625 | 90 | 2,496,767,059 | 2,283,469,913 | 213,297,146 | 91 |
| Project preparation | 1,608 | 1,528 | 95 | 83,639,141 | 79,250,246 | 4,388,895 | 95 |
| Technical assistance | 1,563 | 1,176 | 75 | 298,765,815 | 244,055,134 | 54,710,682 | 82 |
| Training projects | 324 | 324 | 100 | 25,805,773 | 25,806,232 | -459 | 100 |
| Total | 7,807 | 6,812 | 87 | 3,100,973,522 | 2,792,122,739 | 308,850,783 | 90 |

*Excludes closed and transferred projects.

** Excludes agency fees/administrative costs.

# Table 3 presents an overview of status of project implementation by year. Of the US $3.1 billion approved, US $2.79 billion has been disbursed (including US $111.64 million disbursed in 2016). All projects and activities approved between 1991 and the end of 2004 have now been completed. Approved projects (investment and non-investment) have resulted in the phase-out of 488,909 ODP tonnes of consumption and production. As of 31 December 2016, investment projects representing around US $1.92 billion have been completed, resulting in the permanent phase-out of 467,228 ODP tonnes with an overall cost-effectiveness of US $4.12/kg ODP phased out.

Table 3. Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US$) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1991 | 68 | 68 | 100 | 7,950,771 | 7,950,771 | 0 | 100 |
| 1992 | 176 | 176 | 100 | 41,261,377 | 41,261,376 | 0 | 100 |
| 1993 | 217 | 217 | 100 | 73,198,586 | 73,198,587 | 0 | 100 |
| 1994 | 379 | 379 | 100 | 128,630,289 | 128,630,291 | -2 | 100 |
| 1995 | 355 | 355 | 100 | 111,188,308 | 111,188,309 | -1 | 100 |
| 1996 | 257 | 257 | 100 | 83,813,027 | 83,813,028 | 0 | 100 |
| 1997 | 532 | 532 | 100 | 154,314,938 | 154,314,942 | -3 | 100 |
| 1998 | 422 | 422 | 100 | 99,680,368 | 99,680,367 | 1 | 100 |
| 1999 | 546 | 545 | 100 | 152,703,845 | 152,706,437 | -2,592 | 100 |
| 2000 | 426 | 426 | 100 | 109,540,653 | 109,540,523 | 131 | 100 |
| 2001 | 427 | 427 | 100 | 130,138,760 | 130,139,219 | -459 | 100 |
| 2002 | 358 | 357 | 100 | 162,045,816 | 162,045,813 | 4 | 100 |
| 2003 | 247 | 247 | 100 | 157,043,468 | 157,043,467 | 1 | 100 |
| 2004 | 271 | 271 | 100 | 162,382,038 | 162,383,914 | -1,876 | 100 |
| 2005 | 255 | 252 | 99 | 182,206,843 | 179,875,231 | 2,331,613 | 99 |
| 2006 | 261 | 258 | 99 | 121,000,982 | 120,509,964 | 491,019 | 100 |
| 2007 | 213 | 212 | 100 | 120,217,967 | 119,497,470 | 720,496 | 99 |
| 2008 | 355 | 348 | 98 | 122,440,434 | 121,424,448 | 1,015,986 | 99 |
| 2009 | 322 | 309 | 96 | 74,373,972 | 72,254,428 | 2,119,544 | 97 |
| 2010 | 229 | 212 | 93 | 85,945,428 | 80,557,096 | 5,388,332 | 94 |
| 2011 | 265 | 218 | 82 | 202,987,781 | 191,284,143 | 11,703,637 | 94 |
| 2012 | 184 | 113 | 61 | 103,972,962 | 83,100,711 | 20,872,251 | 80 |
| 2013 | 186 | 91 | 49 | 126,795,947 | 112,306,258 | 14,489,690 | 89 |
| 2014 | 230 | 86 | 37 | 96,311,640 | 70,999,549 | 25,312,091 | 74 |
| 2015 | 382 | 34 | 9 | 170,522,416 | 65,833,746 | 104,688,670 | 39 |
| 2016 | 244 | 0 | 0 | 120,304,904 | 582,653 | 119,722,251 | 0 |
| Total | 7,807 | 6,812 | 87 | 3,100,973,522 | 2,792,122,739 | 308,850,783 | 90 |

*Excludes closed and transferred projects.

** Excludes agency fees/administrative costs.

Completed Projects

# Overall, 99.9 per cent of the funds approved for completed investment projects have been disbursed.

Completed investment projects

# Table 4 presents information on investment projects that have been completed since 1991. The table presents the data in total, followed by data according to region, sector, implementation characteristics, and disbursement method.

Table 4. Cumulative completed investment projects

| Item | Number of projects | Approved funds plus adjustment (US $) | Per cent of funds disbursed | Consumption (ODP phased out*) | Production (ODP phased out)* | Average number of months from approval to first disbursement | Average number of months from approval to completion | Overall cost-effectiveness to the Fund (US$/kg.) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TOTAL | 2,625 | 1,924,089,265 | 100 | 265,951 | 201,277 | 15 | 36 | 4.12 |
| Region |  |  |  |  |  |  |  |  |
| Africa | 427 | 141,731,621 | 100 | 17,864 | 0 | 15 | 40 | 7.93 |
| Asia & Pacific | 1,427 | 1,363,645,915 | 100 | 206,727 | 181,327 | 16 | 36 | 3.51 |
| Europe | 133 | 62,203,055 | 99 | 7,714 | 175 | 10 | 32 | 7.88 |
| Latin America and Caribbean | 638 | 356,508,675 | 100 | 33,645 | 19,775 | 14 | 36 | 6.67 |
| Global | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Sector |  |  |  |  |  |  |  |  |
| Aerosol | 124 | 63,046,350 | 100 | 26,883 | 0 | 16 | 41 | 2.35 |
| Destruction | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Foam | 1,000 | 368,561,991 | 100 | 69,181 | 0 | 15 | 34 | 5.33 |
| Fumigants | 118 | 94,929,014 | 100 | 7,557 | 0 | 10 | 46 | 12.56 |
| Halon | 39 | 71,476,177 | 100 | 42,111 | 41,958 | 17 | 30 | 0.85 |
| Multiple sectors | 4 | 2,287,376 | 100 | 419 | 0 | 28 | 78 | 5.46 |
| Other | 8 | 16,059,360 | 100 | 1,574 | 0 | 12 | 20 | 10.20 |
| Phase-out plan | 504 | 318,303,102 | 100 | 47,205 | 10,988 | 15 | 39 | 5.47 |
| Process agent | 30 | 120,252,627 | 100 | 19,573 | 52,162 | 10 | 27 | 1.68 |
| Production | 57 | 346,091,994 | 100 | 0 | 96,169 | 9 | 18 | 3.60 |
| Refrigeration | 610 | 427,655,617 | 100 | 44,103 | 0 | 16 | 39 | 9.70 |
| Solvents | 128 | 94,351,804 | 100 | 7,285 | 0 | 19 | 32 | 12.95 |
| Sterilant | 3 | 1,073,855 | 100 | 60 | 0 | 15 | 34 | 17.77 |
| Implementation characteristics |  |  |  |  |  |  |  |  |
| Agency implementation | 1,659 | 707,468,902 | 100 | 92,119 | 17,381 | 11 | 35 | 6.46 |
| National implementation | 966 | 1,216,620,364 | 100 | 173,832 | 183,896 | 21 | 40 | 3.40 |
| Disbursement method |  |  |  |  |  |  |  |  |
| During implementation | 2,534 | 1,832,004,071 | 100 | 261,235 | 199,719 | 15 | 37 | 3.97 |
| After implementation | 50 | 17,166,608 | 100 | 2,512 | 0 | 23 | 25 | 6.83 |
| Retroactive funding | 36 | 14,138,587 | 100 | 2,100 | 500 | 15 | 8 | $5.44 |
| Country to final beneficiaries | 5 | 60,780,000 | 100 | 103 | 1,058 | 8 | 33 | $52.33 |

Completed non-investment projects

# Table 5 presents data on cumulative completed non-investment projects. Since 1991, 2,659 non-investment projects have been completed at a total value of US $393.36 million.

Table 5.Cumulative completed non-investment projects

| Item | Number of projects | Approved funds plus adjustment (US $) | Per cent of funds disbursed | Average number of months from approval to first disbursement | Average number of months from approval to completion |
| --- | --- | --- | --- | --- | --- |
| TOTAL | 2,659 | 393,362,525 | 99 | 11 | 37 |
| Region |  |  |  |  |  |
| Africa | 759 | 67,762,152 | 98 | 11 | 38 |
| Asia & Pacific | 791 | 113,075,949 | 98 | 13 | 39 |
| Europe | 174 | 16,576,825 | 100 | 9 | 34 |
| Latin America and Caribbean | 646 | 75,083,780 | 100 | 12 | 41 |
| Global | 289 | 120,863,820 | 100 | 6 | 22 |
| Sector |  |  |  |  |  |
| Aerosol | 31 | 2,461,265 | 100 | 11 | 36 |
| Destruction | 4 | 1,028,464 | 98 | 11 | 45 |
| Foam | 27 | 8,121,026 | 100 | 15 | 34 |
| Fumigants | 133 | 20,596,656 | 99 | 9 | 39 |
| Halon | 82 | 11,267,852 | 100 | 17 | 44 |
| Multiple sectors | 1 | 53,792 | 100 | 56 | 58 |
| Other | 1 | 76,499 | 100 | 7 | 38 |
| Phase-out plan | 305 | 29,810,402 | 94 | 11 | 38 |
| Process agent | 0 | 0 | 0 | n/a | n/a |
| Production | 1 | 40,000 | 100 | 4 | 4 |
| Refrigeration | 616 | 80,888,262 | 100 | 16 | 50 |
| Several | 1,425 | 235,825,142 | 99 | 9 | 31 |
| Solvents | 33 | 3,193,165 | 100 | 11 | 26 |
| Sterilant | 0 | 0 | 0 | n/a | n/a |
| Implementation characteristics |  |  |  |  |  |
| Agency implementation | 2,160 | 296,763,558 | 99 | 10 | 36 |
| National implementation | 499 | 96,598,967 | 100 | 15 | 42 |
| Disbursement method |  |  |  |  |  |
| During implementation | 2,629 | 383,449,075 | 99 | 11 | 37 |
| After implementation | 26 | 2,394,315 | 97 | 14 | 21 |
| Retroactive funding | 0 | 0 | 0 | n/a | n/a |
| Country to final beneficiaries | 4 | 7,519,135 | 100 | 7 | 49 |

# The average time from approval to first disbursement for non-investment projects is 11 months. Non-investment projects have been completed, on average, 37 months after they were approved. This figure is influenced by the large number of projects (1,425 of 2,659) in the sector called “several”, which had an average time from approval to completion of 31 months. Non-investment projects in the other sectors were completed between 4 and 58 months after they had been approved.

# Almost all projects were implemented by the agency concerned rather than through national implementation. Agency implementation of non-investment projects normally does not require legal agreements, which may explain the shorter period of time (36 months) compared with nationally-implemented non-investment projects (42 months).

Ongoing Projects

## Ongoing investment projects

# Table 6 presents information on the status of investment projects under implementation by region, sector, and implementation characteristics.

Table 6. Cumulative ongoing investment projects

| Item | Number of projects | Approved funds plus adjustment (US) | Per cent of funds disbursed | Number of projects disbursing | Per cent of projects disbursing | Average number of months from approval to first disbursement | Average number of months from approval to planned completion | Average length of delay in project planned completion | Overall cost-effective-ness to the Fund (US/kg.)* |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GRAND TOTAL | 289 | 557,957,065 | 62 | 183 | 63 | 10 | 47 | 18 | 49.37 |
| Region |  |  |  |  |  |  |  |  |  |
| Africa | 80 | 32,542,960 | 45 | 47 | 59 | 10 | 54 | 21 | 54.46 |
| Asia & Pacific | 129 | 465,445,674 | 65 | 86 | 67 | 11 | 49 | 22 | 49.24 |
| Europe | 17 | 12,195,368 | 65 | 13 | 76 | 11 | 43 | 10 | 33.55 |
| Latin America and Caribbean | 63 | 47,773,063 | 40 | 37 | 59 | 8 | 36 | 4 | 53.82 |
| Global | 0 | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Sector |  |  |  |  |  |  |  |  |  |
| Aerosol | 3 | 19,848,996 | 96 | 3 | 100 | 14 | 118 | 73 | 35.08 |
| Destruction | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Foam | 6 | 11,607,995 | 84 | 6 | 100 | 33 | 85 | 61 | 39.99 |
| Fumigants | 5 | 5,020,759 | 92 | 5 | 100 | 9 | 105 | 49 | 10.22 |
| Halon | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Multiple sectors | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Other | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Phase-out plan | 267 | 435,569,931 | 57 | 161 | 60 | 10 | 44 | 14 | 64.23 |
| Process agent | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Production | 5 | 73,846,900 | 77 | 5 | 100 | 5 | 33 | 12 | 25.36 |
| Refrigeration | 3 | 12,062,484 | 78 | 3 | 100 | 6 | 96 | 66 | 46.39 |
| Solvents | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Sterilant | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Implementation characteristics |  |  |  |  |  |  |  |  |  |
| Agency implementation | 173 | 267,878,237 | 59 | 118 | 68 | 9 | 56 | 27 | 48.88 |
| National implementation | 116 | 290,078,828 | 65 | 65 | 56 | 12 | 35 | 5 | 49.83 |
| Disbursement method |  |  |  |  |  |  |  |  |  |
| During implementation | 264 | 231,861,277 | 46 | 162 | 61 | 10 | 47 | 17 | 37.24 |
| After implementation | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Country to final beneficiaries | 25 | 326,095,788 | 73 | 21 | 84 | 9 | 48 | 25 | 64.26 |

*Based on the ODS to be phased out according to the proposal.

# There are currently 289 investment projects under implementation at a total value of over US $557.96 million. Around 62 per cent of the funds have already been disbursed. The overall average cost-effectiveness of ongoing investment projects is US $49.37/kg ODP to be phased out. The average number of months from approval to first disbursement is 10 months. The average duration of an ongoing investment project is 47 months. Typically, ongoing investment projects are completed 18 months later than originally planned, which could be considered the average delay.

Ongoing non-investment projects

# Table 7 presents information on the status of non-investment projects under implementation by region, sector, and implementation characteristic.

Table 7. Cumulative ongoing non-investment projects

| Item | Number of projects | Approved funds plus adjustment (US) | Per cent of funds disbursed | Number of projects disbursing | Per cent of projects disbursing | Average number of months from approval to first disbursement | Average number of months from approval to planned completion | Average length of delay in project planned completion |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TOTAL | 626 | 126,189,881 | 31 | 351 | 56 | 13 | 38 | 13 |
| Region |  |  |  |  |  |  |  |  |
| Africa | 218 | 19,950,838 | 22 | 119 | 55 | 12 | 37 | 13 |
| Asia & Pacific | 220 | 48,484,931 | 23 | 123 | 56 | 14 | 41 | 14 |
| Europe | 37 | 4,524,430 | 36 | 29 | 78 | 10 | 34 | 10 |
| Latin America and Caribbean | 141 | 19,959,454 | 29 | 76 | 54 | 14 | 38 | 13 |
| Global | 10 | 33,270,228 | 49 | 4 | 40 | 17 | 33 | 7 |
| Sector |  |  |  |  |  |  |  |  |
| Aerosol | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Destruction | 15 | 9,564,588 | 47 | 14 | 93 | 11 | 60 | 34 |
| Foam | 7 | 2,709,816 | 47 | 5 | 71 | 7 | 36 | 18 |
| Fumigants | 4 | 756,747 | 43 | 4 | 100 | 24 | 44 | 24 |
| Halon | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Multiple sectors | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Other | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Phase-out plan | 245 | 37,120,605 | 17 | 119 | 49 | 15 | 44 | 13 |
| Process agent | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Production | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Refrigeration | 24 | 13,181,274 | 33 | 14 | 58 | 20 | 53 | 25 |
| Several | 330 | 62,651,235 | 36 | 195 | 59 | 11 | 31 | 11 |
| Solvents | 1 | 205,616 | 0 | 0 | 0 | n/a | 29 | 15 |
| Sterilant | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Implementation characteristics |  |  |  |  |  |  |  |  |
| Agency implementation | 522 | 91,265,779 | 32 | 288 | 55 | 13 | 39 | 14 |
| National implementation | 104 | 34,924,102 | 29 | 63 | 61 | 13 | 32 | 6 |
| Disbursement method |  |  |  |  |  |  |  |  |
| During implementation | 626 | 126,189,881 | 31 | 351 | 56 | 13 | 38 | 13 |
| After implementation | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Retroactive funding | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Country to final beneficiaries | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |

# There are currently 626 non-investment projects under implementation at a total value of US $126.19 million, with 31 per cent of the funds already disbursed. The average number of months from approval to first disbursement is 13 months. On average, ongoing non-investment projects are completed 38 months from the date of approval, which represents a delay of 13 months.

CLOSED AND TRANSFERRED PROJECTS

# Table 8 presents a summary of closed projects.

Table 8. Closed and transferred projects summary

| Agency | Number of projects | Approved funding (US$) | Adjustments (USS) | Approved funding plus adjustment (US$) | Funds disbursed (US$) | Consumption ODP to be phased out | Consumption ODP phased out |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Closed projects |  |  |  |  |  |  |  |
| UNDP | 78 | 16,947,886 | -10,052,769 | 6,895,117 | 6,895,116 | 671 | 636 |
| UN Environment | 5 | 680,000 | -659,000 | 21,000 | 21,000 | 0 | 0 |
| UNIDO | 58 | 11,185,651 | -6,665,913 | 4,519,738 | 4,519,741 | 1,123 | 338 |
| World Bank | 95 | 30,924,304 | -29,550,785 | 1,373,519 | 1,373,519 | 657 | 581 |
| Bilateral | 14 | 1,149,323 | -921,422 | 227,901 | 227,901 | 221 | 0 |
| Total | 250 | 60,887,164 | -47,849,889 | 13,037,275 | 13,037,277 | 2,671 | 1,555 |

Appendix I

PROJECT IMPLEMENTATION IN 2016 BY COUNTRY

| Country | Phased out in 2016 | Percentage of planned phase-out achieved in 2016 | Estimated funds disbursed in 2016 (US$) | Funds disbursed in 2016 (US$) | Percentage of funds disbursed over estimation in 2016 | Percentage of planned projects completed in 2016 |
| --- | --- | --- | --- | --- | --- | --- |
| Afghanistan | 0.0 |  | 253,392 | 60,018 | 24 | 0 |
| Albania | 0.0 |  | 129,265 | 134,874 | 104 | 0 |
| Algeria | 0.0 |  | 387,214 | 141,539 | 37 | 100 |
| Angola | 0.0 |  | 203,813 | 167,401 | 82 | 33 |
| Antigua and Barbuda | 0.0 |  | 63,615 | 19,812 | 31 | 0 |
| Argentina | -0.1 |  | 504,527 | 522,164 | 103 | 0 |
| Armenia | 0.0 |  | 116,818 | 110,996 | 95 | 40 |
| Bahamas (the) | 0.0 | 0 | 47,579 | 0 | 0 | 0 |
| Bahrain | 0.0 |  | 341,194 | 30,194 | 9 | 33 |
| Bangladesh | 0.0 |  | 219,675 | 95,922 | 44 | 0 |
| Barbados | 0.0 |  | 165,495 | 99,487 | 60 | 0 |
| Belize | 0.0 |  | 25,806 | 62,798 | 243 | 50 |
| Benin | 0.0 | 0 | 96,001 | 64,450 | 67 | 0 |
| Bhutan | 0.0 |  | 79,378 | 107,826 | 136 | 75 |
| Bolivia (Plurinational State of) | 0.5 | 100 | 179,038 | 119,392 | 67 | 50 |
| Bosnia and Herzegovina | 0.0 |  | 138,491 | 98,643 | 71 | 50 |
| Botswana | 0.0 |  | 96,495 | 117,032 | 121 | 0 |
| Brazil | 33.0 | 0 | 7,078,991 | 4,456,779 | 63 | 50 |
| Brunei Darussalam | 0.0 | 0 | 101,184 | 104,528 | 103 | 33 |
| Burkina Faso | 0.0 | 0 | 70,560 | 70,979 | 101 | 0 |
| Burundi | 0.0 |  | 94,500 | 8,201 | 9 | 0 |
| Cabo Verde | 0.0 |  | 52,777 | 222 | 0 | 0 |
| Cambodia | 0.0 | 0 | 135,054 | 328,060 | 243 | 67 |
| Cameroon | 0.0 |  | 302,381 | 211,346 | 70 | 0 |
| Central African Republic (the) | 0.0 |  | 46,000 | 0 | 0 |  |
| Chad | 0.0 | 0 | 78,800 | 104,150 | 132 | 50 |
| Chile | 0.0 | 0 | 653,772 | 390,296 | 60 | 75 |
| China | 449.2 | 96 | 59,368,957 | 58,823,507 | 99 | 35 |
| Colombia | 0.0 |  | 1,892,367 | 871,111 | 46 | 75 |
| Comoros (the) | 0.0 |  | 61,900 | 13,929 | 23 | 0 |
| Congo (the) | 0.0 | 0 | 67,500 | 50,215 | 74 | 0 |
| Cook Islands (the) | 0.0 |  | 52,517 | 54,868 | 104 | 0 |
| Costa Rica | 0.0 |  | 257,027 | 228,486 | 89 | 67 |
| Cote d'Ivoire | 0.0 |  | 311,584 | 453 | 0 | 0 |
| Croatia | 0.0 |  | 69,826 | 113,765 | 163 | 100 |
| Cuba | 0.0 |  | 372,587 | 186,918 | 50 | 0 |
| Democratic People's Republic of Korea (the) | 0.0 |  | 254,005 | 61,553 | 24 | 50 |
| Democratic Republic of the Congo (the) | 0.0 | 0 | 96,400 | 67,396 | 70 | 0 |
| Djibouti | 0.0 |  | 45,799 | 12,057 | 26 | 0 |
| Dominica | 0.0 |  | 48,667 | 0 | 0 |  |
| Dominican Republic (the) | 0.0 |  | 205,640 | 317,025 | 154 | 0 |
| Ecuador | 0.0 | 0 | 140,315 | 202,834 | 145 | 50 |
| Egypt | 0.0 |  | 1,812,424 | 602,827 | 33 | 33 |
| El Salvador | 0.0 | 0 | 114,994 | 121,946 | 106 | 0 |
| Equatorial Guinea | 0.0 | 0 | 97,741 | 131 | 0 | 0 |
| Eritrea | 0.0 |  | 53,500 | 5,952 | 11 | 33 |
| Ethiopia | 0.0 | 0 | 58,000 | 45,050 | 78 | 0 |
| Fiji | 0.0 |  | 64,618 | 64,794 | 100 | 0 |
| Gabon | 0.0 |  | 121,799 | 172,263 | 141 | 0 |
| Gambia (the) | 0.0 | 0 | 52,155 | 46,717 | 90 | 20 |
| Georgia | 0.0 |  | 114,792 | 74,282 | 65 |  |
| Ghana | 0.0 | 0 | 158,253 | 296,891 | 188 | 71 |
| Grenada | 0.0 |  | 64,179 | 36,001 | 56 | 0 |
| Guatemala | 0.0 |  | 279,291 | 554,913 | 199 | 50 |
| Guinea | 0.0 |  | 78,253 | 4,327 | 6 | 0 |
| Guinea-Bissau | 0.0 |  | 28,908 | 703 | 2 | 0 |
| Guyana | 0.0 |  | 121,650 | 98,147 | 81 | 0 |
| Haiti | 0.0 |  | 65,593 | 37,517 | 57 | 0 |
| Honduras | 0.0 |  | 139,237 | 71,297 | 51 | 0 |
| India | 0.0 | 0 | 3,949,078 | 2,457,700 | 62 | 29 |
| Indonesia | 9.3 | 0 | 2,622,512 | 4,146,593 | 158 | 20 |
| Iran (Islamic Republic of) | 1.2 | 4 | 710,113 | 928,108 | 131 | 54 |
| Iraq | 1,451.5 | 100 | 1,003,572 | 194,200 | 19 | 13 |
| Jamaica | 0.0 |  | 85,034 | 106,978 | 126 | 0 |
| Jordan | 0.0 | 0 | 681,728 | 829,849 | 122 | 33 |
| Kenya | 0.0 |  | 129,451 | 282,717 | 218 | 0 |
| Kiribati | 0.0 |  | 26,419 | 39,748 | 150 | 0 |
| Kuwait | 10.9 | 100 | 1,534,198 | 80,621 | 5 | 38 |
| Kyrgyzstan | 0.0 |  | 154,274 | 194,757 | 126 | 0 |
| Lao People’s Democratic Republic (the) | 0.0 |  | 74,502 | 51,235 | 69 | 33 |
| Lebanon | 0.0 |  | 1,281,181 | 838,084 | 65 | 0 |
| Lesotho | 0.0 |  | 55,000 | 29,921 | 54 | 33 |
| Liberia | 0.0 |  | 65,572 | 17,525 | 27 | 50 |
| Libya | 0.0 |  | 405,000 | 353,105 | 87 | 100 |
| Madagascar | 0.0 | 0 | 69,910 | 134,171 | 192 | 25 |
| Malawi | 0.0 | 0 | 62,532 | 75,178 | 120 | 0 |
| Malaysia | -0.1 | 0 | 1,176,726 | 605,694 | 51 | 0 |
| Maldives | 0.0 |  | 193,774 | 241,445 | 125 | 29 |
| Mali | 0.0 | 0 | 85,192 | 132,457 | 155 | 0 |
| Marshall Islands (the) | 0.0 |  | 43,707 | 22,806 | 52 | 33 |
| Mauritania | 0.0 |  | 28,887 | 0 | 0 | 0 |
| Mauritius | 0.0 |  | 120,260 | 62,887 | 52 | 0 |
| Mexico | 22.4 | 18 | 4,472,075 | 6,349,153 | 142 | 40 |
| Micronesia (Federated States of) | 0.0 |  | 38,535 | 5,590 | 15 | 0 |
| Mongolia | 0.5 | 83 | 43,732 | 107,628 | 246 | 75 |
| Montenegro | 0.1 | 100 | 90,000 | 65,623 | 73 | 100 |
| Morocco | 0.0 |  | 138,755 | 39,161 | 28 |  |
| Mozambique | 0.0 |  | 88,839 | 24,504 | 28 | 0 |
| Myanmar | 0.0 |  | 97,112 | 49,279 | 51 | 0 |
| Namibia | 0.0 |  | 85,200 | 127,898 | 150 | 0 |
| Nauru | 0.0 |  | 45,371 | 5,444 | 12 | 0 |
| Nepal | 0.0 | 0 | 76,780 | 21,275 | 28 | 0 |
| Nicaragua | 0.0 | 0 | 118,495 | 149,436 | 126 | 67 |
| Niger (the) | 1.7 | 100 | 178,638 | 41,632 | 23 | 0 |
| Nigeria | 0.0 |  | 942,335 | 513,405 | 54 | 0 |
| Niue | 0.0 |  | 49,107 | 63,317 | 129 | 67 |
| Oman | 0.0 | 0 | 178,285 | 76,940 | 43 | 50 |
| Pakistan | 2.0 | 100 | 490,060 | 390,289 | 80 | 67 |
| Palau | 0.0 |  | 45,510 | 5,000 | 11 | 0 |
| Panama | 0.0 | 0 | 227,585 | 148,125 | 65 | 67 |
| Papua New Guinea | 0.0 |  | 104,654 | 172,848 | 165 | 67 |
| Paraguay | 0.0 | 0 | 200,897 | 124,360 | 62 | 0 |
| Peru | 0.0 |  | 237,600 | 158,022 | 67 | 33 |
| Philippines (the) | -0.1 |  | 802,949 | 598,924 | 75 | 50 |
| Qatar | 0.0 | 0 | 113,500 | 133,202 | 117 | 0 |
| Republic of Moldova (the) | 0.0 |  | 41,540 | 63,947 | 154 | 20 |
| Rwanda | 0.0 | 0 | 57,000 | 31,221 | 55 | 50 |
| Saint Kitts and Nevis | 0.0 |  | 59,560 | 0 | 0 | 0 |
| Saint Lucia | 0.0 |  | 51,250 | 39,379 | 77 | 60 |
| Saint Vincent and the Grenadines | 0.0 |  | 62,000 | 31,244 | 50 |  |
| Samoa | 0.0 |  | 56,436 | 29,060 | 51 | 0 |
| Sao Tome and Principe | 0.0 |  | 49,330 | 54,577 | 111 | 50 |
| Saudi Arabia | 0.0 |  | 1,847,431 | 1,029,187 | 56 | 33 |
| Senegal | 0.0 |  | 179,384 | 26,375 | 15 | 0 |
| Serbia | 0.0 | 0 | 356,856 | 215,187 | 60 | 33 |
| Seychelles | 0.0 |  | 111,000 | 61,681 | 56 | 50 |
| Sierra Leone | 0.0 | 0 | 74,249 | 20,482 | 28 | 40 |
| Solomon Islands | 0.0 |  | 55,920 | 59,435 | 106 | 67 |
| Somalia | 0.5 |  | 59,514 | 34,021 | 57 | 0 |
| South Africa | 24.9 | 100 | 748,560 | 1,127,438 | 151 | 33 |
| South Sudan | 0.0 |  | 14,490 | 8,790 | 61 | 0 |
| Sri Lanka | 0.0 | 0 | 103,564 | 175,426 | 169 | 33 |
| Sudan (the) | 0.0 |  | 390,114 | 286,532 | 73 | 50 |
| Suriname | 0.0 |  | 69,650 | 66,286 | 95 | 0 |
| Swaziland | 0.0 | 0 | 55,321 | 55 | 0 | 25 |
| Syrian Arab Republic | 0.0 |  | 46,001 | 14,380 | 31 |  |
| Thailand | 0.0 |  | 5,798,000 | 3,015,530 | 52 | 50 |
| The former Yugoslav Republic of Macedonia | 0.0 |  | 125,622 | 75,278 | 60 | 100 |
| Timor-Leste | 0.0 |  | 73,201 | 29,650 | 41 | 0 |
| Togo | 0.0 | 0 | 45,532 | 58,283 | 128 | 0 |
| Tonga | 0.0 |  | 49,982 | 23,675 | 47 | 0 |
| Trinidad and Tobago | 0.0 | 0 | 367,790 | 279,888 | 76 | 0 |
| Tunisia | 4.4 | 67 | 345,001 | 439,274 | 127 | 50 |
| Turkey | -0.1 |  | 1,140,298 | 555,164 | 49 | 33 |
| Turkmenistan | 0.7 | 100 | 78,311 | 48,966 | 63 | 0 |
| Tuvalu | 0.0 |  | 35,943 | 32,752 | 91 | 0 |
| Uganda | 0.0 |  | 71,487 | 30,274 | 42 | 25 |
| United Republic of Tanzania (the) | 0.0 | 0 | 36,000 | 37 | 0 | 0 |
| Uruguay | 0.0 | 0 | 221,372 | 186,885 | 84 | 67 |
| Vanuatu | 0.0 |  | 44,317 | 50,746 | 115 | 33 |
| Venezuela (Bolivarian Republic of) | 0.0 |  | 569,577 | 750,043 | 132 | 100 |
| Viet Nam | 9.1 |  | 2,205,503 | 2,057,950 | 93 | 50 |
| Yemen | 1.8 | 0 | 247,427 | 63,285 | 26 | 0 |
| Zambia | 0.0 | 0 | 55,748 | 5,926 | 11 | 25 |
| Zimbabwe | 0.0 |  | 139,786 | 118,343 | 85 | 50 |
| Region: AFR | 0.0 |  | 340,000 | 170,873 | 50 | 100 |
| Region: ASP | 0.0 |  | 116,506 | 214,947 | 184 | 50 |
| Region: EUR | 0.0 |  | 98,161 | 54,961 | 56 | 33 |
| Region: LAC | 0.0 |  | 50,000 | 84,843 | 170 |  |
| Global | 0.0 |  | 3,897,188 | 7,858,889 | 202 | 71 |
| Grand Total | 2,023.3 | 88 | 122,398,851 | 111,642,992 | 91 | 32 |

Appendix II

HCFC PHASE-OUT MANAGEMENT PLAN (HPMP) BY COUNTRY 
AS AT 31 DECEMBER 2016

| Country | Approved phase-out (ODP tonnes) | Funds approved (US$) | Funds disbursed (US$) | Balance (US$) | Funds disbursed (%) |
| --- | --- | --- | --- | --- | --- |
| Afghanistan | 3.4 | 407,000 | 194,450 | 212,550 | 48 |
| Albania | 0.6 | 243,965 | 165,625 | 78,340 | 68 |
| Algeria | 13.5 | 1,809,240 | 80,939 | 1,728,301 | 4 |
| Angola | 1.6 | 176,000 | 91,264 | 84,736 | 52 |
| Antigua and Barbuda | 0.0 | 45,850 | 27,235 | 18,615 | 59 |
| Argentina | 82.4 | 10,650,154 | 8,695,730 | 1,954,424 | 82 |
| Armenia | 2.2 | 744,838 | 462,536 | 282,302 | 62 |
| Bahamas (the) | 0.4 | 183,342 | 134,787 | 48,555 | 74 |
| Bahrain | 6.4 | 814,455 | 31,148 | 783,307 | 4 |
| Bangladesh | 20.8 | 1,516,311 | 1,339,694 | 176,617 | 88 |
| Barbados | 0.0 | 124,000 | 35,375 | 88,625 | 29 |
| Belize | 0.0 | 140,000 | 140,000 | 0 | 100 |
| Benin | 4.8 | 501,224 | 244,610 | 256,614 | 49 |
| Bhutan | 0.3 | 423,000 | 297,504 | 125,496 | 70 |
| Bolivia (Plurinational State of) | 0.5 | 253,500 | 178,313 | 75,187 | 70 |
| Bosnia and Herzegovina | 6.0 | 877,953 | 676,603 | 201,350 | 77 |
| Botswana | 1.1 | 275,000 | 4,281 | 270,719 | 2 |
| Brazil | 295.6 | 25,996,427 | 13,035,130 | 12,961,297 | 50 |
| Brunei Darussalam | 0.6 | 242,900 | 160,051 | 82,849 | 66 |
| Burkina Faso | 2.0 | 390,000 | 327,232 | 62,768 | 84 |
| Burundi | 0.4 | 155,000 | 116,860 | 38,140 | 75 |
| Cabo Verde | 0.0 | 110,290 | 39,992 | 70,299 | 36 |
| Cambodia | 1.5 | 900,000 | 650,000 | 250,000 | 72 |
| Cameroon | 24.1 | 1,123,589 | 960,583 | 163,006 | 85 |
| Central African Republic (the) | 0.5 | 200,000 | 64,000 | 136,000 | 32 |
| Chad | 4.0 | 445,000 | 344,542 | 100,458 | 77 |
| Chile | 35.0 | 2,862,101 | 674,413 | 2,187,688 | 24 |
| China | 2,481.2 | 319,987,505 | 226,247,744 | 93,739,761 | 71 |
| Colombia | 135.9 | 9,539,617 | 6,996,722 | 2,542,895 | 73 |
| Comoros (the) | 0.0 | 114,000 | 44,030 | 69,970 | 39 |
| Congo (the) | 2.2 | 290,000 | 198,710 | 91,290 | 69 |
| Cook Islands (the) | 0.0 | 89,100 | 49,250 | 39,850 | 55 |
| Costa Rica | 15.4 | 991,522 | 941,195 | 50,327 | 95 |
| Cote d'Ivoire | 6.4 | 900,000 | 151,413 | 748,587 | 17 |
| Croatia | 8.1 | 804,707 | 804,104 | 603 | 100 |
| Cuba | 15.1 | 1,591,527 | 1,132,111 | 459,416 | 71 |
| Democratic People’s Republic of Korea (the) | 19.4 | 808,550 | 68,990 | 739,560 | 9 |
| Democratic Republic of the Congo (the) | 5.8 | 427,500 | 330,019 | 97,481 | 77 |
| Djibouti | 0.0 | 99,500 | 60,164 | 39,336 | 60 |
| Dominica | 0.0 | 82,250 | 10,026 | 72,224 | 12 |
| Dominican Republic (the) | 12.5 | 2,349,947 | 1,606,982 | 742,965 | 68 |
| Ecuador | 17.2 | 1,784,909 | 1,663,936 | 120,974 | 93 |
| Egypt | 166.1 | 7,571,840 | 4,513,124 | 3,058,716 | 60 |
| El Salvador | 8.8 | 1,039,277 | 645,753 | 393,524 | 62 |
| Equatorial Guinea | 0.6 | 144,962 | 97,012 | 47,950 | 67 |
| Eritrea | 0.4 | 189,000 | 49,729 | 139,271 | 26 |
| Ethiopia | 2.0 | 280,000 | 85,000 | 195,000 | 30 |
| Fiji | 2.0 | 283,500 | 149,075 | 134,425 | 53 |
| Gabon | 0.0 | 266,000 | 141,350 | 124,650 | 53 |
| Gambia (the) | 0.4 | 168,000 | 74,497 | 93,503 | 44 |
| Georgia | 1.2 | 350,000 | 289,195 | 60,805 | 83 |
| Ghana | 5.8 | 1,050,000 | 716,038 | 333,962 | 68 |
| Grenada | 0.3 | 189,000 | 52,072 | 136,928 | 28 |
| Guatemala | 2.9 | 327,329 | 238,320 | 89,009 | 73 |
| Guinea | 1.2 | 305,000 | 237,912 | 67,088 | 78 |
| Guinea-Bissau | 1.0 | 252,000 | 88,272 | 163,728 | 35 |
| Guyana | 0.3 | 281,180 | 69,381 | 211,799 | 25 |
| Haiti | 0.4 | 167,119 | 40,000 | 127,119 | 24 |
| Honduras | 2.0 | 454,835 | 207,504 | 247,331 | 46 |
| India | 488.2 | 31,195,490 | 17,673,649 | 13,521,841 | 57 |
| Indonesia | 155.6 | 13,777,325 | 7,147,065 | 6,630,260 | 52 |
| Iran (Islamic Republic of) | 217.7 | 12,729,278 | 8,799,275 | 3,930,003 | 69 |
| Iraq | 9.5 | 750,000 | 80,000 | 670,000 | 11 |
| Jamaica | 8.9 | 589,450 | 395,111 | 194,339 | 67 |
| Jordan | 32.2 | 4,285,144 | 3,004,579 | 1,280,565 | 70 |
| Kenya | 14.1 | 810,000 | 612,050 | 197,950 | 76 |
| Kiribati | 0.0 | 98,100 | 60,515 | 37,585 | 62 |
| Kuwait | 209.9 | 7,500,832 | 351,756 | 7,149,076 | 5 |
| Kyrgyzstan | 2.6 | 408,000 | 158,419 | 249,581 | 39 |
| Lao People's Democratic Republic (the) | 0.8 | 252,000 | 90,566 | 161,434 | 36 |
| Lebanon | 41.9 | 4,780,349 | 2,748,191 | 2,032,158 | 57 |
| Lesotho | 0.0 | 168,000 | 113,423 | 54,577 | 68 |
| Liberia | 2.0 | 283,500 | 173,692 | 109,808 | 61 |
| Libya | 24.1 | 1,717,950 | 4,452 | 1,713,498 | 0 |
| Madagascar | 3.7 | 460,000 | 232,482 | 227,518 | 51 |
| Malawi | 2.0 | 273,750 | 135,510 | 138,240 | 50 |
| Malaysia | 186.6 | 13,095,408 | 8,273,945 | 4,821,463 | 63 |
| Maldives | 0.6 | 1,050,000 | 768,631 | 281,369 | 73 |
| Mali | 3.4 | 448,830 | 290,703 | 158,127 | 65 |
| Marshall Islands (the) | 0.1 | 101,700 | 45,603 | 56,097 | 45 |
| Mauritius | 0.0 | 288,450 | 288,450 | 0 | 100 |
| Mexico | 509.4 | 23,840,202 | 15,771,635 | 8,068,567 | 66 |
| Micronesia (Federated States of) | 0.1 | 100,800 | 57,102 | 43,698 | 57 |
| Mongolia | 1.0 | 329,000 | 250,000 | 79,000 | 76 |
| Montenegro | 0.1 | 353,500 | 267,628 | 85,872 | 76 |
| Morocco | 11.0 | 1,249,159 | 985,437 | 263,722 | 79 |
| Mozambique | 0.3 | 150,000 | 13,025 | 136,975 | 9 |
| Myanmar | 0.4 | 159,000 | 14,574 | 144,426 | 9 |
| Namibia | 5.5 | 540,000 | 406,844 | 133,156 | 75 |
| Nauru | 0.0 | 66,600 | 41,885 | 24,715 | 63 |
| Nepal | 0.6 | 189,000 | 38,801 | 150,200 | 21 |
| Nicaragua | 0.7 | 214,500 | 132,199 | 82,301 | 62 |
| Niger (the) | 2.7 | 275,000 | 133,141 | 141,859 | 48 |
| Nigeria | 90.1 | 4,938,830 | 3,319,334 | 1,619,496 | 67 |
| Niue | 0.0 | 65,700 | 54,225 | 11,475 | 83 |
| Oman | 5.3 | 732,046 | 405,683 | 326,363 | 55 |
| Pakistan | 136.3 | 7,997,119 | 5,391,691 | 2,605,428 | 67 |
| Palau | 0.1 | 108,000 | 60,553 | 47,447 | 56 |
| Panama | 5.0 | 600,645 | 315,272 | 285,373 | 52 |
| Papua New Guinea | 2.0 | 991,000 | 466,994 | 524,006 | 47 |
| Paraguay | 6.3 | 567,000 | 330,244 | 236,756 | 58 |
| Peru | 2.7 | 253,000 | 174,910 | 78,090 | 69 |
| Philippines (the) | 40.0 | 3,328,575 | 2,407,982 | 920,593 | 72 |
| Qatar | 22.0 | 1,150,907 | 987,762 | 163,145 | 86 |
| Republic of Moldova (the) | 0.2 | 218,950 | 86,901 | 132,049 | 40 |
| Rwanda | 0.6 | 222,000 | 134,399 | 87,601 | 61 |
| Saint Kitts and Nevis | 0.3 | 147,600 | 58,400 | 89,200 | 40 |
| Saint Lucia | 0.2 | 179,798 | 122,435 | 57,363 | 68 |
| Saint Vincent and the Grenadines | 0.2 | 319,107 | 178,344 | 140,763 | 56 |
| Samoa | 0.1 | 133,650 | 71,252 | 62,398 | 53 |
| Sao Tome and Principe | 0.0 | 109,012 | 88,563 | 20,449 | 81 |
| Saudi Arabia | 353.5 | 10,579,575 | 4,474,568 | 6,105,007 | 42 |
| Senegal | 3.6 | 460,000 | 225,866 | 234,134 | 49 |
| Serbia | 5.2 | 856,790 | 458,100 | 398,690 | 53 |
| Seychelles | 1.4 | 540,000 | 315,000 | 225,000 | 58 |
| Sierra Leone | 0.4 | 168,000 | 95,352 | 72,648 | 57 |
| Solomon Islands | 0.7 | 175,500 | 119,250 | 56,250 | 68 |
| Somalia | 1.8 | 360,374 | 154,829 | 205,545 | 43 |
| South Africa | 94.2 | 5,855,184 | 3,181,286 | 2,673,898 | 54 |
| South Sudan | 0.0 | 20,000 | 0 | 20,000 | 0 |
| Sri Lanka | 4.7 | 591,866 | 366,141 | 225,725 | 62 |
| Sudan (the) | 39.0 | 3,799,913 | 1,437,476 | 2,362,437 | 38 |
| Suriname | 0.2 | 123,500 | 94,182 | 29,318 | 76 |
| Swaziland | 7.9 | 847,920 | 736,772 | 111,148 | 87 |
| Thailand | 164.0 | 15,445,088 | 5,518,483 | 9,926,605 | 36 |
| The former Yugoslav Republic of Macedonia | 1.9 | 721,849 | 601,536 | 120,313 | 83 |
| Timor-Leste | 0.0 | 244,620 | 166,522 | 78,098 | 68 |
| Togo | 0.9 | 315,000 | 248,325 | 66,675 | 79 |
| Tonga | 0.0 | 114,300 | 70,543 | 43,757 | 62 |
| Trinidad and Tobago | 6.7 | 1,229,733 | 698,686 | 531,047 | 57 |
| Tunisia | 9.5 | 1,606,868 | 225,778 | 1,381,090 | 14 |
| Turkey | 384.5 | 11,124,690 | 7,952,367 | 3,172,323 | 71 |
| Turkmenistan | 2.4 | 618,800 | 391,391 | 227,409 | 63 |
| Tuvalu | 0.0 | 82,800 | 50,361 | 32,439 | 61 |
| Uganda | 0.0 | 143,977 | 49,316 | 94,661 | 34 |
| United Republic of Tanzania (the) | 0.6 | 187,875 | 84,911 | 102,964 | 45 |
| Uruguay | 5.2 | 694,004 | 380,004 | 314,000 | 55 |
| Vanuatu | 0.1 | 133,650 | 122,665 | 10,985 | 92 |
| Venezuela (Bolivarian Republic of) | 28.9 | 2,570,920 | 1,697,434 | 873,486 | 66 |
| Viet Nam | 148.6 | 9,564,365 | 7,179,316 | 2,385,049 | 75 |
| Yemen | 11.6 | 625,000 | 176,907 | 448,093 | 28 |
| Zambia | 1.1 | 253,635 | 94,886 | 158,749 | 37 |
| Zimbabwe | 10.0 | 814,818 | 759,538 | 55,280 | 93 |
| Region: ASP | 0.0 | 240,000 | 134,000 | 106,000 | 56 |
| Grand Total | 6,957.8 | 620,494,685 | 399,649,597 | 220,845,088 | 64 |

Progress reports were submitted by the following agencies: Australia, France, Germany, Italy, Japan, the Russian Federation, Spain, UNDP, United Nations Environment Programme (UN Environment), UNIDO and the World Bank.

The Executive Committee requested that detailed information on a project-by-project basis be made available to Committee members, with a printout available upon request (decision 19/23). The database for the Consolidated Progress Report is provided on the Executive Committee’s intranet in the spreadsheet programme, Microsoft Excel 1997-2003.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies. The cost-effectiveness for HPMP multi-year agreements (MYAs) is US $66.04/kg ODP and for stage I of HCFC production phase-out management plan (HPPMP) is US $23.93/kg ODP.

An additional US $141.55 million has been approved for the meetings of the Executive Committee, the operation of the Secretariat, and the Treasurer fees.

The data is presented according to the year when a project was approved. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or annual funding tranche of an MYA of US $1 million is considered one project as is a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP phased out, and percentage of funds disbursed.

Total phased out for the Fund includes 467,228 ODP tonnes from completed investment projects, 14,260 ODP tonnes from completed non-investment projects and 7,421 ODP tonnes from ongoing projects.

Completed projects/activities are defined in decisions 17/22 and 19/23 as projects that have been commissioned and where the ODS addressed has been phased out. A further decision (decision 28/2) extends the definition to cover situations where no further use of CFCs in the sectors covered is in evidence, where an alternative product is being produced (and/or production has begun), and where the equipment using CFCs has been destroyed/dismantled/rendered unusable with respect to ODSs. Work programme activities without an ODS phase-out are considered completed when the activity is finished (e.g., for a workshop, when it has been conducted).

The reason that 100 per cent of funds have not been disbursed for completed projects is that it may take from six months to one year to finalise accounting records.