| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/99/16 29 October 2026 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-ninth Meeting

Montreal, 7–11 December 2026

Item 7(a)(iv) of the provisional agenda

PROGRESS REPORT OF UNEP AS AT 31 DECEMBER 2025

Introduction

# This document presents the progress report of UNEP as at 31 December 2025.

# The progress report of UNEP includes the status of implementation of each ongoing project, reviewed by the Secretariat on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates reported in 2025, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs, which are measured in metric tonnes (mt) and CO2-eq tonnes.

# This document presents a summary of progress in implementation of projects for 2025 and cumulative since 1991 addressing all controlled substances, including Annex F substances (HFCs), under the Montreal Protocol for all projects approved under regular funding and additional voluntary contributions. It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee. As all projects approved under the additional voluntary contributions have been completed and the remaining balances will be returned to the Fund, the Secretariat no longer reports on these projects separately.

Progress in implementation of projects for 2025 and cumulative since 1991

# As of 31 December 2025, the Executive Committee had approved US $521.47 million in projects for UNEP, consisting of US $481.89 million for the implementation of non-investment projects, and US $39.58 million for agency support costs (excluding cancelled and transferred projects). Table 1 provides a summary of project implementation since inception through the end of 2025.

# Table 1. Project summary for UNEP since the inception of the Multilateral Fund

| Items | Cumulative since 1991* |
| --- | --- |
| Number of approvals | 3,233 |
| Number of projects completed | 2,765 |
| Total funds approved (excluding support costs) (US $) | 481,887,196 |
| Total funds disbursed (excluding support costs) (US $) | 412,395,943 |
| Total approved phase-out (ODP tonnes)** | 2,718.8 |
| Total actual phase-out (ODP tonnes)** | 2,283.0 |
| Total approved phase-out (mt)*** | 873.4 |
| Total actual phase-out (mt)*** | 35.9 |
| Total approved phase-out (CO2-eq tonnes)*** | 1,826,294 |
| Total actual phase-out (CO2-eq tonnes)*** | 68,058 |

* Excluding cancelled and transferred projects.

** Including only consumption.

*** For HFC-related projects only (including only consumption).

# In 2025, 102 new projects and activities were approved. This level of funding is expected to result in the phase-out of 2,719 ODP tonnes of consumption of ODS and 873 mt (1,826,294 CO2-eq tonnes) of consumption of HFCs. Annex I shows the status of project implementation per country in 2025.

# Table 2 shows the status of project implementation including fund disbursement per project cluster as at 31 December 2025. Annex II presents analytical information per year since 1991.

Table 2. Status of project implementation by cluster as at 31 December 2025*

| Clusters | Number of projects |  |  | Funding (US$)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Agency programme | 182 | 180 | 99 | 219,020,391 | 205,677,619 | 13,342,772 | 94 |
| CFC individual | 449 | 449 | 100 | 18,859,831 | 18,859,831 | 0 | 100 |
| CFC phase-out plans | 117 | 117 | 100 | 9,549,588 | 9,549,588 | 1 | 100 |
| Disposal | 2 | 2 | 100 | 190,040 | 190,040 | 0 | 100 |
| Energy efficiency | 6 | 0 | 0 | 1,617,200 | 109,657 | 1,507,543 | 7 |
| Government support | 1,063 | 968 | 91 | 100,834,251 | 86,022,781 | 14,811,470 | 85 |
| HCFC individual | 312 | 278 | 89 | 12,780,387 | 11,705,070 | 1,075,316 | 92 |
| HCFC phase-out management plan (HPMP) stage I | 357 | 345 | 97 | 27,708,270 | 26,507,764 | 1,200,506 | 96 |
| HPMP stage II | 225 | 80 | 36 | 44,754,010 | 22,344,233 | 22,409,777 | 50 |
| HPMP stage III | 16 | 2 | 12 | 4,861,825 | 837,463 | 4,024,362 | 17 |
| HFC individual | 316 | 220 | 70 | 26,753,474 | 19,552,176 | 7,201,298 | 73 |
| Kigali HFC implementation plan (KIP) stage I | 66 | 2 | 3 | 4,649,415 | 731,208 | 3,918,207 | 16 |
| Other ODS individual | 90 | 90 | 100 | 6,781,350 | 6,781,350 | 0 | 100 |
| Other ODS sector plans | 32 | 32 | 100 | 3,527,163 | 3,527,163 | 0 | 100 |
| Total | 3,233 | 2,765 | 86 | 481,887,196 | 412,395,943 | 69,491,253 | 86 |

* Excluding cancelled and transferred projects.

** Excluding agency support costs.

# Implementation of projects and activities by UNEP for 2025 and cumulative since 1991 up to 31 December 2025 is summarized as follows:

## Phase-out: In 2025, 19.8 ODP tonnes of consumption of ODS were phased out and 28.2 mt (48,165 CO2-eq tonnes) of consumption of HFCs were phased out and an additional 33.6 ODP tonnes of consumption of ODS and 162.2 mt (380,774 CO2-eq tonnes) of consumption of HFCs were approved for phase-out. Since 1991, 2,283 ODP tonnes had been phased out, of an expected total of 2,719 ODP tonnes of consumption of ODS and 36 mt (68,058 CO2-eq tonnes) had been phased out, of an expected total of 873 mt (1,826,294 CO2-eq tonnes) of consumption of HFCs from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2025, US $23.2 million was disbursed, and US $27.2 million was planned for disbursement based on the 2024 progress report, representing a rate of disbursement of 85 per cent of that planned. Cumulatively, US $412.4 million had been disbursed out of the total US $481.89 million approved for disbursement (excluding agency support costs), representing a rate of disbursement of 86 per cent. In 2025, US $24.05 million was approved for implementation;

## Number of projects completed: In 2025, 70 projects were completed. Since 1991, 2,765 projects of the 3,233 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 86 per cent;

## Speed of delivery – non-investment projects: Projects that were completed in 2025 were completed on average 36 months after their approval. Since 1991, the average time for completion of non-investment projects has been 37 months after their approval. First disbursements under these projects occurred, on average, 12 months after they had been approved;

## Project preparation: Of the 493 project preparation activities approved by the end of 2025, 392 have been completed, leaving 101 ongoing activities. In 2025, 19 project preparation activities were completed;

## Implementation delays: A total of 468 projects were under implementation at the end of 2025, experiencing, on average, a delay of seven months. Twenty-seven of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation, and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2025, 95 MYAs for HPMPs and 57 MYAs for KIPs were under implementation. Since 1991, 327 MYAs have been approved and 175 MYAs have been completed, representing a completion rate of 54 per cent.

# Table 3 summarizes progress made by UNEP since 1991.

## Table 3. Progress made by UNEP since 1991

| Phase-out achieved |  | Disbursement (US $) | Number of projects |  | Speed of delivery for completion of non-investment projects (months) | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes* | CO2-eq tonnes** |  | Approved | Completed |  |  | Approved | Completed |
| 2,283 | 68,058 | 412,395,943 | 3,233 | 2,765 | 37 | 7 | 327 | 175 |

* Consumption of ODS.

** HFC-related projects.

HFC-related projects

# As of 31 December 2025, the Executive Committee had approved 382 HFC-related projects (including 134 preparation activities, 182 technical assistance projects and 66 projects related to stage I of KIPs) amounting to US $31,402,889 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 4 to 8.

Table 4. HFC-related projects approved*

| Clusters | Number of projects |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| HFC individual – preparation projects | 134 | 43 | 32 | 11,992,129 | 5,584,902 | 6,407,227 | 47 |
| HFC individual – technical assistance | 182 | 177 | 97 | 14,761,345 | 13,967,275 | 794,071 | 95 |
| KIP stage I*** | 66 | 2 | 3 | 4,649,415 | 731,208 | 3,918,207 | 16 |
| Total | 382 | 222 | 58 | 31,402,889 | 20,283,384 | 11,119,505 | 65 |

* Excluding cancelled and transferred projects.

** Excluding agency support costs.

*** 873 mt (1,826,294 CO2-eq tonnes) of HFCs was approved for phase-out.

# As of the end of 2025, of the 382 projects, 43 preparation activities, 177 technical assistance projects and two projects related to stage I of KIPs have been completed, leaving 160 ongoing. The ongoing projects are at various stages of implementation.

# Of the total cumulative funding approved of US $31,402,889 (excluding agency support costs), US $20,283,384 has been disbursed, representing a disbursement rate of 65 per cent.

Energy-efficiency projects

# As of 31 December 2025, the Executive Committee had approved six energy-efficiency projects (including five technical assistance pilot projects under the funding window pursuant to decision 91/65 and one technical assistance project for “Twinning of national ozone officers and national energy-efficiency policymakers to support Kigali Amendment”) amounting to US $1,617,200 (excluding agency support costs). A summary of the status of these projects is presented in table 5 and the respective data has already been included in paragraphs 4 to 8.

Table 5. Energy-efficiency projects approved*

| Type | Number of projects |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Pilot projects (decision 91/65) – technical assistance | 5 | 0 | 0 | 824,000 | 109,657 | 714,343 | 13 |
| Other technical assistance | 1 | 0 | 0 | 793,200 | 0 | 793,200 | 0 |
| Total | 6 | 0 | 0 | 1,617,200 | 109,657 | 1,507,543 | 7 |

* Excluding cancelled projects.

** Excluding agency support costs.

# As of the end of 2025, all approved projects were ongoing. Of the total cumulative funding approved of US $1,617,200 (excluding agency support costs), US $109,657 has been disbursed, representing a disbursement rate of 7 per cent.

Issues identified in project implementation in 2025

# Further to the review process, several issues were discussed and satisfactorily addressed, except for issues on 27 projects classified as projects with implementation delays (including 26 projects related to components of MYAs that are subject to procedures for project cancellation, in line with decision 84/45(c); and one technical assistance project). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 100th meeting.

# In addition, issues have been identified regarding projects or tranches of MYAs for the phase-out of HCFCs and HFCs; renewal of IS projects; preparation of HPMPs; projects pursuant to decision 91/66; and enabling activities for HFC phase-down. These issues are also presented in annex III. For each of these projects, a brief description on the status of implementation and the outstanding issues are presented and a recommendation is proposed for consideration by the Executive Committee.

# Details of progress in implementation of projects associated with the HPMPs for Barbados, China (servicing), El Salvador, Ethiopia, Gabon, Grenada, India, Iraq, Mongolia, Mozambique, Quatar, Sao Tome et Principe, Saudi Arabia, Serbia, Sierra Leone, Sri Lanka, Timor-Leste, and the United Republic of Tanzania, with the KIPs for Cambodia, the Congo, the Dominican Republic, and Kyrgyzstan, and reports on projects with specific reporting requirements associated with Bangladesh (HPMP) and Senegal (HPMP), have been submitted to the 99th meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. Outstanding issues for the remaining ongoing projects not included in annex III to the present document, and requests for extension of dates of completion are addressed below.

# Of the 272 ongoing projects, excluding IS and project preparation, 63 projects have revised planned dates of completion since the 2024 progress report.

# In line with decision 95/12(b), the Secretariat noted that renewal requests of IS projects had not been submitted for the last three years for three Article 5 countries namely, Algeria, Myanmar, and Nauru. The primary reasons for non-submission included administrative and institutional challenges, political instability and security situation, and large remaining balances from previously approved phases of IS projects. UNEP reported that it has been actively supporting these countries and plans to submit these renewal requests by 2027, except for Myanmar, where submission is subject to the country’s political situation and the resumption of activities.

# In line with decision 82/11(b), UNEP has requested the extension of the duration of 35 projects pursuant to decision 91/66, as shown in table 6.

Table 6. Projects pursuant to decision 91/66 for which an extension of the completion date has been requested

| Country/project code | Disburse-ment (%) | Activities requiring additional time | Original date of completion (mm-yy) | Date of completion requested (mm-yy) |
| --- | --- | --- | --- | --- |
| Preparation of a national inventory of banks of waste controlled substances and development of a national plan for the management of those substances (decision 91/66) |  |  |  |  |
| Bahamas (the) BHS/HFCIND/38/UNEP/PRP/DES/95 | 8 | Finalization of the inventory and plan of action | Dec-26 | Jun-27 |
| Bhutan BTN/HFCIND/37/UNEP/PRP/DES/95 | 0 | Completion of survey and remaining activities and finalization of the report | Dec-26 | Dec-27 |
| Brunei Darussalam BRN/HFCIND/35/UNEP/PRP/DES/95 | 1 | Completion of data collection, assessment of end-of-life management modalities in consultation with relevant stakeholders, and finalization of policy and action plan recommendations | Dec-26 | Dec-27 |
| Cook Islands (the) COK/HFCIND/23/UNEP/PRP/DES/95 | 0 | Completion of the assessment of modalities and development of policy recommendations and action plans, through consultations between Overseas Environmental Cooperation Center (OECC), Japan and relevant stakeholders, to ensure suitability within the country context | Dec-26 | Dec-27 |
| Fiji FJI/HFCIND/47/UNEP/PRP/DES/95 | 0 |  |  |  |
| Kiribati KIR/HFCIND/23/UNEP/PRP/DES/95 | 0 |  |  |  |
| Marshall Islands (the) MHL/HFCIND/23/UNEP/PRP/DES/95 | 0 |  |  |  |
| Micronesia (Federated States of) FSM/HFCIND/22/UNEP/PRP/DES/95 | 0 |  |  |  |
| Nauru NRU/HFCIND/19/UNEP/PRP/DES/95 | 0 |  |  |  |
| Niue NIU/HFCIND/22/UNEP/PRP/DES/95 | 0 |  |  |  |
| Palau PLW/HFCIND/24/UNEP/PRP/DES/95 | 0 |  |  |  |
| Samoa WSM/HFCIND/32/UNEP/PRP/DES/95 | 0 |  | Dec-26 | Dec-27 |
| Solomon Islands SLB/HFCIND/25/UNEP/PRP/DES/95 | 43 |  | Dec-26 | Dec-27 |
| Tonga TON/HFCIND/24/UNEP/PRP/DES/95 | 0 |  | Dec-26 | Dec-27 |
| Tuvalu TUV/HFCIND/23/UNEP/PRP/DES/95 | 0 |  | Dec-26 | Dec-27 |
| Vanuatu VUT/HFCIND/23/UNEP/PRP/DES/95 | 0 |  | Dec-26 | Dec-27 |
| Region: Asia and the Pacific ASP/HFCIND/72/UNEP/PRP/DES/95 | 0 | Completion of the assessment of modalities and development of policy recommendations and action plans, through consultations between OECC, Japan and relevant stakeholders, to ensure suitability within the country context; and organization of the regional workshop | Dec-26 | Dec-27 |
| Eritrea ERI/HFCIND/31/UNEP/PRP/DES/94 | 78 | Completion of data collection and analysis and finalization of the report | Jun-26 | Jun-27 |
| Eswatini SWZ/HFCIND/43/UNEP/PRP/DES/95 | 0 | Completion of data collection and analysis and finalization of the report | Dec-26 | Jun-27 |
| Gambia (the) GMB/HFCIND/55/UNEP/PRP/DES/95 | 0 | Completion of data collection and analysis and finalization of the report | Dec-26 | Jun-27 |
| Kyrgyzstan KGZ/HFCIND/54/UNEP/PRP/DES/94 | 80 | Completion of data collection and analysis and finalization of the report | Jun-26 | Dec-26 |
| Lao People’s Democratic Republic (the) LAO/HFCIND/47/UNEP/PRP/DES/94 | 24 | Finalization of the national inventory report, assessment of modality options in consultation with relevant stakeholders, and development of policy recommendations and action plans | Jun-26 | Jun-27 |
| Lesotho LSO/HFCIND/37/UNEP/PRP/DES/94 | 50 | Completion of data collection and analysis and finalization of the report | Jun-26 | Jun-27 |
| Malawi MWI/HFCIND/61/UNEP/PRP/DES/94 | 97 | Completion of the internal review and finalization of the report | Jun-26 | Dec-26 |
| Maldives MDV/HFCIND/43/UNEP/PRP/DES/95 | 0 | Completion of analysis of the activities to be implemented and finalization of the report | Dec-26 | Dec-27 |
| Mongolia MNG/HFCIND/43/UNEP/PRP/DES/95 | 0 | Completion of data collection and analysis and finalization of the report | Dec-26 | Dec-27 |
| Nepal NPL/HFCIND/50/UNEP/PRP/DES/95 | 0 | Completion of data collection and analysis and finalization of the report | Dec-26 | Dec-27 |
| Nigeria NGA/HFCIND/171/UNEP/PRP/DES/94 | 40 | Completion of internal review and finalization of the report | Jun-26 | Dec-26 |
| Sierra Leone SLE/HFCIND/53/UNEP/PRP/DES/94 | 0 | Completion of internal review and finalization of the report | May-26 | Dec-26 |
| Sri Lanka LKA/HFCIND/70/UNEP/PRP/DES/95 | 0 | Completion of the survey and remaining activities and finalization of the report | Dec-26 | Dec-27 |
| Timor-Leste TLS/HFCIND/32/UNEP/PRP/DES/95 | 0 | Completion of data collection, assessment of modality options in consultation with relevant stakeholders, and development of policy recommendations and action plans | Dec-26 | Dec-27 |
| Uganda UGA/HFCIND/42/UNEP/PRP/DES/95 | 0 | Completion of survey and finalization of the report | Dec-26 | Jun-27 |
| Yemen YEM/HFCIND/49/UNEP/PRP/DES/93 | 13 | Adaption of field workflows and implementation of safety protocols in response to the ongoing security situation; completion of required data collection as conditions permit; and finalization of the report | Dec-25* | Dec-27 |
| Zambia ZMB/HFCIND/50/UNEP/PRP/DES/94 | 0 | Completion of survey activities and finalization of the report | Jun-26 | Jun-27 |
| Zimbabwe ZWE/HFCIND/74/UNEP/PRP/DES/94 | 49 | Completion of survey activities and finalization of the report | Jun-26 | Jun-27 |

* Date of completion had already been revised to June 2026 (decision 97/12(b)(i)).

Gender mainstreaming

# All UNEP projects are governed by an internal OzonAction plan and a Core Team supporting the Compliance Assistance Programme’s regional teams on women’s participation and economic empowerment; these are aligned with the Multilateral Fund’s policy in this area.  UNEP OzonAction works closely with governments and other relevant stakeholders to ensure that considerations related to women’s participation and representation are effectively incorporated into project design and implementation. UNEP conducted an analysis of 33 stage I of KIPs submitted between 2023 and 2026 for which UNEP is the lead implementing agency. The analysis indicates that all 33 projects include activities and indicators that promote women’s participation and representation; 20 have dedicated budgets for related activities; 24 promote women’s participation in refrigeration and air-conditioning training programmes; 16 promote women’s participation in customs and enforcement training; 26 collect sex-disaggregated data; and 12 engage women’s organizations or specialists in this area. UNEP also works closely with governments to implement specific adjustments or updates to project activities to strengthen the effective implementation of relevant policies at the national level.

Risk management

# UNEP has a systematic risk-monitoring framework for implementing partners, introduced in response to a UN Board of Auditors recommendation (A/80/5/Add.7, para. 70) and issues identified during project implementation across different countries and regions. Automated “Red Flag” checks trigger on overdue financial and audit reports, non-compliance with legal clauses, adverse budget variances, unresolved ineligible expenditures, and adverse audit findings, applied early in the partnership cycle. To ensure that project implementation delays are appropriately addressed, UNEP undertakes regular follow-up with national ozone units, adjust work plans and timelines, conducts management-level missions for high-level government engagement, facilitates stakeholder coordination meetings, and develops implementation roadmaps. Support from senior management is sought, where necessary, to ensure government commitment at the highest level.

Recommendation

# The Executive Committee may wish:

## To note the progress report of UNEP as at 31 December 2025 contained in document UNEP/OzL.Pro/ExCom/99/16;

## To approve the extension of the completion dates of the preparation of a national inventory of banks of waste controlled substances and development of a national plan for the management of those substances (decision 91/66) for the countries listed below to allow completion of the remaining ongoing activities, as reflected in table 6 of document UNEP/OzL.Pro/ExCom/99/16:

### To December 2026:

Kyrgyzstan (KGZ/HFCIND/54/UNEP/PRP/DES/94);

Malawi (MWI/HFCIND/61/UNEP/PRP/DES/94);

Nigeria (NGA/HFCIND/171/UNEP/PRP/DES/94);

Sierra Leone (SLE/HFCIND/53/UNEP/PRP/DES/94);

### To June 2027:

The Bahamas (BHS/HFCIND/38/UNEP/PRP/DES/95);

Eritrea (ERI/HFCIND/31/UNEP/PRP/DES/94);

Eswatini (SWZ/HFCIND/43/UNEP/PRP/DES/95);

The Gambia (GMB/HFCIND/55/UNEP/PRP/DES/95);

The Lao People’s Democratic Republic (LAO/HFCIND/47/UNEP/PRP/DES/94);

Lesotho (LSO/HFCIND/37/UNEP/PRP/DES/94);

Uganda (UGA/HFCIND/42/UNEP/PRP/DES/95);

Zambia (ZMB/HFCIND/50/UNEP/PRP/DES/94);

Zimbabwe (ZWE/HFCIND/74/UNEP/PRP/DES/94);

### To December 2027:

Bhutan (BTN/HFCIND/37/UNEP/PRP/DES/95);

Brunei Darussalam (BRN/HFCIND/35/UNEP/PRP/DES/95);

The Cook Islands (COK/HFCIND/23/UNEP/PRP/DES/95);

Fiji (FJI/HFCIND/47/UNEP/PRP/DES/95);

Kiribati (KIR/HFCIND/23/UNEP/PRP/DES/95);

Maldives (MDV/HFCIND/43/UNEP/PRP/DES/95);

The Marshall Islands (MHL/HFCIND/23/UNEP/PRP/DES/95);

Micronesia (Federated States of) (FSM/HFCIND/22/UNEP/PRP/DES/95);

Mongolia (MNG/HFCIND/43/UNEP/PRP/DES/95);

Nauru (NRU/HFCIND/19/UNEP/PRP/DES/95);

Nepal (NPL/HFCIND/50/UNEP/PRP/DES/95);

Niue (NIU/HFCIND/22/UNEP/PRP/DES/95);

Palau (PLW/HFCIND/24/UNEP/PRP/DES/95);

Samoa (WSM/HFCIND/32/UNEP/PRP/DES/95);

Solomon Islands (SLB/HFCIND/25/UNEP/PRP/DES/95);

Sri Lanka (LKA/HFCIND/70/UNEP/PRP/DES/95);

Timor-Leste (TLS/HFCIND/32/UNEP/PRP/DES/95);

Tonga (TON/HFCIND/24/UNEP/PRP/DES/95);

Tuvalu (TUV/HFCIND/23/UNEP/PRP/DES/95);

Vanuatu (VUT/HFCIND/23/UNEP/PRP/DES/95);

Yemen (YEM/HFCIND/49/UNEP/PRP/DES/93);

Region: Asia and the Pacific (ASP/HFCIND/72/UNEP/PRP/DES/95); and

## To approve also the recommendations related to ongoing projects with specific issues contained in annex III to the present document.

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNEP

PER COUNTRY FOR 2025

# Table 1 of annex I presents the status of project implementation by country for 2025 in achieved phase-out, planned and achieved disbursements and project completion.

Table 1. Status of project implementation by UNEP for 2025

| Country | Phased out in 2025 (ODP tonnes) | Phased out in 2025 (CO2-eq tonnes)* | Estimated funds disbursed in 2025 (US$) | Funds disbursed in 2025 (US$) | Percentage of funds disbursed over estimation in 2025 | Percentage of planned projects completed in 2025** |
| --- | --- | --- | --- | --- | --- | --- |
| Albania | 0.6 | 0 | 37,980 | 100,283 | 264 | 100 |
| Algeria | 0.0 | 0 | 142,236 | 90,000 | 63 |  |
| Angola | 0.0 | 0 | 19,912 | 126,852 | 637 | 100 |
| Antigua and Barbuda | 0.0 | 0 | 48,927 | 33,944 | 69 |  |
| Armenia | 0.0 | 0 | 44,287 | 29 | 0 | 0 |
| Bahamas (the) | 0.0 | 0 | 83,400 | 57,049 | 68 |  |
| Bahrain | 2.0 | 0 | 53,042 | 158,008 | 298 |  |
| Bangladesh | 0.0 | 0 | 249,909 | 170,061 | 68 | 0 |
| Barbados | 0.0 | 0 | 106,940 | 16,502 | 15 |  |
| Belize | 0.0 | 0 | 127,212 | 64,060 | 50 | 100 |
| Benin | 0.0 | 0 | 74,458 | 64,827 | 87 | 0 |
| Bhutan | 0.0 | 0 | 115,801 | 88,037 | 76 | 100 |
| Bolivia (Plurinational State of) | 0.0 | 0 | 89,242 | 28,080 | 31 |  |
| Botswana | 0.0 | 0 | 36,570 | 9,611 | 26 |  |
| Brunei Darussalam | 0.0 | 0 | 142,492 | 104,330 | 73 | 100 |
| Burkina Faso | 0.0 | 0 | 49,607 | 148,429 | 299 | 0 |
| Burundi | 0.0 | 0 | 86,150 | 74,390 | 86 |  |
| Cabo Verde | 0.0 | 0 | 185,768 | 130,484 | 70 | 100 |
| Cambodia | 4.9 | 0 | 180,388 | 271,822 | 151 | 100 |
| Cameroon | 0.0 | 0 | 92,426 | 92,450 | 100 |  |
| Central African Republic (the) | 0.0 | 0 | 18,000 | 72,000 | 400 |  |
| Chad | 0.0 | 0 | 66,600 | 201,245 | 302 |  |
| Chile | 0.0 | 0 | 117,325 | 74,120 | 63 |  |
| China | 0.0 | 0 | 1,857,230 | 1,783,754 | 96 | 100 |
| Comoros (the) | 0.0 | 0 | 131,003 | 3,179 | 2 |  |
| Congo (the) | 0.0 | 0 | 89,101 | 19,863 | 22 |  |
| Cook Islands (the) | 0.0 | 0 | 249,142 | 87,053 | 35 | 0 |
| Costa Rica | 0.0 | 0 | 21,485 | 1,515 | 7 |  |
| Côte d'Ivoire | 0.0 | 0 | 291,328 | 256,193 | 88 |  |
| Democratic Republic of the Congo (the) | 0.0 | 0 | 97,356 | 105,157 | 108 |  |
| Djibouti | 0.0 | 0 | 86,670 | 141,715 | 164 | 100 |
| Dominica | 0.0 | 0 | 53,645 | 34,257 | 64 |  |
| Dominican Republic (the) | 0.0 | 0 | 151,120 | 143,391 | 95 |  |
| Egypt | 0.0 | 0 | 56,000 | 164,738 | 294 |  |
| El Salvador | 0.0 | 0 | 53,741 | 37,613 | 70 | 100 |
| Equatorial Guinea | 0.0 | 0 | 79,340 | 62,400 | 79 |  |
| Eritrea | 0.0 | 0 | 63,242 | 213,125 | 337 | 100 |
| Eswatini | 0.0 | 0 | 101,275 | 122,825 | 121 |  |
| Ethiopia | 0.0 | 0 | 23,386 | 46,486 | 199 | 100 |
| Fiji | 0.0 | 0 | 139,586 | 116,049 | 83 | 33 |
| Gabon | 0.0 | 0 | 122,327 | 181,225 | 148 |  |
| Gambia (the) | 0.0 | 0 | 99,288 | 200,265 | 202 |  |
| Georgia | 0.0 | 0 | 20,500 | 82,000 | 400 | 100 |
| Ghana | 0.0 | 0 | 29,932 | 0 | 0 |  |
| Grenada | 0.0 | 0 | 172,375 | 167,486 | 97 |  |
| Guatemala | 0.0 | 0 | 155,820 | 51,767 | 33 | 100 |
| Guinea | 0.0 | 0 | 51,300 | 122,042 | 238 | 100 |
| Guinea-Bissau | 0.0 | 0 | 122,423 | 210,666 | 172 | 100 |
| Guyana | 0.1 | 0 | 83,875 | 53,948 | 64 |  |
| Honduras | 0.0 | 0 | 71,253 | 48,694 | 68 | 100 |
| India | 0.0 | 0 | 536,672 | 345,133 | 64 |  |
| Iran (Islamic Republic of) | 0.0 | 0 | 159,300 | 90,956 | 57 | 0 |
| Iraq | 0.0 | 0 | 217,476 | 120,008 | 55 |  |
| Jamaica | 0.0 | 0 | 36,545 | 31,437 | 86 |  |
| Kenya | 0.0 | 0 | 93,475 | 196,773 | 211 | 0 |
| Kiribati | 0.0 | 0 | 263,592 | 31,806 | 12 | 0 |
| Kuwait | 0.0 | 0 | 556,899 | 27,085 | 5 |  |
| Kyrgyzstan | 0.0 | 0 | 114,761 | 242,769 | 212 | 100 |
| Lao People's Democratic Republic (the) | 0.0 | 0 | 119,996 | 141,958 | 118 | 100 |
| Lesotho | 0.0 | 0 | 44,400 | 143,978 | 324 |  |
| Liberia | 0.0 | 0 | 68,580 | 123,003 | 179 | 100 |
| Madagascar | 3.4 | 0 | 80,825 | 171,095 | 212 | 100 |
| Malawi | 2.0 | 48,165 | 62,802 | 291,242 | 464 |  |
| Maldives | 0.0 | 0 | 138,597 | 106,931 | 77 | 100 |
| Mali | 0.0 | 0 | 81,480 | 219,996 | 270 | 100 |
| Marshall Islands (the) | 0.0 | 0 | 110,710 | 27,711 | 25 | 50 |
| Mauritania | 0.0 | 0 | 31,750 | 13,750 | 43 |  |
| Mauritius | 0.0 | 0 | 45,000 | 0 | 0 |  |
| Mexico | 0.0 | 0 | 56,949 | 87,724 | 154 |  |
| Micronesia (Federated States of) | 0.0 | 0 | 236,884 | 59,294 | 25 | 0 |
| Mongolia | 0.0 | 0 | 148,679 | 144,597 | 97 | 50 |
| Morocco | 0.0 | 0 | 103,335 | 0 | 0 |  |
| Mozambique | 0.0 | 0 | 128,534 | 152,762 | 119 |  |
| Myanmar | 0.0 | 0 | 45,000 | 0 | 0 | 0 |
| Namibia | 0.0 | 0 | 68,425 | 68,425 | 100 | 100 |
| Nauru | 0.0 | 0 | 151,660 | 5,766 | 4 | 0 |
| Nepal | 0.0 | 0 | 123,057 | 12,681 | 10 | 100 |
| Nicaragua | 0.0 | 0 | 185,932 | 94,458 | 51 |  |
| Niger (the) | 1.7 | 0 | 73,500 | 48,199 | 66 | 100 |
| Nigeria | 0.0 | 0 | 38,080 | 40,400 | 106 |  |
| Niue | 0.0 | 0 | 68,475 | 34,574 | 50 | 0 |
| Oman | 0.0 | 0 | 78,829 | 163,207 | 207 |  |
| Pakistan | 0.0 | 0 | 295,048 | 148,700 | 50 |  |
| Palau | 0.0 | 0 | 218,775 | 75,250 | 34 | 0 |
| Paraguay | 0.0 | 0 | 114,870 | 133,845 | 117 |  |
| Peru | 2.2 | 0 | 138,018 | 116,356 | 84 |  |
| Philippines (the) | 0.0 | 0 | 99,243 | 155,439 | 157 |  |
| Qatar | 0.0 | 0 | 95,079 | 73,187 | 77 |  |
| Republic of Moldova (the) | 0.0 | 0 | 77,280 | 167,991 | 217 | 50 |
| Rwanda | 0.0 | 0 | 49,040 | 90,916 | 185 |  |
| Saint Kitts and Nevis | 0.0 | 0 | 25,500 | 14,372 | 56 |  |
| Saint Lucia | 0.0 | 0 | 160,000 | 19,554 | 12 |  |
| Saint Vincent and the Grenadines | 0.0 | 0 | 149,754 | 40,069 | 27 | 100 |
| Samoa | 0.0 | 0 | 202,514 | 55,568 | 27 | 0 |
| Sao Tome and Principe | 0.0 | 0 | 137,086 | 10,005 | 7 |  |
| Saudi Arabia | 0.0 | 0 | 535,786 | 148,047 | 28 |  |
| Senegal | 0.0 | 0 | 217,289 | 266,384 | 123 | 0 |
| Serbia | 0.0 | 0 | 32,572 | 20,642 | 63 | 0 |
| Seychelles | 0.0 | 0 | 34,209 | 16,488 | 48 |  |
| Sierra Leone | 0.1 | 0 | 126,609 | 75,804 | 60 |  |
| Solomon Islands | 0.0 | 0 | 287,567 | 120,792 | 42 | 0 |
| Somalia | 0.0 | 0 | 79,950 | 105,209 | 132 |  |
| South Sudan | 0.0 | 0 | 50,000 | 110,310 | 221 | 100 |
| Sri Lanka | 0.0 | 0 | 107,781 | 48,780 | 45 | 100 |
| Suriname | 0.0 | 0 | 135,391 | 68,710 | 51 | 100 |
| Syrian Arab Republic (the) | 0.0 | 0 | 310,659 | 29,939 | 10 | 0 |
| Timor-Leste | 0.0 | 0 | 108,121 | 38,547 | 36 | 0 |
| Togo | 0.0 | 0 | 89,460 | 296,404 | 331 |  |
| Tonga | 0.0 | 0 | 196,734 | 115,817 | 59 | 0 |
| Tunisia | 2.8 | 0 | 37,500 | 100,000 | 267 | 100 |
| Tuvalu | 0.0 | 0 | 123,680 | 78,347 | 63 | 0 |
| Uganda | 0.0 | 0 | 43,000 | 0 | 0 |  |
| United Republic of Tanzania (the) | 0.0 | 0 | 46,210 | 119,704 | 259 | 50 |
| Vanuatu | 0.0 | 0 | 249,372 | 78,797 | 32 | 0 |
| Viet Nam | 0.0 | 0 | 171,632 | 48,472 | 28 | 100 |
| Yemen | 0.0 | 0 | 137,006 | 115,022 | 84 |  |
| Zambia | 0.0 | 0 | 97,350 | 3,203 | 3 | 100 |
| Zimbabwe | 0.0 | 0 | 131,770 | 210,714 | 160 |  |
| Region: Asia and the Pacific | 0.0 | 0 | 402,457 | 95,352 | 24 |  |
| Global | 0.0 | 0 | 10,805,809 | 9,922,172 | 92 | 50 |
| Grand total | 19.8 | 48,165 | 27,232,735 | 23,206,647 | 85 | 59 |

* 28.2 mt (48,165 CO2-eq tonnes) in 2025 for HFC-related projects.

** For projects that were planned to be completed in 2025.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNEP

PER YEAR AS AT 31 DECEMBER 2025

# Table 1 of annex II presents an overview of the status of project implementation by year.  All projects and activities approved between 1991 and 2017 have now been completed.

Table 1. Status of project implementation by year*

| Year | Number of projects |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1991 | 11 | 11 | 100 | 1,372,335 | 1,372,335 | 0 | 100 |
| 1992 | 15 | 15 | 100 | 1,711,000 | 1,711,000 | 0 | 100 |
| 1993 | 49 | 49 | 100 | 4,194,343 | 4,194,343 | 0 | 100 |
| 1994 | 58 | 58 | 100 | 4,231,169 | 4,231,169 | 0 | 100 |
| 1995 | 50 | 50 | 100 | 4,047,683 | 4,047,683 | 0 | 100 |
| 1996 | 47 | 47 | 100 | 3,345,039 | 3,345,039 | 0 | 100 |
| 1997 | 87 | 87 | 100 | 7,962,291 | 7,962,291 | 0 | 100 |
| 1998 | 64 | 64 | 100 | 4,669,124 | 4,669,124 | 0 | 100 |
| 1999 | 87 | 87 | 100 | 6,368,983 | 6,368,983 | 0 | 100 |
| 2000 | 85 | 85 | 100 | 6,300,398 | 6,300,398 | 0 | 100 |
| 2001 | 59 | 59 | 100 | 7,411,159 | 7,411,159 | 0 | 100 |
| 2002 | 72 | 72 | 100 | 9,469,401 | 9,469,401 | 0 | 100 |
| 2003 | 78 | 78 | 100 | 11,165,394 | 11,165,394 | 0 | 100 |
| 2004 | 99 | 99 | 100 | 12,362,652 | 12,362,652 | 0 | 100 |
| 2005 | 72 | 72 | 100 | 12,339,483 | 12,339,483 | 0 | 100 |
| 2006 | 108 | 108 | 100 | 12,731,484 | 12,731,484 | 0 | 100 |
| 2007 | 79 | 79 | 100 | 14,611,111 | 14,611,111 | 0 | 100 |
| 2008 | 132 | 132 | 100 | 17,875,070 | 17,875,070 | 0 | 100 |
| 2009 | 115 | 115 | 100 | 17,250,876 | 17,250,876 | 0 | 100 |
| 2010 | 79 | 79 | 100 | 14,356,674 | 14,356,674 | 0 | 100 |
| 2011 | 100 | 100 | 100 | 16,782,433 | 16,782,434 | -1 | 100 |
| 2012 | 80 | 80 | 100 | 16,086,261 | 16,086,261 | 0 | 100 |
| 2013 | 90 | 90 | 100 | 14,152,112 | 14,152,112 | -1 | 100 |
| 2014 | 74 | 74 | 100 | 12,328,954 | 12,328,953 | 1 | 100 |
| 2015 | 180 | 180 | 100 | 21,169,099 | 21,169,098 | 1 | 100 |
| 2016 | 95 | 95 | 100 | 19,552,807 | 19,552,805 | 2 | 100 |
| 2017 | 88 | 88 | 100 | 15,532,086 | 15,532,085 | 1 | 100 |
| 2018 | 173 | 172 | 99 | 23,738,631 | 23,651,458 | 87,173 | 100 |
| 2019 | 110 | 107 | 97 | 14,871,180 | 14,784,683 | 86,496 | 99 |
| 2020 | 130 | 107 | 82 | 15,165,976 | 13,179,022 | 1,986,954 | 87 |
| 2021 | 126 | 109 | 87 | 21,847,003 | 20,770,089 | 1,076,914 | 95 |
| 2022 | 101 | 75 | 74 | 22,864,789 | 19,382,170 | 3,482,619 | 85 |
| 2023 | 125 | 36 | 29 | 27,139,094 | 17,048,683 | 10,090,412 | 63 |
| 2024 | 213 | 6 | 3 | 42,833,659 | 13,954,105 | 28,879,554 | 33 |
| 2025 | 102 | 0 | 0 | 24,047,446 | 246,316 | 23,801,130 | 1 |
| Total | 3,233 | 2,765 | 86 | 481,887,196 | 412,395,943 | 69,491,253 | 86 |

* Excluding closed and transferred projects.

** Excluding agency support costs.

Annex III

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR UNEP

| Country | Project code | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- | --- |
| Algeria | DZA/HPMP2/88/UNEP/TAS/SRV/95 | HCFC phase-out management plan (stage II, first tranche) | 0 | Slow progress in implementation | To request UNEP to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Bolivia (Plurinational State of) | BOL/HPMP2/56/UNEP/TAS/SRV/93 | HCFC phase-out management plan (stage II, second tranche) | 0 | 18 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Bolivia (Plurinational State of) | BOL/HPMP2/61/UNEP/TAS/SRVEE/93 | HCFC phase-out management plan (stage II) (Additional activities to maintain energy efficiency in the refrigeration servicing sector (decision 89/6)) | 0 | 18 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Comoros (the) | COM/HPMP2/37/UNEP/TAS/SRV/94 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Democratic Republic of the Congo (the) | COD/HCFCIND/52/UNEP/TAS/VER/92 | Verification report on the implementation of stage II of the HCFC phase-out management plan | 0 | 18 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Eswatini | SWZ/HPMP2/39/UNEP/TAS/SRV/94 | HCFC phase-out management plan (stage II, second tranche) | 0 | 18 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Eswatini | SWZ/HPMP2/41/UNEP/TAS/SRVEE/94 | HCFC phase-out management plan (stage II) (Additional activities to maintain energy efficiency in the refrigeration servicing sector (decision 89/6)) | 0 | 18 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Equatorial Guinea | GNQ/HCFCIND/17/UNEP/PRP/SRV/84 | Preparation of a HCFC phase-out management plan (stage II) | 15 | Slow progress in implementation | To request UNEP to submit a status report to the 100th meeting on the submission of stage II of the HPMP |
| Ghana | GHA/KIP1/59/UNEP/TAS/SRV/93 | Kigali HFC implementation plan (stage I, first tranche) | 0 | 18 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Ghana | GHA/KIP1/60/UNEP/TAS/SRV/93 | Kigali HFC implementation plan (stage I, first tranche) | 0 | 18 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Guatemala | GTM/HPMP2/64/UNEP/TAS/SRV/93 | HCFC phase-out management plan (stage II, second tranche) | 0 | 18 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Honduras | HND/KIP1/65/UNEP/TAS/SRV/94 | Kigali HFC implementation plan (stage I, first tranche) | 0 | 18 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Iran (Islamic Republic of) | IRN/HPMP2/232/UNEP/TAS/SRV/84 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 96 | 12 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Iran (Islamic Republic of) | IRN/HPMP2/246/UNEP/TAS/SRV/86 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) | 85 | 12 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Iran (Islamic Republic of) | IRN/HPMP2/272/UNEP/TAS/SRV/94 | HCFC phase-out management plan (stage II, fifth tranche) (refrigeration servicing sector) | 0 | 12 and 18 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Iran (Islamic Republic of) | IRN/HPMP3/275/UNEP/TAS/SRV/96 | HCFC phase-out management plan (stage III, first tranche) | 0 | Slow progress in implementation | To request UNEP to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Kuwait | KWT/HPMP2/42/UNEP/TAS/SRV/88 | HCFC phase-out management plan (stage II, first tranche) | 47 | 12 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Mexico | MEX/KIP1/219/UNEP/TAS/PMU/93 | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 0 | 18 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Mongolia | MNG/HPMP2/42/UNEP/TAS/SRVEE/93 | HCFC phase-out management plan (stage II) (Additional activities to maintain energy efficiency in the refrigeration servicing (decision 89/6)) | 0 | 18 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Mozambique | MOZ/KIP1/47/UNEP/TAS/SRV/94 | Kigali HFC implementation plan (stage I, first tranche) | 0 | 18 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Myanmar | MMR/GOV/23/UNEP/INS/NOU/84 | Extension of institutional strengthening project (phase V: 7/2020-6/2022) | 47 | Slow progress in implementation | To request UNEP to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Nauru | NRU/GOV/16/UNEP/INS/NOU/86 | Extension of the institutional strengthening project (phase VI: 1/2021-12/2022) | 7 | Slow progress in implementation | To request UNEP to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Nauru | NRU/HPMP2/15/UNEP/TAS/SRV/86 | HCFC phase-out management plan for PIC countries through regional approach (stage II, first tranche) | 15 | Slow progress in implementation | To request UNEP to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Nauru | NRU/HFCIND/19/UNEP/PRP/DES/95 | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 0 | Slow progress in implementation | To request UNEP to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Nauru | NRU/KIP1/20/UNEP/TAS/SRV/95 | Kigali HFC implementation plan (stage I, first tranche) | 0 | Slow progress in implementation | To request UNEP to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Nauru | NRU/HPMP2/18/UNEP/TAS/SRV/95 | HCFC phase-out management plan (stage II, second tranche) | 0 | Slow progress in implementation | To request UNEP to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Nauru | NRU/HPMP2/21/UNEP/TAS/SRVEE/95 | HCFC phase-out management plan (stage II): Additional activities to maintain energy efficiency in the refrigeration servicing sector (decision 89/6) | 0 | Slow progress in implementation | To request UNEP to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Nepal | NPL/HPMP2/43/UNEP/TAS/SRV/86 | HCFC phase-out management plan (stage II, first tranche) | 43 | 12 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Nepal | NPL/GOV/49/UNEP/INS/NOU/95 | Extension of the institutional strengthening project (phase XII: 1/2025-12/2027) | 0 | Slow progress in implementation | To request UNEP to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Nepal | NPL/HPMP2/47/UNEP/TAS/SRV/95 | HCFC phase-out management plan (stage II, second tranche) | 0 | 12 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Nepal | NPL/HFCIND/50/UNEP/PRP/DES/95 | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 0 | Slow progress in implementation | To request UNEP to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Niger (the) | NER/KIP1/52/UNEP/TAS/SRV/93 | Kigali HFC implementation plan (stage I) | 0 | 18 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Saint Lucia | LCA/HPMP2/41/UNEP/TAS/SRV/94 | HCFC phase-out management plan (stage II, second tranche) | 0 | 18 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Saint Lucia | LCA/KIP1/46/UNEP/TAS/SRV/94 | Kigali HFC implementation plan (stage I, first tranche) | 0 | 18 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Saint Vincent and the Grenadines | VCT/HPMP1/25/UNEP/TAS/SRV/86 | HCFC phase-out management plan (stage I, third tranche) | 31 | 12 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Senegal | SEN/HPMP2/48/UNEP/TAS/SRV/88 | HCFC phase-out management plan (stage II, first tranche) | 91 | 12 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Sierra Leone | SLE/KIP1/54/UNEP/TAS/SRV/94 | Kigali HFC implementation plan (stage I, first tranche) | 0 | 18 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Syrian Arab Republic | SYR/HPMP1/107/UNEP/TAS/SRV/86 | HCFC phase-out management plan (stage I, first tranche) | 75 | 12 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |
| Yemen | YEM/GOV/48/UNEP/INS/NOU/93 | Extension of the institutional strengthening project (phase IX: 1/2024-12/2026) | 23 | Slow progress in implementation | To request UNEP to submit a status report to the 100th meeting on implementation progress |
| Yemen | YEM/HFCIND/49/UNEP/PRP/DES/93 | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 13 | Slow progress in implementation | To request UNEP to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Yemen | YEM/HFCIND/50/UNEP/TAS/ENA/97 | Enabling activities for HFC phase-down | 0 | Slow progress in implementation | To request UNEP to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Zambia | ZMB/HPMP2/48/UNEP/TAS/SRV/94 | HCFC phase-out management plan (stage II, second tranche) | 0 | 18 months delays | To request UNEP to report to the 100th meeting on this project with implementation delays |

UNEP/OzL.Pro/ExCom/99/1

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database, which is provided on the 99th meeting portal on the Multilateral Fund’s website, in the spreadsheet programme, Microsoft Excel.

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 99th meeting.

Funded by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment.

Ongoing projects are all projects that were under implementation as at 31 December 2025. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

Phase-out of ODS is expressed in ODP tonnes and of HFCs in mt and CO2-eq tonnes.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61).

UNEP/OzL.Pro/ExCom/99/39

UNEP/OzL.Pro/ExCom/99/45

UNEP/OzL.Pro/ExCom/99/51

UNEP/OzL.Pro/ExCom/99/52

UNEP/OzL.Pro/ExCom/99/53

UNEP/OzL.Pro/ExCom/99/54

UNEP/OzL.Pro/ExCom/99/56

UNEP/OzL.Pro/ExCom/99/57

UNEP/OzL.Pro/ExCom/99/61

UNEP/OzL.Pro/ExCom/99/62

UNEP/OzL.Pro/ExCom/99/68

UNEP/OzL.Pro/ExCom/99/69

UNEP/OzL.Pro/ExCom/99/70

UNEP/OzL.Pro/ExCom/99/71

UNEP/OzL.Pro/ExCom/99/72

UNEP/OzL.Pro/ExCom/99/73

UNEP/OzL.Pro/ExCom/99/74

UNEP/OzL.Pro/ExCom/99/76

UNEP/OzL.Pro/ExCom/99/43

UNEP/OzL.Pro/ExCom/99/47

UNEP/OzL.Pro/ExCom/99/50

UNEP/OzL.Pro/ExCom/99/58

UNEP/OzL.Pro/ExCom/99/19 or UNEP/OzL.Pro/ExCom/99/20

Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.

The Executive Committee requested bilateral and implementing agencies to provide a brief report on key gender mainstreaming results achieved as part of their annual progress reports, as of 2023, on the basis of the information available to them (decision 90/48(d)).

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.