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اللجنــة التنفيـذيــــة للصنــدوق المــتعــدد الأطـــراف
لتنفيـــذ بروتوكـول مونتريــال 
الاجتماع الثامن والتسعون
مونتريال، 22-26 يونيو/حزيران 2026
البند 6(أ) من جدول الأعمال المؤقت [footnoteRef:1] [1:  UNEP/OzL.Pro/ExCom/98/1 
] 


تقارير الحالة وتقارير عن المشروعات ذات متطلبات إبلاغ محددة وبدون قضايا معلقة
1. تتكون الوثيقة الحالية من قسمين، هما (1) المشروعات المتأخرة في تنفيذها والمشروعات التي طُلبت بشأنها تقارير حالة خاصة، و(2) المشروعات ذات متطلبات الإبلاغ المحددة وبدون قضايا معلقة. ولا تتضمن التقارير المتعلقة بهذه المشروعات، بعد استعراض الأمانة، أي مسائل معلقة، وبالتالي لا تتطلب من اللجنة التنفيذية النظر فيها بشكل فردي.
أولا.	المشروعات المتأخرة في التنفيذ والمشروعات التي طلبت بشأنها تقارير حالة خاصة
2. أحاطت اللجنة التنفيذية علما، في الاجتماع السابع والتسعين، بأن الوكالات الثنائية والوكالات المنفذة ستقدم تقارير في الاجتماع الثامن والتسعين، بشأن 78 مشروعا تأخر تنفيذها و14 مشروعا جاريا أو شرائح من الاتفاقات المتعددة السنوات الموصى بإعداد تقارير حالة إضافية خاصة بها (المقرر 97/9(ج)). وبناء على ذلك، قدمت الوكالات الثنائية والتنفيذية ذات الصلة التقارير المطلوبة إلى الاجتماع الثامن والتسعين. وعند استعراض التقارير، أجرت الأمانة مناقشات مع الوكالات الثنائية والمنفذة وتمت معالجة العديد من المسائل بشكل مرضٍ. ويقدم الجدول 1 موجزا للمشروعات المتأخرة في التنفيذ والمشروعات الموصى بشأنها إعداد تقارير حالة خاصة إضافية بما في ذلك مستويات تقدمها وتوصيات الأمانة والإشارات إلى مرفقات هذه الوثيقة.
الجدول 1. ملخص للمشروعات المتأخرة في التنفيذ والتي طُلبت بشأنها تقارير حالة خاصة
	مستوى التقدم المحرز
	عدد المشاريع
	المقرر
	التوصية
	المرفق

	التأخيرات في التنفيذ

	التقدم
المشاريع الفردية والاتفاقات المتعددة السنوات)
	64
	32/4
	يتم حذفها من التقارير المقبلة
	غير متوفر

	بعض التقدم
المشاريع الفردية والاتفاقات المتعددة السنوات)
	11
	32/4
	الاستمرار في الرصد حتى إنجازها النهائي
	المرفق الأول

	لم يسجل أي تقدم للمرة الأولى (اتفاقات متعددة السنوات)
	0
	84/45
	الاستمرار في الرصد حتى إنجازها النهائي
	غير متوفر

	الإلغاء
	3
	n/a
	\
سيتم إلغاؤها
	غير متوفر

	المجموع
	78
	
	
	

	تفارير الحالة

	لا تنطوي على مسائل معلقة
	10
	51/13
	يتم حذفها من التقارير المقبلة
	غير متوفر

	ما زالت المشاكل تحتاج إلى حل
	4
	51/13
	أن يطلب تقديم تقارير حالة إضافية
	المرفق الثاني

	المجموع
	14
	
	
	



إلغاء المشاريع
3. في الاجتماع السابع والتسعين، طلبت اللجنة التنفيذية من الأمانة أن ترسل رسالة إلى أفغانستان واليونيدو، بصفتها الوكالة المنفذة الرئيسية، بخصوص الإلغاء الممكن لخطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية للبلد (المرحلة الأولى، الشريحة الثالثة (AFG/PHA/79/INV/22)، والمرحلة الأولى، الشريحة الرابعة (AFG/PHA/85/INV/28) والمرحلة الثانية، الشريحة الأولى (AFG/PHA/85/INV/30) (المقرر 97/13(د)).
4. ووفقا للمقرر، أبلغ اليونيدو الأمانة بأن العقوبات بموجب مجلس الأمن في الأمم المتحدة فرضت تدابير مستهدفة على أفغانستان، تتطلب إجراء تحقق رسمي للامتثال لجميع المشاريع قبل المضي فيها. وأضاف اليونيدو أن منظومة الأمم المتحدة تمتنع حاليا عن الإجراءات التي قد تؤدي إلى تزايد التصور بالاعتراف بالسلطات الفعلية في أفغانستان ومن الدعم المباشر للميزانية أو الإجراءات التي يمكن أن تعتبر أنها تضفي الطابع الشرعي لمثل هذه السلطات. وبالنظر إلى أن هذا الوضع قد أدى إلى حواجز إجرائية وقانونية وتشغيلية كبيرة لليونيدو من أجل المضي قدما مع تنفيذ هذه الأنشطة، يرغب اليونيدو طلب إلغاء المشاريع الإضافية التالية في أفغانستان: خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الأولى، الشريحة الرابعة) (AFG/PHA/95/TAS/33)؛ خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية، الشريحة الأولى) (AFG/PHA/95/TAS/34)؛ وتمديد مشروع التعزيز المؤسسي (المرحلة العاشرة: 1/2022-12/2023) (AFG/SEV/95/INS/35)؛ وإعداد جرد وطني لبنوك نفايات المواد الخاضعة للرقابة وإعداد خطة وطنية لإدارة هذه المواد (المقرر 91/66) (AFG/DES/94/PRP/32).
5. ويعرض الجدول 2 حالة الصرف لكل مشروع.
الجدول 2. المشاريع الموصى بإلغائها في أفغانستان
	رمز المشروع
	عنوان المشروع
	الأموال المعتمدة (دولار أمريكي)
	الأموال المنصرفة (دولار أمريكي)
	الرصيد 
(دولار أمريكي)

	AFG/PHA/79/INV/22
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الأولى، الشريحة الثالثة)
	83,000
	11,914
	71,086

	AFG/PHA/85/INV/28
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الأولى، الشريحة الرابعة)
	28,276
	0
	28,276

	AFG/PHA/85/INV/30
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية، الشريحة الأولى)
	90,000
	54,580
	35,420

	AFG/PHA/95/TAS/33
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الأولى الشريحة الرابعة)
	28,453
	 0
	28,453

	AFG/PHA/95/TAS/34
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية، الشريحة الأولى)
	180,908
	 0
	180,908

	AFG/SEV/95/INS/35
	تمديد مشروع التعزيز المؤسسي (المرحلة العاشرة: 1-2022-12/2023)
	192,000
	0
	192,000

	AFG/DES/94/PRP/32
	وإعداد جرد وطني لبنوك نفايات المواد الخاضعة للرقابة وإعداد خطة وطنية لإدارة هذه المواد (المقرر 91/66)
	90,000
	 0
	90,000



6. وبالتشاور مع اليونيدو، تم الاتفاق على أن المشاريع الواردة أعلاه سيتم إلغائها وستعاد الأرصدة المتبقية إلى الاجتماع التاسع والتسعين. وبالإضافة إلى ذلك، اشتملت المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لأفغانستان على شريحتين متبقيتين موافق عليهما من حيث المبدأ ومقرر تقديمهما في عامي 2025 و2026، على التوالي؛ إذ لم تقدم هاتين الشريحتين، ولأنهما أوصي أيضا بإلغائهما. وقد ترغب اللجنة التنفيذية في إلغاء المشاريع الواردة في الجدول 2، فضلا عن الشريحتين المتبقيتين الموافق عليهما من حيث المبدأ بموجب المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لأفغانستان.
تقرير الحالة عن تنفيذ نظام حصص المواد الهيدروفلوروكربونية في موريشيوس
7. وفي الاجتماع الخامس والتسعين، عند الموافقة على المرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي لموريشيوس، أحاطت اللجنة التنفيذية علما بأن حكومة ألمانية ستقدم، كجزء من تقريرها المالي والمرحلي لعام 2024 التي سيتم النظر فيها في الاجتماع الثاني في عام 2025، تحديثا عن حالة تنفيذ نظام حصص المواد الهيدروفلوروكربونية في موريشيوس (المقرر 95/67(ب)(2)). وأبلغت حكومة ألمانيا عن وحود نظام حصص المواد الهيدروفلوروكربونية في موريشيوس منذ يناير/كانون الثاني 2025 وينص على تخصيص الواردات إلى مستوردي المواد الهيدروفلوروكربونية على أساس خط أساس متوسط الواردات من المواد الهيدروفلوروكربونية. ويشمل النظام أيضا حكما لتخصيص جزء صغير من واردات المواد الهيدروفلوروكربونية لمعالجة حالات الطوارئ والطلبات الخاصة لواردات المواد الهيدروفلوروكربونية من المؤسسات الحكومية. وأجريت حلقة عمل ليوم واحد في عام 2025 مع المستوردين ذوي الصلة وأصحاب المصلحة من أجل توعيتهم بأحكام تعديل كيغالي، وبتوصيات خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، فضلا عن الأساس لحسابات حصص المواد الهيدروفلوروكربونية، وكيفية إدارة حصصهم بكفاءة.
التوصية
8. قد ترغب اللجنة التنفيذية فيما يلي:
(1) الإحاطة علما بما يلي:
(1) التقارير عن التأخيرات في التنفيذ وتقارير الحالة المقدمة من الوكالات الثنائية والمنفذة، الواردة في الوثيقة UNEP/OzL.Pro/ExCom/98/6؛
(2) أن الوكالات الثنائية والمنفذة ستقدم تقارير إلى اللجنة التنفيذية في الاجتماع التاسع والتسعين عن 11 مشروعا بتأخيرات في التنفيذ، على النحو المشار إليه في المرفق الأول بالوثيقة الحالية، وعن أربعة مشاريع موصى بتقارير حالة إضافية عنها، على النحو المشار إليه في المرفق الثاني بالوثيقة الحالية، كجزء من التقارير السنوية والمالية والمرحلية للوكالات الثنائية والمنفذة؛
(2) الموافقة على التوصيات بشأن المشاريع الجارية ذات القضايا المعلقة الواردة في العمود الأخير من الجدول في المرفق الثاني بالوثيقة الحالية؛
(3) إلغاء المشاريع التالية لأفغانستان ومطالبة اليونيدو بإعادة الأرصدة المتبقية إلى الاجتماع التاسع والتسعين: خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الأولى، الشريحة الثالثة) (AFG/PHA/79/INV/22)؛ وخطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الأولى، الشريحة الرابعة) (AFG/PHA/85/INV/28)؛ وخطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الأولى، الشريحة الرابعة) (AFG/PHA/95/TAS/33)؛ وخطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية، الشريحة الأولى) (AFG/PHA/85/INV/30)؛ وخطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية، الشريحة الأولى) (AFG/PHA/95/TAS/34) وتمديد مشروع التعزيز المؤسسي (المرحلة العاشرة: 1/2022-12/2023) (AFG/SEV/95/INS/35)؛ وإعداد جرد وطني لبنوك نفايات المواد الخاضعة للرقابة وإعداد خطة وطنية لإدارة هذه المواد (المقرر 91/66) (AFG/DES/94/PRP/32)؛ و
(4) إلغاء الشرائح المعلقة الموافق عليها من حيث المبدأ بموجب المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لأفغانستان.
ثانيا.	المشروعات ذات متطلبات إبلاغ محددة وبدون قضايا معلقة
نظرة عامة
9. يسرد الجدول 3 تقارير عن المشروعات ذات متطلبات إبلاغ محددة وبدون قضايا معلقة.
الجدول 3. تقارير عن المشروعات ذات متطلبات إبلاغ محددة وبدون قضايا معلقة
	البلد
	عنوان المشروع 
	الفقرات

	ألف. 	التقارير المتعلقة بخطط إدارة إزالة االمواد الهيدروكلوروفلوروكربونية

	الأرجنتن
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية – توافر البدائل الممكنة منخفضة إمكانية الاحترار العالمي للهيدروكلوروفلوروكربون-141ب في قطاع الرغاوى والتحول إلى استخدام بدائل عالية إمكانية الاحترار العالمي)
	10-21

	بنغلاديش
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية – تقرير عن عدد تكييفات الهواء التي تستخدم R-290/الهيدروفلوروكربون-32 بموجب مشروع تحويل قطاع تكييف الهواء)
	22-29

	بوتان
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية وأنشطة إضافية للحفاظ على كفاءة الطاقة في قطاع خدمة التبريد بموجب المقرر 89/6 (طلب لتمديد تاريخ إنجاز المشروع)
	30-35

	العراق
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية – إنجاز المرحلة الأولى، وخطة الإزالة الوطنية، ومشروع لاستبدال الكلوروفلوروكربون-12 بالايسوبوتان واستبدال الكلوروفلوروكربون-11 بالسيكلوبنتان في تصنيع التبريد المنزلي في Light Industries)
	36-41

	الكويت
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثالثة) – طلب لتمديد تاريخ إنجاز المشروع
	42-47

	موريتانيا
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الأولى – تقرير مرحلي عن تنفيذ برنامج العمل المرتبط بالشريحة الثالثة والنهائية)
	48-56

	تركيا
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الأولى – تقرير مرحلي عن تنفيذ برنامج العمل المرتبط بالشريحة الخامسة والنهائية)
	57-67

	باء. 	التقرير المتعلق باتفاقات خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي

	متعددة
	اتفاقات لتخفيض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطط التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي
	68-72

	جيم. 	التقرير المتعلق بالأنشطة الإضافية للحفاظ على كفاءة الطاقة في قطاع خدمة التبريد (المقرر 89/6)

	ملديف
	الأنشطة الإضافية للحفاظ على كفاءة الطاقة في قطاع خدمة التبريد بموجب المقرر 89/6(ب) (التقرير المرحلي النهائي) (اليونيب)
	73-81

	دال. 	تقرير متعلق بمشروع تجريبي للحفاظ على كفاءة الطاقة و/أو تعزيزها لتكنولوجيات ومعدات الاستبدال في سياق التخفيض التدريجي للمواد الهيدروفلوروكربونية (المقرر 91/65)

	الكاميرون
	مشروع تجريبي للحفاظ على كفاءة الطاقة و/أو تعزيزها لتكنولوجيات ومعدات الاستبدال في سياق التخفيض التدريجي للمواد الهيدروفلوروكربونية (أنشطة غير استثمارية) (طلب لتمديد تاريخ إنجاز المشروع)
	82-86

	هاء. 	تقرير متعلق بإعداد مشروع لتعزيز كفاءة الطاقة في سياق التخفيض التدريجي للمواد الهيدروفلوروكربونية في قطاع تصنيع التبريد وتكييف الهواء (المقرر 94/60)

	تركيا
	حالة إعداد مشروع لتعزيز كفاء الطاقة وتحويل 29 شركة تصنيع التبريد وتكييف الهواء من استخدام الهيدروفلوروكربون إلى تكنولوجيا منخفضة إمكانية الاحترار العالمي
	87-91

	واو. 	تقرير متعلق بإعداد جرد وطني لبنوك المواد المستخدمة أو غير المرغوبة الخاضعة للرقابة وخطة لجمع مثل هذه المواد ونقلها والتخلص منها (المقرر 91/66)

	موريشيوس
	إعداد جرد وطني لبنوك نفايات المواد الخاضعة للرقابة وإعداد خطة وطنية لإدارة هذه المواد (المقرر 91/66) (طلب لتمديد تاريخ إنجاز المشروع)
	92-96



ألف.	التقارير المتعلقة بخطط إدارة إزالة االمواد الهيدروكلوروفلوروكربونية
الأرجنتين: خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية - توافر البدائل منخفضة إمكانية الاحترار العالمي للهيدروكلوروفلوروكربون-141ب في قطاع الرغاوى والتحول من استخدام بدائل عالية إمكانية الاحترار العالمي) (اليونيدو وحكومة إيطاليا)
معلومات أساسية
10. في اجتماعها الثاني والتسعين، عند الموافقة على الشريحة الثالثة من المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية للأرجنتين (المقرر 92/31)، أحاطت اللجنة التنفيذية، ضمن جملة أمور أخرى، بما يلي:
(1) التحديات التي يمثلها نقص المعروض من البدائل منخفضة إمكانية الاحترار العالمي للهيدروكلوروفلوروكربون-141ب في قطاع الرغاوى، والتي أخرت تنفيذ أنشطة المرحلة الثانية في قطاع رغاوى البوليوريتان وكان من شأن ذلك أن يتيح لحكومة الأرجنتين إزالة 85.92 طن بقدرات استنفاد الأوزون من المواد الهيدروكلوروفلوروكربونية؛
(2) أنه في حالة عدم توفر البدائل في السوق المحلية، فيمكن استخدام البدائل عالية إمكانية الاحترار العالمي، على أساس مرحلة انتقالية فقط، وأن حكومة الأرجنتين ستقدم تقريرا إلى كل اجتماع للجنة التنفيذية بشأن التقدم المحرز نحو ضمان إتاحة التكنولوجيات المختارة، بما في ذلك المكونات المرتبطة بها، على أساس تجاري في البلد، وتفهم أنه لن يتم تمويل تكاليف التشغيل الإضافية إلا بعد اكتمال التحول إلى البدائل المتفق عليها.
11. وأبلغ اليونيدو عن هذه المسألة في اجتماعات متعاقبة للجنة التنفيذية،[footnoteRef:2] أحدثها في الاجتماع التاسع والتسعين، مع ملاحظة أنه بحلول أغسطس/آب 2025 تسلمت ثلاث شركات نظم الأوليفينات الهيدروفلورية وبدأت في وضع صياغات جديدة في السوق المحلي. وبينما كان الموردون وشركات النظم يعملون على تحسين العملية، وبينما تزايد التوافر العام للأوليفينات الهيدروفلورية، ساد الشك في سلسلة التوريد، إذ أن مورد واحد فقط بدأ عمليات التسليم حتى الآن، ولم يكن التحول غير المتكافئ للأوليفينات الهيدروفلوروية كعامل نفخ في المنطقة مستداما بالكامل بعد. وبالرغم من التقدم الملحوظ المحرز، فإن التحديات المتعلقة بالتوافر والسعر، واستقرار سلسلة الإمداد والقاعدة المحدودة من الموردين ما زالت بدون حل، مما أدى إلى الاستخدام الانتقالي المستمر للمواد عالية إمكانية الاحترار العالمي. وأبرز اليونيدو أيضا مدى استعداد شركات النظم المحلية اعتماد الأوليفينات الهيدروفلورية بمجرد معالجة القيود على السعر والإمداد. [2:  الفقرات 2-9 من الوثيقة UNEP/OzL.Pro/ExCom/93/20، والفقرات 5-14 من الوثيقة UNEP/OzL.Pro/ExCom/94/9، والفقرات 5-18 من الوثيقة UNEP/OzL.Pro/ExCom/96/11 ، والفقرات 10-15 و31-32 من الوثيقة UNEP/OzL.Pro/ExCom/97/36.] 

12. وبناء عليه، في الاجتماع السابع والتسعين، طلبت اللجنة التنفيذية إلى حكومة الأرجنتين واليونيدو، وفقا للمقرر 92/31(ج)(2)، تقديم تحديث في الاجتماع الثامن والتسعين بشأن التوافر في السوق المحلي للبدائل منخفضة إمكانية الاحترار العالمي للهيدروكلوروفلوروكربون-141ب في قطاع الرغاوى وبشأن الاستخدام الانتقالي للبدائل عالية إمكانية الاحترار العالمي (المقرر 97/35).[footnoteRef:3] [3:  الموافقة الشمولية على الشريحة الرابعة من المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لأرجنتينا.] 

التقرير المرحلي
13. بالنيابة عن حكومة الأرجنتين، قدم اليونيدو تقريرا يتضمن تحديثا لحالة توافر الأوليفينات الهيدروفلورية وإمداداتها وسعرها وتسليمها لقطاع رغاوى البوليوريتان، وذلك بعد مشاورات إضافية أجريت مع الموردين الرئيسيين وشركات النظم المحلية.
14. وفيما يتعلق بالتوافر، تتنقل الأوليفينات الهيدروفلورية zd(E) -123 في الأرجنتين من مرحلة تجربة إلى ترتيبات توريد أكثر انتظاما. وأبلغت شركات النظم المحلية عن الاحتفاظ بمخزونات تشغيلية كافية لتجنب الاختلالات في التوريد في الربع الثاني من عام 2025. كما يستكشف المورد الوحيد تركيبات بديلة لسلسلة التوريد لخفض الاعتماد على حاويات سعة طن واحد وتحسين استمرار التوريد على الأجل المتوسط.
15. وما زال توزيع للأوليفينات الهيدروفلورية على نطاق صغير يعتمد أساسا على خزانات ton، وما زالت التحديات المرتبطة بإرجاع تلك الحاويات وتدويرها مستمرة. وتجري مناقشات بخصوص إنشاء نظام للتقسيم، مما يمكن أن يحسن من التوافر على المدى القصير. وأعرب القطاع عن القلق إزاء سيناريو المورد الواحد، إذ لا يمكن أن يضمن هذا الترتيب سعرا تنافسيا ويمكن إدخال تكاليف وساطة إضافية.
16. وأبلغ اليونيدو أيضا أن عدم اليقين المتزايد إزاء اللوائح الدولية يمكن أن يؤثر على اعتماد الأوليفينات الهيدروفلورية في الأرجنتين على المدى الطويل. وبينما كانت الأوليفينات الهيدروفلورية هي البديل الرئيسي منخفض إمكانية الاحترار العالمي للهيدروكلوروفلوروكربون-141ب بالنسبة لبعض الاستخدامات، فإن الشواغل إزاء المواد المفلورة والقيود المحتملة على مواد البيرفلورو ألكيل والبولي فلورو ألكيل في بعض الأسواق تنشئ خطر للتغييرات التنظيمية المقبلة، ويحتمل أن تتطلب تحويلات إضافية. ويعتبر ذلك حاسما خاصة بالنسبة لتطبيقات رغاوى الرش، حيث لا يتوافر في الوقت الحاضر أي بدائل مجدية أخرى منخفضة إمكانية الاحترار العالمي.
تعليقات الأمانة
17. عند إبلاغ الأمانة بتحديث بشأن الأسعار الحالية للأوليفينات الهيدروفلورية-zd(E) 123 في الأرجنتين، أشار اليونيدو إلى أنها تختلف حسب اعتمادها على عوامل متعددة، تشمل ما إذا كان يمكن لإحدى شركات النظم شراء حاويات خزانات عادية دولية بدلا من حاويات سعة طن واحد، والأحجام المشتراة، ووجود عقود التوريد طويلة الأجل، وإمكانية التوريد من خلال مكاتب في البرازيل. وإستنادا إلى المناقشات مع مورد التكنولوجيا، لا يتوقع أن يتجاوز السعر التقريبي عن 18 دولارا للكيلوغرام، مما يظل أعلى بكثير من الخيارات البديلة.
18. ومع ملاحظة التوافر المتزايد للأوليفينات الهيدروفلورية والتنسيق الجاري لتجنب الفجوات في التوريد، تساءلت الأمانة عما إذا كان الاستخدام المؤقت للأوليفينات الهيدروفلورية بواسطة شركات النظم وعملائها قد توقف الآن. وأبلغ اليونيدو أن شركة واحدة فقط تستخدم المواد الهيدروفلوروكربونية لم تكن من شركات النظم بل كانت شركة مبيعات تعاني من صعوبات في بيع وإستيراد النظم القائمة على الأوليفينات الهيدروفلورية بدون خسارة استقرارها مدى الحياة خلال الشحن.
19. وأحاطت الأمانة علما مع التقدير بأن حكومة الأرجنتين تستمر في مناقشاتها مع مورد الأوليفينات الهيدروفلورية وشركات النظم، وتحقيق تقدم كذلك في زيادة التوافر وخفض الأسعار. ومع ملاحظة أن مسألة توافر البدائل في تصنيع رغاوي البوليوريتان سيتم مناقشته بموجب البند 9 من جدول أعمال الاجتماع الثامن والتسعين، أدرجت الأمانة المعلومات المحدثة في مشروع رغاوى البوليوريتان في الأرجنتين في الوثيقة UNEP/OzL.Pro/ExCom/98/56.
20. وعلى الرغم من إحراز تقدم كبير، فلم يتم بعد تسوية قضايا التوافر والأسعار للبدائل منخفضة إمكانية الاحترار العالمي، وما زالت البدائل عالية إمكانية الاحترار العالمي تستخدم على أساس انتقالي. وبالتالي، وفقا للمقرر 92/31(ج)(2)، توصي الأمانة بأن تستمر حكومة الأرجنتين في الإبلاغ إلى اللجنة التنفيذية بشأن المسألة.
التوصية
21. قد ترغب اللجنة التنفيذية فيما يلي:
(1) الإحاطة علما بالتقرير عن تحديث حالة توافر البدائل منخفضة إمكانية الاحترار العالمي للهيدروكلوروفلوروكربون-141ب في قطاع الرغاوى وبشأن الاستخدام الانتقالي للبدائل عالية إمكانية الاحترار العالمي في سياق المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لأفغانستان، المقدم من اليونيدو والوارد في الوثيقة UNEP/OzL.Pro/ExCom/98/6؛ و
(2) مطالبة حكومة أفغانستان واليونيدو، بما يتماشى مع المقرر 92/32(ج)(2)، وكجزء من التقرير المرحلي السنوي عن تنفيذ الشريحة النهائية من المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية، المقرر في الاجتماع التاسع والتسعين، تقديم تحديث بشأن التوافر في السوق المحلي للبدائل منخفضة إمكانية الاحترار العالمي للهيدروكلوروفلوروكربون-141ب في قطاع الرغاوى وبشأن الاستخدام الانتقالي للبدائل عالية إمكانية الاحترار العالمي.
بنغلاديش: خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية – تقرير عن عدد أجهزة تكييف الهواء التي تستخدم R-290/الهيدروفلوروكربون-32 بموجب مشروع تحويل قطاع تكييف الهواء (اليوئنديبي)
معلومات أساسية
22. في الاجتماع الرابع والتسعين، وافقت اللجنة التنفيذية على الشريحة الثالثة والنهائية من المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لبنغلادیش، مع ملاحظة أن الحكومة ستقوم، من خلال الیوئندیبي، بالإبلاغ عن عدد أجھزة تكییف الھواء التي تستخدم 290/R-الھیدروفلوروكربون-32 كغاز تبرید، باستثناء منشأة المنتجات التقنیة، التي قامت بالتصنیع سنویا خلال الفترة 2025-2027 بواسطة كل شركة ممولة بموجب مشروع تحویل قطاع تصنیع أجھزة تكییف الھواء، وتمثل ذلك خلال الاجتماع الأول لكل سنة تالیة (المقرر 94/32(ب)(2)).
23. ووفقا للمقرر، قدمت حكومة بنغلاديش، من خلال اليوئنديبي، تقريرا عن الخمس شركات الممولة بموجب مشروع تحويل قطاع تكييف الهواء.
التقرير المرحلي
24. يعرض الجدول 4 أدناه عدد وحدات تكييف الهواء المصنعة من كل من الشركات في الفترة بين يناير/كانون الثاني وديسمبر/كانون الأول 2025.
الجدول 4. وحدات تكييف الهواء المصنعة من 1 يناير/كانون الثاني إلى 31 ديسمبر/كانون الأول 2025
	الشركة
	النوع المجزأ
(السكني)
	جميع الأنواع
(التجارية)

	Walton Hi-Tech Industries
	R-290
	547
	0

	
	HFC-32
	298,521
	3,800

	Cooling Point Engineering Services
	R-290
	0
	0

	
	HFC-32
	0
	20

	Elite Hi-Tech
	R-290
	688
	292

	
	HFC-32
	11,517
	0

	AC Bazar Industries Ltd.
	R-290
	400
	0

	
	HFC-32
	900
	383

	Supreme Air Conditioning Co.
	R-290
	1,682
	0

	
	HFC-32
	14,921[footnoteRef:4] [4:  نتيجة لخطأ مطبعي عير مقصود، أبلغ اليوئنديبي الاجتماع السابع والتسعين عن كمية غير صحيحة تبلغ 136,480 وحدة. والرقم الصحيح هو 13,648 وحدة حتى أكتوبر/تشرين الأول 2025، بينما مستوى الإنتاح المحدث كان 14,921 وحدة حتى 31 31 ديسمبر/كانون الأول 2025.] 

	6,758

	المجموع
	R-290
	3,317
	292

	
	HFC-32
	325,859
	10,961



25. ويشير التقرير إلى أنه حتى ديسمبر/كانون الأول 2025، Walton Hi-Tech Industries و Elite Hi-Tech أنجزت تشغيلها لتحويل مرافق التصنيع فيها مع إطلاق نماذج تكييف الهواء القائمة على R-290 بسعة أقل من 1.5 طن من التبريد[footnoteRef:5] في السوق المحلي منذ الربع الثالث من عام 2025. والشركات الثلاث المتبقية أنجزت جميع المراحل الرئيسية للتحويل وتدقيق السلامة. وأجري التسويق لوحدات تكييف الهواء الجديدة باستخدام التكنولوجيات البديلة في بداية الربع الرابع من عام 2025. وبالإضافة إلى ذلك، فرض الحظر على التصنيع المحلي وعلى إستيراد أجهزة تكييف الهواء القائمة على الهيدروكلوروفلوروكربون-22 بسعة تصل إلى 1.5 طن من التبريد ويتم إنفاذه منذ 1 يناير/كانون الثاني 2026. [5:  طن من التبريد.] 

26. وأبلغ اليوئنديبي أيضا أنه بينما يتزايد استيعاب تكنولوجيا R-290 تدريجيا على مدى الشركات الخمس، مدفوعا بكفاءة الطاقة العالية فيها والإمكانية المنخفضة للاحترار العالمي، يواجه اعتمادها على نطاق أوسع قيود متمثلة في التكاليف الأكثر ارتفاعا، ومشاغل السلامة، والقدرات المحدودة للفنيين. وما زالت تكنولوجيا الهيدروفلوروكربون-32 هي الخيار المفضل نتيجة للبنية التحتية للخدمة المنشأة والتكاليف المنخفضة على نحو أكبر.
تعليقات الأمانة
27. لاحظت الأمانة أن المشروع قد أنشأ بنجاح قدرات تصنيع محلية أولية لأجهزة تكييف الهواء الخالية من المواد الهيدروكلوروفلوروكربونية على مدى الشركات الخمس المشاركة. وضمن محافظ التصنيع فيها، ظهر الهيدروفلوروكربون-32 كالتكنولوجيا التحويلية المسيطرة، بينما كان R-290 الخيار المحتمل الذي قد يزداد في المستقبل بواسطة أربع شركات من هذه الشركات المنتجة لوحدات تكييف الهواء بسعة تقل عن 1.5 طن من التبريد. والمزج بين التحويلات المنجزة، والإحجام الأولية للإنتاج، وإنفاذ التدابير التنظيمية التي تقيد استخدام الهيدروكلوروفلوروكربون-22 يقدم خط أساس مفضل للتحويل المستدام للسوق فيما بعد عام 2025.
28. وما زالت هناك عدة مخاطر ينبغي معالجتها في سياق اعتماد أجهزة تكييف الهواء القائمة على R-290. وهي تشمل أساسا تصورات السلامة المتعلقة بالقابلية للاشتعال، وعدد محدود من القنيين المدربين والمعتمدين القادرين على مناولة التكنولوجيات القائمة على الهيدروكربون، والعوامل في السوق التي تسهم في تكاليف أعلى للمكونات الرئيسية لمثل هذه المعدات. ومن المتوقع أن بعض هذه التحديات، وخاصة التحديات المتعلقة بقدرات قطاع الخدمة على مناولة وتركيب وخدمة وحدات R-290، سيتم معالجتها خلال المرحلة الثالثة من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية، التي سيتم إنجازها بحلول عام 2030. ومن المتوقع معالجة التدابير الإضافية لدعم الاعتماد الأسرع للتكنولوجيات البديلة والمناولة الآمنة للمواد الهيدروكربونية خلال المرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي التي سيتم تقديمها في المستقبل.
التوصية
29. قد ترغب اللجنة التنفيذية في الإحاطة علما بالتقرير عن عدد أجھزة تكییف الھواء التي تستخدم 290/R-الھیدروفلوروكربون-32 كغاز تبرید، المصنعة في عام 2025 بواسطة كل شركة ممولة بموجب مشروع تحویل قطاع تصنیع أجھزة تكییف الھواء، للمرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لبنغلاديش، المقدم من اليوئنديبي والوارد في الوثيقة UNEP/OzL.Pro/ExCom/98/6.
بوتان: خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية والأنشطة الإضافية للحفاظ على كفاءة الطاقة في قطاع خدمة التبريد بموجب المقرر 89/6 (طلب لتمديد تاريخ إنجاز المشروع) (اليونيب واليوئنديبي)
معلومات أساسية
30. في اجتماعها الخامس والتسعين، وافقت اللجنة التنفيذية على الشريحة الرابعة والنهائية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لبوتان بقيمة 147,000 دولارا أمريكيا، بالإضافة إلى تكاليف دعم الوكالة البالغة 18,350 دولارا أمريكيا، والتي تضمنت مبلغ 100,000 دولارا أمريكيا بالإضافة إلى تكاليف دعم الوكالة البالغة 13,000 دولارا أمريكيا لليونيب، من أجل الأنشطة الإضافية للحفاظ على كفاءة الطاقة (المقرر 89/6).[footnoteRef:6] وسيكون تاريخ الإنجاز التشغيلي في 31 ديسمبر/كانون الأول 2026 متماشيا مع اتفاق خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية. [6:  المرفق السابع عشر من الوثيقة UNEP/OzL.Pro/ExCom/95/94.] 

طلب للتمديد
31. أبلغ اليونيب أن المشروع للأنشطة الإضافية للحفاظ على كفاءة الطاقة في قطاع خدمة التبريد يتطلب وقتا إضافيا لإنجازه، وعلى وجه التحديد النشاط لتعزيز النظام للترويج للأجهزة منخفضة إمكانية الاحترار العالمي وتعزيز عملية تسجيل الأجهزة التي قد تواجه تأخيرات أولية والتي تم تسويتها الآن.
32. وبناء عليه، وبالنيابة عن البلد، طلب اليونيب، بصفته الوكالة المنفذة الرئيسية، تمديدا لفترة تنفيذ خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية حتى 31 ديسمبر/كانون الأول 2027 من أجل تمكين إنجاز الأنشطة المذكورة آنفا.
تعليقات الأمانة
33. ولاحظت الأمانة أن البلد استهلك 122 كيلوغراما أو 0.007 أطنان بقدرات استنفاد الأوزون من الهيدروكلوروفلوروكربون-22 في عام 2025، وهو يتماشى مع الهدف المحدد في الاتفاق بين البلد واللجنة التنفيذية. ولاحظت الأمانة أيضا أن أنشطة كفاءة الطاقة المتعلقة بالتدريب والأنشطة الأخرى في خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية يتوقع إنجازها في الوقت المحدد، بحلول ديسمبر/كانون الأول 2026.
34. ونظرا لأن المشاكل التي سببت التأخيرات الأولية في مكون المشروع المتعلق بكفاءة الطاقة قد تم تسويتها، تعتبر الأمانة أن التمديد المطلوب لإنجاز خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية يمكن أن ييسر من إنجاز الأنشطة المتبقية في هذا المكون.
التوصية
35. قد ترغب اللجنة التنفيذية فيما يلي:
(1) الإحاطة علما بالطلب لتمديد تنفيذ خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لبوتان، على النحو الذي قدمه اليونيب والوارد في الوثيقة UNEP/OzL.Pro/ExCom/98/6؛ و
(2) الموافقة، على أساس استثنائي، وعلى أساس الفهم بعدم تقديم طلب آخر لتمديد إنجاز المشروع، على تمديد تاريخ إنجاز المشروع المشار إليه في الفقرة الفرعية (أ) أعلاه، حتى 31 ديسمبر/كانون الأول 2027، من أجل السماح بإنجاز الأنشطة الإضافية للحفاظ على كفاءة الطاقة في قطاع خدمة التبريد المقدم وفقا للمقرر 89/6.
العراق: خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية - إكمال المرحلة الأولى، الخطة الوطنية للإزالة، ومشروع استبدال الكلوروفلوروكربون-12 بالأيزوبوتان والكلوروفلوروكربون-11 بالسيكلوبنتان في تصنيع أجهزة التبريد المنزلي في شركة الصناعات الخفيفة) (اليونيب واليونيدو)
معلومات أساسية
36. في اجتماعها السابع والثمانين، وافقت اللجنة التنفيذية على المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية للعراق، مشيرة إلى أنه لا يمكن النظر في الشريحة الثانية إلا بعد استكمال المرحلة الأولى من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (IRQ/PHA/74/INV/23)، والخطة الوطنية للإزالة (IRQ/PHA/58/INV/09)، ومشروع استبدال غاز التبريد الكلوروفلوروكربون-12 بالأيزوبوتان، وغاز نفخ الرغاوى الكلوروفلوروكربون-11 بالسيكلوبنتان في تصنيع البرادات المنزلية والمجمدات الصندوقية في شركة الصناعات الخفيفة (IRQ/REF/57/INV/07) (المقرر 87/40(ج)). وحتى وقت تقديم الشريحة الثانية إلى الاجتماع الخامس والتسعين، لم تكن اليونيدو قد أنجزت المشروعين المذكورين أعلاه؛ وبناء على ذلك، تمت الموافقة على الشريحة لليونيب فقط، مع الإشارة إلى أنه لن يُنظر في أي تمويل إضافي لليونيدو حتى استيفاء الشرط. وعلاوة على ذلك، وعلى أساس استثنائي، تم تمديد تواريخ استكمال المرحلة الأولى من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية والمشروعين IRQ/REF/57/INV/07 وIRQ/PHA/58/INV/09 إلى 31 ديسمبر/كانون الأول 2025، على أن تقوم اليونيدو بتصحيح حالة تنفيذ المشروعين الأخيرين إلى "جاري" في تقريرها المرحلي السنوي والمالي لعام 2024، وتقديم تقرير إلى الاجتماع السادس والتسعين عن التقدم المحرز في تنفيذ المشروعات الثلاثة (المقرر 95/52).
37. وقدم اليونيدو التقارير المرحلية في الاجتماعين السادس والتسعين والسابع والتسعين. وأكد التقرير المقدم إلى الاجتماع السابع والتسعين أن جميع الأنشطة المنفذة بموجب المرحلة الأولى من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية، بما في ذلك توزيع الأدوات إلى المستفيدين، سيتم إنجازها بحلول ديسمبر/كانون الأول 2025، حسب التمديد المقدم. وبموجب الخطة الوطنية لإزالة، سيتستكمل أيضا شركة النصر العامة جميع الأنشطة بحلول ديسمبر/كانون الأول 2025، وشركة الصلب العراقية لن تشترك بعد ذلك وستستكمل التركيبات بطريقة مستقلة وبمواردها الخاصة، ملتزمة بعدم استخدام المواد الهيدروكلوروفلوروكربونية أو المواد الهيدروفلوروكربونية لتصنيع الرغاوى، وسيتم الإنجاز التشغيلي في شركة الصناعات الخفيفة بحلول 31 ديسمبر/كانون الأول 2025، عندما تنقل اليونيدو ملكية المعدات، بناء على التزام من شركة الصناعات الخفيفة بأنه إذا تم تمديد أعمال التحويل بعد ذلك التاريخ، ستكون الشركة مسؤولة عن الإنجاز, وستقوم وحدة الأوزون الوطنية برصد الامتثال لهذا الاتفاق وسيستمر اليونيدو في تقديم المساعدة التقنية بعد إنجاز المشروع في ديسمبر/كانون الأول 2025، لضمان التحويل المناسب. وأحاطت اللجنة التنفيذية علما بالتقرير وطلبت إلى اليونيدو أن يقدم تقريرا مرحليا عن إنجاز هذه المشروعات إلى الاجتماع الثامن والتسعين (المقرر 97/16).
التقرير المرحلي
38. بالنيابة عن حكومة العراق، قدم اليونيدو التقارير المرحلية للمشروعات التالية:
(1) خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الأولى، الشريحة الثانية) (المساعدة التقنية لقطاع الخدمة) (IRQ/PHA/74/INV/23): نتيجة للتأخيرات في الإفراج الجمركي، تم شراء حزم أدوات[footnoteRef:7] لمائة من الفنيين، وتسليمها وتوزيعها على المستفيدين في أبريد/نيسان 2026، وقدم تقرير إنجاز المشروع في نفس الشهر، وسيتم إعادة الرصيد البالغ 8,063.71 دولارا أمريكيا إلى الاجتماع الثامن والتسعين؛ [7:  بما في ذلك أجهزة إلكترونية للكشف عن التسرب للعديد من غازات التبريد، ومضخات زيت الشحن، ومعدات نفخ النيتروجين المحمولة، ومجموعات أدوات مفتاح عزم الدوران، وزردية Lokring، وفكي التجميع، وموصلات بأقطار مختلفة.] 

(2) الخطة الوطنية للإزالة (التحويل من الكلوروفلوروكربون-11 إلى السيكلوبنتان في مصنعين من مصانع رغاوى البوليوريتان) (IRQ/PHA/58/INV/09): تسلمت شركة النصر العامة جميع المعدات، وقامت باختبارها والتدريب عليها لبدء الإنتاج التجاري، وأنجزت تحويلها في ديسمبر/كانون الأول 2025؛ وتم إلغاء المشروع في شركة الصلب العراقية، وسيتم إعادة الرصيد البالغ 26,319.69 دولارا أمريكيا إلى الاجتماع التاسع والتسعين؛
(3) مشروع استبدال الكلوروفلوروكربون-12 بالإيزوبوتان والكلوروفلوروكربون-11 بالسيكلوبنتان في تصنيع أجهزة التبريد المنزلي في شركة الصناعات الخفيفة (IRQ/REF/57/INV/07): أنجز اليونيدو تركيب المعدات وتشغيلها، وأنجز المشروع تشغيليا في ديسمبر/كانون الأول 2025 وسيستكمل ماليا في يونيه/تموز 2026.
مستوى صرف الأموال
39. في أبريل/نيسان 2026، كانت نسبة صرف الأموال للشريحة الثانية من المرحلة الأولى من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية، وللخطة الوطنية للإزالة، قد بلغت 96.5 في المائة و95.8 في المائة على التوالي؛ وتم صرف المبلغ الإجمالي الموافق عليه لمشروع التحويل في شركة الصناعات الخفيفة، والبالغ 2,161,581 دولار أمريكي، كما هو موضح في الجدول 5. وستعاد الأرصدة المتبقية إلى الاجتماعين الثامن والتسعين والتاسع والتسعين.
الجدول 5. التقرير المالي للمشروعات التي سيتم إنجازها للعراق حتى أبريل/نيسان 2026 (دولار أمريكي)
	المشروعات
	الأموال المعتمدة
	الأموال المنصرفة
	معدل الصرف (%)
	رصيد الصندوق

	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الأولى، الشريحة الثانية)
	230,000
	221,936.29
	96.5
	*8,063.71

	الخطة الوطنية للإزالة (شركة النصر العامة وشركة الصلب العراقية)
	4,353,530
	4,171,591.85
	95.8
	**26,319.69

	التحويل في شركة الصناعات الخفيفة
	2,161,581
	2,161,581
	100.0
	0


* الرصيد الذي سيتم إعادته إلى الاجتماع الثامن والتسعين.
** الرصيد المتبقي الذي سيتم إعادته إلى الاجتماع التاسع والتسعين بعد سداد الالتزامات المعلقة.
تعليقات الأمانة
40. ولاحظت الأمانة أن جميع المشروعات المعلقة قد تم إنجازها تشغيليا الآن، وأن تقرير تنفيذ المشروع للمرحلة الأولى من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية قد تم تقديمه، وأن الأرصدة المتبقية من المرحلة الأولى من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية والخطة الوطنية للإزالة سيتم إعادتها في الاجتماعين الثامن والتسعين والتاسع والتسعين، على التوالي. وبناء على المقرر 87/40(ج)، يمكن أن يقدم اليونيدو الشريحة الثانية من المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية للعراق لنظر اللجنة التنفيذية فقط بمجرد تقديم تقارير تنفيذ المشروع للخطة الوطنية للإزالة ولمشروع التحويل في شركة الصناعات الخفيفة إلى الأمانة.
التوصية
41. قد ترغب اللجنة التنفيذية فيما يلي:
(1) الإحاطة علما بالتقارير النهائية عن التقدم المحرز في استكمال الشريحة الثانية من المرحلة الأولى من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية للعراق (IRQ/PHA/74/INV/23) والشريحة الأولى من الخطة الوطنية للإزالة (IRQ/PHA/58/INV/09)، والمشروع لاستبدال غاز تبريد الكلوروفلوروكربون-12 بالإيزوبوتان وعامل نفخ الرغاوى الكلوروفلوروكربون-11 بالسيكلوبانتان في تصنيع الثلاجات المنزلية والمجمدات الصندوقية في شركة الصناعات الخفيفة (IRQ/REF/57/INV/07) للعراق، على النحو المقدم من اليونيدو والوارد في الوثيقة UNEP/OzL.Pro/ExCom/98/6؛ و
(2) مطالبة اليونيدو بتقديم تقارير إنجاز المشروع للمشروعين IRQ/PHA/58/INV/09 وIRQ/REF/57/INV/07 قبل الاجتماع التاسع والتسعين للسماح بالنظر في الشريحة الثانية من المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لليونيدو، وفقا للمقرر 87/40(ج).
الكويت: خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية) – طلب لتمديد تاريخ إنجاز المشروع (اليونيب واليونيدو)
معلومات أساسية
42. في الاجتماع الثامن والثمانين، وافقت اللجنة التنفيذية على المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية للكويت، على أن ينفذها اليونيب واليونيدو، للفترة من 2021 إلى 2025 لخفض استهلاك المواد الهيدروكلوروفلوروكربونية بنسبة 67.5 في المائة من خط أساس البلد (المقرر 88/51). ويجري حاليا تنفيذ الشريحة الثانية، الموافق عليها في الاجتماع الخامس والتسعين. ومن المقرر تقديم الشريحة الثالثة والنهائية في عام 2025، مع الإنجاز الكامل لخطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية في ديسمبر/كانون الأول 2026، وفقا للاتفاق بين الحكومة واللجنة التنفيذية.
الطلب للتمديد
43. واجهت الكويت ظروف استثنائية ناشئة عن التطورات في المنطقة منذ منتصف عام 2025، التي أثرت على البيئة التشغيلية الشاملة والقدرة على إجراء أنشطة المشروعات المخططة. وبالإضافة إلى ذلك، نتج عن التغييرات في إدارة السلطة العامة للبيئة في مايو/أيار 2025 تعديلات انتقالية أثرت على عمليات التنسيق وصنع القرارات اللازمة للتنفيذ السليم وفي الوقت المحدد للأنشطة المخططة.
44. وبموجب تنفيذ اليونيب، أحرز تقدم في الأنشطة الرئيسية، بما في ذلك التوقيع على اتفاقات مشروع التعاون لكل من الشريحتين والصرف الأولي للسلطة العامة للبيئة؛ غير أن العديد من الأنشطة ما زال معلقا لحين تسوية الطروف المذكورة أعلاه. وبموجب خطة تنفيذ اليونيدو، تم إنشاء مركز الاستصلاح وهو يعمل الآن؛ وتم تسليم معدات المختبرات إلى السلطة العامة للبيئة؛ وأجريت بعثات لتحديد مراكز التدريب وإعداد أطر التراخيص. ولكن ما زال معلقا تسليم بعض المعدات إلى مراكز التدريب، بجانب المعدات للمختبرات للاسترداد وإعادة التدوير والاستصلاح، نتيجة قيود الشحن المرتبطة بالوضع الإقليمي؛ وبعد التسليم سيتم تركيب المعدات وتشغيلها.
45. وفي ضوء ما سبق ذكره أعلاه، طلب اليونيب، بالنيابة عن حكومة الكويت، تمديدا لفترة تنفيذ المشروع حتى 31 ديسمبر/كانون الأول 2027 للسماح باستكمال جميع الأنشطة المتبقية.
تعبلقات الأمانة
46. لاحظت الأمانة التحديات التي تواجهها حكومة الكويت في تنفيذ المرحلة الثانية من خطتها لإدارة إزالة المواد الهيدروكلوروفلوروكربونية التي أخرت الانتهاء من إعداد تخطيط وتنفيذ أنشطة معينة. وطلبت الأمانة توضيحا من اليونيب واليونيدو عن الحالة الراهنة للتنفيذ والتدابير الموجودة لضمان الاستكمال ضمن الإطار الزمني الممتد المطلوب. وأكد اليونيب واليونيدو أن الوضع يجري إدارته بنشاط، مما يسمح لكلا الوكالتين بإحراز تقدم كبير؛ وأن الشريحة الثالثة والنهائية من المقرر تقديمها إلى الاجتماع التاسع والتسعين؛ وأنه يتوقع استكمال جميع الأنشطة المتبقية بحلول 31 ديسمبر/كانون الأول 2027.
التوصية
47. قد ترغب اللجنة التنفيذية فيما يلي:
(1) الإحاطة علما بالطلب لتمديد المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية للكويت، على النحو المقدم من اليونيب والوارد في الوثيقة UNEP/OzL.Pro/ExCom/98/6؛
(2) الموافقة، على أساس استثنائي، على التمديد حتى 31 ديسمبر/كانون الأول 2027 لتاريخ إنجاز المشروع المشار إليه في الفقرة الفرعية (أ) أعلاه وعلى أساس الفهم بعدم الموافقة على تمديد آخر.
موريتانيا: خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الأولى – تقرير مرحلي عن تنفيذ برنامج العمل المرتبط بالشريحة الثالثة والنهائية) اليونيب واليونيدو)
معلومات عامة
48. عند الموافقة على الشريحة الثالثة والنهائية من المرحلة الأولى من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لموريتانيا، طلبت اللجنة التنفيذية إلى حكومة موريتانيا واليونيب واليونيدو أن يقدموا إلى الاجتماع الثامن والتسعين، تقريرا مرحليا عن التقدم المحرز في تنفيذ الأنشطة المتبقية بموجب المرحلة الأولى من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية، بما في ذلك نتائج تقييم الجدوى التقنية والاقتصادية التي توضح بالتفصيل ما إذا كان نظام الاسترداد وإعادة التدوير والاستصلاح الوطني لموريتانيا سيكون مستدامًا أم لا، والإطار التشغيلي للنظام وارتباطاته بمراكز الاسترداد الحالية، والمعدات التي سيتم شراؤها.[footnoteRef:8] [8:  المقرر 97/35 (الموافقة الشمولية).] 

49. وأبلغت حكومة موريتانيا في بيانات برنامجها القطري عن استهلاك 6.32 أطنان بقدرات استنفاد الأوزون من المواد الهيدروكلوروفلوروكربونية في عام 2025، وهو أقل بنسبة 69 في المائة من خط أساس المواد الهيدروكلوروفلوروكربونية اللازم للامتثال في البلد ويتسق مع الحد الأقصى من الاستهلاك المسموح به.
التقرير المرحلي
50. بالنيابة عن حكومة موريتانيا، قدم اليونيب، بصفته الوكالة المنفذة الرئيسية تقريرا مرحليا عن تنفيذ الأنشطة المتبقية بموجب المرحلة الأولى من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية، بما في ذلك نتيجة تقييم استدامة النظام الوطني للاسترداد وإعادة التدوير والاستصلاح.
51. وأنجزت جميع الأنشطة المخططة في قطاع الخدمة بموجب مكون اليونيب للشريحة الثانية على النحو التالي:
(1) برنامج تدريب ضباط الجمارك والإنفاذ: نظمت خمس حلقات عمل، مما أدى إلى تدريب 125 من ضباط الجمارك والإنفاذ؛
(2) برنامج تدريب فنيي التبريد: استكمال تدريب المدربين وجلسات التدريب الوطني اللاحقة، بما مجموعه 30 مدربا وأكثر من 200 من الفنيين المدربين على الممارسات الجيدة للخدمة، بما في ذلك الاسترداد وإعادة التدوير والمناولة الآمنة لغاز التبريد؛
(3) استقصاء وتقييم الاحتياجات في قطاع التبريد وتكييف الهواء: أجري استقصاء شامل وتقييم للاحتياجات، وقدمت بيانات محدثة عن استهلاك المواد الهيدروكلوروفلوروكربونية، وعدد المعدات واحتياجات القطاع؛
(4) الرصد والإبلاغ: أنشأت نظم الرصد، وعزز جمع البيانات بالتنسيق مع الجمارك وأصحاب المصلحة ذوي الصلة.
52. ويجري اليونيدو حاليا تنفيذ الأنشطة وقدمت دراسة الجدوى التقنية والاقتصادية لنظام الاسترداد وإعادة التدوير والاستصلاح إلى الأمانة:
(1) الجدوى التقنية والاقتصادية لنظام الاسترداد وإعادة التدوير والاستصلاح: خلص التقييم إلى أن نظام الاسترداد وإعادة التدوير كان مجديا ويمكن إنشاؤه كنتيجة مجدية على المدى القريب؛ غير أن الاستصلاح لا يرجح أن يكون مجديا اقتصاديا على المدى القريب. وكان الحجم المطلوب للاستصلاح أقل من 60 أطنان بقدرات استنفاد الأوزون في السنة على المدى الوطني، ويعتبر تحقيقه صعبا على مستويات الاستهلاك الحالية. وعرض التقييم أيضا خارطة طريق تنظيمية لتفعيل النظام، وتوافر البنية التحتية، وخطة تنفيذ مفصلة من ست مراحل، وقائمة للمعدات، والتدريب والتراخيص، وتدابير مراقبة الجودة، والأدوار والمسؤوليات المؤسسية؛
(2) المساعدة التقنية ومعدات برنامج لمراكز الاسترداد والتخزين: بعد نقل المسؤوليات من اليوئنديبي إلى اليونيدو، تم توحيد المشتريات لكلا المرحلتين الأولى والثانية في طلب واحد لتعظيم التكاليف واللوجستيات. وتم الانتهاء من عملية الشراء وتسليم المعدات في أبريل/نيسان 2026؛
(3) بناء القدرات الفنية على غازات التبريد البديلة بما في ذلك المواد الهيدروكربوية (R-290): تم تسليم المعدات؛ وسينسق اليونيدو مع وحدة الأوزون الوطنية لتنظيم تدريب لبناء القدرات، من المقرر أن يكون في يونيه/حزيران 2026؛
(4) محددات غاز التبريد أصبحت متوافرة وتم شراء ثلاث وحدات بعد ذلك وتم تسليمها.
53. حتى مايو/أيار 2026، من أصل المبلغ الموافق عليه بموجب المرحلة الأولى وقدره 607,500 دولارا أمريكيا، تم صرف 348,101 دولارا أمريكيا (216,595 دولارا أمريكيا لليونيب و131,506 دولارا أمريكيا لليونيدو)، على النحوا لمبين في الجدول 6. وسيتم صرف الرصيد البالغ 259,399 دولارا أمريكيا بحلول 31 ديسمبر/كانون الأول 2027.
الجدول 6. التقرير المالي للمرحلة الأولى من خطة إدارة إزالة المواد الهيدروكلورفلوروكربونية لموريتانيا (دولار أمريكي)
	الشريحة
	اليونيب
	اليونيدو
	المجموع
	معدل الصرف (%)

	الأولى
	المعتمدة
	150,000
	105,000
	255,000
	79

	
	المنصرفة
	149,845
	50,336
	200,181
	

	الثانية
	المعتمدة
	66,750
	200,000
	266,750
	55

	
	المنصرفة
	66,750
	81,170
	147,920
	

	الثالثة
	المعتمدة
	85,750
	0
	87,750
	0

	
	المنصرفة
	0
	0
	0
	

	المجموع
	المعتمد
	302,500
	305,000
	607,500
	57

	
	المنصرف
	216,595
	131,506
	348,101
	

	
	الرصيد
	85,905
	173,494
	259,399
	



تعليقات الأمانة
54. وتظرا لأن التقييم خلص إلى أن نظام الاسترداد وإعادة التدوير كان مجديا، ولكن نظام الاستصلاح لا يرجح أن يكون مجديا اقتصاديا، أعدت خارطة طريق للتنفيذ على أن تشمل فقط الأنشطة المتعلقة بالاسترداد وإعادة التدوير. ولا يحدد التقرير وجود أي مراكز رسمية للاسترداد في موريتانيا. وبعد استلام تفاصيل عن عدد المعدات ونوعها المشتراة لمراكز الاسترداد والتخزين[footnoteRef:9] فضلا عن قائمة المشتريات[footnoteRef:10] لمراكز الاستصلاح، طلبت الأمانة توضيحا عن العدد الإجمالي لمراكز التخزين والاسترداد الذي سيتم مساعدته وعدد الفنيين الذين سيتم تدريبهم. وأكد اليونيدو أن المعدات سيتم تركيبها وتشغيلها في مركزين للتخزين، وخمسة مراكز استرداد وطنية ومركز تخزين مركزي، وأن التدريب على المناولة الآمنة لغازات التبريد القابلة للاشتعال، وإجراءات الاسترداد وإعادة التدوير، وتشغيل المعدات في مراكز التدريب سيتم تقديمه على الأقل إلى 240 فنيا من فنيي التيريد وتكييف الهواء. [9:  تشمل تسليم عدة معدات من بينها وحدات استرداد غاز التبريد، والخراطيم، والاسطوانات، والموازين، ومضخات التفريغ، ومقاييس المشعبات، وكاشفات التسرب، والمجسات، والأدوات اليدوية ومحددات غاز التبريد.]  [10:  تشكل ضمن أدوات أخرى اسطوانات استرداد بالتفريغ، وماكينات استرداد غاز التبريد، ومضخات تفريغ، ومحطات شحن محمولة، وموازين، ومقاييس مشعبات، وكاشفات التسرب ومجموعات اللحام.] 

الخلاصة
55. تستمر موريتانيا في تلبية أهداف الرقابة على المواد الهيدروكلوروفلوروكربونية المحددة في اتفاقها مع اللجنة التنفيذية، مع استمرار هبوط الاستهلاك. ويقوم البلد بالإنفاذ الفعال لنظام التراخيص والحصص للرقابة على إستيراد المواد الهيدروكلوروفلوروكربونية. وبينما كان هناك تأخيرات في التنفيذ نتيجة لتغيير الوكالة المنفذة، وقيود التوريد العالمية، والتحديات اللوجستية المتعلقة بالشحن وتوضيح إجراءات الإعفاء من الضريبة، تم إجراء تدابير تصحيحية. وتشمل هذه التدابير مراجعة لقائمة المعدات لتعكس التوافر في السوق، وتسوية المشاكل المتعلقة بالشحن والجمارك، والانتهاء من عمليات الشراء. وفي قطاع خدمة التبريد وتكييف الهواء، تم تقديم المعدات والأدوات لدعم المساعدة التقنية وبرنامج معدات لمراكز الاسترداد والتخزين، فضلا عن تسليم محددات غازات التبريد. وتمت الموافقة على الشريحة النهائية في الاجتماع السابع والتسعين ويبلغ معدل الصرف الحالي ما نسبته 57 في المائة، بما في ذلك الشريحة النهائية. وأكد اليونيب واليونيدو أن جميع الأنشطة الأساسية سيتم إنجازها بحلول 31 ديسمبر/كانون الأول 2026، مع الانتهاء منها والتوحيد التشغيلي ليمتد إلى عام 2027.
التوصية
56. قد ترغب اللجنة التنفيذية في الإحاطة علما بالتقرير عن التقدم المحرز في تنفيذ الأتشطة المتبقية بموجب المرحلة الأولى من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لموريتانيا، بما في ذلك نتائج تقييم الجدوى التقنية والاقتصادية لنظام الاسترداد وإعادة التدوير والاستصلاح الوطني، والإطار التشغيلي للنظام وارتباطاته بمراكز الاسترداد الحالية، والمعدات التي سيتم شراؤها المرتبطة بالشريحة الثالثة والنهائية من المرحلة الأولى من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية، المقدم من اليونيب والوارد في الوثيقة UNEP/OzL.Pro/ExCom/98/6.
تركيا: خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الأولى – تقرير مرحلي عن تنفيذ برنامج العمل المرتبط بالشريحة الخامسة والنهائية) (اليونيدو واليونيب)
معلومات أساسية
57. في اجتماعها السادس والتسعين، وعند الموافقة على الشريحة الخامسة والنهائية من المرحلة الأولى من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لتركيا، طلبت اللجنة التنفيذية إلى حكومة تركيا واليونيدو واليونيب أن يقدموا تقارير مرحلية على أساس سنوي عن تنفيذ برامج العمل المرتبطة بالشريحة النهائية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية وتقارير التحقق من خلال إنجاز المشروع.[footnoteRef:11] [11:  المقرر 96/26 (الموافقة الشمولية)] 

58. وأبلغت حكومة تركيا عن استهلاك 2.75 طنا بقدرات استنفاد الأوزون من المواد الهيدروكلوروفلوروكربونية في عام 2024، وهو أقل بنسبة 99.5 في المائة من خط أساس المواد الهيدروكلوروفلوروكربونية اللازم للامتثال. ومنعت تركيا بالفعل إستيراد المواد الهيدروكلوروفلوروكربونية اعتبارا من 1 يناير/كانون الثاني 2015، مما سمح بكميات محدودة فقط من الهيدروكلوروفلوروكربون-22 حصريا لأغراض الخدمة. وإعتبارا من 1 يناير/كانون الثاني 2025، فرض أيضا الحظر على إستيراد الهيدروكلوروفلوروكربون-22 للخدمة، وبذلك استكملت الإزالة الكاملة للمواد الهيدروكلوروفلوروكربونية. ويرد في الجدول 7 استهلاك المواد الهيدروكلوروفلوروكربونية للفترة 2020-2025؟
الجدول 7. استهلاك المواد الهيدروكلوروفلوروكربونية في تركيا (بيانات المادة 7 للفترة 2020-2025)
	المواد الهيدروكلوروفلوروكربونية
	2020
	2021
	2022
	2023
	2024
	2025*
	خط الأساس**

	الهيدروكلوروفلوروكربون-22

	أطنان مترية
	33.15
	63.96
	47.16
	42.48
	50.00
	0.00
	8,007.00

	أطنان بقدرات استنفاد الأوزون
	1.82
	3.52
	2.59
	2.34
	2.75
	0.00
	551.47

	الحد الأقصى للاستهلاك المسموح به
	50.00
	40.00
	30.00
	20.00
	10.00
	0.00
	n/a


* تقرير التحقق
** يشمل خط الأساس الهيدروكلوروفلوروكربون-22 والهيدروكلوروفلوروكربون-141ب والهيدروكلوروفلوروكربون-142ب والهيدروكلوروفلوروكربون-123 والهيدروكلوروفلوروكربون-124. واستهلاكت تركيا الهيدروكلوروفلوروكربون-22 فقط في القترة 2013-2024.
59. وأبلغت حكومة تركيا عن بيانات استهلاك قطاع المواد الهيدروكلوروفلوروكربونية بموجب تقرير تنفيذ البرنامج القطري وهي تتسق مع البيانات المبلغ عنها بموجب المادة 7 من بروتوكول مونتريال. وقدم مشروع تقرير تنفيذ البرنامج القطري لعام 2025 في 5 مايو/أيار 2026، مؤيدا الاستهلاك الصفري للمواد الهيدروكلوروفلوروكربونية كما أشير إليه في التحقق. ويجري حاليا الانتهاء من التقرير النهائي.
تقرير التحقق
60. أكد تقرير التحقق أن تركيا أنجزت الإزالة الكاملة لاستهلاك المواد الهيدروكلوروفلوروكربونية بحلول 1 يناير/كانون الثاني 2025، خمس سنوات قبل الجدول الزمني لبروتوكول مونتريال، وتحقق هذا الإنجاز بفضل الأطر المؤسسية والتنظيمية القوية، والتحويلات القطاعية، والأنشطة الداعمة الحاسمة بموجب خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية.
61. ولإستدامة الإزالة المتسارعة للمواد الهيدروكلوروفلوروكربونية في تركيا، أوصى التحقق بتعزيز التدابير لمنع الواردات غير القانونية من خلال تعزيز الرقابة الجمركية، بما في ذلك الأدوات الرقمية، ومحددات غاز التبريد، والعقوبات، والتعاون الإقليمي، والتدريب الجاري لضباط الجمارك. وأبرز أيضا الحاجة إلى الحفاظ على التدريب المستمر ونظم التراخيض وإدراج مراكز الاستصلاح في الأطر الوطنية لإدارة النفايات، وتحفيز استخدامها، وتوسيع نطاق تكليفها ليشمل المواد الهيدروفلوروكربونية والغازات المفلورة الأخرى. وفي النهاية، دعا إلى التعزيز المؤسسي المستمر لضمان إبقاء الأطر التنظيمية قوية، وشفافة، ومتوافقة مع معايير الاتحاد الأوروبي للغازات المفلورة، ودعم الإبلاغ الفعال والرصد.
التقرير المرحلي
62. بالنيابة عن حكومة تركيا، قدم اليونيدو تقريرا يعرض تحديثا بشأن التقدم المحرز في الأنشطة المتبقية في قطاع خدمة التبريد، بما في ذلك ما يلي:
(1) تدريب ضباط الجمارك والإنفاذ: قدم التدريب إلى 141 من ضباط الإنقاذ والمفتشين بشأن اللوائح الحالية، ومنع التجارة غير القانونية، وتحديد المواد المستنفدة للأوزون المحظورة باستخدام محددات غازالتبريد، لما مجموعه 250 ضابطا تم تدريبهم بموجب المرحلة، بما فيهم 62 أمرأة؛
(2) تدريب وترخيص فنيي التبريد وتكييف الهواء: تم تزويد 25 مدرسة ثانوية مهنية مملوكة للدولة وموجودة في 23 مقاطعة[footnoteRef:12] لتعزيز قدرات تدريبهم العملي في قطاع خدمة التبريد. وتم ترخيص ما مجموعه 7,289 فنيا بموجب نظام المؤهلات الوطني، ومن المقرر في الوقت الحاضر ترخيص 2,000 فنيا إضافيا, وبالإضافة إلى ذلك، في الفترة بين السنتين 2025 و2026، تلقى 1,276 فتيا عبر 11 مقاطعة التدريب على الممارسات الجيدة للخدمة والمناولة الآمنة لغاز التبريد، لما مجموعه 2,178 فنيا بموجب المرحلة، بما فيهم 295 أمرأة؛ [12:  اشتملت المعدات على محللات الغاز، ووحدات استراداد غاز التبريد، واسطوانات الغاز ومجموعات النيتروجين.] 

(3) برنامج الاسترداد وإعادة التدوير والاستصلاح: تعمل المراكز الثلاثة للاسترداد وإعادة التدوير والاستصلاح من الوجهة العملية (المعدات مركبة، والتدريب انتهى، والأنشطة جارية)، ولكن لم يتم بعد تشغيلها على النحو القانوني. وسيتم استكمال إدماجها التنظيمي الكامل فقط في عام 2026 بمجرد دخول النشرات ذات الصلة حيز التنفيذ. وتم إعداد النشرة التي تنظم الجمع المراعي للبيئة، والتخزين المؤقت، والنقل، واستصلاح الغازات المفلورة وتمت مناقشتها مع أصحاب المصلحة ذوي الصلة وتجري إجراءات الموافقة الوطنية المتبقية للتأييد النهائي قبل النشر الرسمي. ويتم شراء المعدات لتعزيز المراكز المهنية (بما في ذلك محددات التسرب، وأدوات الاسترداد، والموازين) من أجل توزيعها في عام 2026؛
(4) وحدة تنفيذ ورصد المشروع: التنسيق المستمر للأنشطة المتبقية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لضمان إستدامة إزالة المواد الهيدروكلوروفلوروكربونية بدعم من المستشارين الفنيين الوطنيين، ومستشار فني وتدقيقات.
63. حتى أبريل/نيسان 2026، من أصل المبلغ المعتمد للمرحلة الأولى وقدره 14,223,540 دولار أمريكي (14,120,090 دولار أمريكي لليونيدو و103,450 دولارا أمريكيا لليونيب) تم صرف 12,345,708 دولار أمريكي (12,242,258 دولار أمريكي لليونيدو و103,450 دولارا أمريكيا لليونيب) وأعيد مبلغ 318,150 دولارا أمريكيا، على النحو المبين في الجدول 8. وسيتم صثرف الرصيد وقدره 1,877,832 دولار أمريكي في عام 2026.
الجدول 8. التقرير المالي للمرحلة الأولى من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لتركيا (دولار أمريكي)
	المشروع/الشريحة
	اليونيدو
	اليونيب
	المجموع*
	معدل الصرف (%)

	مشروع جامع لرغاوى البوليوريتان والبوليسترين المسحوب بالضغط
	المعتمدة
	7,713,490
	0
	7,713,490
	96.2

	
	المنصرفة
	7,419,768
	0
	7,419,768
	

	الشريحة الأولى
	المعتمدة
	807,750
	103,450
	911,200
	99.7

	
	المنصرفة
	805,351
	103,450
	908,801
	

	الشريحة الثانية
	المعتمدة
	2,500,000
	0
	2,500,000
	98.5

	
	المنصرفة
	2,461,825
	0
	2,461,825
	

	الشريحة الثالثة
	المعتمدة
	1,598,850
	0
	1,598,850
	71.6

	
	المنصرفة
	1,144,850
	0
	1,144,850
	

	الشريحة الرابعة
	المعتمدة
	859,400
	0
	859,400
	44.5

	
	المنصرفة
	382,057
	0
	382,057
	

	الشريحة الخامسة
	المعتمدة
	640,600
	0
	640,600
	4.4

	
	المنصرفة
	28,407
	0
	28,407
	

	المجموع
	المعتمدة
	14,120,090
	103,450
	14,223,540
	86.8

	
	المنصرفة
	12,242,258
	103,450
	12,345,708
	


* أنجزت المشروعات الاستثمارية في شركات رغاوى البوليوريتان والبوليسترين المسحوب بالضغط في ديسمبر/كانون الأول 2019، مع إعادة الأرصدة غير المستخدمة البالغة 293,722 دولارا أمريكيا إلى الصندوق في الاجتماع الرابع والثمانين. وأعيدت الأرصدة غير المستخدمة البالغة 1,605 دولارا أمريكيا و794 دولارا أمريكيا و22,029 دولارا أمريكيا من الشريحتين الأولى والثانية إلى الصندوق في الاجتماعات التاسع والسبعين والحادي والثمانين والسابع والثمانين.
64. وأدرجت السياسة الجنسانية للصندوق المتعدد الأطراف في أنشطة خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية. وشاركت الفنيات من النساء في نظم التراخيص، وتضمنت المدارس المهنية مدربات من النساء، واشتركت النساء في  جلسات تدريب ضباط الجمارك ومختلف برامج التوعية. وأوصي بالاستراتيجيات لتعزيز مشاركة المرأة ورصدها في الأدوار الفنية والإدارية، وفي التعيين والتدريب. وعزز هذا من إستدامة الإنجازات عن طريق المشاركة الأوسع نطاقا في القوى العاملة.
تعليقات الأمانة
65. أحاطت الأمانة علما مع التقدير بأن تركيا حققت الإزالة الكاملة للمواد الهيدروكلوروفلوروكربونية في 1 يناير/كانون الثاني 2025، قبل خمس سنوات من الجدول الزمني لبروتوكول مونتريال، وأكد اليونيدو أن المرحلة الأولى من خطة إدارة المواد الهيدروكلوروفلوروكربونية سيتم إنجازها تشغيليا بحلول 31 ديسمبر/كانون الأول 2026، على النحو المحدد في الاتفاق والمشار إليه في الاجتماع السادس والتسعين للجنة التنفيذية. وتبلغ نسبة الصرف المالي للمرحلة ما نسبته 86.8 في المائة، ومن المتوقع بحلول ديسمبر/كانون الأول 2026، الانتهاء من مدفوعات المشروع النهائية المتعهد بها أساسا للمشتريات الجارية لأدوات الخدمة لفنيي التدريب، وأنشطة التدريب، ومعدات المختبرات والتدريب للمدارس المهنية.
66. وبناء على الطلب، أكد اليونيدو أنه اعتبارا من 1 يناير/كانون الثاني 2025، تم الحظر الكامل لاستخدام المواد الهيدروكلوروفلوروكربونية في تركيا، باستثناء التطبيقات الحرجة وللمختبرات، مما أزال وضعها في السوق بفاعلية. ولإستدامة الإزالة، أدخل قانون المناخ الصادر في 9 يوليه/تموز 2025 عقوبات إدارية كبيرة وغرامات مالية على الأفراد والهيئات المشتركة في الاستخدام غير القانوني، والإستيراد والاتجار غير القانوني أو وضع المواد المستنفذة للأوزون في السوق. والجهود المبذولة في التدريب والتوعية التي تستهدف ضباط الجمارك والفنيين وأصحاب المصلحة الآخرين تدعم اعتماد البدائل، بينما تضمن آليات التنسيق، بما فيها فريق الأوزون، المشاركة المستمرة لأصحاب المصلحة. وتقدم تلك التدابير معا أساسا قويا للإستدامة طويلة الأجل لإزالة المواد الهيدروكلوروفلوروكربونية في تركيا.
التوصية
67. قد ترغب اللجنة التنفيذية في الإحاطة علما بالتقرير المرحلي عن تنفيذ برنامج العمل المرتبط بالشريحة الخامسة والنهائية من المرحلة الأولى من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لتركيا، المقدم من اليونيدو والوارد في الوثيقة UNEP/OzL.Pro/ExCom/98/6.
باء.	تقرير متعلق باتفاقات خطط التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي
اتفاقات لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطط التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي
معلومات أساسية
68. في اجتماعها الخامس والتسعين، توصلت اللجنة التنفيذية إلى توافق في الآراء بشأن نموذج الاتفاق للمرحلة الأولى من خطط التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي.[footnoteRef:13] وسيتم تطبيق النموذج الموافق عليه على الخطط الموافق عليها سابقا المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي بين الاجتماعين الثاني والتسعين والخامس والتسعين. وفي اجتماعها السادس والتسعين، توصلت اللجنة التنفيذية إلى توافق في الآراء بشأن المبادئ التوجيهية لتمويل تكاليف الهيدروفلوروكربون،[footnoteRef:14] وقدمت وضوحا أكبر بشأن نقطة البداية، مما كان له أثر على مشاريع الاتفاقات. وتمت مناقشة المراجعات على مشاريع الاتفاقات في اجتماعات التنسيق فيما بين الوكالات،[footnoteRef:15] وفي اجتماعها السابع والتسعين، وافقت اللجنة التنفيذية على الاتفاقات لــ14 خطة من خطط التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي الموافق عليها بين الاجتماعات الثاني والتسعين والخامس والتسعين. [13:  المقرر 95/90 والمرفق السابع والخمسون من الوثيقة UNEP/OzL.Pro/ExCom/95/94.]  [14:  المقرر 96/50.]  [15:  المعقود في سبتمبر/أيلول 2925.] 

تعليقات الأمانة
69. لضمان الاتساق والدقة لمشروع الاتفاقات بين الحكومات المعنية واللجنة التنفيذية، أعدت الأمانه هذه الاتفاقات على أساس النموذج الموافق عليه والجداول الزمنية لالتزامات التخفيص التدريجي للمواد الهيدروفلوروكربونية وشرائح التمويل بموجب خطط التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي الموافق عليها بين الاجتماعات الثاني والتسعين والخامس والتسعين وأدخلت التعديلات التالية، عند الضرورة:
(1) الفقرة 2، وفقا للمقرر 96/50(ھ) للبلدان ذات الاستهلاك المنخفض باستهلاك في قطاع الخدمة فقط حيث لا تطبق نقطة البداية، وللبلدان بخلاف البلدان ذات الاستهلاك المنخفض حيث تغطي نقطة البداية جميع المواد الهيدروفلوروكربونية معا؛
(2) الفقرة 9، وفقا للمقرر 96/4 في حذف مهمة الرصد لكبير مسؤولي التقييم، لحذف الكلمات "الرصد و"؛
(3) التذييلان 1-ألف و2-ألف، ليعكسا تلك المقررات التي يمكن أن تختلف لبلدان الاستهلاك المنخفض مع الخدمة، وبلدان الاستهلاك المنخفض مع الخدمة والتصنيع، والبلدان بخلاف بلدان الاستهلاك المنخفض؛ و
(4) بالنسبة للبلدان بخلاف بلدان الاستهلاك المنخفض مع التصنيع، التذييل 1-ألف والصف 4 من التذييل 2-ألف، ليشملا نص مفاده "يحدد فيما بعد" إذ أن هذه سيتنهي إعدادها فقط بمجرد استكمال المناقشات حول نقطة البداية للتخفيضات المجمعة في الاستهلاك، وبالتالي الاستهلاك المتبقي المؤهل.
70. وترد في مقترحات المشروعات التي لديها طلبات للشرائح مقدمة في هذا الاجتماع، الاتفاقات لبلدين لديها خطط التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي المعتمدة سابقا (المكسيك ونيجيريا)، وترد الاتفاقات المتبقية لهذه الخطط المعتمدة سابقا في المرفقات من الثالث إلى السادس والثلاثين بالوثيقة الحالية. واستعرضت الوكالات المنفذة الرئيسية جميع الاتفاقات وقدمت مدخلات، تركز بصفة خاصة على التذييل 5-ألف ("مؤسسات الرصد والأدوار") للإشارة التفصيلية والموثوقة إلى كيفية رصد التقدم المحرز في تنفيذ الخطة، والإشارة إلى المنظمات والمؤسسات المسؤولة عن الأنشطة وإستدامة أهداف خفض الاستهلاك المحققة من خلال الاتفاقات. وأحاطت اللجنة التنفيذية علما مع التقدير بالجهود التي بذلتها جميع الوكالات المنفذة والثنائية في مراجعة الاتفاقات والتحقق من صحتها.
71. وبالتالي، تقدم الأمانة لموافقة اللجنة التنفيذية على 34 مشروعا لخطط التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي لبنن، وكمبوديا، وتشاد، والسلفادور، وإسواتيني، وغامبيا، وغانا، وغرينادا، والأردن، وقيرغيزستان، وجمهورية لاو الديمقراطية الشعبية، وليسوتو، وليبيريا، وملاوي، وماليزيا، والجبل الأسود، وموزامبيق، ومقدونيا الشمالية، و12 بلدا جزريا في المحيط الهادئ (جزر كوك، وكيريباتي، وجزر مارشال، وولايات ميكرونيزيا الموحدة، وناورو، ونيوي، وبالاو، وساموا، وجزر سليمان، وتونغا، وتوفالو وفانواتو)، وبنما، وباراغواي، وبيرو، ورواندا، وسانت لوسيا، والسنغال، وسيشيل، وسيراليون، وتوغو، وترينيداد وتوباغو، وتونس، وتركيا، وأوروغواي، وفييت نام وزمبابوي، على النحو الوارد في المرفقات من الثالث إلى السادس والثلاثين بالوثيقة الحالية.
التوصية
72. قد ترغب اللجنة التنفيذية في الموافقة على ما يلي:
(1) مشروع الاتفاق بين حكومة بنن واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الثالث بالتقرير الحالي؛
(2) مشروع الاتفاق بين حكومة كمبوديا واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الرابع بالتقرير الحالي؛
(3) مشروع الاتفاق بين حكومة تشاد واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الخامس بالتقرير الحالي؛
(4) مشروع الاتفاق بين حكومة السلفادور واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق السادس بالتقرير الحالي؛
(5) مشروع الاتفاق بين حكومة إسواتيني واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق السابع بالتقرير الحالي؛
(6) مشروع الاتفاق بين حكومة غامبيا واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الثامن بالتقرير الحالي؛
(7) مشروع الاتفاق بين حكومة غانا واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق التاسع بالتقرير الحالي؛
(8) مشروع الاتفاق بين حكومة غرينادا واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق العاشر بالتقرير الحالي؛
(9) مشروع الاتفاق بين حكومة الأردن واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الحادي عشر بالتقرير الحالي؛
(10) مشروع الاتفاق بين حكومة قيرغيزستان واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الثاني عشر بالتقرير الحالي؛
(11) مشروع الاتفاق بين حكومة جمهورية لاو الديمقراطية الشعبية واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الثالث عشر بالتقرير الحالي؛
(12) مشروع الاتفاق بين حكومة ليسوتو واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الرابع عشر بالتقرير الحالي؛
(13) مشروع الاتفاق بين حكومة ليبيريا واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الخامس عشر بالتقرير الحالي؛
(14) مشروع الاتفاق بين حكومة ملاوي واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الواردة في المرفق السادس عشر بالتقرير الحالي؛
(15) مشروع الاتفاق بين حكومة ماليزيا واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق السابع عشر بالتقرير الحالي؛
(16) مشروع الاتفاق بين حكومة الجبل الأسود واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الثامن عشر بالتقرير الحالي؛
(17) مشروع الاتفاق بين حكومة موزامبيق واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق التاسع عشر بالتقرير الحالي؛
(18) مشروع الاتفاق بين حكومة مقدونيا الشمالية واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق العشرين بالتقرير الحالي؛
(19) مشروع الاتفاق بين حكومات البلدان الجزرية في المحيط الهادئ واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الحادي والعشرين بالتقرير الحالي؛
(20) مشروع الاتفاق بين حكومة بنما واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الثاني والعشرين بالتقرير الحالي؛
(21) مشروع الاتفاق بين حكومة باراغواي واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الثالث والعشرين بالتقرير الحالي؛
(22) مشروع الاتفاق بين حكومة بيرو واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الرابع والعشرين بالتقرير الحالي؛
(23) مشروع الاتفاق بين حكومة رواندا واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الخامس والعشرين بالتقرير الحالي؛
(24) مشروع الاتفاق بين حكومة سانت لوسيا واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق السادس والعشرين بالتقرير الحالي؛
(25) مشروع الاتفاق بين حكومة السنغال واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق السابع والعشرين بالتقرير الحالي؛
(26) مشروع الاتفاق بين حكومة سيشيل واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الثامن والعشرين بالتقرير الحالي؛
(29) مشروع الاتفاق بين حكومة سيراليون واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق التاسع والعشرين بالتقرير الحالي؛
(30) مشروع الاتفاق بين حكومة توغو واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الثلاثين بالتقرير الحالي؛
(33) مشروع الاتفاق بين حكومة ترينيداد وتوباغو واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الحادي والثلاثين بالتقرير الحالي؛
(36) مشروع الاتفاق بين حكومة تونس واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الثاني والثلاثين بالتقرير الحالي؛
(ه ه)	مشروع الاتفاق بين حكومة تركيا واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الثالث والثلاثين بالتقرير الحالي؛
(وو)	مشروع الاتفاق بين حكومة أوروغواي واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الرابع والثلاثين بالتقرير الحالي؛
(زز)	مشروع الاتفاق بين حكومة فييت نام واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق الخامس والثلاثين بالتقرير الحالي؛
(34) مشروع الاتفاق بين حكومة زمبابوي واللجنة التنفيذية لخفض استهلاك المواد الهيدروفلوروكربونية وفقا للمرحلة الأولى من خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي، الوارد في المرفق السادس والثلاثين بالتقرير الحالي.
جيم.	التقرير المتعلق بالأنشطة الإضافية للحفاظ على كفاءة الطاقة في قطاع خدمة التبريد (المقرر 89/6)
ملديف: الأنشطة الإضافية للحفاظ على كفاءة الطاقة في قطاع خدمة التبريد بموجب المقرر 89/6(ب) (التقرير المرحلي النهائي) (اليونيب)
معلومات أساسية
73. في الاجتماع الحادي والتسعين، وافقت اللجنة التنفيذية على مشروع الأنشطة الإضافية لإدخال بدائل للمواد الهيدروكلوروفلوروكربونية منخفضة أو معدومة إمكانية الاحترار العالمي، وللحفاظ على كفاءة استخدام الطاقة في قطاع خدمة التبريد في ملديف، بمبلغ 100,000 دولارا أمريكيا، بالإضافة إلى تكاليف دعم الوكالة البالغة 13,000 دولار أمريكي، لليونيب.[footnoteRef:16] وتم تمديد تاريخ إنجاز المشروع إلى 30 يونيه/حزيران 2025 في الاجتماع الثالث والتسعين.[footnoteRef:17] وفي الاجتماع الخامس والتسعين، وكجزء من التقرير المرحلي السنوي عن المشروع،[footnoteRef:18] أدرجت خطة عمل محدثة لتنفيذ أنشطة المشروع بأحدث تواريخ التنفيذ المتوقعة حتى مارس/آذار 2025. [16:  المقرر 91/60(أ).]  [17:  المقرر 93/20(ب).]  [18:  الفقرات 72-80 من الوثيقة UNEP/OzL.Pro/ExCom/95/20.] 

74. وفي الاجتماع السادس والتسعين، وافقت اللجنة التنفيذية، على أساس استثنائي، وعلى أساس الفهم بعدم الموافقة على تمديد آخر، على تمديد تاريخ إنجاز المشروع حتى 30 يونيه/حزيران 2026، وطلبت من حكومة ملديف واليونيب الاستمرار في تقديم التقارير المرحلية عن تنفيذ المشروع، على أساس سنوي حتى إنجازه وتقديم تقرير إنجاز المشروع إلى ثاني اجتماع للجنة التنفيذية في عام 2026 (المقرر 96/14(ب) و(ج)).
75. ووفقا للمقرر96/14 (ج)، قدم اليونيب، بالنيابة عن حكومة ملديف تقريرا مرحليا إلى الاجتماع الحالي.
التقرير المرحلي
76. ويتمثل الهدف من مشروع كفاءة الطاقة في جعل برنامج التوسيم الطوعي لكفاءة الطاقة للأجهزة والمعدات الموجود ويسمى Hakathari إجباريا وهو يغطي معدات معينة، بما في ذلك تكييفات الهواء[footnoteRef:19] والمبردات المنزلية. وتشمل مخصصات التوسيم الإجبارية بموجب برنامج Hakathari معلومات عن غاز التبريد وإمكانيته لاستنفاد الأوزون وإمكانيته للاحترار العالمي. وحدد البرنامج أيضا المتطلبات الدنيا من المؤهلات للأجهزة المختبرة[footnoteRef:20] لتكون مؤهلة لملصقات كفاة الطاقة مع ضمان أن متطلبات المؤهلات هذه تستوفى المعايير الدنيا لأداء الطاقة الموجودة بالفعل في البلد. [19:  المرحلة الواحدة، وتكييفات الهواء المجزأة والأحادية النوع لكل من السرعة الثابتة والسرعة المتغيرة، حتى قدرات مصنفة تبلغ 24,226 وحدة حرارية بريطانية في الساعة (تعادل 7.1 كيلو واط).]  [20:  يجري الاختبار في مختبر معتمد من سلطة معترف بها وهي الموقعة على ترتيبات الاعتراف المتبادل مثل التعاون الدولي في اعتماد المختبرات/التعاون لاعتماد المختبرات في آسيا والمحيط الهادئ حسب معايير الاختبار المعينة أو بروتوكولات مختبرات الاختبار (باستعمال ISO/IEC 17025).] 

77. واشتمل المشروع على أنشطة لتحسين التنسيق والتعاون بين أصحاب المصلحة، وسلطات الطاقة ذات الصلة، ووحدة الأوزون الوطنية من خلال بناء قدرات الموظفين الرئيسيين وأصحاب المصلحة لضمان النظر المستدام لغاز التبريد في برنامج التوسيم، وإرشاد إعداد نهج الاستعراض لنوع غاز التبريد وإمكانية الاحترار العالمي، وفهم التحديات التنظيمية المتعلقة بمعلومات توسيم غازات التبريد منخفضة إمكانية الاحترار العالمي، وزيادة التوعية ذات الصلة ببرنامج التوسيم مع التركيز على زيادة الطلب على تكييفات الهواء والثلاجات التي تعمل بغازات تبريد بإمكانية منخفضة أو معدومة للاحترار العالمي بين جميع ملصقات منتجات كفاءة الطاقة؛ ودراسة لسلوك المستهلك لتقييم أثر المشروع.
78. وحتى أبريل/نيسان 2026، تم إنجاز الأنشطة التالية: جلسات تدريب/معلومات للمستوردين وضباط الجمارك ووكالات المرافق، ومصممي المباني، ومطوري المباني وشركات البناء؛ والانتهاء من إعداد معايير التشغيل القياسية وإعداد نص لإيلاء الأولوية للمنتجات الممتثلة Hakathari في مشتريات الحكومة التي سيتم استكمالها في يونيه/حزيران 2026؛ وإعداد مواد توعية وتقييم الأثر للمستخدمين النهائيين، في انتظار النشر النهائي في يونيه/حزيران 2026 فضلا عن الاستقصاء لدراسة سلوك المستهلك، والذي سيتم الانتهاء من التقرير بشأنه بحلول يونيه/حزيران 2026.
79. ومن أصل المبلغ 100,000 دولارا أمريكيا المعتمد للمشروع، تم صرف 49,560 دولارا أمريكيا (49.6 في المائة). والرصيد الملتزم به وقدره 50,440 سيتم صرفه بحلول 30 يونيه/حزيران 2026. ويقدم الجدول 9 تحديثا عن الأنشطة منذ تقديم التقرير المرحلي السابق.
الجدول 9. تحديث لتنفيذ الأنشطة للحفاظ على كفاءة الطاقة في قطاع خدمة التبريد في ملديف
	النشاط
	المخرجات/الهدف
	الأموال المعتمدة (دولار أمريكي)
	الحالة
	تواريخ الإنجاز المتوقعة

	بناء قدرات الموظفين وأصحاب المصلحة

	التنسيق والتعاون مع الوكالات ذات الصلة من خلال التدريب على بناء القدرات
	جولة دراسية، تقرير وتوصيات
	35,000
	نظمت وحدة الأوزون الوطنية جولة دراسية إلى ماليزيا في عام 2025، بما في ذلك زيارات لإدارة البيئة ولجنة الطاقة ضمن وزارة تحويل الطاقة وتحويل المياه. وأجريت أيضا زيارات لمختبر SIRIM لاختبار كفاءة الطاقة و Iwatani Malaysia Sdn. Bhd. ومن المتوقع الانتهاء في يونيه/حزيران 2026 من إعداد إجراءات التشغيل القياسية المحدثة، بما في ذلك القسم الجديد لاختبار التحقق، إستنادا إلى نتائج الجولة الدراسية فضلا عن إعداد/الموافقة على نص لإيلاء الأولوية للمنتجات الممتثلة Hakathari في مشتريات الحكومة.
	يونيه/حزيران 2026

	جلسات تدريب/معلومات للمستوردين وضباط الجمارك، ووكالات المرافق، ومصممي المباني، ومطوري المباني وشركات البناء
	خمس حلقات عمل/دورات معلومات لما مجموعه 140 مشاركا
	13,000
	أجريت جلستان تدريب للمستوردين، وجلستان تدريب لسلطات الجمارك والتجارة، وجلستان توعية وجلسة معلومات لما مجموعه 142 مشاركا [footnoteRef:21] (بما فيهم 78 أمرأة) [21:  بما فيهم المستوردين، وضباط الجمارك، ووكالات المرافق، ومصممي المباني، ومطوري المباني، وشركات البناء.] 

	استكملت

	[bookmark: _Hlk115084759]التوعية وتقييم الأثر

	إعداد ونقل مواد التوعية
	إصدار ونشر خمسة شرائط توعية بالفيديو ورسوم بيانية
	37,000
	تم التوقيع على العقد ولوائح القصص لشرائط الفيديو؛ ومن المتوقع الانتهاء من نشر مواد التوعية في يونيه/حزيران 2026.
	يونيه/حزيران 2026

	دراسة عن سلوك المستهلك
	إعدت ونفذت دراسة واحدة عن سلوك المستهلك
	15,000
	أعدت الاختصاصات واستبيان للدراسة، وتم التعاقد مع الشركة، واستكمل الاستقصاء. ويقوم المستشار حالبا بعملية صياغة التقرير.
	يونيه/حزيران 2026

	المجموع
	100,000
	
	



تعليقات الأمانة
80. أحاطت الأمانة علما بالتقدم المحرز في تنفيذ المشروع، وبصفة خصة إنجاز جميع أنشطة بناء القدرات، بما في ذلك الجولة الدراسبة إلى ماليزيا في عام 2025، وجلسات التدريب للمستوردين وضباط الجمارك، والتعديلات على وثيقة برنامج Hakathari، مع ملاحظة أن هدف التدريب قد تم تجاوزه (142 مشاركا مدربين مقابل 140). وأكد اليونيب أن جميع الأنشطة المتبقية سيتم إنجازها بحلول يونيه/حزيران 2026 وسيتم تقديم تقرير إنجاز المشروع وفقا للمقرر 96/14(ج).
التوصية
81. قد ترغب اللجنة التنفيذية في الإحاطة علما بالتقرير المرحلي النهائي عن المشروع بشأن الأنشطة الإضافية لإدخال بدائل للمواد الهيدروكلوروفلوروكربونية بإمكانية منخفضة أو معدومة للاحترار العالمي وبشأن الحفاظ على كفاءة الطاقة في قطاع خدمة التبريد في ملديف، على النحو المقدم من اليونيب والوارد في الوثيقة UNEP/OzL.Pro/ExCom/98/6.
دال.	تقرير متعلق بمشروع تجريبي للحفاظ على كفاءة الطاقة و/أو تعزيزها لتكنولوجيات ومعدات الاستبدال في سياق التخفيض التدريجي للمواد الهيدروفلوروكربونية (المقرر 91/65)
الكاميرون: مشروع تجريبي للحفاظ على كفاءة الطاقة و/أو تعزيزها لتكنولوجيات ومعدات الاستبدال في سياق التخفيض التدريجي للمواد الهيدروفلوروكربونية (أنشطة غير استثمارية) (طلب لتمديد تاريخ إنجاز المشروع) (اليونيدو)
معلومات أساسية
82. في اجتماعها الرابع والتسعين، وافقت اللجنة التنفيذية على المشروع التجريبي للحفاظ على كفاءةء الطاقة و/أو تعزيزها لتكنولوجيات ومعدات الاستبدال في سياق التخفيض التدريجي للمواد الهيدروفلوروكربونية (أنشطة غير استثمارية) للكاميرون، على أن ينفذه اليونيدو، مع ملاحظة أن المشروع سيتم إنجازه تشغيليا في موعد أقصاه 30 يونيه/حزيران 2026 وسيتم تقديم تقرير مفصل عن المشروع إلى اللجنة التنفيذية في غضون ستة أشهر من تاريخ إنجاز المشروع (المقرر 95/64).
الطلب للتمديد
83. مرت الكاميرون بتغييرات وزارية عديدة بين نهاية عام 2024 وبعد الانتخابات الرئاسية في عام 2025. ونتيجة لذلك، أصبحت الموافقات المحصول عليها سابقا للشروع في المشروع والبدء في جمع البيانات غير صالحة. وحصلت وحدة الأوزون الوطنية على التصريح اللازم للتجديد في نهاية فبراير/شباط 2026 وبعدها بدأ جمع البيانات والمعلومات، وعقدت حلقة عمل للبدء في مارس/آذار 2026. والترتيبات المؤسسية مستقرة الآن، مما يمكن من الإنجاز الفعال وفي الوقت المناسب لأنشطة المشروع المتبقية بحلول نهاية عام 2026 وتقديم التقرير عن المشروع في عام 2027.
84. وفي ضوء هذه التأخيرات وللسماح باستكمال أنشطة المشروع، طلب اليونيدو، بالنيابة عن حكومة الكاميرون، تمديدا لفترة تنفيذ المشروع حتى 31 ديسمبر/كانون الأول 2026.
تعليقات الأمانة
85. تعترف الأمانة بالتحديات التي واجهتها حكومة الكاميروع. وبناء على طلب من الأمانة، شرح اليونيدو أنه لم يتم الإبلاغ عن التأخيرات كجزء من تقريره المرحلي السنوي والمالي، إذ أنها حدثت خلال النصف الثاني من عام 2025 كنتيجة للتغييرات الوزارية. وأكد اليونيدو كذلك أن الوضع مستقرا الآن وأن المشروع يمكن إنجازه تشغيليا بحلول ديسمبر/كانون الأول 2026.
التوصية
86. قد ترغب اللجنة التنفيذية فيما يلي:
(1) الإحاطة علما بالطلب لتمديد المشروع التجريبي للحفاظ على كفاءة الطاقة و/أو تعزيزها لتكنولوجيات ومعدات الاستبدال في سياق التخفيض التدريجي للمواد الهيدروفلوروكربونية (أنشطة غير استثمارية) في الكاميرون، على النحو المقدم من اليونيدو والوارد في الوثيقة UNEP/OzL.Pro/ExCom/98/6؛
(2) الموافقة، على أساس استثنائي، وعلى أساس الفهم بعدم الموافقة على تمديد آخر، على التمديد حتى 31 ديسمبر/كانون الأول 2026 لتاريخ إنجاز المشروع المشار إليه في الفقرة الفرعية (أ) أعلاه.
هاء. 	تقرير متعلق بإعداد مشروع لتعزيز كفاءة الطاقة في سياق التخفيض التدريجي للمواد الهيدروفلوروكربونية في قطاع تصنيع التبريد وتكييف الهواء (المقرر 94/60)
تركيا: حالة إعداد مشروع لتعزيز كفاء الطاقة وتحويل 29 شركة تصنيع التبريد وتكييف الهواء من استخدام الهيدروفلوروكربون إلى تكنولوجيا منخفضة إمكانية الاحترار العالمي (اليونيدو)
معلومات أساسية
87. عند الموافقة على خطة التنفيذ المتعلقة بالمواد الهيدروفلوروكربونية بموجب تعديل كيغالي لتركيا في الاجتماع الخامس والتسعين، أحاطت اللجنة التنفيذية علما بعدة أمور من بينها أنه خلال تنفيذ المرحلة الأولى من هذه الخطة وفي موعد أقصاه الاجتماع الثامن والتسعين، سيسمح لحكومة تركيا، على أساس استثنائي، بتقديم مشروعات استثمارية في قطاع التبريد وتكييف الهواء وقطاع الرغاوى لتحقيق تخفيضات إضافية في استهلاك المواد الهيدروفلوروكربونية (المقرر 95/74(ب)(2)). وفي نفس الاجتماع، وافقت اللجنة التنفيذية على إعداد مشروع لتعزيز كفاءة الطاقة وللتحول من استخدام المواد الهيدروفلوروكربونية إلى تكنولوجيا منخفضة إمكانية الاحترار العالمي لــ29 شركة تصنيع للتبريد وتكييف الهواء في تركيا، بمبلغ 220,000 دولارا أمريكيا، بالإضافة إلى تكاليف دعم الوكالة البالغة 15,400 دولارا أمريكيا لليونيدو (الكقرر 95/38).
حالة الإعداد
88. أبلغ اليونيدو الأمانة بحدوث تقدم جيد في إعداد المشروع ولكن لا يمكن تقديمه إلى الاجتماع الثامن والتسعين إذ ما زالت هناك أنشطة ينبغي استكمالها. وبالتالي سيقدم المشروع إلى الاجتماع التاسع والتسعين. وأشار التقرير المرحلي المفصل المقدم من اليونيدو إلى تعيين الخبراء ذوي الصلة واستكمال سلسلة من أنشطة مشاركة أصحاب المصلحة لإدخال المشروع ذو كفاءة الطاقة إلى 100 من أصحاب المصلحة في القطاع. وبالتوازي، أجريت أنشطة التوعية واجتماعات المعلومات على الإنترنت لتقديم الأهداف والمدى والمتطلبات للمشروع، فضلا عن إطاره ومعايير الأهلية والمعلومات التقنية المتوقعة من الشركات المشتركة. ويكمل هذا حلقة عمل على الإنترنت بشأن نافذة كفاءة الطاقة، والخيارات التقنية، وحسابات تفصيلية عن كفاءة الطاقة والخطوات المطلوبة لإعداد مقترحات المشروع فضلا عن المشاركة المباشرة مع الشركات والمشاركة في المعارض الصناعية والأحداث التي تركز على قطاع التبريد وتكييف الهواء التجاري.
89. وبدأت دعوة لتقديم الطلبات من خلال الموقع الشبكي لوحدة الأوزون الوطنية في تركيا. وبعد تقديم النقترحات، أعدت نماذج جمع البيانات بواسطة خبراء دوليين وتم تبادلها مع الشركات المتقدمة لجمع بيانات تقنية وتشغيلية مفصلة. وقدم دعم إضافي من خلال حلقة عمل في اسطنبول واجتماعات مشاورات فردية مع الشركات المختارة. واستبعدت بعض الشركات المقدمة للطلبات نتيجة لعدم التوافق مع أهداف المشروع أو بسبب الانسحاب الطوعي. وفي المرحلة الحالية، تستمر سبع شركات لها ما مجموعه 10 مقترحات مشروعات في جمع البيانات. ومن المبلغ المعتمد وقدره 220,000 دولارا أمريكيا، تم صرف 117,714 دولارا أمريكيا، ومن المتوقع تقديم المشروع إلى الاجتماع التاسع والتسعين.
تعليقات الأمانة
90. أحاطت الأمانة علما مع التقدير بالعمل المبذول في إعداد المشروع حتى الآن، والتأكيد من اليونيدو بأن المقترح سيقدم إلى الاجتماع التاسع والتسعين.
التوصية
91. قد ترغب اللجنة التنفيذية في الأحاطة علما بما يلي:
(1) التقرير المرحلي عن إعداد مشروع لتعزيز كفاءة الطاقة وتحويل 29 شركة تصنيع التبريد وتكييف الهواء من استخدام المواد الهيدروفلوروكربونية إلى تكنولوجيا منخفضة إمكانية الاحترار العالمي في تركيا، المقدم من اليونيدو والوارد في الوثيقة UNEP/OzL.Pro/ExCom/98/6؛
(2) أن المشروع المشار إليه في الفقرة الفرعية (أ) أعلاه سيقدمه اليونيدو إلى الاجتماع التاسع والتسعين.
واو. 	تقرير متعلق بإعداد جرد وطني لبنوك المواد المستخدمة أو غير المرغوبة الخاضعة للرقابة وخطة لجمع مثل هذه المواد ونقلها والتخلص منها (المقرر 91/66) 
موريشيوس: إعداد جرد وطني لبنوك نفايات المواد الخاضعة للرقابة وإعداد خطة وطنية لإدارة هذه المواد (المقرر 91/66) (طلب لتمديد تاريخ إنجاز المشروع)
معلومات أساسية
92. في الاجتماع الرابع والتسعين، وافقت اللجنة التنفيذية على إعداد جرد وطني لبنوك نفايات المواد الخاضعة للرقابة وإعداد خطة وطنية لإدارة هذه المواد (المقرر 91/66) لموريشيوس، على أن تنفذه حكومة ألمانيا (المقرر 94/20).[footnoteRef:22] ويتماشى تاريخ الإنجاز التشغيلي مع المقرر وهو يونيه/حزيران 2026.[footnoteRef:23] [22:  المقرر بشأن الموافقة الشمولية.]  [23:  أربعة وعشرون شهرا من تاريخ الموافقة على المشروع.] 

الطلب للتمديد
93. أفادت حكومة ألمانيا بأن عملية تعيين مستشار وطني لإعداد الجرد الوطني للبنوك وإعداد خطة عمل وطنية قد تأخرت نتيجة لتحديات إدارية. وحتى ديسمبر/كانون الأول 2025، بدا أن التعيين بحلول يناير/كانون الثاني 2026 كان ممكنا؛ غير أنه لم يستكمل حسب المخطط نتيجة لتغير في نظام تكنولوجيا المعلومات في الوكالة الثنائية، الذي أثر على العمليات الإدارية والمالية، فضلا عن عدم وجود تأكيد للامتثال لظروف معينة من جانب مقدم العرض. ونتيجة لذلك، وحتى مايو/أيار 2026، ظلت عملية التعيين جارية؛ ولم يتم صرف أي أموال، وما زالت أنشطة المشروع في مرحلة التخطيط. وأشارت حكومة ألمانيا إلى أنه بمجرد تعيين المستشار، من المتوقع أن يتم استكمال أنشطة الاستقصاء والتحليل والإبلاغ على نحو السرعة، مع توقع النتائج المؤقتة بحلول ديسمبر/كانون الأول 2026.
94. وفي ضوء ما ذكر أعلاه، طلبت حكومة ألمانيا، بالنيابة عن حكومة موريشيوس، تمديدا لفترة تنفيذ المشروع حتى 30 يونيه/حزيران 2027.
تعليقات الأمانة
95. تعترف الأمانة بالتحديات المواجهة في تعيين مستشار لأنشطة الاستقصاء وتعتبر أنه إستنادا إلى المعلومات المقدمة، فإن التمديد المطلوب سييسر إنجاز المشروع.
التوصية
96. قد ترغب اللجنة التنفيذية فيما يلي:
(1) الإحاطة علما بالطلب لتمديد إعداد جرد وطني لبنوك نفايات المواد الخاضعة للرقابة وإعداد خطة وطنية لإدارة هذه المواد (المقرر 91/66) في موريشيوس، على النحو المقدم من حكومة ألمانيا والوارد في الوثيقة UNEP/OzL.Pro/ExCom/98/6؛
(2) الموافقة، على أساس استثنائي، وعلى أساس الفهم بعدم الموافقة على أي تمديد آخر، على التمديد حتى 30 يونيه/حزيران 2027 لتاريخ إنجاز المشروع المشار إليه في الفقرة الفرعية (أ) أعلاه.
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إن وثائق ما قبل دورات اللجنة التنفيذية للصندوق المتعدد الأطراف لتنفيذ بروتوكول مونتريال 
قد تصدر دون إخلال بأي قرار تتخذه اللجنة التنفيذية بعد صدورها.
28
27
المرفق الأول

المشاريع المصنفة على أنّها "سجّلت بعض التقدم" والتي يوصى بمواصلة رصدها

	البلد
	رمز المشروع
	عنوان المشروع
	الوكالة

	جمهورية الكونغو الديمقراطية 
	DRC/PHA/88/INV/49
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية، الشريحة الأولى)
	اليوئنديبي

	جمهورية إيران الإسلامية
	IRA/PHA/92/INV/267
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية، الشريحة الرابعة) (قطاع الرغاوى)
	اليوئنديبي

	جمهورية إيران الإسلامية
	IRA/PHA/86/INV/245
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية، الشريحة الثالثة) (قطاع الرغاوى)
	اليوئنديبي

	جمهورية إيران الإسلامية
	IRA/PHA/86/TAS/248
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية، الشريحة الثالثة) (قطاع خدمة التبريد)
	اليونيب

	جمهورية إيران الإسلامية
	IRA/PHA/92/INV/266
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية، الشريحة الرابعة) (قطاع التبريد التجاري)
	اليوئنديبي

	الكويت
	KUW/PHA/88/TAS/42
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية، الشريحة الأولى)
	اليونيب

	قطر
	QAT/PHA/88/INV/26
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية، الشريحة الأولى)
	اليونيدو

	الجمهورية العربية السورية
	SYR/PHA/86/INV/107
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الأولى، الشريحة الأولى)
	اليونيدو

	الجمهورية العربية السورية
	SYR/PHA/86/TAS/106
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الأولى، الشريحة الأولى)
	اليونيب

	الجمهورية العربية السورية
	SYR/PHA/91/INV/112
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الأولى، الشريحة الثانية) (قطاع رغاوى البوليوريتان)
	اليونيدو

	الجمهورية العربية السورية
	SYR/PHA/91/TAS/114
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الأولى، الشريحة الثانية)
	اليونيب
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المرفق الثاني

المشاريع التي طلب بشأنها تقارير حالة إضافية
	البلد
	رمز المشروع
	عنوان المشروع
	الوكالة
	التوصية إلى الاجتماع الثامن والتسعين

	ميانمار
	MYA/SEV/84/INS/22
	تمديد مشروع التعزيز المؤسسي (المرحلة الخامسة: 7/2020-6/2022)
	اليونيب
	أن تطلب إلى اليونيب تقديم تقرير الحالة إلى الاجتماع التاسع والتسعين بشأن استئناف الأنشطة

	نيبال
	NEP/PHA/86/TAS/43
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية، الشريحة الأولى)

	اليونيب
	أن تطلب إلى اليونيب تقديم تقرير الحالة إلى الاجتماع التاسع والتسعين بشأن حالة تنفيذ الأنشطة وتحويل الأموال إلى الحكومة

	سيشيل
	SEY/EEF/93/TAS/32
	خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الأولى) (أنشطة إضافية للحفاظ على كفاءة الطاقة في قطاع الخدمة بموجب المقرر 89/6(ب)
	ألمانيا
	أن تطلب إلى حكومة ألمانيا تقديم تقرير الحالة إلى الاجتماع التاسع والتسعين بشأن التقدم المحرز في التنفيذ

	اليمن
	YEM/SEV/93/INS/47
	تمديد مشروع التعزيز المؤسسي (المرحلة التاسعة: 1/2024 -12/2026)
	اليونيب
	أن تطلب إلى اليونيب تقديم تقرير الحالة إلى الاجتماع التاسع والتسعين بشأن التقدم المحرز في التنفيذ
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Annex III
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF BENIN
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. [bookmark: _Hlk146706470][bookmark: _Hlk128135089][bookmark: _Hlk130660551]This Agreement represents the understanding of the Government of Benin (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 1,687,551 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
[bookmark: _Hlk130659199]The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
[bookmark: _Hlk128740135]The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
[bookmark: _Hlk130666479]Flexibility in the reallocation of funds
[bookmark: _Hlk130666540]The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(g) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
[bookmark: _Hlk131268859]Non-compliance with the Targets in the Agreement
[bookmark: _Hlk131270712]Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
[bookmark: _Hlk130668684]The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	[bookmark: _Hlk131268561]Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	1,875,057
	1,875,057
	1,875,057
	1,875,057
	1,875,057
	1,687,551
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	1,875,057
	1,875,057
	1,875,057
	1,875,057
	1,875,057
	1,687,551
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	117,500
	0
	0
	102,500
	0
	0
	220,000

	2.2
	Support costs for Lead IA (US $)
	15,275
	0
	0
	13,325
	0
	0
	28,600

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	60,000
	0
	0
	80,000
	0
	0
	140,000

	2.4
	Support costs for Cooperating IA (US $)
	7,800
	0
	0
	10,400
	0
	0
	18,200

	3.1
	Total agreed funding (US $)
	177,500
	0
	0
	182,500
	0
	0
	360,000

	3.2
	Total support costs (US $)
	23,075
	0
	0
	23,725
	0
	0
	46,800

	3.3
	Total agreed costs (US $)
	200,575
	0
	0
	206,225
	0
	0
	406,800


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
[bookmark: _Hlk130669478]APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase-down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase-in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate-relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit, under the Ministry of Living Environment and Sustainable Development, is responsible for monitoring the progress of implementation of activities in the Plan.
Monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of training and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA.
The Ministry of Living Environment and Sustainable Development will be responsible for the sustainability of consumption reduction targets achieved through the Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2-A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex IV
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF CAMBODIA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2029)
Purpose
1. This Agreement represents the understanding of the Government of Cambodia (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 1,137,038 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
10. The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
11. Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
12. The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
13. The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
14. The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
15. The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(a) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(b) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(c) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
16. Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
17. The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNDP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
18. The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6-A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
19. Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
20. The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
21. The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
22. The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
23. All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
24. This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	n/a
	1,263,376
	1,263,376
	1,263,376
	1,263,376
	1,263,376
	1,137,038
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	n/a
	1,263,376
	1,263,376
	1,263,376
	1,263,376
	1,263,376
	1,137,038
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	126,300
	0
	0
	108,000
	0
	0
	44,500
	278,800

	2.2
	Support costs for Lead IA (US $)
	16,419
	0
	0
	14,040
	0
	0
	5,785
	36,244

	2.3
	Cooperating IA (UNDP) agreed funding (US $)
	123,810
	0
	0
	38,075
	0
	0
	0
	161,885

	2.4
	Support costs for Cooperating IA (US $)
	11,143
	0
	0
	3,427
	0
	0
	0
	14,570

	3.1
	Total agreed funding (US $)
	250,110
	0
	0
	146,075
	0
	0
	44,500
	440,685

	3.2
	Total support costs (US $)
	27,562
	0
	0
	17,467
	0
	0
	5,785
	50,814

	3.3
	Total agreed costs (US $)
	277,672
	0
	0
	163,542
	0
	0
	50,285
	491,499

	4.1.1
	Deductions of HFCs agreed under this Agreement (CO2-eq tonnes)
	126,338

	4.1.2
	Deductions of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU) under the Ministry of Environment (MoE) will be responsible for the overall monitoring of all activities under the Plan, as well as the planning, coordination, and daily work of project implementation.
28. Monitoring will be conducted to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of training and other expected outcomes; and HFC consumption verification. Stakeholders include industries, technical institutions, non-governmental organizations, the Government and technical experts.
29. The General Department of Customs and Excise (GDCE), in collaboration with the NOU, will carry out annual monitoring, reporting, verification and enforcement activities related to HFC consumption in the Country. The NOU is responsible for determining and allocating HFC quota to eligible importers, and for issuing the import and export permits based on the allocated quota. The GDCE will control and monitor the import and export of HFCs at the points of entry. The NOU will liaise with HFC importers and exporters to obtain the data necessary for the reconciliation of statistics on a periodical basis.
30. The MoE will be responsible for the sustainability of consumption reduction targets achieved through this Agreement. The NOU will undertake surveys to gauge the situation of HFC phase-down, potential illegal imports, and the penetration of alternative technologies in the country in different subsectors to examine the achievements of HFC phase-down at a national level.
31. The NOU will undertake regular inspections at any mobile air-conditioning training centre that has received training equipment under the Plan to monitor the condition of this equipment.
32. The NOU will monitor the implementation of capacity-building activities for trainers, assessors and technicians across sectors; activities to build the capacity of technicians to maintain/enhance energy efficiency in the servicing sector; training for customs and enforcement officers; and training for importers and customs brokers.
33. The NOU will submit annual reports on the status of implementation to the Lead IA and the Cooperating IA to monitor the implementation progress of the Plan.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
35. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. [bookmark: _Hlk131269422]In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $6.98 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex V
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF CHAD
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Chad (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 3,216,251 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
39. The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
40. Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
41. The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
42. The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
43. The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
44. The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(a) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(b) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(c) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
45. Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
46. The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
47. The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
48. Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
49. The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
50. The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
51. The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
52. All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
53. This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	3,573,612
	3,573,612
	3,573,612
	3,573,612
	3,573,612
	3,216,251
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	3,573,612
	3,573,612
	3,573,612
	3,573,612
	3,573,612
	3,216,251
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	141,000
	0
	0
	94,000
	0
	0
	235,000

	2.2
	Support costs for Lead IA (US $)
	18,330
	0
	0
	12,220
	0
	0
	30,550

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	75,000
	0
	0
	50,000
	0
	0
	125,000

	2.4
	Support costs for Cooperating IA (US $)
	9,750
	0
	0
	6,500
	0
	0
	16,250

	3.1
	Total agreed funding (US $)
	216,000
	0
	0
	144,000
	0
	0
	360,000

	3.2
	Total support costs (US $)
	28,080
	0
	0
	18,720
	0
	0
	46,800

	3.3
	Total agreed costs (US $)
	244,080
	0
	0
	162,720
	0
	0
	406,800


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit, under the Ministry of Environment, Fisheries and Sustainable Development, is responsible for monitoring the progress of implementation of the Plan’s activities in the Country.
57. Monitoring will be conducted to ensure the efficient and effective implementation of the Plan; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of training and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA.
58. The Ministry of Environment, Fisheries and Sustainable Development will be responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
60. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex VI
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF EL SALVADOR
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of El Salvador (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 830,126 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
64. The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
65. Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
66. The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
67. The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
68. The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
69. The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(a) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(b) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(c) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
70. Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
71. The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or the evaluation programme of the Lead IA taking part in this Agreement.
72. The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
73. Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
74. The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
75. The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
76. The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
77. All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
78. This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	922,362
	922,362
	922,362
	922,362
	922,362
	830,126
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	922,362
	922,362
	922,362
	922,362
	922,362
	830,126
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	180,000
	0
	0
	144,000
	0
	36,000
	360,000

	2.2
	Support costs for Lead IA (US $)
	23,400
	0
	0
	18,720
	0
	4,680
	46,800

	3.1
	Total agreed funding (US $)
	180,000
	0
	0
	144,000
	0
	36,000
	360,000

	3.2
	Total support costs (US $)
	23,400
	0
	0
	18,720
	0
	4,680
	46,800

	3.3
	Total agreed costs (US $)
	203,400
	0
	0
	162,720
	0
	40,680
	406,800


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Ministry of Environment and Natural Resources (MARN), will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA.
82. The MARN is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
83. The project monitoring unit of the Plan will assist the NOU in the following activities:
(a) Follow up on activities described in each project, including training courses, seminars, workshops and presentations;
(b) Monitor the purchase of equipment, materials and tools, as well as contracts for services, to be in line with each project and comply with the Lead IA’s rules and regulations;
(c) Assist in the reporting on project activities, taking into account schedules defined in each component, and support the NOU in solving deviations to finalize all activities in time;
(d) Support the NOU in defining and selecting beneficiaries, always as a supporting activity;
(e) Support the NOU in data gathering to make the required reports to the Multilateral Fund Secretariat for the tranche requests, and also to the Lead IA;
(f) Monitor and promote, when necessary, the actions to comply with gender balance; and
(g) Carry out any other monitoring or evaluation activity requested by the NOU.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
(k) Ensuring that disbursements made to the Country are based on the use of the indicators;
(l) Providing assistance with the policy, management and technical support when required; and
(m) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
1. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex VII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF ESWATINI
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2030)
Purpose
1. This Agreement represents the understanding of the Government of Eswatini (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 94,950 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
88. The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
89. Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
90. The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
91. The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
92. The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
93. The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(a) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(b) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(c) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
94. Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
95. The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNDP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
96. The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
97. Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
98. The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
99. The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
100. The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
101. All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
102. This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	10
	n/a

	
	
	CO2‑eq tonnes
	105,500
	105,500
	105,500
	105,500
	105,500
	94,950
	94,950
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	105,500
	105,500
	105,500
	105,500
	105,500
	94,950
	94,950
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	63,500
	0
	0
	51,500
	0
	0
	0
	115,000

	2.2
	Support costs for Lead IA (US $)
	8,255
	0
	0
	6,695
	0
	0
	0
	14,950

	2.3
	Cooperating IA (UNDP) agreed funding (US $)
	0
	0
	0
	30,000
	0
	0
	0
	30,000

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	3,900
	0
	0
	0
	3,900

	3.1
	Total agreed funding (US $)
	63,500
	0
	0
	81,500
	0
	0
	0
	145,000

	3.2
	Total support costs (US $)
	8,255
	0
	0
	10,595
	0
	0
	0
	18,850

	3.3
	Total agreed costs (US $)
	71,755
	0
	0
	92,095
	0
	0
	0
	163,850


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. Overall monitoring will be provided by the Eswatini Environment Authority (EEA), through the national ozone unit (NOU), with assistance from the Lead IA. The NOU will submit annual progress reports of status of implementation of the Plan to the Lead IA.
106. Consumption will be monitored and determined from official data of import and export of substances as registered by the relevant Government departments. The NOU will compile and report the following data and information each year on or before the relevant deadlines.
(a) Reports on the consumption of the substances to be submitted to the Ozone Secretariat in line with Article 7 of the Montreal Protocol; and
(b) Reports on country programme data to be submitted to the Secretariat of the Multilateral Fund.
1. Monitoring of the development of the Plan and verification of achievement of performance targets will be assigned to an independent local company or to independent local consultant(s) by the Lead IA. The company or consultant(s) responsible for verification will have full access to relevant technical and financial information related to the implementation of the Plan.
1. The EEA will be responsible for the sustainability of consumption reduction targets achieved through this Agreement. 
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
110. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex VIII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF THE GAMBIA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of the Gambia (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 244,363 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(g) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	271,515
	271,515
	271,515
	271,515
	271,515
	244,363
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	271,515
	271,515
	271,515
	271,515
	271,515
	244,363
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	50,150
	0
	0
	42,250
	0
	0
	92,400

	2.2
	Support costs for Lead IA (US $)
	6,520
	0
	0
	5,492
	0
	0
	12,012

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	30,000
	0
	0
	47,600
	0
	0
	77,600

	2.4
	Support costs for Cooperating IA (US $)
	3,900
	0
	0
	6,188
	0
	0
	10,088

	3.1
	Total agreed funding (US $)
	80,150
	0
	0
	89,850
	0
	0
	170,000

	3.2
	Total support costs (US $)
	10,420
	0
	0
	11,680
	0
	0
	22,100

	3.3
	Total agreed costs (US $)
	90,570
	0
	0
	101,530
	0
	0
	192,100


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit, under the Ministry of Environment, Climate Change and Natural Resources (MECCNAR) is responsible for monitoring the progress of implementation of activities in the Plan.
Monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of training and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA.
The MECCNAR will be responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex IX
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF GHANA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2030)
Purpose
1. This Agreement represents the understanding of the Government of Ghana (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 767,003 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
121. The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
122. Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
123. The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
124. The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
125. The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
126. The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(a) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(b) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
(c) Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
(d) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
127. Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
128. The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) and UNEP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
129. The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
130. Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
131. The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
132. The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
133. The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
134. All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
135. This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	freeze
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	1,805,702
	1,805,702
	1,805,702
	1,805,702
	1,805,702
	1,625,132
	1,625,132
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	56.7
	56.7
	56.7
	56.7
	56.7
	57.5
	57.5
	n/a

	
	
	CO2‑eq tonnes
	n/a
	782,656
	782,656
	782,656
	782,656
	782,656
	767,003
	767,003
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	132,500
	0
	0
	0
	79,000
	0
	0
	20,500
	232,000

	2.2
	Support costs for Lead IA (US $)
	17,225
	0
	0
	0
	10,270
	0
	0
	2,665
	30,160

	2.3
	Cooperating IA (UNEP) agreed funding (US $)
	55,500
	0
	0
	0
	25,500
	0
	0
	12,000
	93,000

	2.4
	Support costs for Cooperating IA (US $)
	7,215
	0
	0
	0
	3,315
	0
	0
	1,560
	12,090

	3.1
	Total agreed funding (US $)
	188,000
	0
	0
	0
	104,500
	0
	0
	32,500
	325,000

	3.2
	Total support costs (US $)
	24,440
	0
	0
	0
	13,585
	0
	0
	4,225
	42,250

	3.3
	Total agreed costs (US $)
	212,440
	0
	0
	0
	118,085
	0
	0
	36,725
	367,250


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Environmental Protection Agency, will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration.
1. In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA. The Environmental Protection Agency is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
141. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
APPENDIX 8-A: SECTOR-SPECIFIC ARRANGEMENTS
1. The Government of the Country is allowed to submit a funding request for phasing down HFCs in the firefighting sector, for consideration by the Executive Committee in line with the agreed cost guidelines for that sector, once the Government has identified the consumption and revised the Article 7 and the country programme data.
UNEP/OzL.Pro/ExCom/98/6
Annex IX

UNEP/OzL.Pro/ExCom/98/6
Annex IX


2
3
Annex X
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF GRENADA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2030)
Purpose
1. This Agreement represents the understanding of the Government of Grenada (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 47,534 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(g) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNDP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	10
	n/a

	
	
	CO2‑eq tonnes
	n/a
	52,815
	52,815
	52,815
	52,815
	52,815
	47,534
	47,534
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	52,815
	52,815
	52,815
	52,815
	52,815
	47,534
	47,534
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	27,500
	0
	0
	0
	44,000
	0
	0
	16,342
	87,842

	2.2
	Support costs for Lead IA (US $)
	3,575
	0
	0
	0
	5,720
	0
	0
	2,124
	11,419

	2.3
	Cooperating IA (UNDP) agreed funding (US $)
	45,000
	0
	0
	0
	12,158
	0
	0
	0
	57,158

	2.4
	Support costs for Cooperating IA (US $)
	5,850
	0
	0
	0
	1,581
	0
	0
	0
	7,431

	3.1
	Total agreed funding (US $)
	72,500
	0
	0
	0
	56,158
	0
	0
	16,342
	145,000

	3.2
	Total support costs (US $)
	9,425
	0
	0
	0
	7,301
	0
	0
	2,124
	18,850

	3.3
	Total agreed costs (US $)
	81,925
	0
	0
	0
	63,459
	0
	0
	18,466
	163,850


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phasedown pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase-in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Ministry of Climate Resilience, the Environment and Renewable Energy, will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration.
In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA. 
The Ministry of Climate Resilience, the Environment and Renewable Energy is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XI
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF JORDAN
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2030)
Purpose
1. This Agreement represents the understanding of the Government of Jordan (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 1,278,531 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2030 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
(g) Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
(h) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNIDO has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4-A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	To be determined (TBD)*


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	2,808,101
	2,808,101
	2,808,101
	2,808,101
	2,808,101
	2,527,291
	2,527,291
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	35.6
	39.2
	43.1
	46.8
	50.4
	51.3
	54.5
	n/a

	
	
	CO2‑eq tonnes
	n/a
	1,809,703
	1,707,013
	1,596,587
	1,492,613
	1,393,191
	1,367,791
	1,278,531
	n/a

	2.1
	Lead IA (UNIDO) agreed funding (US $)
	2,540,680
	0
	0
	0
	1,802,170
	0
	0
	497,233
	4,840,083

	2.2
	Support costs for Lead IA (US $)
	177,848
	0
	0
	0
	126,152
	0
	0
	34,806
	338,806

	3.1
	Total agreed funding (US $)
	2,540,680
	0
	0
	0
	1,802,170
	0
	0
	497,233
	4,840,083

	3.2
	Total support costs (US $)
	177,848
	0
	0
	0
	126,152
	0
	0
	34,806
	338,806

	3.3
	Total agreed costs (US $)
	2,718,528
	0
	0
	0
	1,928,322
	0
	0
	532,039
	5,178,889

	4.1.1
	Deductions of HFCs agreed under this Agreement (CO2-eq tonnes)
	1,231,104

	4.1.2
	Deductions of HFCs from previously approved projects (CO2-eq tonnes)
	*211,530

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


* Noting that 36.25 mt (51,837.5 CO2-eq tonnes) of HFC-134a, 39.75 mt (70,516.5 CO2-eq tonnes) of R-407C, and 42.70 mt (89,175.6 CO2‑eq tonnes) of R-410A would be deducted from the starting point for sustained aggregate reduction in HFCs once it has been established (decision 81/62).
APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), under the Ministry of Environment, will monitor the implementation of the Plan’s activities, coordinate with relevant stakeholders, follow up on regulatory measures, monitor training and awareness activities, collect HFC consumption data, and support verification measures undertaken by the Lead IA.
2. The Ministry of Environment, through the NOU and in coordination with relevant national institutions, will also be responsible for ensuring the sustainability of the HFC consumption reduction targets achieved under the Agreement, including through the continued implementation of the licensing and control system, stakeholder coordination, and capacity-building support.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
(k) Ensuring that disbursements made to the Country are based on the use of the indicators;
(l) Providing assistance with the policy, management and technical support when required; and
(m) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
2. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.86 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF KYRGYZSTAN
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2029)
Purpose
1. This Agreement represents the understanding of the Government of Kyrgyzstan (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 405,344 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
154. The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
155. Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
156. The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
157. The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
158. The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
159. The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(a) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(b) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(c) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
160. Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
161. The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) and UNEP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
162. The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
163. Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
164. The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
165. The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
166. The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
167. All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
168. This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	450,382
	450,382
	450,382
	450,382
	450,382
	405,344
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	450,382
	450,382
	450,382
	450,382
	450,382
	405,344
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	51,000
	0
	0
	79,000
	0
	0
	0
	130,000

	2.2
	Support costs for Lead IA (US $)
	6,630
	0
	0
	10,270
	0
	0
	0
	16,900

	2.3
	Cooperating IA (UNEP) agreed funding (US $)
	30,000
	0
	0
	30,000
	0
	0
	0
	60,000

	2.4
	Support costs for Cooperating IA (US $)
	3,900
	0
	0
	3,900
	0
	0
	0
	7,800

	3.1
	Total agreed funding (US $)
	81,000
	0
	0
	109,000
	0
	0
	0
	190,000

	3.2
	Total support costs (US $)
	10,530
	0
	0
	14,170
	0
	0
	0
	24,700

	3.3
	Total agreed costs (US $)
	91,530
	0
	0
	123,170
	0
	0
	0
	214,700


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Ministry of Natural Resources, Ecology, and Technical Supervision, will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA. The Ministry of Natural Resources, Ecology, and Technical Supervision is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
173. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XIII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF THE LAO PEOPLE’S DEMOCRATIC REPUBLIC AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2030)
Purpose
1. This Agreement represents the understanding of the Government of the Lao People’s Democratic Republic (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 291,803 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(g) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNDP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	10
	n/a

	
	
	CO2‑eq tonnes
	324,226
	324,226
	324,226
	324,226
	324,226
	291,803
	291,803
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	324,226
	324,226
	324,226
	324,226
	324,226
	291,803
	291,803
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	34,000
	0
	0
	80,000
	0
	0
	0
	114,000

	2.2
	Support costs for Lead IA (US $)
	4,420
	0
	0
	10,400
	0
	0
	0
	14,820

	2.3
	Cooperating IA (UNDP) agreed funding (US $)
	76,000
	0
	0
	0
	0
	0
	0
	76,000

	2.4
	Support costs for Cooperating IA (US $)
	9,880
	0
	0
	0
	0
	0
	0
	9,880

	3.1
	Total agreed funding (US $)
	110,000
	0
	0
	80,000
	0
	0
	0
	190,000

	3.2
	Total support costs (US $)
	14,300
	0
	0
	10,400
	0
	0
	0
	24,700

	3.3
	Total agreed costs (US $)
	124,300
	0
	0
	90,400
	0
	0
	0
	214,700


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Ministry of Natural Resources and Environment (MNRE), will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA. The MNRE is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
The monitoring, reporting, verification and enforcement of HFC consumption levels will be carried out by the NOU in collaboration with the Customs Department and the Department of Industry under the Ministry of Industry and Commerce. The NOU is responsible for determining national HFC quotas and allocating them to eligible importers, while the Department of Industry is a licensing authority for issuing import and export permits based on the quotas allocated by the NOU. The Customs Department will control and monitor the import and export of HFCs at the point of entry. The NOU will liaise with concerned stakeholders including the Department of Industry, the Customs Department and HFC importers to obtain the data necessary for the periodic reconciliation of statistics.
The NOU will be responsible for the following:
(a) Carrying out surveys to gauge the status of HFC phase-down, potential illegal imports, and penetration of low-GWP alternative technologies in different subsectors;
(b) Carrying out regular inspections of the condition of training equipment acquired under the Plan for mobile air-conditioning training centre(s);
(c) Monitoring the implementation of capacity-building activities for trainers, assessors and technicians, including activities to maintain or enhance energy efficiency in the servicing sector, training for customs and enforcement officers, and training for importers and customs brokers; and
(d) Submitting annual progress reports on the status of implementation to the Lead IA and the Cooperating IA to monitor progress.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XIV
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF LESOTHO
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Lesotho (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 49,936 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(g) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6-A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4-A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	103,221
	103,221
	103,221
	103,221
	103,221
	92,899
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	39.5
	39.5
	39.5
	39.5
	39.5
	51.6
	n/a

	
	
	CO2‑eq tonnes
	62,420
	62,420
	62,420
	62,420
	62,420
	49,936
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	64,000
	0
	0
	50,000
	0
	0
	114,000

	2.2
	Support costs for Lead IA (US $)
	8,320
	0
	0
	6,500
	0
	0
	14,820

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	18,000
	0
	0
	13,000
	0
	0
	31,000

	2.4
	Support costs for Cooperating IA (US $)
	2,340
	0
	0
	1,690
	0
	0
	4,030

	3.1
	Total agreed funding (US $)
	82,000
	0
	0
	63,000
	0
	0
	145,000

	3.2
	Total support costs (US $)
	10,660
	0
	0
	8,190
	0
	0
	18,850

	3.3
	Total agreed costs (US $)
	92,660
	0
	0
	71,190
	0
	0
	163,850


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Lesotho Meteorological Services, will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA. Lesotho Meteorological Services is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
2. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES 
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XV
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF LIBERIA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Liberia (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 122,817 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
185. The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
186. Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
187. The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
188. The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
189. The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
190. The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(a) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(b) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(c) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
191. Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
192. The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. The Government of Germany has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
193. The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
194. Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
195. The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
196. The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
197. The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
198. All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
199. This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	180,909
	180,909
	180,909
	180,909
	180,909
	162,818
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	27.8
	27.8
	30.0
	30.0
	32.1
	n/a

	
	
	CO2‑eq tonnes
	180,909
	130,532
	130,532
	126,616
	126,616
	122,817
	n/a

	2.1
	Lead IA (Germany) agreed funding (US $)
	72,500
	0
	0
	72,500
	0
	0
	145,000

	2.2
	Support costs for Lead IA (US $)
	9,425
	0
	0
	9,425
	0
	0
	18,850

	3.1
	Total agreed funding (US $)
	72,500
	0
	0
	72,500
	0
	0
	145,000

	3.2
	Total support costs (US $)
	9,425
	0
	0
	9,425
	0
	0
	18,850

	3.3
	Total agreed costs (US $)
	81,925
	0
	0
	81,925
	0
	0
	163,850


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Liberia Environmental Protection Agency, will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and the delivery of outcomes, the NOU will facilitate the verification of HFC consumption to be undertaken by the Lead IA. The Liberia Environmental Protection Agency is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
203. The NOU, with assistance from the Lead IA, will establish a robust monitoring and evaluation process to track the implementation of the Plan. This will include development and implementation of a comprehensive data collection system to gather information on the import, export, and consumption on HFCs, periodic reporting to the Lead IA on project implementation status that will ensure transparency and accountability, monitoring of reductions in HFC consumption, compliance with phase‑down schedules, assessing adoption of alternative technologies in different applications, mobilising personnel and other resources for project implementation and monitoring project progress and coordination with relevant national institutions and stakeholders (e.g., industry representatives, enforcement bodies, civil society) for their active engagement in implementation of different project activities. The NOU will also undertake quarterly and annual reviews in collaboration with the Lead IA to monitor project progress, identify challenges, and recalibrate strategies where necessary.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
(k) Ensuring that disbursements made to the Country are based on the use of the indicators;
(l) Providing assistance with the policy, management and technical support when required; and
(m) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
205. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XVI
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF MALAWI
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2030)
Purpose
1. [bookmark: _Hlk188450574]This Agreement represents the understanding of the Government of Malawi (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 197,488 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2030 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(g) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6-A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4-A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	10
	n/a

	
	
	CO2‑eq tonnes
	n/a
	428,435
	428,435
	428,435
	428,435
	428,435
	385,591
	385,591
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	51.1
	49.1
	49.9
	51.1
	51.9
	52.5
	52.9
	54
	n/a

	
	
	CO2‑eq tonnes
	209,337
	217,890
	214,626
	209,580
	206,020
	203,508
	201,736
	197,488
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	39,000
	0
	0
	58,200
	0
	0
	0
	17,000
	114,200

	2.2
	Support costs for Lead IA (US $)
	5,070
	0
	0
	7,566
	0
	0
	0
	2,210
	14,846

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	29,000
	0
	0
	43,800
	0
	0
	0
	0
	72,800

	2.4
	Support costs for Cooperating IA (US $)
	3,770
	0
	0
	5,694
	0
	0
	0
	0
	9,464

	3.1
	Total agreed funding (US $)
	68,000
	0
	0
	102,000
	0
	0
	0
	17,000
	187,000

	3.2
	Total support costs (US $)
	8,840
	0
	0
	13,260
	0
	0
	0
	2,210
	24,310

	3.3
	Total agreed costs (US $)
	76,840
	0
	0
	115,260
	0
	0
	0
	19,210
	211,310


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Ministry of Natural Resources and Climate Change, will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA. The Ministry of Natural Resources and Climate Change is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
2. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES 
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XVII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF MALAYSIA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2029)
Purpose
1. This Agreement represents the understanding of the Government of Malaysia (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 24,033,345 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
(g) Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
(h) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. The World Bank has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	n/a
	26,703,717
	26,703,717
	26,703,717
	26,703,717
	26,703,717
	24,033,345
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	26,703,717
	26,703,717
	26,703,717
	26,703,717
	26,703,717
	24,033,345
	n/a

	2.1
	Lead IA (World Bank) agreed funding (US $)
	3,042,912
	0
	3,246,290
	0
	2,336,655
	0
	649,258
	9,275,115

	2.2
	Support costs for Lead IA (US $)
	213,004
	0
	227,240
	0
	163,566
	0
	45,448
	649,258

	3.1
	Total agreed funding (US $)
	3,042,912
	0
	3,246,290
	0
	2,336,655
	0
	649,258
	9,275,115

	3.2
	Total support costs (US $)
	213,004
	0
	227,240
	0
	163,566
	0
	45,448
	649,258

	3.3
	Total agreed costs (US $)
	3,255,916
	0
	3,473,530
	0
	2,500,221
	0
	694,706
	9,924,373

	4.1.1
	Deductions of HFCs under this Agreement (CO2-eq tonnes)
	2,763,452

	4.1.2
	Deductions of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The monitoring process will be managed by the Department of Environment (DOE) through the national ozone unit (NOU) with the assistance of the Lead IA.
1. Consumption will be monitored and determined based on official import and export data for the Substances recorded by relevant Government departments.
1. The DOE shall compile relevant data and prepare the following on or before the relevant due dates:
(a) Annual reports on consumption of the Substances to be submitted to the Ozone Secretariat; and
(b) Periodic reports on the implementation progress of the Plan, to be submitted through the Lead IA to the Executive Committee of the Multilateral Fund with Tranche Implementation Plans and HFC consumption verification reports.
1. Consumption will be monitored annually throughout the implementation of the Plan and accordingly reflected in the progress report on the implementation of the Plan.
The NOU in the DOE shall prepare, with the Lead IA, the final implementation progress report and the Lead IA shall submit the same.
The DOE, along with its Government partner agencies, will be responsible for the sustainability of consumption reduction targets achieved through this Agreement, and for reviewing all related reports and data and instituting control and policy measures that facilitate HFC control and reductions according to this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
(k) Ensuring that disbursements made to the Country are based on the use of the indicators;
(l) Providing assistance with the policy, management and technical support when required; and
(m) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $6.71 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XVIII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF MONTENEGRO
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Montenegro (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 125,577 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2-A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2-A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1-A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(g) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNIDO has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	155,854
	155,854
	155,854
	155,854
	155,854
	140,269
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	12.3
	14.1
	15.8
	17.6
	19.4
	n/a

	
	
	CO2‑eq tonnes
	155,854
	136,739
	133,949
	131,158
	128,368
	125,577
	n/a

	2.1
	Lead IA (UNIDO) agreed funding (US $)
	115,050
	0
	0
	74,550
	0
	0
	189,600

	2.2
	Support costs for Lead IA (US $)
	14,956
	0
	0
	9,692
	0
	0
	24,648

	3.1
	Total agreed funding (US $)
	115,050
	0
	0
	74,550
	0
	0
	189,600

	3.2
	Total support costs (US $)
	14,956
	0
	0
	9,692
	0
	0
	24,648

	3.3
	Total agreed costs (US $)
	130,006
	0
	0
	84,242
	0
	0
	214,248


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. All monitoring activities will be coordinated and managed through the Plan’s monitoring and management unit within the national ozone unit (NOU).
The NOU, under the Environmental Protection Agency (EPA), is responsible for coordinating the Country’s action plan with respect to ozone layer protection and facilitation of HFC phase-down. The NOU is in charge of implementing the country programmes under the Montreal Protocol. Implementation of the planned project activities will be allocated to the NOU in cooperation with the Lead IA. The NOU as a management body has a responsibility toward EPA and the Ministry of Ecology, Sustainable Development and Northern Region Development as a decision-making body. The NOU, under the EPA, is responsible for ensuring the sustainability of the consumption reduction targets achieved under this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
(k) Ensuring that disbursements made to the Country are based on the use of the indicators;
(l) Providing assistance with the policy, management and technical support when required; and
(m) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
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1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin. 
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Annex XIX
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF MOZAMBIQUE
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2030)
Purpose
1. This Agreement represents the understanding of the Government of Mozambique (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 589,730 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund;
(ii) Changes that would modify any clause of this Agreement;
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(g) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNDP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6-A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	10
	n/a

	
	
	CO2-eq tonnes
	655,255
	655,255
	655,255
	655,255
	655,255
	589,730
	589,730
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	655,255
	655,255
	655,255
	655,255
	655,255
	589,730
	589,730
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	83,500
	0
	81,500
	0
	0
	0
	42,000
	207,000

	2.2
	Support costs for Lead IA (US $)
	10,855
	0
	10,595
	0
	0
	0
	5,460
	26,910

	2.3
	Cooperating IA (UNDP) agreed funding (US $)
	86,000
	0
	6,000
	0
	0
	0
	26,000
	118,000

	2.4
	Support costs for Cooperating IA (US $)
	11,180
	0
	780
	0
	0
	0
	3,380
	15,340

	3.1
	Total agreed funding (US $)
	169,500
	0
	87,500
	0
	0
	0
	68,000
	325,000

	3.2
	Total support costs (US $)
	22,035
	0
	11,375
	0
	0
	0
	8,840
	42,250

	3.3
	Total agreed costs (US $)
	191,535
	0
	98,875
	0
	0
	0
	76,840
	367,250


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit, under the Ministry of Land and Environment, is responsible for monitoring the progress of implementation of activities in the Plan.
Monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of training and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA.
The Ministry of Land and Environment will be responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required; 
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
UNEP/OzL.Pro/ExCom/98/6
Annex XIX

UNEP/OzL.Pro/ExCom/98/6
Annex XIX


2
3
Annex XX
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF NORTH MACEDONIA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2029)
Purpose
1. This Agreement represents the understanding of the Government of North Macedonia (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 323,345 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
(g) Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
(h) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNIDO has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	 HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	n/a
	397,843
	397,843
	397,843
	397,843
	397,843
	358,059
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	4.8
	7.3
	9.7
	9.7
	9.7
	18.7
	n/a

	
	
	CO2‑eq tonnes
	n/a
	378,557
	368,915
	359,272
	359,272
	359,272
	323,345
	n/a

	2.1
	Lead IA (UNIDO) agreed funding (US $)
	103,555
	0
	0
	90,445
	0
	22,000
	0
	216,000

	2.2
	Support costs for Lead IA (US $)
	13,462
	0
	0
	11,758
	0
	2,860
	0
	28,080

	3.1
	Total agreed funding (US $)
	103,555
	0
	0
	90,445
	0
	22,000
	0
	216,000

	3.2
	Total support costs (US $)
	13,462
	0
	0
	11,758
	0
	2,860
	0
	28,080

	3.3
	Total agreed costs (US $)
	117,017
	0
	0
	102,203
	0
	24,860
	0
	244,080

	4.1.1
	 Deduction of HFCs under this Agreement (CO2-eq tonnes)
	74,498

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Ministry of Environment and Physical Planning, will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the duration of the Plan.
1. Monitoring will be conducted throughout implementation to ensure an effective overall project coordination, stakeholder engagement, timely execution of activities under each tranche, and delivery of expected outcomes. The NOU will also facilitate the verification of HFC consumption to be undertaken by the Lead IA.
1. The Ministry of Environment and Physical Planning will be responsible for ensuring the sustainability of the consumption reduction targets achieved under this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
(k) Ensuring that disbursements made to the Country are based on the use of the indicators;
(l) Providing assistance with the policy, management and technical support when required; and
(m) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
APPENDIX 8-A: SECTOR-SPECIFIC ARRANGEMENTS 
1. During the implementation of stage I of the Plan, the Country will be allowed, on an exceptional basis, to submit a project to phase out the consumption of HFC-152a in the extruded polystyrene foam manufacturing sector.
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Annex XXI
DRAFT AGREEMENT BETWEEN THE GOVERNMENTS OF THE PACIFIC ISLAND COUNTRIES (THE COOK ISLANDS, KIRIBATI, THE MARSHALL ISLANDS,
THE FEDERATED STATES OF MICRONESIA, NAURU, NIUE, PALAU, SAMOA,
SOLOMON ISLANDS, TONGA, TUVALU, VANUATU)
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Governments of the Cook Islands, Kiribati, the Marshall Islands, the Federated States of Micronesia, Nauru, Niue, Palau, Samoa, Solomon Islands, Tonga, Tuvalu, and Vanuatu (each hereinafter referred to as “the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 149,357 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
240. The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
241. Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
242. The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
243. The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
244. The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
245. The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(a) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(b) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and 
(c) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
246. Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
247. The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and the Government of Australia has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
248. The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6-A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
249. Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
250. The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
251. The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
252. The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
253. All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
254. This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
THE PACIFIC ISLAND COUNTRIES - OVERALL FUNDING
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	181,404
	181,404
	181,404
	181,404
	181,404
	163,260
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	11.5
	11.5
	11.5
	17.7
	n/a

	
	
	CO2-eq tonnes
	181,404
	181,404
	160,549
	160,549
	160,549
	149,357
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	683,000
	0
	0
	559,000
	0
	0
	1,242,000

	2.2
	Support costs for Lead IA (US $)
	88,790
	0
	0
	72,670
	0
	0
	161,460

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	295,000
	0
	0
	93,000
	0
	0
	388,000

	2.4
	Support costs for Cooperating IA (US $)
	38,350
	0
	0
	12,090
	0
	0
	50,440

	3.1
	Total agreed funding (US $)
	978,000
	0
	0
	652,000
	0
	0
	1,630,000

	3.2
	Total support costs (US $)
	127,140
	0
	0
	84,760
	0
	0
	211,900

	3.3
	Total agreed costs (US $)
	1,105,140
	0
	0
	736,760
	0
	0
	1,841,900


GOVERNMENT OF THE COOK ISLANDS
APPENDIX 1-A.1: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.1: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	6,461
	6,461
	6,461
	6,461
	6,461
	5,814
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	6,461
	6,461
	6,461
	6,461
	6,461
	5,814
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	23,250
	0
	0
	44,250
	0
	0
	67,500

	2.2
	Support costs for Lead IA (US $)
	3,023
	0
	0
	5,752
	0
	0
	8,775

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	23,250
	0
	0
	44,250
	0
	0
	67,500

	3.2
	Total support costs (US $)
	3,023
	0
	0
	5,752
	0
	0
	8,775

	3.3
	Total agreed costs (US $)
	26,273
	0
	0
	50,002
	0
	0
	76,275


GOVERNMENT OF KIRIBATI
APPENDIX 1-A.2: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.2: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	8,509
	8,509
	8,509
	8,509
	8,509
	7,658
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	8,509
	8,509
	8,509
	8,509
	8,509
	7,658
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	15,000
	0
	0
	11,000
	0
	0
	26,000

	2.2
	Support costs for Lead IA (US $)
	1,950
	0
	0
	1,430
	0
	0
	3,380

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	15,000
	0
	0
	11,000
	0
	0
	26,000

	3.2
	Total support costs (US $)
	1,950
	0
	0
	1,430
	0
	0
	3,380

	3.3
	Total agreed costs (US $)
	16,950
	0
	0
	12,430
	0
	0
	29,380


GOVERNMENT OF THE MARSHALL ISLANDS
APPENDIX 1-A.3: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.3: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	15,926
	15,926
	15,926
	15,926
	15,926
	14,333
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	15,926
	15,926
	15,926
	15,926
	15,926
	14,333
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	11,750
	0
	0
	7,750
	0
	0
	19,500

	2.2
	Support costs for Lead IA (US $)
	1,527
	0
	0
	1,008
	0
	0
	2,535

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	11,750
	0
	0
	7,750
	0
	0
	19,500

	3.2
	Total support costs (US $)
	1,527
	0
	0
	1,008
	0
	0
	2,535

	3.3
	Total agreed costs (US $)
	13,277
	0
	0
	8,758
	0
	0
	22,035


GOVERNMENT OF THE FEDERATED STATES OF MICRONESIA
APPENDIX 1-A.4: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.4: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	13,600
	13,600
	13,600
	13,600
	13,600
	12,240
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	13,600
	13,600
	13,600
	13,600
	13,600
	12,240
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	63,500
	0
	0
	27,500
	0
	0
	91,000

	2.2
	Support costs for Lead IA (US $)
	8,255
	0
	0
	3,575
	0
	0
	11,830

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	63,500
	0
	0
	27,500
	0
	0
	91,000

	3.2
	Total support costs (US $)
	8,255
	0
	0
	3,575
	0
	0
	11,830

	3.3
	Total agreed costs (US $)
	71,755
	0
	0
	31,075
	0
	0
	102,830


GOVERNMENT OF NAURU
APPENDIX 1-A.5: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.5: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	2,378
	2,378
	2,378
	2,378
	2,378
	2,140
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	2,378
	2,378
	2,378
	2,378
	2,378
	2,140
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	10,500
	0
	0
	6,500
	0
	0
	17,000

	2.2
	Support costs for Lead IA (US $)
	1,365
	0
	0
	845
	0
	0
	2,210

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	10,500
	0
	0
	6,500
	0
	0
	17,000

	3.2
	Total support costs (US $)
	1,365
	0
	0
	845
	0
	0
	2,210

	3.3
	Total agreed costs (US $)
	11,865
	0
	0
	7,345
	0
	0
	19,210


GOVERNMENT OF NIUE
APPENDIX 1-A.6: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.6: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	236
	236
	236
	236
	236
	212
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	236
	236
	236
	236
	236
	212
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	9,250
	0
	0
	5,250
	0
	0
	14,500

	2.2
	Support costs for Lead IA (US $)
	1,202
	0
	0
	683
	0
	0
	1,885

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	9,250
	0
	0
	5,250
	0
	0
	14,500

	3.2
	Total support costs (US $)
	1,202
	0
	0
	683
	0
	0
	1,885

	3.3
	Total agreed costs (US $)
	10,452
	0
	0
	5,933
	0
	0
	16,385


GOVERNMENT OF PALAU
APPENDIX 1-A.7: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.7: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	10,368
	10,368
	10,368
	10,368
	10,368
	9,331
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	10,368
	10,368
	10,368
	10,368
	10,368
	9,331
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	57,500
	0
	0
	46,500
	0
	0
	104,000

	2.2
	Support costs for Lead IA (US $)
	7,475
	0
	0
	6,045
	0
	0
	13,520

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	57,500
	0
	0
	46,500
	0
	0
	104,000

	3.2
	Total support costs (US $)
	7,475
	0
	0
	6,045
	0
	0
	13,520

	3.3
	Total agreed costs (US $)
	64,975
	0
	0
	52,545
	0
	0
	117,520


GOVERNMENT OF SAMOA
APPENDIX 1-A.8: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.8: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	20,557
	20,557
	20,557
	20,557
	20,557
	18,501
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	20,557
	20,557
	20,557
	20,557
	20,557
	18,501
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	66,000
	0
	0
	58,000
	0
	0
	124,000

	2.2
	Support costs for Lead IA (US $)
	8,580
	0
	0
	7,540
	0
	0
	16,120

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	66,000
	0
	0
	58,000
	0
	0
	124,000

	3.2
	Total support costs (US $)
	8,580
	0
	0
	7,540
	0
	0
	16,120

	3.3
	Total agreed costs (US $)
	74,580
	0
	0
	65,540
	0
	0
	140,120


GOVERNMENT OF SOLOMON ISLANDS
APPENDIX 1-A.9: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.9: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	69,516
	69,516
	69,516
	69,516
	69,516
	62,564
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	30.0
	30.0
	30.0
	30.0
	n/a

	
	
	CO2-eq tonnes
	69,516
	69,516
	48,661
	48,661
	48,661
	48,661
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	74,125
	0
	0
	66,125
	0
	0
	140,250

	2.2
	Support costs for Lead IA (US $)
	9,637
	0
	0
	8,596
	0
	0
	18,233

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	74,125
	0
	0
	66,125
	0
	0
	140,250

	3.2
	Total support costs (US $)
	9,637
	0
	0
	8,596
	0
	0
	18,233

	3.3
	Total agreed costs (US $)
	83,762
	0
	0
	74,721
	0
	0
	158,483


GOVERNMENT OF TONGA
APPENDIX 1-A.10: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.10: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	7,676
	7,676
	7,676
	7,676
	7,676
	6,908
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	7,676 
	7,676 
	7,676 
	7,676 
	7,676 
	6,908
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	60,750
	0
	0
	49,750
	0
	0
	110,500

	2.2
	Support costs for Lead IA (US $)
	7,898
	0
	0
	6,467
	0
	0
	14,365

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	60,750
	0
	0
	49,750
	0
	0
	110,500

	3.2
	Total support costs (US $)
	7,898
	0
	0
	6,467
	0
	0
	14,365

	3.3
	Total agreed costs (US $)
	68,648
	0
	0
	56,217
	0
	0
	124,865


GOVERNMENT OF TUVALU
APPENDIX 1-A.11: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.11: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	2,648
	2,648
	2,648
	2,648
	2,648
	2,383
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	2,648
	2,648
	2,648
	2,648
	2,648
	2,383
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	12,250
	0
	0
	8,250
	0
	0
	20,500

	2.2
	Support costs for Lead IA (US $)
	1,592
	0
	0
	1,073
	0
	0
	2,665

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	12,250
	0
	0
	8,250
	0
	0
	20,500

	3.2
	Total support costs (US $)
	1,592
	0
	0
	1,073
	0
	0
	2,665

	3.3
	Total agreed costs (US $)
	13,842
	0
	0
	9,323
	0
	0
	23,165


GOVERNMENT OF VANUATU
APPENDIX 1-A.12: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.12: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	23,529
	23,529
	23,529
	23,529
	23,529
	21,176
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	23,529
	23,529
	23,529
	23,529
	23,529
	21,176
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	31,625
	0
	0
	52,625
	0
	0
	84,250

	2.2
	Support costs for Lead IA (US $)
	4,112
	0
	0
	6,841
	0
	0
	10,953

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	31,625
	0
	0
	52,625
	0
	0
	84,250

	3.2
	Total support costs (US $)
	4,112
	0
	0
	6,841
	0
	0
	10,953

	3.3
	Total agreed costs (US $)
	35,737
	0
	0
	59,466
	0
	0
	95,203


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. Under the respective Ministries or Agencies, i.e., the Cook Islands National Environment Service; the Kiribati Ministry of Environment, Lands and Agricultural Development; the Marshall Islands Environmental Protection Authority; the Federated States of Micronesia Department of Environment, Climate Change and Emergency Management; the Nauru Department of Environmental Management and Agriculture; the Niue Ministry of Natural Resources; the Palau Environmental Quality Protection Board; the Samoa Ministry of Natural Resources and Environment; the Solomon Islands Ministry of Mines, Energy and Rural Electrification; the Tonga Ministry of Meteorology, Energy, Information, Disaster Management, Environment, Climate Change and Communications; the Tuvalu Ministry of Home Affairs, Climate Change and Environment; and the Vanuatu Ministry of Climate Change Adaptation, Meteorology, Geohazards, Energy, Environment and Disaster Management, the national ozone units (NOUs) will be responsible for the overall project monitoring of all activities under the Plan, as well as the planning, coordination, and daily work of project implementation.
258. The NOUs will coordinate closely with national industries, technical institutions, non‑governmental organizations and government departments, as well as technical experts, the Lead IA and the Cooperating IA, to ensure the smooth implementation of the Plan. Moreover, the NOUs will work in collaboration with respective national Energy-Efficiency Authorities to explore synergies between HFC phase‑down and energy efficiency in the national implementation of policy and regulations, capacity building, raising awareness and communications.
259. Annual consumption of HFCs will be monitored through the NOUs in collaboration with the Customs Authority of each Country. The NOUs will also liaise with importers of HFCs to obtain the necessary data for reconciliation of statistics on a periodic basis.
260. The NOUs will undertake national market surveys to gauge the situation of HFC phase‑down, potential illegal imports, and the penetration of alternative technologies with low global-warming potential in different subsectors. In case of a risk of non-compliance with obligations or not meeting the maximum allowance for total consumption of Annex F substances, the NOUs will report to the Lead IA and Cooperating IA to identify specific interventions needed for achieving the HFC phase-down targets.
261. The NOUs will monitor the implementation of capacity-building activities with relevant agencies, including competency-based training and assessment for refrigeration and air‑conditioning and mobile air‑conditioning technicians, activities to build the capacity of technicians to maintain and/or enhance energy efficiency in the servicing sector while phasing down HFCs, and training for customs and enforcement officers.
262. The NOUs will submit annual progress reports on the status of implementation of respective national components to the Lead IA and Cooperating IA to monitor the implementation progress of the Plan.
263. The Ministries and Agencies listed in paragraph 1 above will be responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
265. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XXII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF PANAMA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2029)
Purpose
1. This Agreement represents the understanding of the Government of Panama (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 2,289,047 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
(g) Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
(h) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	 HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	n/a
	2,543,386
	2,543,386
	2,543,386
	2,543,386
	2,543,386
	2,289,047
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in % 
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	2,543,386
	2,543,386
	2,543,386
	2,543,386
	2,543,386
	2,289,047
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	331,100
	0
	0
	264,880
	0
	0
	66,220
	662,200

	2.2
	Support costs for Lead IA (US $)
	23,177
	0
	0
	18,542
	0
	0
	4,635
	46,354

	3.1
	Total agreed funding (US $)
	331,100
	0
	0
	264,880
	0
	0
	66,220
	662,200

	3.2
	Total support costs (US $)
	23,177
	0
	0
	18,542
	0
	0
	4,635
	46,354

	3.3
	Total agreed costs (US $)
	354,277
	0
	0
	283,422
	0
	0
	70,855
	708,554

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	254,339

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the General Sub-Directorate of Environmental Health in the General Directorate of Public Health at the Ministry of Health (MINSA), will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, strengthening of education centres and pilot projects, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA.
The MINSA coordinates all activities aimed at achieving and sustaining the commitments to reduce HFC consumption with different entities at the national level, including the Ministry of Commerce and Industry, Ministry of Education and other institutions in the academic sector, the Ministry of Environment, the National Customs Authority, the National Energy Secretariat, civil society associations and the productive sectors.
The MINSA is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
(k) Ensuring that disbursements made to the Country are based on the use of the indicators;
(l) Providing assistance with the policy, management and technical support when required; and
(m) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $5.21 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XXIII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF PARAGUAY
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Paraguay (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 1,516,124 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(g) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	1,684,582
	1,684,582
	1,684,582
	1,684,582
	1,684,582
	1,516,124
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	1,684,582
	1,684,582
	1,684,582
	1,684,582
	1,684,582
	1,516,124
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	235,675
	0
	0
	188,540
	0
	47,135
	471,350

	2.2
	Support costs for Lead IA (US $)
	16,497
	0
	0
	13,198
	0
	3,300
	32,995

	3.1
	Total agreed funding (US $)
	235,675
	0
	0
	188,540
	0
	47,135
	471,350

	3.2
	Total support costs (US $)
	16,497
	0
	0
	13,198
	0
	3,300
	32,995

	3.3
	Total agreed costs (US $)
	252,172
	0
	0
	201,738
	0
	50,435
	504,345

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	168,458

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Ministry of Environment and Sustainable Development (MADES), will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA.
1. The MADES is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
(k) Ensuring that disbursements made to the Country are based on the use of the indicators;
(l) Providing assistance with the policy, management and technical support when required; and
(m) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
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1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $5.60 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin. 
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Annex XXIV
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF PERU
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2029)
Purpose
1. This Agreement represents the understanding of the Government of Peru (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 2,462,149 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
(g) Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
(h) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	2,735,721
	2,735,721
	2,735,721
	2,735,721
	2,735,721
	2,462,149
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	2,735,721
	2,735,721
	2,735,721
	2,735,721
	2,735,721
	2,462,149
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	283,140
	0
	0
	283,140
	0
	0
	62,718
	628,998

	2.2
	Support costs for Lead IA (US $)
	19,820
	0
	0
	19,820
	0
	0
	4,390
	44,030

	3.1
	Total agreed funding (US $)
	283,140
	0
	0
	283,140
	0
	0
	62,718
	628,998

	3.2
	Total support costs (US $)
	19,820
	0
	0
	19,820
	0
	0
	4,390
	44,030

	3.3
	Total agreed costs (US $)
	302,960
	0
	0
	302,960
	0
	0
	67,108
	673,028

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	273,572

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. Overall supervision will be provided by the Ministry of Production (PRODUCE), through the national ozone office (NOO), with assistance from the Lead IA.
1. Consumption will be monitored and determined from official data on the import and export of substances as registered by relevant Government departments. The NOO will compile and report the following data and information each year on, or before the deadlines:
(a) Annual reports on the consumption of the substances to be submitted to the Ozone Secretariat, 
(b) Annual reports on progress in Plan implementation to be submitted to the Executive Committee of the Multilateral Fund, and
(c) Annual reports on progress in gender indicators according to the guidelines established by the Multilateral Fund of the Montreal Protocol and the specific activities approved for the projects.
The NOO and the Lead IA will jointly hire a qualified independent entity to conduct a qualitative and quantitative performance assessment of the implementation of the Plan. The agency responsible for evaluation will have full access to relevant technical and financial information related to the implementation of the Plan.
The PRODUCE is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
(k) Ensuring that disbursements made to the Country are based on the use of the indicators;
(l) Providing assistance with the policy, management and technical support when required; and
(m) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $4.60 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
APPENDIX 8-A: SECTOR-SPECIFIC ARRANGEMENTS
1. A project to phase out HFCs contained in imported pre-blended polyols in the Country’s polyurethane foam sector will be subject to the decision taken by the Committee on whether it would fund the phase-out of HFCs contained in imported pre-blended polyols.
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Annex XXV
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF RWANDA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Rwanda (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1-A (“The Substances”) to a sustained level of 254,008 CO2-equivalent (CO2-eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2-A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2-A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1-A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4-A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4-A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(g) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6-A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2-A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2-eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2-A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4-A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	338,197
	338,197
	338,197
	338,197
	338,197
	304,377
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	24.9
	n/a

	
	
	CO2‑eq tonnes
	338,197
	338,197
	338,197
	338,197
	338,197
	254,008
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	48,400
	0
	0
	44,000
	0
	17,600
	110,000

	2.2
	Support costs for Lead IA (US $)
	6,292
	0
	0
	5,720
	0
	2,288
	14,300

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	27,500
	0
	0
	44,000
	0
	5,500
	77,000

	2.4
	Support costs for Cooperating IA (US $)
	3,575
	0
	0
	5,720
	0
	715
	10,010

	3.1
	Total agreed funding (US $)
	75,900
	0
	0
	88,000
	0
	23,100
	187,000

	3.2
	Total support costs (US $)
	9,867
	0
	0
	11,440
	0
	3,003
	24,310

	3.3
	Total agreed costs (US $)
	85,767
	0
	0
	99,440
	0
	26,103
	211,310


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase-down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase-in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit, under the Ministry of Environment, is responsible for monitoring the progress of implementation of activities in the Plan.
Monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of training and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA.
The Ministry of Environment in the Country will be responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4-A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4-A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
2.	After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2-A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XXVI
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF SAINT LUCIA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Saint Lucia (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 75,362 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1-A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(g) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6-A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4-A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes) 

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	83,735
	83,735
	83,735
	83,735
	83,735
	75,362
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	83,735
	83,735
	83,735
	83,735
	83,735
	75,362
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	43,000
	0
	0
	38,000
	0
	13,000
	94,000

	2.2
	Support costs for Lead IA (US $)
	5,590
	0
	0
	4,940
	0
	1,690
	12,220

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	27,000
	0
	0
	24,000
	0
	0
	51,000

	2.4
	Support costs for Cooperating IA (US $)
	3,510
	0
	0
	3,120
	0
	0
	6,630

	3.1
	Total agreed funding (US $)
	70,000
	0
	0
	62,000
	0
	13,000
	145,000

	3.2
	Total support costs (US $)
	9,100
	0
	0
	8,060
	0
	1,690
	18,850

	3.3
	Total agreed costs (US $)
	79,100
	0
	0
	70,060
	0
	14,690
	163,850


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU) will be responsible for the day-to-day execution of all components of the project, including monitoring, evaluation and reporting. It will be supported by the Ministry of Agriculture, Fisheries, Food Security and Sustainable Development who will manage the budget and exercise oversight of the procurement processes. The Ministry will also be responsible for the sustainability of consumption reduction targets achieved through this Agreement.
Upon project launch the NOU and the Montreal Protocol Technical Working Group will plan for the execution of each component and for the day-to-day execution of all activities approved under the Plan, including monitoring of all project activities, generating periodic monitoring and evaluation reports on project activities, targets achieved, adjustments, and remedial actions to be taken, if necessary, to ensure that targets are met. A consultant will be contracted to assist in delivering these tasks.
The Lead IA will be responsible for ensuring that periodic progress and financial reports are generated, tranche progress is monitored and funds are disbursed in accordance with this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
2. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XXVII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF SENEGAL
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Senegal (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 2,215,780 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(g) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	2,786,915
	2,786,915
	2,786,915
	2,786,915
	2,786,915
	2,508,224
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	20.5
	n/a

	
	
	CO2‑eq tonnes
	2,786,915
	2,786,915
	2,786,915
	2,786,915
	2,786,915
	2,215,780
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	168,000
	0
	0
	138,000
	0
	84,000
	390,000

	2.2
	Support costs for Lead IA (US $)
	21,840
	0
	0
	17,940
	0
	10,920
	50,700

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	127,500
	0
	0
	317,500
	0
	25,000
	470,000

	2.4
	Support costs for Cooperating IA (US $)
	8,925
	0
	0
	22,225
	0
	1,750
	32,900

	3.1
	Total agreed funding (US $)
	295,500
	0
	0
	455,500
	0
	109,000
	860,000

	3.2
	Total support costs (US $)
	30,765
	0
	0
	40,165
	0
	12,670
	83,600

	3.3
	Total agreed costs (US $)
	326,265
	0
	0
	495,665
	0
	121,670
	943,600

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	571,135

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Ministry of the Environment and Ecological Transition (MEET), will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the activities, including training, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA. The MEET is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
Consumption will be monitored and determined from the official data on the import and export of substances registered by the relevant Government departments.
The NOU will compile and report on the following data and information each year on or before the agreed deadlines:
(a) Annual reports on the consumption of substances submitted to the Ozone Secretariat; and
(b) Annual reports on progress achieved in the Plan’s implementation submitted to the Executive Committee of the Multilateral Fund.
The NOU and the Lead IA will jointly hire a qualified independent entity to conduct a qualitative and quantitative performance assessment of the implementation of the Plan.
The agency responsible for evaluation will have full access to relevant technical and financial information related to the implementation of the Plan, and will prepare and submit to the NOU and the Lead IA a draft consolidated report at the end of each annual implementation plan. The report will include assessment findings and, where appropriate, recommendations for improvements or adjustments, as well as the Country’s situation with regard to compliance with the provisions of this Agreement. After incorporating the comments and explanations, if any, from the NOU and the Lead IA, the agency responsible for evaluation will finalize the report and submit it to the MEET and the Lead IA. The MEET will endorse the final report, and the Lead IA will transmit it to the relevant meeting of the Executive Committee together with the implementation plan and annual reports.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $5.28 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XXVIII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF SEYCHELLES
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND FOR
THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Seychelles (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 224,460 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(g) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and the Government of Germany has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	249,400
	249,400
	249,400
	249,400
	249,400
	224,460
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	249,400
	249,400
	249,400
	249,400
	249,400
	224,460
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	64,836
	0
	0
	20,424
	0
	0
	85,260

	2.2
	Support costs for Lead IA (US $)
	8,429
	0
	0
	2,655
	0
	0
	11,084

	2.3
	Cooperating IA (Germany) agreed funding (US $)
	16,844
	0
	0
	55,896
	0
	0
	72,740

	2.4
	Support costs for Cooperating IA (US $)
	2,190
	0
	0
	7,266
	0
	0
	9,456

	3.1
	Total agreed funding (US $)
	81,680
	0
	0
	76,320
	0
	0
	158,000

	3.2
	Total support costs (US $)
	10,619
	0
	0
	9,921
	0
	0
	20,540

	3.3
	Total agreed costs (US $)
	92,299
	0
	0
	86,241
	0
	0
	178,540


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. Overall monitoring will be provided by the Ministry of Environment, Climate, Energy and Natural Resources through the national ozone unit (NOU), with assistance from the Lead IA. The NOU will submit annual progress reports of status of implementation of the Plan to the Lead IA.
Consumption will be monitored and determined from the official data on the import and export of substances, as registered by the relevant Government departments. The NOU will compile and report the following data and information each year on or before the relevant deadlines:
(a) Reports on the consumption of substances to be submitted to the Ozone Secretariat in line with Article 7 of the Montreal Protocol; and
(b) Reports on country programme data to be submitted to the Secretariat of the Multilateral Fund.
The monitoring of the development of the Plan and verification of the achievement of performance targets will be assigned to an independent local company or to independent local consultant(s) by the Lead IA. The company or consultant(s) responsible for verification will have full access to relevant technical and financial information related to the implementation of the Plan.
The Ministry of Environment, Climate, Energy and Natural Resources will be responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XXIX
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF SIERRA LEONE
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Sierra Leone (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 315,815 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(g) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	350,905
	350,905
	350,905
	350,905
	350,905
	315,815
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	1.5
	3.2
	4.9
	6.6
	8.3
	10.0
	n/a

	
	
	CO2‑eq tonnes
	345,642
	339,676
	333,711
	327,746
	321,780
	315,815
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	65,500
	0
	0
	38,817
	0
	0
	104,317

	2.2
	Support costs for Lead IA (US $)
	8,515
	0
	0
	5,046
	0
	0
	13,561

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	21,000
	0
	0
	54,683
	0
	0
	75,683

	2.4
	Support costs for Cooperating IA (US $)
	2,730
	0
	0
	7,109
	0
	0
	9,839

	3.1
	Total agreed funding (US $)
	86,500
	0
	0
	93,500
	0
	0
	180,000

	3.2
	Total support costs (US $)
	11,245
	0
	0
	12,155
	0
	0
	23,400

	3.3
	Total agreed costs (US $)
	97,745
	0
	0
	105,655
	0
	0
	203,400


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit, under the Ministry of the Environment and Climate Change, is responsible for monitoring the progress of implementation of activities in the Plan.
Monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of training and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA.
The Ministry of the Environment and Climate Change will be responsible for the sustainability of consumption reduction targets achieved through the Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XXX
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF TOGO
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS IN ACCORDANCE
WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Togo (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 956,162 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(g) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	1,124,896
	1,124,896
	1,124,896
	1,124,896
	1,124,896
	1,012,406
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	15.0
	n/a

	
	
	CO2‑eq tonnes
	1,124,896
	1,124,896
	1,124,896
	1,124,896
	1,124,896
	956,162
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	117,500
	0
	0
	102,500
	0
	0
	220,000

	2.2
	Support costs for Lead IA (US $)
	15,275
	0
	0
	13,325
	0
	0
	28,600

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	70,000
	0
	0
	70,000
	0
	0
	140,000

	2.4
	Support costs for Cooperating IA (US $)
	9,100
	0
	0
	9,100
	0
	0
	18,200

	3.1
	Total agreed funding (US $)
	187,500
	0
	0
	172,500
	0
	0
	360,000

	3.2
	Total support costs (US $)
	24,375
	0
	0
	22,425
	0
	0
	46,800

	3.3
	Total agreed costs (US $)
	211,875
	0
	0
	194,925
	0
	0
	406,800


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), under the Ministry of Environment, Forestry Resources, Coastal Protection, and Climate Change, is responsible for monitoring the progress of implementation of activities in the Plan. The NOU will submit annual progress reports of status of implementation of the Plan to the Lead IA. Monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation, overall project coordination, stakeholder engagement and coordination, smooth implementation of activities planned under the various tranches, delivery of training and other expected outcomes, and facilitation of the HFC consumption verification undertaken by the Lead IA.
2. Consumption will be monitored and determined from the official data on the import and export of substances as registered by the relevant Government departments. The NOU will compile and report on the following data and information each year on or before the relevant deadlines:
321. Reports on the consumption of substances to be submitted to the Ozone Secretariat in line with Article 7 of the Montreal Protocol; and
(f) Reports on country programme data to be submitted to the Secretariat of the Multilateral Fund.
3. Monitoring of the development of the Plan and verification of the achievement of performance targets will be assigned to an independent local company or to independent local consultant(s) by the Lead IA. The company or consultant(s) responsible for verification will have full access to relevant technical and financial information related to the implementation of the Plan.
4. The Ministry of Environment, Forestry Resources, Coastal Protection, and Climate Change will be responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
1. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
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1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XXXI
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF TRINIDAD AND TOBAGO
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2029)
Purpose
1. This Agreement represents the understanding of the Government of Trinidad and Tobago (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 5,113,608 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; 
(g) Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
(h) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4-A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	n/a
	5,681,787
	5,681,787
	5,681,787
	5,681,787
	5,681,787
	5,113,608
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	5,681,787
	5,681,787
	5,681,787
	5,681,787
	5,681,787
	5,113,608
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	543,249
	0
	0
	516,677
	0
	0
	117,769
	1,177,695

	2.2
	Support costs for Lead IA (US $)
	38,028
	0
	0
	36,167
	0
	0
	8,244
	82,439

	3.1
	Total agreed funding (US $)
	543,249
	0
	0
	516,677
	0
	0
	117,769
	1,177,695

	3.2
	Total support costs (US $)
	38,028
	0
	0
	36,167
	0
	0
	8,244
	82,439

	3.3
	Total agreed costs (US $)
	581,277
	0
	0
	552,844
	0
	0
	126,013
	1,260,134

	4.1.1
	Deductions of HFCs under this Agreement (CO2-eq tonnes)
	568,179

	4.1.2
	Deductions of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Ministry of Planning, Economic Affairs and Development (MPEAD), will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA.
2. The NOU will organize the collection and analysis of project data, standardize reporting formats, and convene periodic evaluation meetings. It will prepare internal progress reports, annual Plan implementation reports, and tranche submissions for the Executive Committee. The NOU will also monitor gender indicators, track private sector trends in HFC use, and stay updated on alternative technologies through participation in stakeholder-led technical meetings.
3. The MPEAD is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
(k) Ensuring that disbursements made to the Country are based on the use of the indicators;
(l) Providing assistance with the policy, management and technical support when required; and
(m) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
2. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $4.15 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin. 
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Annex XXXII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF TUNISIA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2030)
Purpose
1. This Agreement represents the understanding of the Government of Tunisia (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 1,803,694 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2030 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; 
(g) Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
(h) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNIDO has agreed to be the lead implementing agency (the “Lead IA”) and UNEP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6-A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	Freeze
	Freeze
	Freeze
	Freeze
	Freeze
	10
	10
	n/a

	
	
	CO2-eq tonnes
	2,367,840
	2,367,840
	2,367,840
	2,367,840
	2,367,840
	2,131,056
	2,131,056
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	23.8
	n/a

	
	
	CO2-eq tonnes
	2,367,840
	2,367,840
	2,367,840
	2,367,840
	2,367,840
	2,131,056
	1,803,694
	n/a

	2.1
	Lead IA (UNIDO) agreed funding (US $)
	1,526,566
	0
	0
	435,875
	0
	0
	104,740
	2,067,181 

	2.2
	Support costs for Lead IA (US $)
	106,860
	0
	0
	30,511
	0
	0
	7,332
	144,703

	2.3
	Cooperating IA (UNEP) agreed funding (US $)
	50,000
	0
	0
	45,000
	0
	0
	15,000
	110,000 

	2.4
	Support costs for Cooperating IA (US $)
	6,500
	0
	0
	5,850
	0
	0
	1,950
	14,300

	3.1
	Total agreed funding (US $)
	1,576,566
	0
	0
	480,875
	0
	0
	119,740
	2,177,181

	3.2
	Total support costs (US $)
	113,360
	0
	0
	36,361
	0
	0
	9,282
	159,003

	3.3
	Total agreed costs (US $)
	1,689,926
	0
	0
	517,236
	0
	0
	129,022
	2,336,184

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	629,563

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), under the National Agency for the Protection of the Environment (ANPE), will monitor the effectiveness of implementation of the different components under the Plan, including compliance with phase-down levels and impact of all activities against the set objectives and goals.
1. The ANPE, in close cooperation and coordination with the NOU and support of the Lead IA, will play a key role in the monitoring of the Plan and will be responsible for the sustainability of consumption reduction targets achieved through this Agreement. 
1. The NOU will undertake monitoring, reporting and record-keeping on:
332. HFC import and export, including data collected from local importers;
332. HFC use by different sectors, including data collected from manufacturers and surveys conducted by the project management unit;
332. Amounts of recovered, recycled, and unwanted HFCs;
332. Regular updates on the Plan’s deliverables as per targeted milestones;
332. Plans, progress reports and completion reports of components and projects; and
332. Information on HFC-based equipment banks and status of their operation and retirement.
1. The verification will, in addition to other tasks, cover the reports generated regarding achievements under the Plan.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and the Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $6.92 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
APPENDIX 8-A: SECTOR-SPECIFIC ARRANGEMENTS
1. During the implementation of stage I of the Plan, a project to phase out HFCs contained in imported pre-blended polyols in the Country’s polyurethane foam sector would be subject to the Executive Committee’s consideration of funding the phase-out of HFCs contained in imported pre-blended polyols. 
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Annex XXXIII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF TÜRKIYE
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Türkiye (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 31,790,838 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 or 12 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 or 12 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
(g) Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
(h) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNIDO has agreed to be the lead implementing agency (the “Lead IA”) and UNDP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	37,117,410
	37,117,410
	37,117,410
	37,117,410
	37,117,410
	33,405,669
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances 
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	14.4
	n/a

	
	
	CO2‑eq tonnes
	37,117,410
	37,117,410
	37,117,410
	37,117,410
	37,117,410
	31,790,838
	n/a

	2.1
	Lead IA (UNIDO) agreed funding (US $)
	1,943,985
	0
	0
	5,262,222
	0
	1,120,080
	8,326,287

	2.2
	Support costs for Lead IA (US $)
	136,079
	0
	0
	368,355
	0
	78,406
	582,840

	2.3
	Cooperating IA (UNDP) agreed funding (US $)
	845,445
	0
	0
	1,637,040
	0
	358,641
	2,841,126

	2.4
	Support costs for Cooperating IA (US $)
	59,181
	0
	0
	114,593
	0
	25,105
	198,879

	3.1
	Total agreed funding (US $)
	2,789,430
	0
	0
	6,899,262
	0
	1,478,721
	11,167,413

	3.2
	Total support costs (US $)
	195,260
	0
	0
	482,948
	0
	103,511
	781,719

	3.3
	Total agreed costs (US $)
	2,984,690
	0
	0
	7,382,210
	0
	1,582,232
	11,949,132

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	5,326,572

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), under the Directorate of Climate Change (DCC) of the Ministry of Environment, Urbanization and Climate Change (MoEUCC), is responsible for monitoring the progress of implementation of activities in the Plan.
1. The monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation, overall project coordination, stakeholder engagement and coordination, smooth implementation of activities planned under various tranches, delivery of training and other expected outcomes and facilitation of HFC consumption verification undertaken by the Lead IA.
1. The DCC will be responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $4.19 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
APPENDIX 8-A: SECTOR-SPECIFIC ARRANGEMENTS 
1. During the implementation of stage I of the Plan and no later than at the 98th meeting, the Country will be allowed, on an exceptional basis, to submit investment projects in the refrigeration, air-conditioning and foam sectors to achieve additional HFC reductions.
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DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF URUGUAY
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Uruguay (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 911,188 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; 
(g) Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
(h) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6-A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	Freeze
	Freeze
	Freeze
	Freeze
	Freeze
	10
	n/a

	
	
	CO2-eq tonnes
	1,012,431
	1,012,431
	1,012,431
	1,012,431
	1,012,431
	911,188
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	1,012,431
	1,012,431
	1,012,431
	1,012,431
	1,012,431
	911,188
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	126,927
	0
	0
	92,413
	0
	0
	219,340

	2.2
	Support costs for Lead IA (US $)
	16,500
	0
	0
	12,014
	0
	0
	28,514

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	49,860
	0
	0
	55,800
	0
	0
	105,660

	2.4
	Support costs for Cooperating IA (US $)
	6,482
	0
	0
	7,254
	0
	0
	13,736

	3.1
	Total agreed funding (US $)
	176,787
	0
	0
	148,213
	0
	0
	325,000

	3.2
	Total support costs (US $)
	22,982
	0
	0
	19,268
	0
	0
	42,250

	3.3
	Total agreed costs (US $)
	199,769
	0
	0
	167,481
	0
	0
	367,250

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	101,243

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Ministry of Environment, will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and the delivery of outcomes, the NOU will facilitate the verification of HFC consumption to be undertaken by the Lead IA. 
The Ministry of Environment is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA[s] and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and the Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
APPENDIX 8-A: SECTOR-SPECIFIC ARRANGEMENTS 
1. During the implementation of stage I of the Plan, a project to phase out HFCs contained in imported pre-blended polyols in the Country’s polyurethane foam sector will be subject to the decision taken by the Committee on whether it would fund the phase-out of HFCs contained in imported pre-blended polyols.
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DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF VIET NAM
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2029)
Purpose
1. This Agreement represents the understanding of the Government of Viet Nam (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 12,592,224 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
(g) Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
(h) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. The World Bank has agreed to be the lead implementing agency (the “Lead IA”) and UNEP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	n/a
	13,991,360
	13,991,360
	13,991,360
	13,991,360
	13,991,360
	12,592,224
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	13,991,360
	13,991,360
	13,991,360
	13,991,360
	13,991,360
	12,592,224
	n/a

	2.1
	Lead IA (World Bank) agreed funding (US $)
	1,557,792
	0
	0
	1,513,187
	0
	0
	522,204
	3,593,183

	2.2
	Support costs for Lead IA (US $)
	109,045
	0
	0
	105,923
	0
	0
	36,554
	251,522

	2.3
	Cooperating IA (UNEP) agreed funding (US $)
	461,696
	0
	0
	440,301
	0
	0
	155,983
	1,057,980

	2.4
	Support costs for Cooperating IA (US $)
	55,150
	0
	0
	52,595
	0
	0
	18,633
	126,378

	3.1
	Total agreed funding (US $)
	2,019,488
	0
	0
	1,953,488
	0
	0
	678,187
	4,651,163

	3.2
	Total support costs (US $)
	164,195
	0
	0
	158,518
	0
	0
	55,187
	377,900

	3.3
	Total agreed costs (US $)
	2,183,683
	0
	0
	2,112,006
	0
	0
	733,374
	5,029,063

	4.1.1
	Deductions of HFCs under this Agreement (CO2-eq tonnes)
	1,438,128

	4.1.2
	Deductions of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The Viet Nam National Focal Point for the Implementation of the Montreal Protocol, which is the Country’s national ozone unit (NOU) under the Department of Climate Change (DCC) in the Ministry of Agriculture and Environment (MAE), is responsible for managing and coordinating the Country’s overall Montreal Protocol implementation programme, including all phase-down activities and measures controlling Annex F substances (HFCs). The management and implementation of this Agreement will be undertaken by the Plan’s project management unit (PMU) which falls under the direct authority of the NOU in the DCC.
The MAE, through the PMU and the NOU, will collaborate and coordinate with the Ministry of Industry and Trade (MOIT) and the Department of Customs (DOC) to implement the import/control system for HFCs; review annual HFC import/export license applications; and establish and publish the annual import quotas for HFCs for the period 2024 through 2029.
In order to assist the MAE in monitoring and evaluating the progress of implementation of this Agreement, the PMU and the NOU will:
(a) Update the NOU’s management information system (MIS) that captures and tracks all relevant and required data on the importation of Montreal Protocol-controlled substances on an annual basis;
(b) Update the data on the actual amount of imported HFCs;
(c) Monitor and report, in cooperation with the DOC, any incidents of illegal import of HFCs;
(d) Monitor the progress of HFC phase-down on the demand side;
(e) Maintain a project MIS on HFC consumption and related activities;
(f) Compile periodic progress reports of the Plan implementation and HFC phase-down achievements for sharing with the MAE, the MOIT, and the Ministry of Finance (MOF);
(g) Prepare Tranche Implementation Reports and Plans according to the schedule set forth in Appendix 2-A;
(h) Prepare other monitoring reports as required by the MAE or other Government authorities and by Executive Committee decision, in coordination with the Lead IA; and
(i) Carry out safety and technical reviews of all relevant activities undertaken under the Plan.
The MAE, along with its Government partner agencies (MOIT and MOF), will be responsible for the sustainability of consumption reduction targets achieved through this Agreement; reviewing the PMU reports and data; and instituting control and policy measures which facilitate HFC control and reductions according to the Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $6.47 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XXXVI
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF ZIMBABWE
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Zimbabwe (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 761,510 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(e) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(f) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
(g) Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
(h) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNDP and the Government of France have agreed to be the cooperating implementing agencies (the “Cooperating IAs”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IAs taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IAs will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IAs are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IAs with the fees set out in rows 2.2, 2.4 and 2.6 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IAs to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IAs with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2018*
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	1,210,624
	1,210,624
	1,210,624
	1,210,624
	1,210,624
	1,089,561
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	21.9
	21.9
	21.9
	21.9
	26.3
	37.1
	n/a

	
	
	CO2‑eq tonnes
	n/a
	945,654
	945,654
	945,654
	945,654
	892,463
	761,510
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	0
	151,500
	0
	0
	106,500
	0
	54,000
	312,000

	2.2
	Support costs for Lead IA (US $)
	0
	19,695
	0
	0
	13,845
	0
	7,020
	40,560

	2.3
	Cooperating IA (UNDP) agreed funding (US $)
	326,954
	90,000
	0
	0
	0
	0
	30,000
	446,954

	2.4
	Support costs for Cooperating IA (US $)
	22,887
	11,700
	0
	0
	0
	0
	3,900
	38,487

	2.5
	Cooperating IA (France) agreed funding (US $)
	100,000
	0
	0
	0
	0
	0
	0
	100,000

	2.6
	Support costs for Cooperating IA (US $)
	13,000
	0
	0
	0
	0
	0
	0
	13,000

	3.1
	Total agreed funding (US $)
	426,954
	241,500
	0
	0
	106,500
	0
	84,000
	858,954

	3.2
	Total support costs (US $)
	35,887
	31,395
	0
	0
	13,845
	0
	10,920
	92,047

	3.3
	Total agreed costs (US $)
	462,841
	272,895
	0
	0
	120,345
	0
	94,920
	951,001

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	449,114

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	20,735

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


* Approved at the 82nd meeting to phase out 14.50 mt (20,735 CO2‑eq tonnes) of HFC-134a in the manufacturing of domestic refrigerators at Capri (decision 82/81).
APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. Overall monitoring will be provided by the Ministry of Environment, Climate and Wildlife, through the national ozone unit (NOU), with assistance from the Lead IA. The NOU will submit annual progress reports of status of implementation of the Plan to the Lead IA.
1. Consumption will be monitored and determined from the official data on the import and export of substances as registered by the relevant Government departments. The NOU will compile and report the following data and information each year on or before the relevant deadlines:
(a) Reports on the consumption of the substances to be submitted to the Ozone Secretariat in line with Article 7 of the Montreal Protocol; and
(b) Reports on country programme data to be submitted to the Secretariat of the Multilateral Fund.
Monitoring of development of the Plan and verification of the achievement of the performance targets will be assigned to an independent local company or to independent local consultant(s) by the Lead IA. The company or consultant(s) responsible for verification will have full access to relevant technical and financial information related to the implementation of the Plan.
The Ministry of Environment, Climate and Wildlife will be responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IAs;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IAs and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IAs, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IAs on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IAs will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IAs, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $3.66 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.

	
	
	
	
	







1
8
9
image1.png




image2.png




