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STATUS REPORTS AND REPORTS ON PROJECTS WITH SPECIFIC REPORTING REQUIREMENTS WITH NO OUTSTANDING ISSUES   
The present document consists of two sections, namely (i) projects with implementation delays and projects for which special status reports were requested, and (ii) projects with specific reporting requirements with no outstanding issues. The reporting on these projects, after the Secretariat’s review, have no outstanding issues and therefore do not require the Executive Committee to consider them individually.
I.	Projects with implementation delays and for which special status reports were requested
At the 97th meeting, the Executive Committee noted that the bilateral and implementing agencies would report, at the 98th meeting, on 78 projects with implementation delays and 14 ongoing projects or tranches of multi‑year agreements (MYAs) recommended for additional status reports (decision 97/9(c)). Accordingly, relevant bilateral and implementing agencies submitted the requested reports to the 98th meeting. In reviewing the reports, the Secretariat held discussions with bilateral and implementing agencies and several issues have been satisfactorily addressed. Table 1 provides a summary of projects with implementation delays and projects recommended for additional status reports including their levels of progress, recommendations by the Secretariat and references to annexes to the present document.
Table 1. Summary of projects with implementation delays and additional status reports 
	Level of progress
	Number of projects
	Decision
	Recommendation
	Annex

	Implementation delays

	Progress 
(Individual projects and MYAs)
	64
	32/4
	To be removed from future reporting
	n/a

	Some progress 
(Individual projects and MYAs)
	11
	32/4
	To continue monitoring until their final completion
	Annex I

	No progress for the first time (MYAs)
	0
	84/45
	To continue monitoring until their final completion 
	n/a

	Cancellation
	3
	n/a
	To be cancelled 
	n/a

	Total
	78
	
	
	

	Status reports

	No outstanding issues
	10
	51/13
	To be removed from future reporting
	n/a

	Issues still need to be resolved 
	4
	51/13
	To request submission of additional status reports 
	Annex II

	Total
	14
	
	
	



Project cancellation

At the 97th meeting, the Executive Committee requested the Secretariat to send a letter to Afghanistan and to UNIDO, as the lead implementing agency, regarding possible cancellation of the HCFC phase-out management plan (HPMP) for the country (stage I, third tranche (AFG/PHA/79/INV/22), stage I, fourth tranche (AFG/PHA/85/INV/28) and stage II, first tranche (AFG/PHA/85/INV/30)) (decision 97/13(d)).
In line with the decision, UNIDO informed the Secretariat that the UN Security Council sanctions have imposed targeted measures on Afghanistan, requiring all projects to undergo formal compliance verification before proceeding. UNIDO added that the UN system currently refrains from actions that may give rise to a perception of recognizing the de facto authorities in Afghanistan and from direct budgetary support or actions that could be seen as legitimizing such authorities. Considering that this situation has created significant procedural, legal, and operational barriers for UNIDO to proceed with the implementation of these projects, UNIDO would like to request the cancellation of the following additional projects in Afghanistan: HPMP (stage I, fourth tranche) (AFG/PHA/95/TAS/33); HPMP (stage II, first tranche) (AFG/PHA/95/TAS/34); extension of institutional strengthening project (phase X: 1/2022‑12/2023) (AFG/SEV/95/INS/35); and preparation of national inventory of banks of waste controlled substances and development of a national plan for management of these substances (decision 91/66) (AFG/DES/94/PRP/32).
Table 2 presents the status of disbursements for each project. 
Table 2. Projects recommended for cancellation for Afghanistan
	Project code
	Project title
	Funds 
approved 
(US $)
	Funds disbursed (US $)
	Balance (US $)

	AFG/PHA/79/INV/22
	HCFC phase-out management plan (stage I, third tranche)
	83,000
	11,914
	71,086

	AFG/PHA/85/INV/28
	HCFC phase-out management plan (stage I, fourth tranche)
	28,276
	0
	28,276

	AFG/PHA/85/INV/30
	HCFC phase-out management plan (stage II, first tranche)
	90,000
	54,580
	35,420

	AFG/PHA/95/TAS/33
	HCFC phase-out management plan (stage I, fourth tranche) 
	28,453
	 0
	28,453

	AFG/PHA/95/TAS/34
	HCFC phase-out management plan (stage II, first tranche) 
	180,908
	 0
	180,908

	AFG/SEV/95/INS/35
	Extension of institutional strengthening project (phase X: 1/2022-12/2023)
	192,000
	0
	192,000

	AFG/DES/94/PRP/32
	Preparation of national inventory of banks of waste controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	 0
	90,000



In consultation with UNIDO, it was agreed that the projects listed above would be cancelled and the remaining balances would be returned to the 99th meeting. In addition, stage II of the HPMP for Afghanistan included two remaining tranches approved in principle and scheduled for submission in 2025 and 2026, respectively; as these have not been submitted, they are also recommended for cancellation. The Executive Committee may wish to cancel the projects listed in table 2, as well as the two remaining tranches approved in principle under stage II of the HPMP for Afghanistan.    
Status report on the implementation of the HFC quota system in Mauritius

At its 95th meeting, in approving stage I of the Kigali HFC implementation plan (KIP) for Mauritius, the Executive Committee noted that the Government of Germany would provide, as part of its 2024 financial and progress report to be considered at the second meeting in 2025, an update on the status of implementation of the HFC quota system in Mauritius (decision 95/67(b)(ii)). The Government of Germany reported that the HFC quota system has been in place in Mauritius since January 2025 and provides for the allocation of imports to HFC importers based on baseline HFC average imports. The system also includes a provision to earmark a small portion of HFC imports to address emergencies and special requests for HFC imports from Government institutions. A one-day workshop was conducted in 2025 with relevant importers and stakeholders to sensitize them on Kigali Amendment provisions, the KIP recommendations, as well as the basis for HFC quota calculations, and how they can manage their quota effectively.
Recommendation

The Executive Committee may wish:
To note:
The reports on implementation delays and the status reports submitted by bilateral and implementing agencies, contained in document UNEP/OzL.Pro/ExCom/98/6; 
That bilateral and implementing agencies would report to the Executive Committee at the 99th meeting on 11 projects with implementation delays, as indicated in annex I to the present document, and on four projects recommended for additional status reports, as indicated in annex II to the present document, as part of the 2025 annual and financial progress report of the bilateral and implementing agencies; 
To approve the recommendations on ongoing projects with specific issues listed in the last column of the table in annex II to the present document;  
To cancel the following projects for Afghanistan and to request UNIDO to return the remaining balances to the 99th meeting: HCFC phase-out management plan (HPMP) (stage I, third tranche) (AFG/PHA/79/INV/22); HPMP (stage I, fourth tranche) (AFG/PHA/85/INV/28); HPMP (stage I, fourth tranche) (AFG/PHA/95/TAS/33); HPMP (stage II, first tranche) (AFG/PHA/85/INV/30); HPMP (stage II, first tranche) (AFG/PHA/95/TAS/34); extension of institutional strengthening project (phase X: 1/2022‑12/2023) (AFG/SEV/95/INS/35); and preparation of national inventory of banks of waste controlled substances and development of a national plan for management of these substances (decision 91/66) (AFG/DES/94/PRP/32); and
To cancel the outstanding tranches approved in principle under stage II of the HPMP for Afghanistan.
II.	Projects with specific reporting requirements with no outstanding issues
An overview
Table 3 lists the reports on projects with specific reporting requirements with no outstanding issues.
Table 3. Reports on projects with specific reporting requirements with no outstanding issues
	Country 
	Project title 
	Paragraphs 

	A. Reports related to HCFC phase-out management plans 

	Argentina
	HCFC phase-out management plan (stage II – availability of low‑global‑warming‑potential alternatives to HCFC‑141b in the foam sector and transitional use of high-global-warming‑potential alternatives)
	10–21

	Bangladesh
	HCFC phase-out management plan (stage II – report on the number of air conditioners using R-290/HFC-32 under the air-conditioning sector conversion project)
	22–29

	Bhutan
	HCFC phase‑out management plan and additional activities to maintain energy efficiency in the refrigeration servicing sector under decision 89/6 (request for extension of project completion date)
	30–35

	Iraq
	HCFC phase-out management plan (stage II – completion of stage I, national phase out plan, and project to replace CFC-12 with isobutane and CFC-11 with cyclopentane in domestic refrigeration manufacturing at Light Industries)
	36–41

	Kuwait
	HCFC phase-out management plan (stage II) – request for extension of the project completion date
	42–47

	Mauritania
	HCFC phase‑out management plan (stage I – progress report on the implementation of the work programme associated with the third and final tranche)
	48–56

	Türkiye
	HCFC phase-out management plan (stage I – progress report on the implementation of the work programme associated with the fifth and final tranche)
	57–67

	B. Report related to Kigali HFC implementation plan Agreements

	Multiple
	Agreements for the reduction in consumption of HFCs in accordance with stage I of Kigali HFC implementation plans
	68–72

	C. Report related to additional activities to maintain energy efficiency in the refrigeration servicing sector (decision 89/6) 

	Maldives
	Additional activities to maintain energy efficiency in the refrigeration servicing sector under decision 89/6(b) (final progress report) (UNEP)
	73–81

	D. Report related to pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (decision 91/65)

	Cameroon
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non‑investment activities) (request for extension of project completion date)
	82–86

	E. Report related to project preparation for enhancing energy efficiency in the context of HFC phase-down in the refrigeration and air-conditioning manufacturing sector (decision 94/60)

	Türkiye
	Status of preparation of a project to enhance energy efficiency and to convert 29 refrigeration and air-conditioning manufacturing enterprises from the use of hydrofluorocarbons to low‑global‑warming‑potential technology
	87–91

	F. Report related to preparation of a national inventory of banks of used or unwanted controlled substances and a plan for the collection, transport, and disposal of such substances (decision 91/66)

	Mauritius
	Preparation of a national inventory of banks of waste controlled substances and development of a national plan for management of these substances (decision 91/66) (request for extension of project completion date)
	92–96


1. Reports related to HCFC phase-out management plans 
Argentina: HCFC phase-out management plan (stage II – availability of low‑global‑warming‑potential alternatives to HCFC‑141b in the foam sector and transitional use of high-global-warming‑potential alternatives) (UNIDO and the Government of Italy)
Background
1. At its 92nd meeting, in approving the third tranche of stage II of the HCFC phase-out management plan (HPMP) for Argentina (decision 92/31), the Executive Committee noted, inter alia:
(a) The challenges presented by the lack of supply of low-global-warming-potential (GWP) alternatives to HCFC-141b in the foam sector, which had delayed the implementation of stage II activities in the polyurethane (PU) foam sector that would have allowed the Government of Argentina to phase out 85.92 ODP tonnes of HCFCs; and
(b) That, in the event that alternatives were not available on the local market, high‑GWP alternatives could be used, on a transitional basis only, and that the Government of Argentina would report to each Executive Committee meeting on the progress made towards ensuring that the selected technologies, including the associated components, were available on a commercial basis in the country, on the understanding that incremental operating costs would not be funded until the transition to the agreed alternatives was complete.
2. UNIDO has reported on this issue at successive Executive Committee meetings,[footnoteRef:2] most recently at the 97th meeting, noting that by August 2025 three systems houses had received HFOs and begun placing new formulations on the local market. While suppliers and systems houses were working to improve the process, and while overall HFO availability had increased, supply‑chain uncertainty persisted, as only one supplier had begun deliveries so far, and the uneven transition to HFOs as blowing agents in the region was not yet fully sustainable. Despite notable progress, challenges related to availability and pricing, supply‑chain stability and limited supplier base remained unresolved, resulting in the continued transitional use of high‑GWP substances. UNIDO also highlighted the willingness of the local systems houses to adopt HFOs once price and supply constraints had been addressed. [2:  Paragraphs 2–9 of document UNEP/OzL.Pro/ExCom/93/20, paragraphs 5–14 of document UNEP/OzL.Pro/ExCom/94/9, paragraphs 5–18 of document UNEP/OzL.Pro/ExCom/96/11 and paragraphs 10–15 and 31–32 of document UNEP/OzL.Pro/ExCom/97/36.] 

3. Accordingly, at the 97th meeting, the Executive Committee requested the Government of Argentina and UNIDO, in line with decision 92/31(c)(ii), to provide an update at the 98th meeting on the local market availability of low-GWP alternatives to HCFC-141b in the foam sector and on the transitional use of high‑GWP alternatives (decision 97/35).[footnoteRef:3] [3:  Blanket approval of the fourth tranche of stage II of the HPMP for Argentina.] 

Progress report
4. On behalf of the Government of Argentina, UNIDO submitted a report providing an update on the status of availability, supply and price of HFOs for the PU foam sector upon additional consultations held with key suppliers and local systems houses.
With regard to availability, HFO‑1233zd(E) in Argentina is currently transitioning from a trial phase to a more regular supply arrangement. Local systems houses have reported maintaining sufficient operational inventories to avoid supply disruptions in the second quarter of 2025. The sole supplier is also exploring alternative supply‑chain configurations to reduce reliance on ton tanks and to improve medium‑term supply continuity.
Smaller-scale distribution of HFOs still relies primarily on ton tanks, and logistical challenges associated with the return and rotation of those containers persist. Discussions are ongoing regarding the establishment of a local fractionation scheme, which could improve short‑term availability. The sector has expressed concern that, under a single‑supplier scenario, such an arrangement may not ensure competitive pricing and could introduce additional intermediation costs.
UNIDO also reported that growing uncertainty around international regulations could affect the long‑term adoption of HFOs in Argentina. While HFO is currently the main low‑GWP alternative to HCFC‑141b for certain uses, concerns about fluorinated substances and possible restrictions on per- and polyfluoroalkyl substances (PFAS) in some markets create a risk of future regulatory changes, potentially requiring additional transitions. This is especially critical for spray foam applications, where no other viable low‑GWP alternatives are currently available.
Secretariat’s comments
In updating the Secretariat on the current prices of HFO‑1233zd(E) in Argentina, UNIDO indicated that they varied depending on several factors, including whether a given systems house could procure international standard tank containers rather than ton tanks, volumes purchased, existence of long‑term supply contracts, and possibility of sourcing through offices in Brazil. Based on discussions with the technology supplier, the approximate price is not expected to exceed US $18/kg, remaining significantly higher than alternative options.
Noting the increasing availability of HFOs and ongoing coordination to avoid supply gaps, the Secretariat inquired whether the temporary use of HFCs by systems houses and their clients had now ceased. UNIDO reported that the only enterprise using HFCs was not a systems house but rather a reseller that was still experiencing difficulties buying and importing HFO-based systems without losing most lifetime stability during shipment.
5. The Secretariat notes with appreciation that the Government of Argentina continued discussions with the HFO supplier and systems houses, and that further progress in increasing availability and reducing prices was achieved. Noting that the issue of availability of alternatives in PU foam manufacturing will be discussed under agenda item 9 of the 98th meeting, the Secretariat has included the updated information related to the PU foam project in Argentina in document UNEP/OzL.Pro/ExCom/98/56.
6. Despite the additional significant progress made, the issues of availability and pricing of low-GWP alternatives have still not been fully resolved, and high-GWP alternatives are still being used on a transitional basis. Therefore, in line with decision 92/31(c)(ii), the Secretariat recommends that the Government of Argentina continue reporting to the Executive Committee on the matter.
Recommendation
7. The Executive Committee may wish:
(a) [bookmark: _Hlk152497896]To note the report on the update on the status of availability of low‑global‑warming‑potential (GWP) alternatives to HCFC-141b in the foam sector and on the transitional use of high‑GWP alternatives in the context of stage II of the HCFC phase‑out management plan (HPMP) for Argentina, provided by UNIDO and contained in document UNEP/OzL.Pro/ExCom/98/6; and
(b) To request the Government of Argentina and UNIDO, in line with decision 92/31(c)(ii), to provide as part of the yearly progress report on the implementation of the final tranche of stage II of the HPMP, due at the 99th meeting, an update on local market availability of low‑GWP alternatives to HCFC‑141b in the foam sector and on the transitional use of high‑GWP alternatives.
Bangladesh: HCFC phase-out management plan (stage II – report on the number of air conditioners using R-290/HFC-32 under the air-conditioning sector conversion project) (UNDP)
Background
At the 94th meeting, the Executive Committee approved the third and final tranche of stage II of the HCFC phase-out management plan (HPMP) for Bangladesh, noting that the Government, through UNDP, would report the number of air conditioners using R-290/HFC-32 as the refrigerant, excluding Unitech Products, that were manufactured each year during the period 2025–2027 by each of the enterprises funded under the air-conditioning (AC) sector conversion project, doing so at the first meeting of every following year (decision 94/32(b)(ii)). 
In line with the decision, the Government of Bangladesh, through UNDP, has submitted a report on the five enterprises funded under the AC sector conversion project.
Progress report
Table 4 below provides the number of AC units manufactured by each of the enterprises between January and December 2025.
Table 4. AC units manufactured from 1 January to 31 December 2025
	Enterprise
	Split type
(residential)
	All types (commercial)

	Walton Hi-Tech Industries
	R-290
	547
	0

	
	HFC-32
	298,521
	3,800

	Cooling Point Engineering Services
	R-290
	0
	0

	
	HFC-32
	0
	20

	Elite Hi-Tech
	R-290
	688
	292

	
	HFC-32
	11,517
	0

	AC Bazar Industries Ltd.
	R-290
	400
	0

	
	HFC-32
	900
	383

	Supreme Air Conditioning Co.
	R-290
	1,682
	0

	
	HFC-32
	14,921[footnoteRef:4] [4:  Due to an inadvertent typographical error, an incorrect quantity of 136,480 units was reported by UNDP to the 97th meeting. The correct figure was 13,648 units as of October 2025, while the updated production level is 14,921 units as of 31 December 2025.] 

	6,758

	Total
	R-290
	3,317
	292

	
	HFC-32
	325,859
	10,961



The report indicates that, as of December 2025, Walton Hi-Tech Industries and Elite Hi-Tech had operationally completed the conversion of their manufacturing facilities with the launch of R-290-based room air-conditioner models with a capacity of less than 1.5 TR[footnoteRef:5] to the local market since the third quarter of 2025. The remaining three enterprises have completed all conversion milestones and safety audit. Marketing of new AC units using the alternative technologies was undertaken beginning the fourth quarter of 2025. Additionally, the ban on the local manufacturing and import of HCFC-22-based room air conditioners with a capacity of up to 1.5 TR was enacted and is being enforced since 1 January 2026.  [5:  Ton of refrigeration] 

UNDP also reported that, while the uptake of R‑290 technology is gradually increasing across the five enterprises, driven by its high energy efficiency and low global‑warming potential, its wider adoption is constrained by higher costs, safety concerns, and limited technician capacity. HFC‑32 technology remains the preferred option due to established servicing infrastructure and lower costs.
Secretariat’s comments
The Secretariat notes that the project has successfully established an initial domestic manufacturing capacity for HCFC-free air conditioners across the five participating enterprises. Within their manufacturing portfolios, HFC-32 has emerged as the dominant transitional technology, while R-290 is positioned as a potential option that may be scaled up in the future by four of these enterprises producing room AC units with a capacity below 1.5 TR. The combination of completed conversions, initial production volumes, and the enforcement of regulatory measures limiting HCFC-22 use provides a favourable baseline for sustained market transformation beyond 2025.
Several risks remain to be addressed in the context of the adoption of R-290-based air conditioners. These primarily include safety perceptions related with flammability, a limited number of trained and certified technicians capable of handling hydrocarbon-based technologies, and market factors contributing to higher costs of key components for such equipment. Some of these challenges, particularly those related to the capacity of the servicing sector to handle, install and service R-290 units, are expected to be addressed during stage III of the HPMP, to be completed by 2030. Additional measures to support the faster adoption of alternative technologies and the safe handling of hydrocarbons are expected to be addressed during stage I of the Kigali HFC implementation plan, to be submitted in the future.
Recommendation
The Executive Committee may wish to note the report on the number of air conditioners using R‑290/HFC-32 as the refrigerant that were manufactured in 2025 by each of the enterprises funded under the air-conditioning sector conversion project of stage II of the HCFC phase-out management plan for Bangladesh, provided by UNDP and contained in document UNEP/OzL.Pro/ExCom/98/6.
Bhutan: HCFC phase‑out management plan and additional activities to maintain energy efficiency in the refrigeration servicing sector under decision 89/6 (request for extension of project completion date) (UNEP and UNDP)
Background
At its 95th meeting, the Executive Committee approved the fourth and final tranche of the HCFC phase-out management plan (HPMP) for Bhutan in the amount of US $147,000, plus agency support costs of US $18,350, which included US $100,000 plus agency support costs of US $13,000, for UNEP, for additional activities to maintain energy efficiency (decision 89/6).[footnoteRef:6] The operational completion date in line with the HPMP Agreement is 31 December 2026. [6:  Annex XVII to document UNEP/OzL.Pro/ExCom/95/94] 

Request for extension

UNEP reported that the project for additional activities to maintain energy efficiency in the refrigeration servicing sector requires additional time to complete, specifically, the activity to enhance the scheme to promote low-global-warming-potential appliances and to strengthen the appliance registration process that had faced initial delays and are now resolved.
Accordingly, on behalf of the country, UNEP, as the lead implementing agency, requested an extension of the implementation period of the HPMP to 31 December 2027 to enable the completion of the aforementioned activities.
Secretariat’s comments
The Secretariat noted that the country consumed 122 kilograms or 0.007 ODP tonnes of HCFC-22 in 2025, which is in line with the target specified in the Agreement between the country and the Executive Committee. The Secretariat also noted that the energy efficiency activities related to training and the other activities of the HPMP are expected to be completed on time, by December 2026.
Given that the issues that caused the initial delays in the energy efficiency-related project component have been resolved, the Secretariat considers that the requested extension of implementation of the HPMP would facilitate the completion of the remaining activities in that component.
Recommendation
The Executive Committee may wish:
(c) To note the request for the extension of the implementation of the HCFC phase-out management plan (HPMP) for Bhutan, as submitted by UNEP and contained in document UNEP/OzL.Pro/ExCom/98/6; and
(d) To approve, on an exceptional basis, and on the understanding that no further extension of project implementation would be requested, the extension to 31 December 2027 of the complete date of the project referred to in subparagraph (a) above, to allow the completion of the additional activities to maintain energy efficiency in the refrigeration servicing sector submitted in line with decision 89/6.
Iraq: HCFC phase-out management plan (stage II – completion of stage I, national phase‑out plan, and project to replace CFC-12 with isobutane and CFC-11 with cyclopentane in domestic refrigeration manufacturing at Light Industries) (UNEP and UNIDO)
Background
8. At its 87th meeting, the Executive Committee approved stage II of the HCFC phase-out management plan (HPMP) for Iraq, noting that its second tranche could only be considered upon completion of stage I of the HPMP (IRQ/PHA/74/INV/23), the national phase-out plan (NPP) (IRQ/PHA/58/INV/09), and the project to replace refrigerant CFC-12 with isobutane and foam-blowing agent CFC-11 with cyclopentane in the manufacturing of domestic refrigerators and chest freezers at Light Industries Company (IRQ/REF/57/INV/07) (decision 87/40(c)). At the time of second tranche submission to the 95th meeting, the projects listed above had not been completed by UNIDO; accordingly, the tranche had been approved for UNEP only, noting that no further funding would be considered for UNIDO until the condition was fulfilled. Furthermore, on an exceptional basis, the completion dates for stage I of the HPMP and projects IRQ/REF/57/INV/07 and IRQ/PHA/58/INV/09 were extended to 31 December 2025, on the understanding that UNIDO would correct the implementation status of the latter two to “ongoing” (ONG) in its 2024 annual and financial progress reports, and submit to the 96th meeting a report on progress achieved in the implementation of all three projects (decision 95/52).
9. UNIDO presented the progress reports at the 96th and 97th meetings. The report submitted at the 97th meeting confirmed that all activities implemented under stage I of the HPMP, including the distribution of tools to beneficiaries, would be completed by December 2025, as per the extension provided. Under the NPP, Nassr State Company would also complete all activities by December 2025, Iraqi Steel would no longer participate and would complete the installation independently with its own resources, committing not to use HCFCs or HFCs for foam manufacturing, and the project for Light Industries would be operationally completed by 31 December 2025, when UNIDO would transfer the ownership of equipment, upon commitment by Light Industries that, if conversion work extended beyond that date, the enterprise would be responsible for the completion. The national ozone unit would monitor compliance with this agreement and UNIDO would continue providing technical assistance after completion of the project in December 2025 to ensure proper conversion. The Executive Committee noted the report and requested UNIDO to submit to the 98th meeting a progress report on the completion of those projects (decision 97/16).
Progress report
10. On behalf of the Government of Iraq, UNIDO submitted progress reports for the following projects:
(a) HPMP (stage I, second tranche) (servicing sector technical assistance) (IRQ/PHA/74/INV/23): Due to customs clearance delays, toolkits[footnoteRef:7] for 100 technicians were procured, delivered and distributed to beneficiaries in April 2026; the project completion report (PCR) was submitted in the same month, and a balance of US $8,063.71 will be returned at the 98th meeting; [7:  Including electronic leak detectors, charging oil pumps, portable nitrogen‑blowing equipment, torque wrench tool sets, Lokring pliers, assembly jaws, and connectors of varying diameters.] 

(b) NPP (conversion from CFC‑11 to cyclopentane at two polyurethane foam manufacturers) (IRQ/PHA/58/INV/09): Nassr State Company received all equipment, carried out testing and training to commence commercial production, and completed its conversion in December 2025; the project at Iraqi Steel was cancelled, and a balance of US $26,319.69 will be returned at the 99th meeting; and
(c) Project to replace CFC-12 with isobutane and CFC-11 with cyclopentane in domestic refrigeration manufacturing at Light Industries (IRQ/REF/57/INV/07): UNIDO completed equipment installation and commissioning; the project was operationally completed in December 2025 and will be financially completed in June 2026.
Level of fund disbursement
11. As of April 2026, fund disbursement for the second tranche of stage I of the HPMP and for the NPP had reached 96.5 and 95.8 per cent, respectively; and the total amount of US $2,161,581 approved for the conversion project at Light Industries had been disbursed, as shown in table 5. The remaining balances will be returned to the 98th and 99th meetings.
Table 5. Financial report for projects to be completed for Iraq as of April 2026 (US $)
	Projects
	Funds approved
	Funds disbursed
	Disbursement rate (%)
	Fund
balance

	HPMP (stage I, 2nd tranche)
	230,000
	221,936.29
	96.5
	*8,063.71

	NPP (Nassr State Company and Iraqi Steel)
	4,353,530
	4,171,591.85
	95.8
	**26,319.69

	Conversion at Light Industries
	2,161,581
	2,161,581
	100.0
	0


* Balance to be returned at the 98th meeting
** Remaining balance to be returned at the 99th meeting after paying pending obligations for US $155,618.46.
Secretariat’s comments
12. The Secretariat notes that all outstanding projects have now been operationally completed, that the PCR for stage I of the HPMP has been submitted, and that the remaining balances from stage I of the HPMP and from the NPP will be returned at the 98th and 99th meetings, respectively. In accordance with decision 87/40(c), UNIDO’s second tranche of stage II of the HPMP for Iraq can be submitted for the consideration of the Executive Committee only once the PCRs for the NPP and for the conversion project at Light Industries are submitted to the Secretariat.
Recommendation
13. The Executive Committee may wish:
(a) To note the final reports on progress achieved in completing the second tranche of stage I of the HCFC phase‑out management plan (HPMP) (IRQ/PHA/74/INV/23), the first tranche of the national phase-out plan (IRQ/PHA/58/INV/09), and the project to replace refrigerant CFC‑12 with isobutane and foam-blowing agent CFC-11 with cyclopentane in the manufacturing of domestic refrigerators and chest freezers at Light Industries Company (IRQ/REF/57/INV/07) for Iraq, as submitted by UNIDO and contained in document UNEP/OzL.Pro/ExCom/98/6; and
(b) To request UNIDO to submit the project completion reports for the projects IRQ/PHA/58/INV/09 and IRQ/REF/57/INV/07 prior to the 99th meeting to allow for the consideration of UNIDO’s second tranche of stage II of the HPMP, in line with decision 87/40(c).
Kuwait: HCFC phase-out management plan (stage II) – request for extension of the project completion date (UNEP and UNIDO)

Background

At the 88th meeting, the Executive Committee approved stage II of the HCFC phase-out management plan (HPMP) for Kuwait, to be implemented by UNEP and UNIDO, for the period from 2021 to 2025 to reduce HCFC consumption by 67.5 per cent of the country’s baseline (decision 88/51). The second tranche, approved at the 95th meeting, is currently under implementation. The third and final tranche was scheduled for submission in 2025, with the overall completion of the HPMP planned for December 2026, in line with the Agreement between the Government and the Executive Committee. 
Request for extension

Kuwait has encountered exceptional circumstances arising from developments in the region since mid-2025, which have affected the overall operational environment and the ability to carry out planned project activities. In addition, changes in the management of the Environment Public Authority (EPA) in May 2025 resulted in transitional adjustments that have impacted coordination and decision‑making processes essential for the sound and timely implementation of planned activities. 
Under UNEP’s implementation, key activities have advanced, including the signing of Project Cooperation Agreements for both tranches and initial disbursements to the EPA; however, several activities remain outstanding pending resolution of the above circumstances. Under UNIDO’s implementation plan, the reclamation centre has been established and is operational; laboratory equipment has been delivered to the EPA; and missions have been conducted to identify training centres and develop certification frameworks. However, the delivery of certain equipment for the training centres, along with equipment for laboratory for the recovery, recycling and reclamation centre, remain pending due to shipping constraints associated with the regional situation; after delivery, the equipment would be installed and commissioned. 
In light of the above, UNEP, on behalf of the Government of Kuwait, has requested an extension of the project implementation period to 31 December 2027 to allow for the completion of all remaining activities.
Secretariat’s comments

The Secretariat notes the challenges faced by the Government of Kuwait in implementing stage II of its HPMP, which have delayed the finalization of planning and implementation of certain activities. The Secretariat sought clarification from UNEP and UNIDO on the current status of implementation and the measures in place to ensure completion within the requested extended timeframe. UNEP and UNIDO confirmed that the situation is being actively managed, allowing both implementing agencies to make substantive progress; that the third and final tranche is planned for submission at the 99th meeting; and that all remaining activities are expected to be completed by 31 December 2027.
Recommendation 
The Executive Committee may wish: 
To note the request for extension of stage II of the HCFC phase-out management plan for Kuwait, as submitted by UNEP and contained in document UNEP/OzL.Pro/ExCom/98/6; and
To approve, on an exceptional basis, and on the understanding that no further extension would be approved, the extension to 31 December 2027 of the completion date of the project referred to in subparagraph (a) above.
Mauritania: HCFC phase‑out management plan (stage I – progress report on the implementation of the work programme associated with the third and final tranche) (UNEP and UNIDO)
Background
In approving the third and final tranche of stage I of the HCFC phase-out management plan (HPMP) for Mauritania, the Executive Committee requested the Government of Mauritania, UNEP and UNIDO to provide, to the 98th meeting, a report on progress made in implementing the remaining activities under stage I of the HPMP, including the outcome of the techno-economic feasibility assessment detailing whether a national recovery, recycling and reclaiming (RRR) scheme for Mauritania would be sustainable or not, the operational framework for the scheme and its links to the existing recovery centres, and equipment to be procured.[footnoteRef:8]  [8:  Decision 97/35 (blanket approval)] 

The Government of Mauritania reported in its country programme data a consumption of 6.32 ODP tonnes of HCFCs in 2025, which is 69 per cent below the country’s HCFC baseline for compliance and is in accordance with the maximum allowable consumption for that year.
Progress report
On behalf of the Government of Mauritania, UNEP, as the lead implementing agency, has submitted a progress report on the implementation of the remaining activities under stage I of the HPMP including the outcome of the assessment of sustainability of the national RRR scheme.
All activities planned in the servicing sector under the UNEP component of the second tranche have been completed as follows:
(a) [bookmark: _Hlk126934425][bookmark: _Hlk126663552]Training programme for customs and enforcement officers: Five training workshops were delivered, resulting in the training of 125 customs and enforcement officers;
(b) Training programme for refrigeration technicians: Training-of-trainers and subsequent national training sessions were completed, with a total of 30 trainers and over 200 technicians trained on good servicing practices, including recovery, recycling and safe handling of refrigerants;
(c) Survey and needs assessment in the refrigeration and air-conditioning (RAC) sector: A comprehensive survey and needs assessment were conducted, providing updated data on HCFC consumption, equipment population and sector needs; and
(d) Monitoring and reporting: Monitoring systems were established, and data collection was strengthened in coordination with the customs and relevant stakeholders. 
Activities implemented by UNIDO are ongoing and the techno-economic feasibility study of the national RRR scheme was submitted to the Secretariat:
(a) Techno-economic feasibility assessment of the RRR scheme: The assessment concluded that a recovery and recycling scheme was feasible and could be established as a viable near-term outcome; however, reclamation was unlikely to be economically viable in the near term. The volume required for reclamation viability is less than 60 tonnes per year nationally, which is considered difficult to achieve at current consumption levels. The assessment also outlined a regulatory roadmap to operationalize the scheme, infrastructure availability, a detailed six-phase implementation plan, equipment list, training and certification, quality control measures, and institutional roles and responsibilities;
(b) Technical assistance and equipment programme for recovery and storage centres: Following the transfer of responsibilities from UNDP to UNIDO, procurement for both the first and second tranches was consolidated into a single order to optimize costs and logistics. The procurement process was finalized and equipment delivered in April 2026;
(c) Technical capacity-building for alternative refrigerants including hydrocarbons (R-290): The equipment has been delivered; UNIDO will coordinate with the national ozone unit to organize capacity-building training, scheduled for June 2026; and
(d) Refrigerant identifiers became available and three units were subsequently procured and delivered in April 2026.
As of May 2026, of the US $607,500 approved under stage I, US $348,101 had been disbursed (US $216,595 for UNEP and US $131,506 for UNIDO), as shown in table 6. The balance of US $259,399 will be disbursed by 31 December 2027.
Table 6. Financial report of stage I of the HPMP for Mauritania (US $)
	Tranche
	UNEP
	UNIDO
	Total
	Disbursement rate (%)

	First
	Approved
	150,000
	105,000
	255,000
	79

	
	Disbursed
	149,845
	50,336
	200,181
	

	Second
	Approved
	66,750
	200,000
	266,750
	55

	
	Disbursed
	66,750
	81,170
	147,920
	

	Third
	Approved
	85,750
	0
	87,750
	0

	
	Disbursed
	0
	0
	0
	

	Total
	Approved
	302,500
	305,000
	607,500
	57

	
	Disbursed
	216,595
	131,506
	348,101
	

	
	Balance
	85,905
	173,494
	259,399
	


Secretariat’s comments
Since the assessment concluded that a recovery and recycling scheme was feasible, but a reclamation scheme was unlikely to be economically viable, a roadmap for implementation was developed to only include activities related to recovery and recycling. The report does not identify any existing formal recovery centres in Mauritania. After receiving details on the number and type of equipment procured for the recovery and storage centres[footnoteRef:9] as well as a procurement list[footnoteRef:10] for the recovery centres, the Secretariat requested clarification on the total number of storage and recovery centres to be assisted and the number of technicians to be trained. UNIDO confirmed that equipment would be installed and commissioned at two storage centres, five regional recovery centres and one central storage centre, and that training on the safe handling of flammable refrigerants, recovery and recycling procedures, and equipment operation at the training centres would be provided to at least 240 RAC technicians. [9:  Includes delivery of inter alia refrigerant recovery units, hoses, cylinders, scales, vacuum pumps, manifold gauges, leak detectors, sensors, hand-tools and refrigerant identifiers. ]  [10:  Includes inter alia vacuum recovery cylinders, refrigerant recovery machines, vacuum pumps, portable charging stations, scales, manifold gauges, leak detectors and brazing kits.] 

Conclusion
Mauritania continues to meet the HCFC control targets established in its Agreement with the Executive Committee, with consumption continuing to decline. The country effectively enforces a licensing and quota system to control the import of HCFCs. While there have been implementation delays due to change of the implementing agency, global supply constraints, and logistical challenges related to shipment and clarification of tax-exemption procedures, corrective measures have been undertaken. These measures include a revision of the equipment list to reflect market availability, resolution of shipment and customs‑related issues, and finalization of procurement processes. In the RAC servicing sector, equipment and tools have been provided to support the technical assistance and equipment programme for recovery and storage centres, as well as delivery of refrigerant identifiers. The final tranche was approved at the 97th meeting and the current disbursement rate, including the final tranche, is 57 per cent. UNEP and UNIDO confirmed that all core activities would be completed by 31 December 2026, with finalization and operational consolidation extending into 2027.
Recommendation
The Executive Committee may wish to note the report on progress made in implementing the remaining activities under stage I of the HCFC phase-out management plan (HPMP) for Mauritania, including the outcome of the techno-economic feasibility assessment of a national recovery, recycling and reclaiming scheme, the operational framework for the scheme and its links to the existing recovery centres, and equipment to be procured associated with the third and final tranche of stage I of the HPMP, submitted by UNEP and contained in document UNEP/OzL.Pro/ExCom/98/6.
Türkiye: HCFC phase-out management plan (stage I – progress report on the implementation of the work programme associated with the fifth and final tranche) (UNIDO and UNEP)
Background
At its 96th meeting, in approving the fifth and final tranche of stage I of the HCFC phase-out management plan (HPMP) for Türkiye, the Executive Committee requested the Government of Türkiye, UNIDO and UNEP to submit, on a yearly basis, progress reports on the implementation of the work programmes associated with the final tranche of the HPMP and verification reports through completion of the project.[footnoteRef:11] [11:  Decision 96/26 (blanket approval)] 

The Government of Türkiye reported a consumption of 2.75 ODP tonnes of HCFCs in 2024, which is 99.5 per cent below the HCFC baseline for compliance. Türkiye had already prohibited the import of HCFCs as of 1 January 2015, allowing only limited quantities of HCFC-22 exclusively for servicing purposes. As of 1 January 2025, the import of HCFC-22 for servicing has also been banned, thereby completing the total phase-out of HCFCs. The 2020–2025 HCFC consumption is shown in table 7.
Table 7. HCFC consumption in Türkiye (2020–2025 Article 7 data)
	HCFC
	2020
	2021
	2022
	2023
	2024
	2025*
	Baseline**

	HCFC-22

	Metric tonnes (mt)
	33.15
	63.96
	47.16
	42.48
	50.00
	0.00
	8,007.00

	ODP tonnes
	1.82
	3.52
	2.59
	2.34
	2.75
	0.00
	551.47

	Maximum allowable consumption
	50.00
	40.00
	30.00
	20.00
	10.00
	0.00
	n/a


* Verification report
** Baseline consumption includes HCFC-22, HCFC-141b, HCFC-142b, HCFC-123 and HCFC-124. Türkiye only consumed HCFC‑22 in 2013-2024.
The Government of Türkiye reported HCFC sector consumption data under the 2024 country programme (CP) implementation report that is consistent with the data reported under Article 7 of the Montreal Protocol. A draft 2025 CP implementation report was submitted on 5 May 2026, corroborating the zero consumption of HCFCs as indicated in the verification. The final report is currently being finalized.
Verification report
The verification report confirmed that Türkiye completely phased out HCFC consumption by 1 January 2025, five years ahead of the Montreal Protocol schedule, and that this achievement was enabled by strong institutional and regulatory frameworks, sectoral conversions, and decisive supporting activities under the HPMP.
To sustain Türkiye’s accelerated HCFC phase‑out, the verification recommended strengthening measures to prevent illegal imports through enhanced customs vigilance, including digital tools, refrigerant identifiers, sanctions, regional cooperation, and ongoing training for customs officers. It also underscored the need to maintain continuous training and certification systems and to integrate reclamation centres into national waste management frameworks, incentivize their use, and expand their mandate to include HFCs and other fluorinated gases (F-gases). Finally, it called for continued institutional strengthening to ensure that regulatory frameworks remain robust, transparent, aligned with the European Union standards for F‑gases, and supported by effective reporting and monitoring.
Progress report
On behalf of the Government of Türkiye, UNIDO submitted a report providing an update on the progress achieved in the remaining activities in the refrigeration servicing sector, including:
Training of customs and enforcement officers: Training was provided to an additional 141 customs enforcement and inspection officers on current regulations, prevention of illegal trade, and identification of banned ozone-depleting substances (ODSs) using refrigerant identifiers, for a total of 250 officers trained under the stage, including 62 women;
Training and certification of refrigeration and air-conditioning (RAC) technicians: Twenty‑five state-owned vocational high schools located in 23 provinces were equipped[footnoteRef:12] to strengthen their practical training capacities in the refrigeration servicing sector. A total of 7,289 technicians have been certified under the national qualification scheme, and an additional 2,000 are currently scheduled for certification. Additionally, between 2025 and 2026, 1,276 technicians across 11 provinces received training on good servicing practices and safe refrigerant handling, for a total of 2,178 under the stage, including 295 women; [12:  Equipment included gas analyzers, refrigerant recovery units, gas cylinders and nitrogen kits.] 

Recovery, recycling and reclamation (RRR) programme: The three RRR centres are operational in practice (equipment installed, training done, activities ongoing), but they are not yet legally commissioned. Their full regulatory integration will only be complete in 2026 once the relevant circular enters into force. The circular regulating the environmentally sound collection, temporary storage, transport, and reclamation of F-gases has been prepared and discussed with relevant stakeholders and is undergoing the remaining national approval procedures for final endorsement prior to official publication. Equipment to strengthen vocational centres (including leak detectors, recovery tools, and scales) is being procured for distribution in 2026; and
Project implementation and monitoring unit (PMU): Continued coordination of the remaining HPMP activities to ensure the sustainability of the HCFC phase-out with the support of national technical consultants, a technical advisor and audits.
As of April 2026, of the US $14,223,540 approved for stage I (US $14,120,090 for UNIDO and US $103,450 for UNEP), US $12,345,708 had been disbursed (US $12,242,258 for UNIDO and US $103,450 for UNEP) and US $318,150 had been returned, as shown in table 8. The balance of US $1,877,832 will be disbursed in 2026.
Table 8. Financial report of stage I of the HPMP for Türkiye (US $)
	Project/Tranche
	UNIDO
	UNEP
	* Total
	Disbursement rate (%)

	Umbrella project for polyurethane (PU) and extruded polystyrene (XPS) foam
	Approved
	7,713,490
	0
	7,713,490
	96.2

	
	Disbursed
	7,419,768
	0
	7,419,768
	

	First tranche
	Approved
	807,750
	103,450
	911,200
	99.7

	
	Disbursed
	805,351
	103,450
	908,801
	

	Second tranche
	Approved
	2,500,000
	0
	2,500,000
	98.5

	
	Disbursed
	2,461,825
	0
	2,461,825
	

	Third tranche
	Approved
	1,598,850
	0
	1,598,850
	71.6

	
	Disbursed
	1,144,850
	0
	1,144,850
	

	Fourth tranche
	Approved
	859,400
	0
	859,400
	44.5

	
	Disbursed
	382,057
	0
	382,057
	

	Fifth tranche
	Approved
	640,600
	0
	640,600
	4.4

	
	Disbursed
	28,407
	0
	28,407
	

	Total
	Approved
	14,120,090
	103,450
	14,223,540
	86.8

	
	Disbursed
	12,242,258
	103,450
	12,345,708
	


* Investment projects at PU and XPS foam enterprises were completed in December 2019, with the unused balances of US $293,722 returned to the Fund at the 84th meeting. Unused balances of US $1,605, US $794, and US $22,029 from the first and second tranches were returned to the Fund at the 79th, 81st, and 87th meetings.
The Multilateral Fund gender policy was integrated into HPMP activities. Female technicians participated in certification schemes, vocational schools included female trainees, and in customs officers’ training sessions and various awareness programmes involved women. Strategies were recommended to enhance and monitor women’s participation in technical and managerial roles, in recruitment and training. This strengthens the sustainability of achievements by ensuring broader workforce participation.
Secretariat’s comments
The Secretariat notes with appreciation that Türkiye has achieved total HCFC phase-out on 1 January 2025, five years ahead of the Montreal Protocol control schedule. UNIDO confirmed that stage I of the HPMP would be operationally completed by 31 December 2026, as established in the Agreement and indicated at the 96th meeting of the Executive Committee. Financial disbursement for the stage is at 86.8 per cent, and final project payments, primarily committed to the ongoing procurement of servicing tools for refrigeration technicians, training activities, and laboratory and training equipment for vocational schools, are expected to be finalized by December 2026.
Upon request, UNIDO confirmed that, as of 1 January 2025, HCFC use had been fully banned in Türkiye, except for critical and laboratory applications, effectively eliminating their placement on the market. To sustain the phase-out, the Climate Law of 9 July 2025 introduced significant administrative sanctions and financial penalties for individuals and entities involved in the illegal use, import, trade, or placing on the market of ODSs. Ongoing training and awareness efforts targeting customs officers, technicians, and other stakeholders support the adoption of alternatives, while coordination mechanisms, including the Ozone Panel, ensure continued stakeholder engagement. Together, those measures provide a robust foundation for long-term sustainability of HCFC phase-out in Türkiye.
Recommendation
The Executive Committee may wish to note the progress report on the implementation of the work programme associated with the fifth and final tranche of stage I of the HCFC phase-out management plan for Türkiye, provided by UNIDO and contained in document UNEP/OzL.Pro/ExCom/98/6.
1. Report related to Kigali HFC implementation plans Agreements
Agreements for the reduction in consumption of HFCs in accordance with stage I of Kigali HFC implementation plans
Background
At its 95th meeting, the Executive Committee reached consensus on the template Agreement for stage I of the Kigali HFC implementation plans (KIPs).[footnoteRef:13] The agreed template would be applied to the KIPs previously approved between the 92nd and 95th meetings. At its 96th meeting, the Executive Committee reached consensus on the HFC cost funding guidelines,[footnoteRef:14] providing more clarity on the starting point, which has implications on the draft Agreements. Revisions to draft Agreements were discussed at the Inter-agency Coordination Meeting,[footnoteRef:15] and at its 97th meeting, the Executive Committee approved the Agreements for 14 KIPs approved between the 92nd and 95th meetings. [13:  Decision 95/90 and annex LVII of document UNEP/OzL.Pro/ExCom/95/94]  [14:  Decision 96/50]  [15:  Held in September 2025] 

Secretariat’s comments
To ensure consistency and accuracy of the draft Agreements between the respective Governments and the Executive Committee, the Secretariat prepared them based on the agreed template and the schedules of HFC phase‑down commitments and funding tranches under KIPs approved between the 92nd and 95th meetings and made the following adjustments, where required:
(e) Paragraph 2, in line with decision 96/50(e) for low-volume-consuming (LVC) countries with consumption in servicing only where the starting point is not applied, and for non‑LVC countries where the starting point covers all HFCs together;
(f) Paragraph 9, in line with decision 96/4 in removing the monitoring function of the Senior Evaluation Officer, to remove the words “monitoring and”;
(g) Appendices 1-A and 2-A, to reflect those decisions which may vary for LVC countries with servicing, LVC countries with servicing and manufacturing, and non-LVC countries; and
(h) For non-LVC countries and LVC countries with manufacturing, Appendix 1-A and row 4 of Appendix 2-A, to include the text “To be determined (TBD)” as these would only be finalized once discussions on the starting point for aggregate reductions in consumption, and thus the remaining eligible consumption, have been completed.
Agreements for two countries with previously approved KIPs (Mexico and Nigeria) are included in project proposals with tranche requests presented at this meeting, and the remaining Agreements for previously approved KIPs are contained in annexes III to XXXVI to this document. Lead implementing agencies have reviewed and provided input on all Agreements, focusing in particular on Appendix 5-A (“Monitoring Institutions and Roles”) for a detailed and credible indication of how progress in the implementation of the plan is to be monitored, and the indication of organizations and institutions responsible for the activities and the sustainability of consumption reduction targets achieved through the Agreements. The Secretariat notes with appreciation the efforts of all implementing and bilateral agencies in reviewing and validating the Agreements.
The Secretariat is hereby presenting for the approval of the Executive Committee 34 draft KIP Agreements for: Benin, Cambodia, Chad, El Salvador, Eswatini, The Gambia, Ghana, Grenada, Jordan, Kyrgyzstan, Lao People’s Democratic Republic, Lesotho, Liberia, Malawi, Malaysia, Montenegro, Mozambique, North Macedonia, the 12 Pacific island countries (the Cook Islands, Kiribati, the Marshall Islands, the Federated States of Micronesia, Nauru, Niue, Palau, Samoa, Solomon Islands, Tonga, Tuvalu and Vanuatu), Panama, Paraguay, Peru, Rwanda, Saint Lucia, Senegal, Seychelles, Sierra Leone, Togo, Trinidad and Tobago, Tunisia, Türkiye, Uruguay, Viet Nam and Zimbabwe, as contained in annexes III to XXXVI to the present document.
Recommendation
14. The Executive Committee may wish to approve:
(a) The draft Agreement between the Government of Benin and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the Kigali HFC implementation plan (KIP), contained in annex III to the present report;
(b) The draft Agreement between the Government of Cambodia and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex IV to the present report;
(c) The draft Agreement between the Government of Chad and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex V to the present report;
(d) The draft Agreement between the Government of El Salvador and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex VI to the present report;
(e) The draft Agreement between the Government of Eswatini and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex VII to the present report;
(f) The draft Agreement between the Government of The Gambia and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex VIII to the present report;
(g) The draft Agreement between the Government of Ghana and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex IX to the present report;
(h) The draft Agreement between the Government of Grenada and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex X to the present report;
(i) The draft Agreement between the Government of Jordan and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XI to the present report;
(j) The draft Agreement between the Government of Kyrgyzstan and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XII to the present report;
(k) The draft Agreement between the Government of the Lao People’s Democratic Republic and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XIII to the present report;
(l) The draft Agreement between the Government of Lesotho and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XIV to the present report;
(m) The draft Agreement between the Government of Liberia and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XV to the present report; and
(n) The draft Agreement between the Government of Malawi and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XVI to the present report;
(o) The draft Agreement between the Government of Malaysia and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XVII to the present report;
(p) The draft Agreement between the Government of Montenegro and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XVIII to the present report;
(q) The draft Agreement between the Government of Mozambique and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XIX to the present report;
(r) The draft Agreement between the Government of North Macedonia and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XX to the present report;
(s) The draft Agreement between the Governments of the Pacific island countries and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XXI to the present report;
(t) The draft Agreement between the Government of Panama and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XXII to the present report;
(u) The draft Agreement between the Government of Paraguay and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XXIII to the present report;
(v) The draft Agreement between the Government of Peru and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XXIV to the present report;
(w) The draft Agreement between the Government of Rwanda and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XXV to the present report;
(x) The draft Agreement between the Government of Saint Lucia and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XXVI to the present report;
(y) The draft Agreement between the Government of Senegal and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XXVII to the present report;
(z) The draft Agreement between the Government of Seychelles and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XXVIII to the present report;
(aa) The draft Agreement between the Government of Sierra Leone and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XXIX to the present report;
(ab) The draft Agreement between the Government of Togo and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XXX to the present report;
(ac) The draft Agreement between the Governments of Trinidad and Tobago and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XXXI to the present report;
(ad) The draft Agreement between the Government of Tunisia and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XXXII to the present report;
(ae) The draft Agreement between the Government of Türkiye and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XXXIII to the present report;
(af) The draft Agreement between the Government of Uruguay and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XXXIV to the present report; 
(ag) The draft Agreement between the Government of Viet Nam and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XXXV to the present report; and
(ah) The draft Agreement between the Government of Zimbabwe and the Executive Committee for the reduction in consumption of HFCs in accordance with stage I of the KIP, contained in annex XXXVI to the present report
1. Report on additional activities to maintain energy efficiency in the refrigeration servicing sector (decision 89/6) 
Maldives: Additional activities to maintain energy efficiency in the refrigeration servicing sector under decision 89/6(b) (final progress report) (UNEP)
Background
At the 91st meeting, the Executive Committee approved the project on additional activities for the introduction of alternatives to HCFCs with low- or zero-global-warming potential (GWP) and on maintaining energy efficiency in the refrigeration servicing sector in Maldives, in the amount of US $100,000, plus agency support costs of US $13,000, for UNEP.[footnoteRef:16] The project completion date was extended to 30 June 2025 at the 93rd meeting.[footnoteRef:17] At the 95th meeting, as part of the yearly progress report on the project,[footnoteRef:18] an updated workplan for implementation of project activities was included with the latest expected completion dates until March 2025. [16:  Decision 91/60(a)]  [17:  Decision 93/20(b)]  [18:  UNEP/OzL.Pro/ExCom/95/20, paragraphs 72-80] 

At the 96th meeting, the Executive Committee  approved, on exceptional basis, and on the understanding that no further extension would be approved, the extension to 30 June 2026 of the completion date of the project and requested the Government of Maldives and UNEP to continue submitting progress reports for the implementation of the project, on a yearly basis until its completion and to submit a project completion report (PCR) to the second meeting of the Executive Committee in 2026 (decision 96/14(b) and (c)).
In line with decision 96/14(c), UNEP, on behalf of the Government of Maldives, has submitted a progress report to the present meeting.
Progress report
The objective of the energy efficiency project was to make mandatory the existing voluntary energy efficiency labelling programme for appliances and equipment called Hakathari which covered certain equipment, including air conditioners[footnoteRef:19] and domestic refrigerators. The mandated label specifications under the Hakathari programme include information on the refrigerant and its ozone depleting potential and GWP. The programme also establishes the minimum qualification requirements for tested[footnoteRef:20] appliances to be eligible for the energy efficiency labels ensuring that these meet the minimum energy performance standards already present in the country.  [19:  Single-phase, single-split and unitary type air conditioners of both fixed speed and variable speed, up to rated capacities of 24,226 BTU/hr (equivalent to 7.1 kW).]  [20:  Testing is done by a laboratory accredited by a recognized authority which is a Mutual Recognition Arrangement signatory such as International Laboratory Accreditation Cooperation / Asia Pacific Laboratory Accreditation Cooperation as per certain test standards or protocols for testing laboratories (using ISO/IEC 17025).] 

The project included activities to improve the coordination and collaboration between stakeholders, the relevant energy authorities, and the National Ozone Unit (NOU) through capacity‑building of key staff and stakeholders to ensure sustained consideration of the refrigerant in the labelling programme, guide the development of the review approach for refrigerant type and GWP, and understand regulatory challenges related to low-GWP refrigerant labelling information; to raise awareness related to the labelling programme focusing on increasing the demand for air conditioners and refrigerators operating with low- or zero-GWP refrigerants among all labeled energy-efficient products; and a consumer behavior study to evaluate the impact of the project.
As of April 2026, the following activities had been completed: the training/information sessions for importers, customs officers, utility agencies, building designers, building developers and construction companies; the finalisation of the standard operating procedures (SOP) and the development of a clause to prioritize Hakathari‑compliant products in government procurement that will be completed in June 2026; and development of outreach and impact assessment awareness materials for end users, awaiting final dissemination in June 2026 as well as the survey for the consumer behaviour study, the report of which is being finalized by June 2026. 
Of the US $100,000 approved for the project, US $49,560 (49.6 per cent) had been disbursed. The obligated balance of US $50,440 will be disbursed by 30 June 2026. Table 9 provides an update on the activities since the submission of the previous progress report.
Table 9. Updated on the implementation of activities to maintain energy efficiency in the refrigeration servicing sector in Maldives
	Activity
	Deliverable/target
	Approved funds
(US $)
	Status
	Expected finalization dates

	Capacity-building of key staff and stakeholders

	Coordination and collaboration with relevant agencies through capacity‑building training
	Study tour, report and recommendations 
	35,000
	The NOU organized a study tour to Malaysia in 2025, including visits to the Department of Environment and the Energy Commission under the Ministry of Energy Transition and Water Transformation. Site visits were also conducted to the SIRIM Energy Efficiency Testing Laboratory and Iwatani Malaysia Sdn. Bhd. The finalization of the revised SOP, including the new verification testing section, based on the study tour findings as well as the development/approval of the clause to prioritize Hakathari-compliant products in government procurement is expected to be finalized in June 2026.
	June 2026

	Training/information sessions for importers, customs officers, utility agencies, building designers, building developers, and construction enterprises
	Five workshops/ information sessions for a total of 140 participants
	13,000
	Two training sessions for importers, two training sessions for customs and trade authorities, two awareness sessions and one information session have been conducted for a total of 142 participants[footnoteRef:21] (including 78 women). [21:  Including importers, customs officers, utility agencies, building designers, building developers, and construction companies.] 

	Completed

	[bookmark: _Hlk115084759]Outreach and impact assessment

	Development and dissemination of outreach materials
	Five awareness videos and five infographics produced and disseminated
	37,000
	The contract has been signed and storyboards for the videos have been prepared; the dissemination of the outreach materials is expected to be finalized in June 2026. 
	June 2026

	Consumer behaviour study
	One consumer behaviour study developed and implemented
	15,000
	The terms of reference and the questionnaire for the study have been developed, the company has been contracted, and the survey has been completed. The consultant is in the process of drafting the report.
	June 2026

	Total
	100,000
	
	


Secretariat’s comments
The Secretariat noted the progress achieved in the implementation of the project, in particular the completion of all capacity-building activities, including the study tour to Malaysia in 2025, the training sessions for importers and customs officers, and the amendments to the Hakathari programme document, noting that the training target had been exceeded (142 participants trained against 140). UNEP confirmed that all remaining activities will be completed by June 2026 and that the PCR will be submitted in line with decision 96/14(c).
Recommendation
The Executive Committee may wish to note the final progress report on the project on additional activities for the introduction of alternatives to HCFCs with low- or zero-global-warming potential and on maintaining energy efficiency in the refrigeration servicing sector in Maldives, as submitted by UNEP and contained in document UNEP/OzL.Pro/ExCom/98/6.
1. Report on pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (decision 91/65)
Cameroon: Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non‑investment activities) (request for extension of project completion date) (UNIDO)
Background

At its 94th meeting, the Executive Committee approved the pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non‑investment activities) for Cameroon, to be implemented by UNIDO, noting that the project would be operationally completed no later than 30 June 2026 and a detailed project report would be submitted to the Executive Committee within six months of the date of completion of the project (decision 94/54).
Request for extension

Cameroon experienced several cabinet reshuffles between the end of 2024 and following the presidential election in 2025. As a result, previously obtained authorizations to initiate the project and commence data collection became invalid. The national ozone unit obtained the necessary renewed authorization at the end of February 2026, after which data and information collection commenced, and an inception workshop was held in March 2026. Institutional arrangements are now stable, enabling the timely and effective completion of the remaining project activities by the end of 2026 and the submission of the project report in 2027.
In light of these delays and to allow for the completion of project activities, UNIDO, on behalf of the Government of Cameroon, has requested an extension of the project implementation period to 31 December 2026.
Secretariat’s comments

The Secretariat acknowledges the challenges faced by the Government of Cameroon. Upon request by the Secretariat, UNIDO explained that the delays had not been reported as part of its 2024 annual and financial progress report, as they occurred during the second half of 2025 as a result of the cabinet reshuffles. UNIDO further confirmed that the situation is now stable and that the project can be operationally completed by December 2026.
Recommendation 

The Executive Committee may wish: 
To note the request for extension of the pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non‑investment activities) in Cameroon, as submitted by UNIDO and contained in document UNEP/OzL.Pro/ExCom/98/6; and
To approve, on an exceptional basis, and on the understanding that no further extension would be approved, the extension to 31 December 2026 of the completion date of the project referred to in subparagraph (a) above.
1. Report on project preparation for enhancing energy efficiency in the context of HFC phase-down in the refrigeration and air-conditioning manufacturing sector (decision 94/60)
Türkiye: Status of preparation of a project to enhance energy efficiency and to convert 29 refrigeration and air-conditioning manufacturing enterprises from the use of hydrofluorocarbons to low‑global‑warming‑potential technology (UNIDO)
Background
In approving the Kigali HFC implementation plan (KIP) for Türkiye at the 95th meeting, the Executive Commtiee noted inter alia that, during the implementation of stage I of the KIP and no later than the 98th meeting, the Government of Türkiye would be allowed, on an exceptional basis, to submit investment projects in the refrigeration, air-conditioning and foam sectors to achieve additional reductions in hydrofluorocarbon (HFC) consumption (decision 95/74(b)(vi)). At the same meeting, the Committee approved the preparation of a project to enhance energy efficiency and to convert the use of HFCs to a technology with low global‑warming potential (GWP) for 29 refrigeration and air-conditioning (RAC) manufacturing enterprises in Türkiye, in the amount of US $220,000, plus agency support costs of US $15,400, for UNIDO (decision 95/39).
Status of preparation
UNIDO informed the Secretariat that the preparation of the project was progressing well but that it could not be submitted to the 98th meeting as there were still activities to be completed. The project will therefore be submitted to the 99th meeting. A detailed progress report submitted by UNIDO indicated that relevant experts were recruited and a series of stakeholder engagement activities was completed to introduce the energy-efficiency project to 100 sector stakeholders. In parallel, outreach activities and online information meetings were conducted to present the objectives, scope and requirements of the project, as well as its framework, eligibility criteria and technical information expected from participating enterprises. This was complemented by an online workshop on the energy‑efficiency window, technical options, detailed energy‑efficiency calculations and steps required to prepare the project proposals as well as direct engagement with enterprises and participation in industry fairs and events focused on the commercial RAC sector.
A call for applications was launched through Türkiye’s national ozone unit’s website. Following proposal submissions, data collection templates developed by international experts were shared with applicant enterprises to gather detailed technical and operational information. Additional support was provided through a workshop in Istanbul and individual consultation meetings with selected enterprises. Some applicant enterprises were excluded due to misalignment with project objectives or voluntary withdrawal. At the current stage, seven enterprises with a total of 10 project proposals continue data collection. Of the approved US $220,000, US $117,714 has been disbursed, and the project is expected to be submitted to the 99th meeting.
Secretariat’s comments
The Secretariat notes with appreciation the work put into the preparation of the project so far, and the confirmation from UNIDO that the proposal will be submitted to the 99th meeting.
Recommendation
The Executive Committee may wish to note:
(ai) The progress report on the preparation of a project to enhance energy efficiency and to convert 29 refrigeration and air-conditioning manufacturing enterprises from the use of hydrofluorocarbons to low-global-warming-potential technology in Türkiye, submitted by UNIDO and contained in document UNEP/OzL.Pro/ExCom/98/6; and
(aj) That the project referred to in subparagraph (a) above will be submitted by UNIDO to the 99th meeting.
1. Report on preparation of a national inventory of banks of used or unwanted controlled substances and a plan for the collection, transport, and disposal of such substances (decision 91/66)
Mauritius: Preparation of a national inventory of banks of waste controlled substances and development of a national plan for management of these substances (decision 91/66) (request for extension of project completion date) (Government of Germany)

Background

At the 94th meeting, the Executive Committee approved the preparation of a national inventory of banks of waste controlled substances and development of a national plan for management of these substances (decision 91/66) for Mauritius, to be implemented by the Government of Germany (decision 94/20).[footnoteRef:22] The operational completion date in line with the decision is June 2026.[footnoteRef:23] [22:  Blanket approval decision]  [23:  Twenty-four months from the date of approval of the project.] 

Request for extension

The Government of Germany reported that the recruitment process for a national consultant to prepare the national inventory of banks and develop the national action plan had been delayed due to administrative challenges. As of December 2025, recruitment by January 2026 appeared feasible; however, it could not be completed as planned due to an information technology system change at the bilateral agency, which affected administrative and financial processes, as well as the absence of compliance confirmation for certain conditions on the bidder’s side. As a result, as of May 2026, the recruitment process remained ongoing; no funds had been disbursed, and project activities remained at the planning phase. The Government of Germany indicated that once the consultant is recruited, survey activities, analysis, and reporting are expected to be completed expeditiously, with interim results anticipated by December 2026. 
In light of the above, the Government of Germany, on behalf of the Government of Mauritius, has requested an extension of the project implementation period to 30 June 2027.
Secretariat’s comments

The Secretariat acknowledges the challenges experienced in recruiting a consultant for the survey activities and considers, based on the information provided, that the requested extension would facilitate the completion of the project.
Recommendation 

The Executive Committee may wish: 
To note the request for extension of the preparation of a national inventory of banks of waste controlled substances and development of a national plan for management of these substances (decision 91/66) in Mauritius, as submitted by the Government of Germany and contained in document UNEP/OzL.Pro/ExCom/98/6; and 
To approve, on an exceptional basis, and on the understanding that no further extension would be approved, the extension to 30 June 2027 of the completion date of the project referred to in subparagraph (a) above. 
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Annex I

PROJECTS THAT ARE CLASSIFIED AS “SOME PROGRESS” AND ARE RECOMMENDED FOR CONTINUED MONITORING
	Country
	Project code
	Project title
	Agency

	Democratic Republic of the Congo (the) 
	DRC/PHA/88/INV/49
	HCFC phase-out management plan (stage II, first tranche)
	UNDP

	Iran (Islamic Republic of)
	IRA/PHA/92/INV/267
	HCFC phase-out management plan (stage II, fourth tranche) (foam sector)
	UNDP

	Iran (Islamic Republic of) 
	IRA/PHA/86/INV/245
	HCFC phase-out management plan (stage II, third tranche) (foam sector)
	UNDP

	Iran (Islamic Republic of) 
	IRA/PHA/86/TAS/248
	HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector)
	UNEP

	Iran (Islamic Republic of) 
	IRA/PHA/92/INV/266
	HCFC phase-out management plan (stage II, fourth tranche) (commercial refrigeration sector)
	UNDP

	Kuwait 
	KUW/PHA/88/TAS/42
	HCFC phase-out management plan (stage II, first tranche)
	UNEP

	Qatar 
	QAT/PHA/88/INV/26
	HCFC phase-out management plan (stage II, first tranche)
	UNIDO

	Syrian Arab Republic (the) 
	SYR/PHA/86/INV/107
	HCFC phase-out management plan (stage I, first tranche)
	UNIDO

	Syrian Arab Republic (the) 
	SYR/PHA/86/TAS/106
	HCFC phase-out management plan (stage I, first tranche)
	UNEP

	Syrian Arab Republic (the) 
	SYR/PHA/91/INV/112
	HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector)
	UNIDO

	Syrian Arab Republic (the) 
	SYR/PHA/91/TAS/114
	HCFC phase-out management plan (stage I, second tranche)
	UNEP
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PROJECTS FOR WHICH ADDITIONAL STATUS REPORTS ARE REQUESTED
	Country
	Project code
	Project title
	Agency
	Recommendation to the 98th meeting

	Myanmar 
	MYA/SEV/84/INS/22
	Extension of institutional strengthening project (phase V: 7/2020-6/2022)
	UNEP
	To request UNEP to submit a status report to the 99th meeting on the resumption of activities 

	Nepal 
	NEP/PHA/86/TAS/43
	HCFC phase-out management plan (stage II, first tranche)
	UNEP
	To request UNEP to submit a status report to the 99th meeting on the status of implementation of activities and transfer of funds to the Government

	Seychelles 
	SEY/EEF/93/TAS/32
	HCFC phase-out management plan (stage I) (Additional activities to maintain energy efficiency in the servicing sector under decision 89/6(b))
	Germany
	To request the Government of Germany to submit a status report to the 99th meeting on implementation progress

	Yemen
	YEM/SEV/93/INS/47
	Extension of the institutional strengthening project (phase IX: 1/2024-12/2026)
	UNEP
	To request UNEP to submit a status report to the 99th meeting on implementation progress
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Annex III
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF BENIN
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. [bookmark: _Hlk146706470][bookmark: _Hlk128135089][bookmark: _Hlk130660551]This Agreement represents the understanding of the Government of Benin (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 1,687,551 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
[bookmark: _Hlk130659199]The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
[bookmark: _Hlk128740135]The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
[bookmark: _Hlk130666479]Flexibility in the reallocation of funds
[bookmark: _Hlk130666540]The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(a) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
[bookmark: _Hlk131268859]Non-compliance with the Targets in the Agreement
[bookmark: _Hlk131270712]Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
[bookmark: _Hlk130668684]The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	[bookmark: _Hlk131268561]Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	1,875,057
	1,875,057
	1,875,057
	1,875,057
	1,875,057
	1,687,551
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	1,875,057
	1,875,057
	1,875,057
	1,875,057
	1,875,057
	1,687,551
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	117,500
	0
	0
	102,500
	0
	0
	220,000

	2.2
	Support costs for Lead IA (US $)
	15,275
	0
	0
	13,325
	0
	0
	28,600

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	60,000
	0
	0
	80,000
	0
	0
	140,000

	2.4
	Support costs for Cooperating IA (US $)
	7,800
	0
	0
	10,400
	0
	0
	18,200

	3.1
	Total agreed funding (US $)
	177,500
	0
	0
	182,500
	0
	0
	360,000

	3.2
	Total support costs (US $)
	23,075
	0
	0
	23,725
	0
	0
	46,800

	3.3
	Total agreed costs (US $)
	200,575
	0
	0
	206,225
	0
	0
	406,800


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
[bookmark: _Hlk130669478]APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase-down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase-in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate-relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit, under the Ministry of Living Environment and Sustainable Development, is responsible for monitoring the progress of implementation of activities in the Plan.
Monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of training and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA.
The Ministry of Living Environment and Sustainable Development will be responsible for the sustainability of consumption reduction targets achieved through the Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(a) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(b) Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
(c) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(d) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(e) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
(f) Providing assistance with the policy, management and technical support when required;
(g) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2-A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex IV
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF CAMBODIA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2029)
Purpose
1. This Agreement represents the understanding of the Government of Cambodia (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 1,137,038 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
23. The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
24. Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
25. The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
26. The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
27. The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
28. The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(a) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(b) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(c) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
29. Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
30. The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNDP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
31. The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6-A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
32. Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
33. The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
34. The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
35. The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
36. All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
37. This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	n/a
	1,263,376
	1,263,376
	1,263,376
	1,263,376
	1,263,376
	1,137,038
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	n/a
	1,263,376
	1,263,376
	1,263,376
	1,263,376
	1,263,376
	1,137,038
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	126,300
	0
	0
	108,000
	0
	0
	44,500
	278,800

	2.2
	Support costs for Lead IA (US $)
	16,419
	0
	0
	14,040
	0
	0
	5,785
	36,244

	2.3
	Cooperating IA (UNDP) agreed funding (US $)
	123,810
	0
	0
	38,075
	0
	0
	0
	161,885

	2.4
	Support costs for Cooperating IA (US $)
	11,143
	0
	0
	3,427
	0
	0
	0
	14,570

	3.1
	Total agreed funding (US $)
	250,110
	0
	0
	146,075
	0
	0
	44,500
	440,685

	3.2
	Total support costs (US $)
	27,562
	0
	0
	17,467
	0
	0
	5,785
	50,814

	3.3
	Total agreed costs (US $)
	277,672
	0
	0
	163,542
	0
	0
	50,285
	491,499

	4.1.1
	Deductions of HFCs agreed under this Agreement (CO2-eq tonnes)
	126,338

	4.1.2
	Deductions of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU) under the Ministry of Environment (MoE) will be responsible for the overall monitoring of all activities under the Plan, as well as the planning, coordination, and daily work of project implementation.
41. Monitoring will be conducted to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of training and other expected outcomes; and HFC consumption verification. Stakeholders include industries, technical institutions, non-governmental organizations, the Government and technical experts.
42. The General Department of Customs and Excise (GDCE), in collaboration with the NOU, will carry out annual monitoring, reporting, verification and enforcement activities related to HFC consumption in the Country. The NOU is responsible for determining and allocating HFC quota to eligible importers, and for issuing the import and export permits based on the allocated quota. The GDCE will control and monitor the import and export of HFCs at the points of entry. The NOU will liaise with HFC importers and exporters to obtain the data necessary for the reconciliation of statistics on a periodical basis.
43. The MoE will be responsible for the sustainability of consumption reduction targets achieved through this Agreement. The NOU will undertake surveys to gauge the situation of HFC phase-down, potential illegal imports, and the penetration of alternative technologies in the country in different subsectors to examine the achievements of HFC phase-down at a national level.
44. The NOU will undertake regular inspections at any mobile air-conditioning training centre that has received training equipment under the Plan to monitor the condition of this equipment.
45. The NOU will monitor the implementation of capacity-building activities for trainers, assessors and technicians across sectors; activities to build the capacity of technicians to maintain/enhance energy efficiency in the servicing sector; training for customs and enforcement officers; and training for importers and customs brokers.
46. The NOU will submit annual reports on the status of implementation to the Lead IA and the Cooperating IA to monitor the implementation progress of the Plan.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
48. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. [bookmark: _Hlk131269422]In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $6.98 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex V
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF CHAD
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Chad (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 3,216,251 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
52. The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
53. Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
54. The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
55. The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
56. The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
57. The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(a) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(b) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(c) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
58. Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
59. The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
60. The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
61. Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
62. The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
63. The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
64. The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
65. All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
66. This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	3,573,612
	3,573,612
	3,573,612
	3,573,612
	3,573,612
	3,216,251
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	3,573,612
	3,573,612
	3,573,612
	3,573,612
	3,573,612
	3,216,251
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	141,000
	0
	0
	94,000
	0
	0
	235,000

	2.2
	Support costs for Lead IA (US $)
	18,330
	0
	0
	12,220
	0
	0
	30,550

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	75,000
	0
	0
	50,000
	0
	0
	125,000

	2.4
	Support costs for Cooperating IA (US $)
	9,750
	0
	0
	6,500
	0
	0
	16,250

	3.1
	Total agreed funding (US $)
	216,000
	0
	0
	144,000
	0
	0
	360,000

	3.2
	Total support costs (US $)
	28,080
	0
	0
	18,720
	0
	0
	46,800

	3.3
	Total agreed costs (US $)
	244,080
	0
	0
	162,720
	0
	0
	406,800


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit, under the Ministry of Environment, Fisheries and Sustainable Development, is responsible for monitoring the progress of implementation of the Plan’s activities in the Country.
70. Monitoring will be conducted to ensure the efficient and effective implementation of the Plan; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of training and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA.
71. The Ministry of Environment, Fisheries and Sustainable Development will be responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
73. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex VI
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF EL SALVADOR
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of El Salvador (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 830,126 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
77. The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
78. Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
79. The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
80. The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
81. The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
82. The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(a) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(b) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(c) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
83. Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
84. The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or the evaluation programme of the Lead IA taking part in this Agreement.
85. The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
86. Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
87. The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
88. The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
89. The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
90. All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
91. This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	922,362
	922,362
	922,362
	922,362
	922,362
	830,126
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	922,362
	922,362
	922,362
	922,362
	922,362
	830,126
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	180,000
	0
	0
	144,000
	0
	36,000
	360,000

	2.2
	Support costs for Lead IA (US $)
	23,400
	0
	0
	18,720
	0
	4,680
	46,800

	3.1
	Total agreed funding (US $)
	180,000
	0
	0
	144,000
	0
	36,000
	360,000

	3.2
	Total support costs (US $)
	23,400
	0
	0
	18,720
	0
	4,680
	46,800

	3.3
	Total agreed costs (US $)
	203,400
	0
	0
	162,720
	0
	40,680
	406,800


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Ministry of Environment and Natural Resources (MARN), will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA.
95. The MARN is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
96. The project monitoring unit of the Plan will assist the NOU in the following activities:
(a) Follow up on activities described in each project, including training courses, seminars, workshops and presentations;
(b) Monitor the purchase of equipment, materials and tools, as well as contracts for services, to be in line with each project and comply with the Lead IA’s rules and regulations;
(c) Assist in the reporting on project activities, taking into account schedules defined in each component, and support the NOU in solving deviations to finalize all activities in time;
(d) Support the NOU in defining and selecting beneficiaries, always as a supporting activity;
(e) Support the NOU in data gathering to make the required reports to the Multilateral Fund Secretariat for the tranche requests, and also to the Lead IA;
(f) Monitor and promote, when necessary, the actions to comply with gender balance; and
(g) Carry out any other monitoring or evaluation activity requested by the NOU.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
(k) Ensuring that disbursements made to the Country are based on the use of the indicators;
(l) Providing assistance with the policy, management and technical support when required; and
(m) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
1. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex VII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF ESWATINI
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2030)
Purpose
1. This Agreement represents the understanding of the Government of Eswatini (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 94,950 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
101. The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
102. Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
103. The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
104. The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
105. The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
106. The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(a) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(b) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(c) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
107. Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
108. The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNDP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
109. The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
110. Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
111. The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
112. The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
113. The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
114. All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
115. This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	10
	n/a

	
	
	CO2‑eq tonnes
	105,500
	105,500
	105,500
	105,500
	105,500
	94,950
	94,950
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	105,500
	105,500
	105,500
	105,500
	105,500
	94,950
	94,950
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	63,500
	0
	0
	51,500
	0
	0
	0
	115,000

	2.2
	Support costs for Lead IA (US $)
	8,255
	0
	0
	6,695
	0
	0
	0
	14,950

	2.3
	Cooperating IA (UNDP) agreed funding (US $)
	0
	0
	0
	30,000
	0
	0
	0
	30,000

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	3,900
	0
	0
	0
	3,900

	3.1
	Total agreed funding (US $)
	63,500
	0
	0
	81,500
	0
	0
	0
	145,000

	3.2
	Total support costs (US $)
	8,255
	0
	0
	10,595
	0
	0
	0
	18,850

	3.3
	Total agreed costs (US $)
	71,755
	0
	0
	92,095
	0
	0
	0
	163,850


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. Overall monitoring will be provided by the Eswatini Environment Authority (EEA), through the national ozone unit (NOU), with assistance from the Lead IA. The NOU will submit annual progress reports of status of implementation of the Plan to the Lead IA.
119. Consumption will be monitored and determined from official data of import and export of substances as registered by the relevant Government departments. The NOU will compile and report the following data and information each year on or before the relevant deadlines.
(a) Reports on the consumption of the substances to be submitted to the Ozone Secretariat in line with Article 7 of the Montreal Protocol; and
(b) Reports on country programme data to be submitted to the Secretariat of the Multilateral Fund.
1. Monitoring of the development of the Plan and verification of achievement of performance targets will be assigned to an independent local company or to independent local consultant(s) by the Lead IA. The company or consultant(s) responsible for verification will have full access to relevant technical and financial information related to the implementation of the Plan.
1. The EEA will be responsible for the sustainability of consumption reduction targets achieved through this Agreement. 
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
123. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex VIII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF THE GAMBIA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of the Gambia (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 244,363 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(a) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	271,515
	271,515
	271,515
	271,515
	271,515
	244,363
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	271,515
	271,515
	271,515
	271,515
	271,515
	244,363
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	50,150
	0
	0
	42,250
	0
	0
	92,400

	2.2
	Support costs for Lead IA (US $)
	6,520
	0
	0
	5,492
	0
	0
	12,012

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	30,000
	0
	0
	47,600
	0
	0
	77,600

	2.4
	Support costs for Cooperating IA (US $)
	3,900
	0
	0
	6,188
	0
	0
	10,088

	3.1
	Total agreed funding (US $)
	80,150
	0
	0
	89,850
	0
	0
	170,000

	3.2
	Total support costs (US $)
	10,420
	0
	0
	11,680
	0
	0
	22,100

	3.3
	Total agreed costs (US $)
	90,570
	0
	0
	101,530
	0
	0
	192,100


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit, under the Ministry of Environment, Climate Change and Natural Resources (MECCNAR) is responsible for monitoring the progress of implementation of activities in the Plan.
Monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of training and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA.
The MECCNAR will be responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(a) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required;
Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex IX
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF GHANA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2030)
Purpose
1. This Agreement represents the understanding of the Government of Ghana (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 767,003 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
134. The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
135. Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
136. The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
137. The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
138. The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
139. The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(a) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(b) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
(c) Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
(d) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
140. Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
141. The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) and UNEP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
142. The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
143. Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
144. The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
145. The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
146. The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
147. All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
148. This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	freeze
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	1,805,702
	1,805,702
	1,805,702
	1,805,702
	1,805,702
	1,625,132
	1,625,132
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	56.7
	56.7
	56.7
	56.7
	56.7
	57.5
	57.5
	n/a

	
	
	CO2‑eq tonnes
	n/a
	782,656
	782,656
	782,656
	782,656
	782,656
	767,003
	767,003
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	132,500
	0
	0
	0
	79,000
	0
	0
	20,500
	232,000

	2.2
	Support costs for Lead IA (US $)
	17,225
	0
	0
	0
	10,270
	0
	0
	2,665
	30,160

	2.3
	Cooperating IA (UNEP) agreed funding (US $)
	55,500
	0
	0
	0
	25,500
	0
	0
	12,000
	93,000

	2.4
	Support costs for Cooperating IA (US $)
	7,215
	0
	0
	0
	3,315
	0
	0
	1,560
	12,090

	3.1
	Total agreed funding (US $)
	188,000
	0
	0
	0
	104,500
	0
	0
	32,500
	325,000

	3.2
	Total support costs (US $)
	24,440
	0
	0
	0
	13,585
	0
	0
	4,225
	42,250

	3.3
	Total agreed costs (US $)
	212,440
	0
	0
	0
	118,085
	0
	0
	36,725
	367,250


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Environmental Protection Agency, will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration.
1. In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA. The Environmental Protection Agency is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
154. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
APPENDIX 8-A: SECTOR-SPECIFIC ARRANGEMENTS
1. The Government of the Country is allowed to submit a funding request for phasing down HFCs in the firefighting sector, for consideration by the Executive Committee in line with the agreed cost guidelines for that sector, once the Government has identified the consumption and revised the Article 7 and the country programme data.
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Annex X
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF GRENADA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2030)
Purpose
1. This Agreement represents the understanding of the Government of Grenada (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 47,534 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(a) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNDP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	10
	n/a

	
	
	CO2‑eq tonnes
	n/a
	52,815
	52,815
	52,815
	52,815
	52,815
	47,534
	47,534
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	52,815
	52,815
	52,815
	52,815
	52,815
	47,534
	47,534
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	27,500
	0
	0
	0
	44,000
	0
	0
	16,342
	87,842

	2.2
	Support costs for Lead IA (US $)
	3,575
	0
	0
	0
	5,720
	0
	0
	2,124
	11,419

	2.3
	Cooperating IA (UNDP) agreed funding (US $)
	45,000
	0
	0
	0
	12,158
	0
	0
	0
	57,158

	2.4
	Support costs for Cooperating IA (US $)
	5,850
	0
	0
	0
	1,581
	0
	0
	0
	7,431

	3.1
	Total agreed funding (US $)
	72,500
	0
	0
	0
	56,158
	0
	0
	16,342
	145,000

	3.2
	Total support costs (US $)
	9,425
	0
	0
	0
	7,301
	0
	0
	2,124
	18,850

	3.3
	Total agreed costs (US $)
	81,925
	0
	0
	0
	63,459
	0
	0
	18,466
	163,850


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phasedown pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase-in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Ministry of Climate Resilience, the Environment and Renewable Energy, will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration.
In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA. 
The Ministry of Climate Resilience, the Environment and Renewable Energy is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(a) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required;
Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XI
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF JORDAN
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2030)
Purpose
1. This Agreement represents the understanding of the Government of Jordan (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 1,278,531 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2030 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNIDO has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4-A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	To be determined (TBD)*


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	2,808,101
	2,808,101
	2,808,101
	2,808,101
	2,808,101
	2,527,291
	2,527,291
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	35.6
	39.2
	43.1
	46.8
	50.4
	51.3
	54.5
	n/a

	
	
	CO2‑eq tonnes
	n/a
	1,809,703
	1,707,013
	1,596,587
	1,492,613
	1,393,191
	1,367,791
	1,278,531
	n/a

	2.1
	Lead IA (UNIDO) agreed funding (US $)
	2,540,680
	0
	0
	0
	1,802,170
	0
	0
	497,233
	4,840,083

	2.2
	Support costs for Lead IA (US $)
	177,848
	0
	0
	0
	126,152
	0
	0
	34,806
	338,806

	3.1
	Total agreed funding (US $)
	2,540,680
	0
	0
	0
	1,802,170
	0
	0
	497,233
	4,840,083

	3.2
	Total support costs (US $)
	177,848
	0
	0
	0
	126,152
	0
	0
	34,806
	338,806

	3.3
	Total agreed costs (US $)
	2,718,528
	0
	0
	0
	1,928,322
	0
	0
	532,039
	5,178,889

	4.1.1
	Deductions of HFCs agreed under this Agreement (CO2-eq tonnes)
	1,231,104

	4.1.2
	Deductions of HFCs from previously approved projects (CO2-eq tonnes)
	*211,530

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


* Noting that 36.25 mt (51,837.5 CO2-eq tonnes) of HFC-134a, 39.75 mt (70,516.5 CO2-eq tonnes) of R-407C, and 42.70 mt (89,175.6 CO2‑eq tonnes) of R-410A would be deducted from the starting point for sustained aggregate reduction in HFCs once it has been established (decision 81/62).
APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), under the Ministry of Environment, will monitor the implementation of the Plan’s activities, coordinate with relevant stakeholders, follow up on regulatory measures, monitor training and awareness activities, collect HFC consumption data, and support verification measures undertaken by the Lead IA.
2. The Ministry of Environment, through the NOU and in coordination with relevant national institutions, will also be responsible for ensuring the sustainability of the HFC consumption reduction targets achieved under the Agreement, including through the continued implementation of the licensing and control system, stakeholder coordination, and capacity-building support.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
(k) Ensuring that disbursements made to the Country are based on the use of the indicators;
(l) Providing assistance with the policy, management and technical support when required; and
(m) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
2. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.86 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF KYRGYZSTAN
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2029)
Purpose
1. This Agreement represents the understanding of the Government of Kyrgyzstan (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 405,344 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
167. The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
168. Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
169. The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
170. The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
171. The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
172. The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(a) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(b) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(c) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
173. Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
174. The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) and UNEP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
175. The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
176. Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
177. The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
178. The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
179. The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
180. All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
181. This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	450,382
	450,382
	450,382
	450,382
	450,382
	405,344
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	450,382
	450,382
	450,382
	450,382
	450,382
	405,344
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	51,000
	0
	0
	79,000
	0
	0
	0
	130,000

	2.2
	Support costs for Lead IA (US $)
	6,630
	0
	0
	10,270
	0
	0
	0
	16,900

	2.3
	Cooperating IA (UNEP) agreed funding (US $)
	30,000
	0
	0
	30,000
	0
	0
	0
	60,000

	2.4
	Support costs for Cooperating IA (US $)
	3,900
	0
	0
	3,900
	0
	0
	0
	7,800

	3.1
	Total agreed funding (US $)
	81,000
	0
	0
	109,000
	0
	0
	0
	190,000

	3.2
	Total support costs (US $)
	10,530
	0
	0
	14,170
	0
	0
	0
	24,700

	3.3
	Total agreed costs (US $)
	91,530
	0
	0
	123,170
	0
	0
	0
	214,700


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Ministry of Natural Resources, Ecology, and Technical Supervision, will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA. The Ministry of Natural Resources, Ecology, and Technical Supervision is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
186. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XIII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF THE LAO PEOPLE’S DEMOCRATIC REPUBLIC AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2030)
Purpose
1. This Agreement represents the understanding of the Government of the Lao People’s Democratic Republic (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 291,803 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(a) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNDP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	10
	n/a

	
	
	CO2‑eq tonnes
	324,226
	324,226
	324,226
	324,226
	324,226
	291,803
	291,803
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	324,226
	324,226
	324,226
	324,226
	324,226
	291,803
	291,803
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	34,000
	0
	0
	80,000
	0
	0
	0
	114,000

	2.2
	Support costs for Lead IA (US $)
	4,420
	0
	0
	10,400
	0
	0
	0
	14,820

	2.3
	Cooperating IA (UNDP) agreed funding (US $)
	76,000
	0
	0
	0
	0
	0
	0
	76,000

	2.4
	Support costs for Cooperating IA (US $)
	9,880
	0
	0
	0
	0
	0
	0
	9,880

	3.1
	Total agreed funding (US $)
	110,000
	0
	0
	80,000
	0
	0
	0
	190,000

	3.2
	Total support costs (US $)
	14,300
	0
	0
	10,400
	0
	0
	0
	24,700

	3.3
	Total agreed costs (US $)
	124,300
	0
	0
	90,400
	0
	0
	0
	214,700


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Ministry of Natural Resources and Environment (MNRE), will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA. The MNRE is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
The monitoring, reporting, verification and enforcement of HFC consumption levels will be carried out by the NOU in collaboration with the Customs Department and the Department of Industry under the Ministry of Industry and Commerce. The NOU is responsible for determining national HFC quotas and allocating them to eligible importers, while the Department of Industry is a licensing authority for issuing import and export permits based on the quotas allocated by the NOU. The Customs Department will control and monitor the import and export of HFCs at the point of entry. The NOU will liaise with concerned stakeholders including the Department of Industry, the Customs Department and HFC importers to obtain the data necessary for the periodic reconciliation of statistics.
The NOU will be responsible for the following:
(a) Carrying out surveys to gauge the status of HFC phase-down, potential illegal imports, and penetration of low-GWP alternative technologies in different subsectors;
(b) Carrying out regular inspections of the condition of training equipment acquired under the Plan for mobile air-conditioning training centre(s);
(c) Monitoring the implementation of capacity-building activities for trainers, assessors and technicians, including activities to maintain or enhance energy efficiency in the servicing sector, training for customs and enforcement officers, and training for importers and customs brokers; and
(d) Submitting annual progress reports on the status of implementation to the Lead IA and the Cooperating IA to monitor progress.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(a) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required;
Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XIV
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF LESOTHO
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Lesotho (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 49,936 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6-A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4-A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	103,221
	103,221
	103,221
	103,221
	103,221
	92,899
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	39.5
	39.5
	39.5
	39.5
	39.5
	51.6
	n/a

	
	
	CO2‑eq tonnes
	62,420
	62,420
	62,420
	62,420
	62,420
	49,936
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	64,000
	0
	0
	50,000
	0
	0
	114,000

	2.2
	Support costs for Lead IA (US $)
	8,320
	0
	0
	6,500
	0
	0
	14,820

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	18,000
	0
	0
	13,000
	0
	0
	31,000

	2.4
	Support costs for Cooperating IA (US $)
	2,340
	0
	0
	1,690
	0
	0
	4,030

	3.1
	Total agreed funding (US $)
	82,000
	0
	0
	63,000
	0
	0
	145,000

	3.2
	Total support costs (US $)
	10,660
	0
	0
	8,190
	0
	0
	18,850

	3.3
	Total agreed costs (US $)
	92,660
	0
	0
	71,190
	0
	0
	163,850


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Lesotho Meteorological Services, will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA. Lesotho Meteorological Services is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
2. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES 
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XV
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF LIBERIA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Liberia (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 122,817 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
198. The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
199. Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
200. The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
201. The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
202. The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
203. The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(a) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(b) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(c) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
204. Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
205. The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. The Government of Germany has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
206. The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
207. Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
208. The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
209. The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
210. The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
211. All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
212. This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	180,909
	180,909
	180,909
	180,909
	180,909
	162,818
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	27.8
	27.8
	30.0
	30.0
	32.1
	n/a

	
	
	CO2‑eq tonnes
	180,909
	130,532
	130,532
	126,616
	126,616
	122,817
	n/a

	2.1
	Lead IA (Germany) agreed funding (US $)
	72,500
	0
	0
	72,500
	0
	0
	145,000

	2.2
	Support costs for Lead IA (US $)
	9,425
	0
	0
	9,425
	0
	0
	18,850

	3.1
	Total agreed funding (US $)
	72,500
	0
	0
	72,500
	0
	0
	145,000

	3.2
	Total support costs (US $)
	9,425
	0
	0
	9,425
	0
	0
	18,850

	3.3
	Total agreed costs (US $)
	81,925
	0
	0
	81,925
	0
	0
	163,850


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Liberia Environmental Protection Agency, will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and the delivery of outcomes, the NOU will facilitate the verification of HFC consumption to be undertaken by the Lead IA. The Liberia Environmental Protection Agency is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
216. The NOU, with assistance from the Lead IA, will establish a robust monitoring and evaluation process to track the implementation of the Plan. This will include development and implementation of a comprehensive data collection system to gather information on the import, export, and consumption on HFCs, periodic reporting to the Lead IA on project implementation status that will ensure transparency and accountability, monitoring of reductions in HFC consumption, compliance with phase‑down schedules, assessing adoption of alternative technologies in different applications, mobilising personnel and other resources for project implementation and monitoring project progress and coordination with relevant national institutions and stakeholders (e.g., industry representatives, enforcement bodies, civil society) for their active engagement in implementation of different project activities. The NOU will also undertake quarterly and annual reviews in collaboration with the Lead IA to monitor project progress, identify challenges, and recalibrate strategies where necessary.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
(k) Ensuring that disbursements made to the Country are based on the use of the indicators;
(l) Providing assistance with the policy, management and technical support when required; and
(m) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
218. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XVI
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF MALAWI
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2030)
Purpose
1. [bookmark: _Hlk188450574]This Agreement represents the understanding of the Government of Malawi (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 197,488 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2030 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6-A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4-A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	10
	n/a

	
	
	CO2‑eq tonnes
	n/a
	428,435
	428,435
	428,435
	428,435
	428,435
	385,591
	385,591
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	51.1
	49.1
	49.9
	51.1
	51.9
	52.5
	52.9
	54
	n/a

	
	
	CO2‑eq tonnes
	209,337
	217,890
	214,626
	209,580
	206,020
	203,508
	201,736
	197,488
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	39,000
	0
	0
	58,200
	0
	0
	0
	17,000
	114,200

	2.2
	Support costs for Lead IA (US $)
	5,070
	0
	0
	7,566
	0
	0
	0
	2,210
	14,846

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	29,000
	0
	0
	43,800
	0
	0
	0
	0
	72,800

	2.4
	Support costs for Cooperating IA (US $)
	3,770
	0
	0
	5,694
	0
	0
	0
	0
	9,464

	3.1
	Total agreed funding (US $)
	68,000
	0
	0
	102,000
	0
	0
	0
	17,000
	187,000

	3.2
	Total support costs (US $)
	8,840
	0
	0
	13,260
	0
	0
	0
	2,210
	24,310

	3.3
	Total agreed costs (US $)
	76,840
	0
	0
	115,260
	0
	0
	0
	19,210
	211,310


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Ministry of Natural Resources and Climate Change, will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA. The Ministry of Natural Resources and Climate Change is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
2. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES 
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XVII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF MALAYSIA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2029)
Purpose
1. This Agreement represents the understanding of the Government of Malaysia (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 24,033,345 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
(a) Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
(b) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. The World Bank has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	n/a
	26,703,717
	26,703,717
	26,703,717
	26,703,717
	26,703,717
	24,033,345
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	26,703,717
	26,703,717
	26,703,717
	26,703,717
	26,703,717
	24,033,345
	n/a

	2.1
	Lead IA (World Bank) agreed funding (US $)
	3,042,912
	0
	3,246,290
	0
	2,336,655
	0
	649,258
	9,275,115

	2.2
	Support costs for Lead IA (US $)
	213,004
	0
	227,240
	0
	163,566
	0
	45,448
	649,258

	3.1
	Total agreed funding (US $)
	3,042,912
	0
	3,246,290
	0
	2,336,655
	0
	649,258
	9,275,115

	3.2
	Total support costs (US $)
	213,004
	0
	227,240
	0
	163,566
	0
	45,448
	649,258

	3.3
	Total agreed costs (US $)
	3,255,916
	0
	3,473,530
	0
	2,500,221
	0
	694,706
	9,924,373

	4.1.1
	Deductions of HFCs under this Agreement (CO2-eq tonnes)
	2,763,452

	4.1.2
	Deductions of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The monitoring process will be managed by the Department of Environment (DOE) through the national ozone unit (NOU) with the assistance of the Lead IA.
1. Consumption will be monitored and determined based on official import and export data for the Substances recorded by relevant Government departments.
1. The DOE shall compile relevant data and prepare the following on or before the relevant due dates:
(a) Annual reports on consumption of the Substances to be submitted to the Ozone Secretariat; and
(b) Periodic reports on the implementation progress of the Plan, to be submitted through the Lead IA to the Executive Committee of the Multilateral Fund with Tranche Implementation Plans and HFC consumption verification reports.
1. Consumption will be monitored annually throughout the implementation of the Plan and accordingly reflected in the progress report on the implementation of the Plan.
The NOU in the DOE shall prepare, with the Lead IA, the final implementation progress report and the Lead IA shall submit the same.
The DOE, along with its Government partner agencies, will be responsible for the sustainability of consumption reduction targets achieved through this Agreement, and for reviewing all related reports and data and instituting control and policy measures that facilitate HFC control and reductions according to this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(a) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $6.71 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XVIII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF MONTENEGRO
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Montenegro (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 125,577 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2-A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2-A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1-A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(a) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNIDO has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	155,854
	155,854
	155,854
	155,854
	155,854
	140,269
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	12.3
	14.1
	15.8
	17.6
	19.4
	n/a

	
	
	CO2‑eq tonnes
	155,854
	136,739
	133,949
	131,158
	128,368
	125,577
	n/a

	2.1
	Lead IA (UNIDO) agreed funding (US $)
	115,050
	0
	0
	74,550
	0
	0
	189,600

	2.2
	Support costs for Lead IA (US $)
	14,956
	0
	0
	9,692
	0
	0
	24,648

	3.1
	Total agreed funding (US $)
	115,050
	0
	0
	74,550
	0
	0
	189,600

	3.2
	Total support costs (US $)
	14,956
	0
	0
	9,692
	0
	0
	24,648

	3.3
	Total agreed costs (US $)
	130,006
	0
	0
	84,242
	0
	0
	214,248


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(a) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. All monitoring activities will be coordinated and managed through the Plan’s monitoring and management unit within the national ozone unit (NOU).
The NOU, under the Environmental Protection Agency (EPA), is responsible for coordinating the Country’s action plan with respect to ozone layer protection and facilitation of HFC phase-down. The NOU is in charge of implementing the country programmes under the Montreal Protocol. Implementation of the planned project activities will be allocated to the NOU in cooperation with the Lead IA. The NOU as a management body has a responsibility toward EPA and the Ministry of Ecology, Sustainable Development and Northern Region Development as a decision-making body. The NOU, under the EPA, is responsible for ensuring the sustainability of the consumption reduction targets achieved under this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
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1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin. 
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Annex XIX
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF MOZAMBIQUE
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2030)
Purpose
1. This Agreement represents the understanding of the Government of Mozambique (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 589,730 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund;
Changes that would modify any clause of this Agreement;
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(a) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNDP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6-A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	10
	n/a

	
	
	CO2-eq tonnes
	655,255
	655,255
	655,255
	655,255
	655,255
	589,730
	589,730
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	655,255
	655,255
	655,255
	655,255
	655,255
	589,730
	589,730
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	83,500
	0
	81,500
	0
	0
	0
	42,000
	207,000

	2.2
	Support costs for Lead IA (US $)
	10,855
	0
	10,595
	0
	0
	0
	5,460
	26,910

	2.3
	Cooperating IA (UNDP) agreed funding (US $)
	86,000
	0
	6,000
	0
	0
	0
	26,000
	118,000

	2.4
	Support costs for Cooperating IA (US $)
	11,180
	0
	780
	0
	0
	0
	3,380
	15,340

	3.1
	Total agreed funding (US $)
	169,500
	0
	87,500
	0
	0
	0
	68,000
	325,000

	3.2
	Total support costs (US $)
	22,035
	0
	11,375
	0
	0
	0
	8,840
	42,250

	3.3
	Total agreed costs (US $)
	191,535
	0
	98,875
	0
	0
	0
	76,840
	367,250


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit, under the Ministry of Land and Environment, is responsible for monitoring the progress of implementation of activities in the Plan.
Monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of training and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA.
The Ministry of Land and Environment will be responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee including the activities implemented by the Cooperating IA;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required; 
Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
Providing assistance for policy development when required;
Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XX
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF NORTH MACEDONIA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2029)
Purpose
1. This Agreement represents the understanding of the Government of North Macedonia (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 323,345 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
(a) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNIDO has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	 HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	n/a
	397,843
	397,843
	397,843
	397,843
	397,843
	358,059
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	4.8
	7.3
	9.7
	9.7
	9.7
	18.7
	n/a

	
	
	CO2‑eq tonnes
	n/a
	378,557
	368,915
	359,272
	359,272
	359,272
	323,345
	n/a

	2.1
	Lead IA (UNIDO) agreed funding (US $)
	103,555
	0
	0
	90,445
	0
	22,000
	0
	216,000

	2.2
	Support costs for Lead IA (US $)
	13,462
	0
	0
	11,758
	0
	2,860
	0
	28,080

	3.1
	Total agreed funding (US $)
	103,555
	0
	0
	90,445
	0
	22,000
	0
	216,000

	3.2
	Total support costs (US $)
	13,462
	0
	0
	11,758
	0
	2,860
	0
	28,080

	3.3
	Total agreed costs (US $)
	117,017
	0
	0
	102,203
	0
	24,860
	0
	244,080

	4.1.1
	 Deduction of HFCs under this Agreement (CO2-eq tonnes)
	74,498

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Ministry of Environment and Physical Planning, will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the duration of the Plan.
1. Monitoring will be conducted throughout implementation to ensure an effective overall project coordination, stakeholder engagement, timely execution of activities under each tranche, and delivery of expected outcomes. The NOU will also facilitate the verification of HFC consumption to be undertaken by the Lead IA.
1. The Ministry of Environment and Physical Planning will be responsible for ensuring the sustainability of the consumption reduction targets achieved under this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
APPENDIX 8-A: SECTOR-SPECIFIC ARRANGEMENTS 
1. During the implementation of stage I of the Plan, the Country will be allowed, on an exceptional basis, to submit a project to phase out the consumption of HFC-152a in the extruded polystyrene foam manufacturing sector.
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Annex XXI
DRAFT AGREEMENT BETWEEN THE GOVERNMENTS OF THE PACIFIC ISLAND COUNTRIES (THE COOK ISLANDS, KIRIBATI, THE MARSHALL ISLANDS,
THE FEDERATED STATES OF MICRONESIA, NAURU, NIUE, PALAU, SAMOA,
SOLOMON ISLANDS, TONGA, TUVALU, VANUATU)
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Governments of the Cook Islands, Kiribati, the Marshall Islands, the Federated States of Micronesia, Nauru, Niue, Palau, Samoa, Solomon Islands, Tonga, Tuvalu, and Vanuatu (each hereinafter referred to as “the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 149,357 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
253. The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
254. Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
255. The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
256. The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
(a) That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
(b) That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
(c) That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
(d) That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
257. The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
258. The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
(a) Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
(i) Issues potentially concerning the rules and policies of the Multilateral Fund; 
(ii) Changes that would modify any clause of this Agreement; 
(iii) Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
(iv) Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
(v) Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
(b) Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and 
(c) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
259. Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
260. The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and the Government of Australia has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
261. The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6-A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
262. Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
263. The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
264. The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
265. The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
266. All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
267. This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
THE PACIFIC ISLAND COUNTRIES - OVERALL FUNDING
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	181,404
	181,404
	181,404
	181,404
	181,404
	163,260
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	11.5
	11.5
	11.5
	17.7
	n/a

	
	
	CO2-eq tonnes
	181,404
	181,404
	160,549
	160,549
	160,549
	149,357
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	683,000
	0
	0
	559,000
	0
	0
	1,242,000

	2.2
	Support costs for Lead IA (US $)
	88,790
	0
	0
	72,670
	0
	0
	161,460

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	295,000
	0
	0
	93,000
	0
	0
	388,000

	2.4
	Support costs for Cooperating IA (US $)
	38,350
	0
	0
	12,090
	0
	0
	50,440

	3.1
	Total agreed funding (US $)
	978,000
	0
	0
	652,000
	0
	0
	1,630,000

	3.2
	Total support costs (US $)
	127,140
	0
	0
	84,760
	0
	0
	211,900

	3.3
	Total agreed costs (US $)
	1,105,140
	0
	0
	736,760
	0
	0
	1,841,900


GOVERNMENT OF THE COOK ISLANDS
APPENDIX 1-A.1: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.1: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	6,461
	6,461
	6,461
	6,461
	6,461
	5,814
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	6,461
	6,461
	6,461
	6,461
	6,461
	5,814
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	23,250
	0
	0
	44,250
	0
	0
	67,500

	2.2
	Support costs for Lead IA (US $)
	3,023
	0
	0
	5,752
	0
	0
	8,775

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	23,250
	0
	0
	44,250
	0
	0
	67,500

	3.2
	Total support costs (US $)
	3,023
	0
	0
	5,752
	0
	0
	8,775

	3.3
	Total agreed costs (US $)
	26,273
	0
	0
	50,002
	0
	0
	76,275


GOVERNMENT OF KIRIBATI
APPENDIX 1-A.2: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.2: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	8,509
	8,509
	8,509
	8,509
	8,509
	7,658
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	8,509
	8,509
	8,509
	8,509
	8,509
	7,658
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	15,000
	0
	0
	11,000
	0
	0
	26,000

	2.2
	Support costs for Lead IA (US $)
	1,950
	0
	0
	1,430
	0
	0
	3,380

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	15,000
	0
	0
	11,000
	0
	0
	26,000

	3.2
	Total support costs (US $)
	1,950
	0
	0
	1,430
	0
	0
	3,380

	3.3
	Total agreed costs (US $)
	16,950
	0
	0
	12,430
	0
	0
	29,380


GOVERNMENT OF THE MARSHALL ISLANDS
APPENDIX 1-A.3: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.3: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	15,926
	15,926
	15,926
	15,926
	15,926
	14,333
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	15,926
	15,926
	15,926
	15,926
	15,926
	14,333
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	11,750
	0
	0
	7,750
	0
	0
	19,500

	2.2
	Support costs for Lead IA (US $)
	1,527
	0
	0
	1,008
	0
	0
	2,535

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	11,750
	0
	0
	7,750
	0
	0
	19,500

	3.2
	Total support costs (US $)
	1,527
	0
	0
	1,008
	0
	0
	2,535

	3.3
	Total agreed costs (US $)
	13,277
	0
	0
	8,758
	0
	0
	22,035


GOVERNMENT OF THE FEDERATED STATES OF MICRONESIA
APPENDIX 1-A.4: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.4: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	13,600
	13,600
	13,600
	13,600
	13,600
	12,240
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	13,600
	13,600
	13,600
	13,600
	13,600
	12,240
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	63,500
	0
	0
	27,500
	0
	0
	91,000

	2.2
	Support costs for Lead IA (US $)
	8,255
	0
	0
	3,575
	0
	0
	11,830

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	63,500
	0
	0
	27,500
	0
	0
	91,000

	3.2
	Total support costs (US $)
	8,255
	0
	0
	3,575
	0
	0
	11,830

	3.3
	Total agreed costs (US $)
	71,755
	0
	0
	31,075
	0
	0
	102,830


GOVERNMENT OF NAURU
APPENDIX 1-A.5: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.5: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	2,378
	2,378
	2,378
	2,378
	2,378
	2,140
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	2,378
	2,378
	2,378
	2,378
	2,378
	2,140
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	10,500
	0
	0
	6,500
	0
	0
	17,000

	2.2
	Support costs for Lead IA (US $)
	1,365
	0
	0
	845
	0
	0
	2,210

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	10,500
	0
	0
	6,500
	0
	0
	17,000

	3.2
	Total support costs (US $)
	1,365
	0
	0
	845
	0
	0
	2,210

	3.3
	Total agreed costs (US $)
	11,865
	0
	0
	7,345
	0
	0
	19,210


GOVERNMENT OF NIUE
APPENDIX 1-A.6: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.6: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	236
	236
	236
	236
	236
	212
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	236
	236
	236
	236
	236
	212
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	9,250
	0
	0
	5,250
	0
	0
	14,500

	2.2
	Support costs for Lead IA (US $)
	1,202
	0
	0
	683
	0
	0
	1,885

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	9,250
	0
	0
	5,250
	0
	0
	14,500

	3.2
	Total support costs (US $)
	1,202
	0
	0
	683
	0
	0
	1,885

	3.3
	Total agreed costs (US $)
	10,452
	0
	0
	5,933
	0
	0
	16,385


GOVERNMENT OF PALAU
APPENDIX 1-A.7: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.7: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	10,368
	10,368
	10,368
	10,368
	10,368
	9,331
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	10,368
	10,368
	10,368
	10,368
	10,368
	9,331
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	57,500
	0
	0
	46,500
	0
	0
	104,000

	2.2
	Support costs for Lead IA (US $)
	7,475
	0
	0
	6,045
	0
	0
	13,520

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	57,500
	0
	0
	46,500
	0
	0
	104,000

	3.2
	Total support costs (US $)
	7,475
	0
	0
	6,045
	0
	0
	13,520

	3.3
	Total agreed costs (US $)
	64,975
	0
	0
	52,545
	0
	0
	117,520


GOVERNMENT OF SAMOA
APPENDIX 1-A.8: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.8: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	20,557
	20,557
	20,557
	20,557
	20,557
	18,501
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	20,557
	20,557
	20,557
	20,557
	20,557
	18,501
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	66,000
	0
	0
	58,000
	0
	0
	124,000

	2.2
	Support costs for Lead IA (US $)
	8,580
	0
	0
	7,540
	0
	0
	16,120

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	66,000
	0
	0
	58,000
	0
	0
	124,000

	3.2
	Total support costs (US $)
	8,580
	0
	0
	7,540
	0
	0
	16,120

	3.3
	Total agreed costs (US $)
	74,580
	0
	0
	65,540
	0
	0
	140,120


GOVERNMENT OF SOLOMON ISLANDS
APPENDIX 1-A.9: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.9: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	69,516
	69,516
	69,516
	69,516
	69,516
	62,564
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	30.0
	30.0
	30.0
	30.0
	n/a

	
	
	CO2-eq tonnes
	69,516
	69,516
	48,661
	48,661
	48,661
	48,661
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	74,125
	0
	0
	66,125
	0
	0
	140,250

	2.2
	Support costs for Lead IA (US $)
	9,637
	0
	0
	8,596
	0
	0
	18,233

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	74,125
	0
	0
	66,125
	0
	0
	140,250

	3.2
	Total support costs (US $)
	9,637
	0
	0
	8,596
	0
	0
	18,233

	3.3
	Total agreed costs (US $)
	83,762
	0
	0
	74,721
	0
	0
	158,483


GOVERNMENT OF TONGA
APPENDIX 1-A.10: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.10: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	7,676
	7,676
	7,676
	7,676
	7,676
	6,908
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	7,676 
	7,676 
	7,676 
	7,676 
	7,676 
	6,908
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	60,750
	0
	0
	49,750
	0
	0
	110,500

	2.2
	Support costs for Lead IA (US $)
	7,898
	0
	0
	6,467
	0
	0
	14,365

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	60,750
	0
	0
	49,750
	0
	0
	110,500

	3.2
	Total support costs (US $)
	7,898
	0
	0
	6,467
	0
	0
	14,365

	3.3
	Total agreed costs (US $)
	68,648
	0
	0
	56,217
	0
	0
	124,865


GOVERNMENT OF TUVALU
APPENDIX 1-A.11: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.11: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	2,648
	2,648
	2,648
	2,648
	2,648
	2,383
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	2,648
	2,648
	2,648
	2,648
	2,648
	2,383
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	12,250
	0
	0
	8,250
	0
	0
	20,500

	2.2
	Support costs for Lead IA (US $)
	1,592
	0
	0
	1,073
	0
	0
	2,665

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	12,250
	0
	0
	8,250
	0
	0
	20,500

	3.2
	Total support costs (US $)
	1,592
	0
	0
	1,073
	0
	0
	2,665

	3.3
	Total agreed costs (US $)
	13,842
	0
	0
	9,323
	0
	0
	23,165


GOVERNMENT OF VANUATU
APPENDIX 1-A.12: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A.12: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	23,529
	23,529
	23,529
	23,529
	23,529
	21,176
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	23,529
	23,529
	23,529
	23,529
	23,529
	21,176
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	31,625
	0
	0
	52,625
	0
	0
	84,250

	2.2
	Support costs for Lead IA (US $)
	4,112
	0
	0
	6,841
	0
	0
	10,953

	2.3
	Cooperating IA (Australia) agreed funding (US $)
	0
	0
	0
	0
	0
	0
	0

	2.4
	Support costs for Cooperating IA (US $)
	0
	0
	0
	0
	0
	0
	0

	3.1
	Total agreed funding (US $)
	31,625
	0
	0
	52,625
	0
	0
	84,250

	3.2
	Total support costs (US $)
	4,112
	0
	0
	6,841
	0
	0
	10,953

	3.3
	Total agreed costs (US $)
	35,737
	0
	0
	59,466
	0
	0
	95,203


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. Under the respective Ministries or Agencies, i.e., the Cook Islands National Environment Service; the Kiribati Ministry of Environment, Lands and Agricultural Development; the Marshall Islands Environmental Protection Authority; the Federated States of Micronesia Department of Environment, Climate Change and Emergency Management; the Nauru Department of Environmental Management and Agriculture; the Niue Ministry of Natural Resources; the Palau Environmental Quality Protection Board; the Samoa Ministry of Natural Resources and Environment; the Solomon Islands Ministry of Mines, Energy and Rural Electrification; the Tonga Ministry of Meteorology, Energy, Information, Disaster Management, Environment, Climate Change and Communications; the Tuvalu Ministry of Home Affairs, Climate Change and Environment; and the Vanuatu Ministry of Climate Change Adaptation, Meteorology, Geohazards, Energy, Environment and Disaster Management, the national ozone units (NOUs) will be responsible for the overall project monitoring of all activities under the Plan, as well as the planning, coordination, and daily work of project implementation.
271. The NOUs will coordinate closely with national industries, technical institutions, non‑governmental organizations and government departments, as well as technical experts, the Lead IA and the Cooperating IA, to ensure the smooth implementation of the Plan. Moreover, the NOUs will work in collaboration with respective national Energy-Efficiency Authorities to explore synergies between HFC phase‑down and energy efficiency in the national implementation of policy and regulations, capacity building, raising awareness and communications.
272. Annual consumption of HFCs will be monitored through the NOUs in collaboration with the Customs Authority of each Country. The NOUs will also liaise with importers of HFCs to obtain the necessary data for reconciliation of statistics on a periodic basis.
273. The NOUs will undertake national market surveys to gauge the situation of HFC phase‑down, potential illegal imports, and the penetration of alternative technologies with low global-warming potential in different subsectors. In case of a risk of non-compliance with obligations or not meeting the maximum allowance for total consumption of Annex F substances, the NOUs will report to the Lead IA and Cooperating IA to identify specific interventions needed for achieving the HFC phase-down targets.
274. The NOUs will monitor the implementation of capacity-building activities with relevant agencies, including competency-based training and assessment for refrigeration and air‑conditioning and mobile air‑conditioning technicians, activities to build the capacity of technicians to maintain and/or enhance energy efficiency in the servicing sector while phasing down HFCs, and training for customs and enforcement officers.
275. The NOUs will submit annual progress reports on the status of implementation of respective national components to the Lead IA and Cooperating IA to monitor the implementation progress of the Plan.
276. The Ministries and Agencies listed in paragraph 1 above will be responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
278. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XXII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF PANAMA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2029)
Purpose
1. This Agreement represents the understanding of the Government of Panama (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 2,289,047 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	 HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	n/a
	2,543,386
	2,543,386
	2,543,386
	2,543,386
	2,543,386
	2,289,047
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in % 
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	2,543,386
	2,543,386
	2,543,386
	2,543,386
	2,543,386
	2,289,047
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	331,100
	0
	0
	264,880
	0
	0
	66,220
	662,200

	2.2
	Support costs for Lead IA (US $)
	23,177
	0
	0
	18,542
	0
	0
	4,635
	46,354

	3.1
	Total agreed funding (US $)
	331,100
	0
	0
	264,880
	0
	0
	66,220
	662,200

	3.2
	Total support costs (US $)
	23,177
	0
	0
	18,542
	0
	0
	4,635
	46,354

	3.3
	Total agreed costs (US $)
	354,277
	0
	0
	283,422
	0
	0
	70,855
	708,554

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	254,339

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the General Sub-Directorate of Environmental Health in the General Directorate of Public Health at the Ministry of Health (MINSA), will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, strengthening of education centres and pilot projects, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA.
The MINSA coordinates all activities aimed at achieving and sustaining the commitments to reduce HFC consumption with different entities at the national level, including the Ministry of Commerce and Industry, Ministry of Education and other institutions in the academic sector, the Ministry of Environment, the National Customs Authority, the National Energy Secretariat, civil society associations and the productive sectors.
The MINSA is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $5.21 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XXIII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF PARAGUAY
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Paraguay (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 1,516,124 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(a) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	1,684,582
	1,684,582
	1,684,582
	1,684,582
	1,684,582
	1,516,124
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	1,684,582
	1,684,582
	1,684,582
	1,684,582
	1,684,582
	1,516,124
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	235,675
	0
	0
	188,540
	0
	47,135
	471,350

	2.2
	Support costs for Lead IA (US $)
	16,497
	0
	0
	13,198
	0
	3,300
	32,995

	3.1
	Total agreed funding (US $)
	235,675
	0
	0
	188,540
	0
	47,135
	471,350

	3.2
	Total support costs (US $)
	16,497
	0
	0
	13,198
	0
	3,300
	32,995

	3.3
	Total agreed costs (US $)
	252,172
	0
	0
	201,738
	0
	50,435
	504,345

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	168,458

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Ministry of Environment and Sustainable Development (MADES), will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA.
1. The MADES is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
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1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $5.60 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin. 
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Annex XXIV
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF PERU
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2029)
Purpose
1. This Agreement represents the understanding of the Government of Peru (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 2,462,149 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
(a) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	2,735,721
	2,735,721
	2,735,721
	2,735,721
	2,735,721
	2,462,149
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	2,735,721
	2,735,721
	2,735,721
	2,735,721
	2,735,721
	2,462,149
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	283,140
	0
	0
	283,140
	0
	0
	62,718
	628,998

	2.2
	Support costs for Lead IA (US $)
	19,820
	0
	0
	19,820
	0
	0
	4,390
	44,030

	3.1
	Total agreed funding (US $)
	283,140
	0
	0
	283,140
	0
	0
	62,718
	628,998

	3.2
	Total support costs (US $)
	19,820
	0
	0
	19,820
	0
	0
	4,390
	44,030

	3.3
	Total agreed costs (US $)
	302,960
	0
	0
	302,960
	0
	0
	67,108
	673,028

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	273,572

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. Overall supervision will be provided by the Ministry of Production (PRODUCE), through the national ozone office (NOO), with assistance from the Lead IA.
1. Consumption will be monitored and determined from official data on the import and export of substances as registered by relevant Government departments. The NOO will compile and report the following data and information each year on, or before the deadlines:
(a) Annual reports on the consumption of the substances to be submitted to the Ozone Secretariat, 
(b) Annual reports on progress in Plan implementation to be submitted to the Executive Committee of the Multilateral Fund, and
(c) Annual reports on progress in gender indicators according to the guidelines established by the Multilateral Fund of the Montreal Protocol and the specific activities approved for the projects.
The NOO and the Lead IA will jointly hire a qualified independent entity to conduct a qualitative and quantitative performance assessment of the implementation of the Plan. The agency responsible for evaluation will have full access to relevant technical and financial information related to the implementation of the Plan.
The PRODUCE is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $4.60 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
APPENDIX 8-A: SECTOR-SPECIFIC ARRANGEMENTS
1. A project to phase out HFCs contained in imported pre-blended polyols in the Country’s polyurethane foam sector will be subject to the decision taken by the Committee on whether it would fund the phase-out of HFCs contained in imported pre-blended polyols.
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Annex XXV
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF RWANDA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Rwanda (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1-A (“The Substances”) to a sustained level of 254,008 CO2-equivalent (CO2-eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2-A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2-A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1-A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4-A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4-A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6-A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2-A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2-eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2-A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4-A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	338,197
	338,197
	338,197
	338,197
	338,197
	304,377
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	24.9
	n/a

	
	
	CO2‑eq tonnes
	338,197
	338,197
	338,197
	338,197
	338,197
	254,008
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	48,400
	0
	0
	44,000
	0
	17,600
	110,000

	2.2
	Support costs for Lead IA (US $)
	6,292
	0
	0
	5,720
	0
	2,288
	14,300

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	27,500
	0
	0
	44,000
	0
	5,500
	77,000

	2.4
	Support costs for Cooperating IA (US $)
	3,575
	0
	0
	5,720
	0
	715
	10,010

	3.1
	Total agreed funding (US $)
	75,900
	0
	0
	88,000
	0
	23,100
	187,000

	3.2
	Total support costs (US $)
	9,867
	0
	0
	11,440
	0
	3,003
	24,310

	3.3
	Total agreed costs (US $)
	85,767
	0
	0
	99,440
	0
	26,103
	211,310


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase-down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase-in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit, under the Ministry of Environment, is responsible for monitoring the progress of implementation of activities in the Plan.
Monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of training and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA.
The Ministry of Environment in the Country will be responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4-A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4-A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee including the activities implemented by the Cooperating IA;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required;
Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
2.	After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
Providing assistance for policy development when required;
Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2-A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XXVI
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF SAINT LUCIA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Saint Lucia (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 75,362 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1-A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6-A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4-A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes) 

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	83,735
	83,735
	83,735
	83,735
	83,735
	75,362
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	83,735
	83,735
	83,735
	83,735
	83,735
	75,362
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	43,000
	0
	0
	38,000
	0
	13,000
	94,000

	2.2
	Support costs for Lead IA (US $)
	5,590
	0
	0
	4,940
	0
	1,690
	12,220

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	27,000
	0
	0
	24,000
	0
	0
	51,000

	2.4
	Support costs for Cooperating IA (US $)
	3,510
	0
	0
	3,120
	0
	0
	6,630

	3.1
	Total agreed funding (US $)
	70,000
	0
	0
	62,000
	0
	13,000
	145,000

	3.2
	Total support costs (US $)
	9,100
	0
	0
	8,060
	0
	1,690
	18,850

	3.3
	Total agreed costs (US $)
	79,100
	0
	0
	70,060
	0
	14,690
	163,850


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU) will be responsible for the day-to-day execution of all components of the project, including monitoring, evaluation and reporting. It will be supported by the Ministry of Agriculture, Fisheries, Food Security and Sustainable Development who will manage the budget and exercise oversight of the procurement processes. The Ministry will also be responsible for the sustainability of consumption reduction targets achieved through this Agreement.
Upon project launch the NOU and the Montreal Protocol Technical Working Group will plan for the execution of each component and for the day-to-day execution of all activities approved under the Plan, including monitoring of all project activities, generating periodic monitoring and evaluation reports on project activities, targets achieved, adjustments, and remedial actions to be taken, if necessary, to ensure that targets are met. A consultant will be contracted to assist in delivering these tasks.
The Lead IA will be responsible for ensuring that periodic progress and financial reports are generated, tranche progress is monitored and funds are disbursed in accordance with this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
2. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XXVII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF SENEGAL
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Senegal (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 2,215,780 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(a) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	2,786,915
	2,786,915
	2,786,915
	2,786,915
	2,786,915
	2,508,224
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	20.5
	n/a

	
	
	CO2‑eq tonnes
	2,786,915
	2,786,915
	2,786,915
	2,786,915
	2,786,915
	2,215,780
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	168,000
	0
	0
	138,000
	0
	84,000
	390,000

	2.2
	Support costs for Lead IA (US $)
	21,840
	0
	0
	17,940
	0
	10,920
	50,700

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	127,500
	0
	0
	317,500
	0
	25,000
	470,000

	2.4
	Support costs for Cooperating IA (US $)
	8,925
	0
	0
	22,225
	0
	1,750
	32,900

	3.1
	Total agreed funding (US $)
	295,500
	0
	0
	455,500
	0
	109,000
	860,000

	3.2
	Total support costs (US $)
	30,765
	0
	0
	40,165
	0
	12,670
	83,600

	3.3
	Total agreed costs (US $)
	326,265
	0
	0
	495,665
	0
	121,670
	943,600

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	571,135

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Ministry of the Environment and Ecological Transition (MEET), will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the activities, including training, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA. The MEET is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
Consumption will be monitored and determined from the official data on the import and export of substances registered by the relevant Government departments.
The NOU will compile and report on the following data and information each year on or before the agreed deadlines:
(a) Annual reports on the consumption of substances submitted to the Ozone Secretariat; and
(b) Annual reports on progress achieved in the Plan’s implementation submitted to the Executive Committee of the Multilateral Fund.
The NOU and the Lead IA will jointly hire a qualified independent entity to conduct a qualitative and quantitative performance assessment of the implementation of the Plan.
The agency responsible for evaluation will have full access to relevant technical and financial information related to the implementation of the Plan, and will prepare and submit to the NOU and the Lead IA a draft consolidated report at the end of each annual implementation plan. The report will include assessment findings and, where appropriate, recommendations for improvements or adjustments, as well as the Country’s situation with regard to compliance with the provisions of this Agreement. After incorporating the comments and explanations, if any, from the NOU and the Lead IA, the agency responsible for evaluation will finalize the report and submit it to the MEET and the Lead IA. The MEET will endorse the final report, and the Lead IA will transmit it to the relevant meeting of the Executive Committee together with the implementation plan and annual reports.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(a) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required;
Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $5.28 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XXVIII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF SEYCHELLES
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND FOR
THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Seychelles (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 224,460 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(a) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and the Government of Germany has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	249,400
	249,400
	249,400
	249,400
	249,400
	224,460
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	249,400
	249,400
	249,400
	249,400
	249,400
	224,460
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	64,836
	0
	0
	20,424
	0
	0
	85,260

	2.2
	Support costs for Lead IA (US $)
	8,429
	0
	0
	2,655
	0
	0
	11,084

	2.3
	Cooperating IA (Germany) agreed funding (US $)
	16,844
	0
	0
	55,896
	0
	0
	72,740

	2.4
	Support costs for Cooperating IA (US $)
	2,190
	0
	0
	7,266
	0
	0
	9,456

	3.1
	Total agreed funding (US $)
	81,680
	0
	0
	76,320
	0
	0
	158,000

	3.2
	Total support costs (US $)
	10,619
	0
	0
	9,921
	0
	0
	20,540

	3.3
	Total agreed costs (US $)
	92,299
	0
	0
	86,241
	0
	0
	178,540


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. Overall monitoring will be provided by the Ministry of Environment, Climate, Energy and Natural Resources through the national ozone unit (NOU), with assistance from the Lead IA. The NOU will submit annual progress reports of status of implementation of the Plan to the Lead IA.
Consumption will be monitored and determined from the official data on the import and export of substances, as registered by the relevant Government departments. The NOU will compile and report the following data and information each year on or before the relevant deadlines:
(a) Reports on the consumption of substances to be submitted to the Ozone Secretariat in line with Article 7 of the Montreal Protocol; and
(b) Reports on country programme data to be submitted to the Secretariat of the Multilateral Fund.
The monitoring of the development of the Plan and verification of the achievement of performance targets will be assigned to an independent local company or to independent local consultant(s) by the Lead IA. The company or consultant(s) responsible for verification will have full access to relevant technical and financial information related to the implementation of the Plan.
The Ministry of Environment, Climate, Energy and Natural Resources will be responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(a) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required;
Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XXIX
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF SIERRA LEONE
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Sierra Leone (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 315,815 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(a) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	350,905
	350,905
	350,905
	350,905
	350,905
	315,815
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	1.5
	3.2
	4.9
	6.6
	8.3
	10.0
	n/a

	
	
	CO2‑eq tonnes
	345,642
	339,676
	333,711
	327,746
	321,780
	315,815
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	65,500
	0
	0
	38,817
	0
	0
	104,317

	2.2
	Support costs for Lead IA (US $)
	8,515
	0
	0
	5,046
	0
	0
	13,561

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	21,000
	0
	0
	54,683
	0
	0
	75,683

	2.4
	Support costs for Cooperating IA (US $)
	2,730
	0
	0
	7,109
	0
	0
	9,839

	3.1
	Total agreed funding (US $)
	86,500
	0
	0
	93,500
	0
	0
	180,000

	3.2
	Total support costs (US $)
	11,245
	0
	0
	12,155
	0
	0
	23,400

	3.3
	Total agreed costs (US $)
	97,745
	0
	0
	105,655
	0
	0
	203,400


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit, under the Ministry of the Environment and Climate Change, is responsible for monitoring the progress of implementation of activities in the Plan.
Monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of training and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA.
The Ministry of the Environment and Climate Change will be responsible for the sustainability of consumption reduction targets achieved through the Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(a) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required;
Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XXX
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF TOGO
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS IN ACCORDANCE
WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Togo (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 956,162 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
(a) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	1,124,896
	1,124,896
	1,124,896
	1,124,896
	1,124,896
	1,012,406
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	15.0
	n/a

	
	
	CO2‑eq tonnes
	1,124,896
	1,124,896
	1,124,896
	1,124,896
	1,124,896
	956,162
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	117,500
	0
	0
	102,500
	0
	0
	220,000

	2.2
	Support costs for Lead IA (US $)
	15,275
	0
	0
	13,325
	0
	0
	28,600

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	70,000
	0
	0
	70,000
	0
	0
	140,000

	2.4
	Support costs for Cooperating IA (US $)
	9,100
	0
	0
	9,100
	0
	0
	18,200

	3.1
	Total agreed funding (US $)
	187,500
	0
	0
	172,500
	0
	0
	360,000

	3.2
	Total support costs (US $)
	24,375
	0
	0
	22,425
	0
	0
	46,800

	3.3
	Total agreed costs (US $)
	211,875
	0
	0
	194,925
	0
	0
	406,800


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), under the Ministry of Environment, Forestry Resources, Coastal Protection, and Climate Change, is responsible for monitoring the progress of implementation of activities in the Plan. The NOU will submit annual progress reports of status of implementation of the Plan to the Lead IA. Monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation, overall project coordination, stakeholder engagement and coordination, smooth implementation of activities planned under the various tranches, delivery of training and other expected outcomes, and facilitation of the HFC consumption verification undertaken by the Lead IA.
2. Consumption will be monitored and determined from the official data on the import and export of substances as registered by the relevant Government departments. The NOU will compile and report on the following data and information each year on or before the relevant deadlines:
334. Reports on the consumption of substances to be submitted to the Ozone Secretariat in line with Article 7 of the Montreal Protocol; and
(a) Reports on country programme data to be submitted to the Secretariat of the Multilateral Fund.
3. Monitoring of the development of the Plan and verification of the achievement of performance targets will be assigned to an independent local company or to independent local consultant(s) by the Lead IA. The company or consultant(s) responsible for verification will have full access to relevant technical and financial information related to the implementation of the Plan.
4. The Ministry of Environment, Forestry Resources, Coastal Protection, and Climate Change will be responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
1. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
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1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XXXI
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF TRINIDAD AND TOBAGO
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2029)
Purpose
1. This Agreement represents the understanding of the Government of Trinidad and Tobago (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 5,113,608 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; 
Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4-A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	n/a
	5,681,787
	5,681,787
	5,681,787
	5,681,787
	5,681,787
	5,113,608
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	5,681,787
	5,681,787
	5,681,787
	5,681,787
	5,681,787
	5,113,608
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	543,249
	0
	0
	516,677
	0
	0
	117,769
	1,177,695

	2.2
	Support costs for Lead IA (US $)
	38,028
	0
	0
	36,167
	0
	0
	8,244
	82,439

	3.1
	Total agreed funding (US $)
	543,249
	0
	0
	516,677
	0
	0
	117,769
	1,177,695

	3.2
	Total support costs (US $)
	38,028
	0
	0
	36,167
	0
	0
	8,244
	82,439

	3.3
	Total agreed costs (US $)
	581,277
	0
	0
	552,844
	0
	0
	126,013
	1,260,134

	4.1.1
	Deductions of HFCs under this Agreement (CO2-eq tonnes)
	568,179

	4.1.2
	Deductions of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Ministry of Planning, Economic Affairs and Development (MPEAD), will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and delivery of outcomes, the NOU will facilitate verification of HFC consumption to be undertaken by the Lead IA.
2. The NOU will organize the collection and analysis of project data, standardize reporting formats, and convene periodic evaluation meetings. It will prepare internal progress reports, annual Plan implementation reports, and tranche submissions for the Executive Committee. The NOU will also monitor gender indicators, track private sector trends in HFC use, and stay updated on alternative technologies through participation in stakeholder-led technical meetings.
3. The MPEAD is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
(k) Ensuring that disbursements made to the Country are based on the use of the indicators;
(l) Providing assistance with the policy, management and technical support when required; and
(m) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
2. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $4.15 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin. 
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Annex XXXII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF TUNISIA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2030)
Purpose
1. This Agreement represents the understanding of the Government of Tunisia (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 1,803,694 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2030 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; 
Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNIDO has agreed to be the lead implementing agency (the “Lead IA”) and UNEP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6-A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	Freeze
	Freeze
	Freeze
	Freeze
	Freeze
	10
	10
	n/a

	
	
	CO2-eq tonnes
	2,367,840
	2,367,840
	2,367,840
	2,367,840
	2,367,840
	2,131,056
	2,131,056
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	23.8
	n/a

	
	
	CO2-eq tonnes
	2,367,840
	2,367,840
	2,367,840
	2,367,840
	2,367,840
	2,131,056
	1,803,694
	n/a

	2.1
	Lead IA (UNIDO) agreed funding (US $)
	1,526,566
	0
	0
	435,875
	0
	0
	104,740
	2,067,181 

	2.2
	Support costs for Lead IA (US $)
	106,860
	0
	0
	30,511
	0
	0
	7,332
	144,703

	2.3
	Cooperating IA (UNEP) agreed funding (US $)
	50,000
	0
	0
	45,000
	0
	0
	15,000
	110,000 

	2.4
	Support costs for Cooperating IA (US $)
	6,500
	0
	0
	5,850
	0
	0
	1,950
	14,300

	3.1
	Total agreed funding (US $)
	1,576,566
	0
	0
	480,875
	0
	0
	119,740
	2,177,181

	3.2
	Total support costs (US $)
	113,360
	0
	0
	36,361
	0
	0
	9,282
	159,003

	3.3
	Total agreed costs (US $)
	1,689,926
	0
	0
	517,236
	0
	0
	129,022
	2,336,184

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	629,563

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), under the National Agency for the Protection of the Environment (ANPE), will monitor the effectiveness of implementation of the different components under the Plan, including compliance with phase-down levels and impact of all activities against the set objectives and goals.
1. The ANPE, in close cooperation and coordination with the NOU and support of the Lead IA, will play a key role in the monitoring of the Plan and will be responsible for the sustainability of consumption reduction targets achieved through this Agreement. 
1. The NOU will undertake monitoring, reporting and record-keeping on:
345. HFC import and export, including data collected from local importers;
345. HFC use by different sectors, including data collected from manufacturers and surveys conducted by the project management unit;
345. Amounts of recovered, recycled, and unwanted HFCs;
345. Regular updates on the Plan’s deliverables as per targeted milestones;
345. Plans, progress reports and completion reports of components and projects; and
345. Information on HFC-based equipment banks and status of their operation and retirement.
1. The verification will, in addition to other tasks, cover the reports generated regarding achievements under the Plan.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee including the activities implemented by the Cooperating IA;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and the Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required;
Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
Providing assistance for policy development when required;
Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $6.92 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
APPENDIX 8-A: SECTOR-SPECIFIC ARRANGEMENTS
1. During the implementation of stage I of the Plan, a project to phase out HFCs contained in imported pre-blended polyols in the Country’s polyurethane foam sector would be subject to the Executive Committee’s consideration of funding the phase-out of HFCs contained in imported pre-blended polyols. 
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Annex XXXIII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF TÜRKIYE
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Türkiye (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 31,790,838 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 or 12 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 or 12 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNIDO has agreed to be the lead implementing agency (the “Lead IA”) and UNDP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	37,117,410
	37,117,410
	37,117,410
	37,117,410
	37,117,410
	33,405,669
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances 
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	14.4
	n/a

	
	
	CO2‑eq tonnes
	37,117,410
	37,117,410
	37,117,410
	37,117,410
	37,117,410
	31,790,838
	n/a

	2.1
	Lead IA (UNIDO) agreed funding (US $)
	1,943,985
	0
	0
	5,262,222
	0
	1,120,080
	8,326,287

	2.2
	Support costs for Lead IA (US $)
	136,079
	0
	0
	368,355
	0
	78,406
	582,840

	2.3
	Cooperating IA (UNDP) agreed funding (US $)
	845,445
	0
	0
	1,637,040
	0
	358,641
	2,841,126

	2.4
	Support costs for Cooperating IA (US $)
	59,181
	0
	0
	114,593
	0
	25,105
	198,879

	3.1
	Total agreed funding (US $)
	2,789,430
	0
	0
	6,899,262
	0
	1,478,721
	11,167,413

	3.2
	Total support costs (US $)
	195,260
	0
	0
	482,948
	0
	103,511
	781,719

	3.3
	Total agreed costs (US $)
	2,984,690
	0
	0
	7,382,210
	0
	1,582,232
	11,949,132

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	5,326,572

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), under the Directorate of Climate Change (DCC) of the Ministry of Environment, Urbanization and Climate Change (MoEUCC), is responsible for monitoring the progress of implementation of activities in the Plan.
1. The monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation, overall project coordination, stakeholder engagement and coordination, smooth implementation of activities planned under various tranches, delivery of training and other expected outcomes and facilitation of HFC consumption verification undertaken by the Lead IA.
1. The DCC will be responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required;
Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
Providing assistance for policy development when required;
Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $4.19 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
APPENDIX 8-A: SECTOR-SPECIFIC ARRANGEMENTS 
1. During the implementation of stage I of the Plan and no later than at the 98th meeting, the Country will be allowed, on an exceptional basis, to submit investment projects in the refrigeration, air-conditioning and foam sectors to achieve additional HFC reductions.
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Annex XXXIV
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF URUGUAY
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Uruguay (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 911,188 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; 
(a) Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
(b) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) and UNIDO has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6-A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	Freeze
	Freeze
	Freeze
	Freeze
	Freeze
	10
	n/a

	
	
	CO2-eq tonnes
	1,012,431
	1,012,431
	1,012,431
	1,012,431
	1,012,431
	911,188
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	1,012,431
	1,012,431
	1,012,431
	1,012,431
	1,012,431
	911,188
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	126,927
	0
	0
	92,413
	0
	0
	219,340

	2.2
	Support costs for Lead IA (US $)
	16,500
	0
	0
	12,014
	0
	0
	28,514

	2.3
	Cooperating IA (UNIDO) agreed funding (US $)
	49,860
	0
	0
	55,800
	0
	0
	105,660

	2.4
	Support costs for Cooperating IA (US $)
	6,482
	0
	0
	7,254
	0
	0
	13,736

	3.1
	Total agreed funding (US $)
	176,787
	0
	0
	148,213
	0
	0
	325,000

	3.2
	Total support costs (US $)
	22,982
	0
	0
	19,268
	0
	0
	42,250

	3.3
	Total agreed costs (US $)
	199,769
	0
	0
	167,481
	0
	0
	367,250

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	101,243

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), operating under the Ministry of Environment, will be responsible for monitoring the progress of implementation of the Plan’s tranches and ensuring that the planned activities, including training, are efficiently and effectively carried out throughout the Plan’s duration. In addition to monitoring overall project coordination, stakeholder engagement, and the delivery of outcomes, the NOU will facilitate the verification of HFC consumption to be undertaken by the Lead IA. 
The Ministry of Environment is the institution responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee including the activities implemented by the Cooperating IA;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
Coordinating the activities of the Cooperating IA[s] and ensuring the appropriate sequence of activities;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and the Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required;
Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
Providing assistance for policy development when required;
Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
APPENDIX 8-A: SECTOR-SPECIFIC ARRANGEMENTS 
1. During the implementation of stage I of the Plan, a project to phase out HFCs contained in imported pre-blended polyols in the Country’s polyurethane foam sector will be subject to the decision taken by the Committee on whether it would fund the phase-out of HFCs contained in imported pre-blended polyols.
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Annex XXXV
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF VIET NAM
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2029)
Purpose
1. This Agreement represents the understanding of the Government of Viet Nam (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 12,592,224 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
(a) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. The World Bank has agreed to be the lead implementing agency (the “Lead IA”) and UNEP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee.
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption (CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	n/a
	13,991,360
	13,991,360
	13,991,360
	13,991,360
	13,991,360
	12,592,224
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	13,991,360
	13,991,360
	13,991,360
	13,991,360
	13,991,360
	12,592,224
	n/a

	2.1
	Lead IA (World Bank) agreed funding (US $)
	1,557,792
	0
	0
	1,513,187
	0
	0
	522,204
	3,593,183

	2.2
	Support costs for Lead IA (US $)
	109,045
	0
	0
	105,923
	0
	0
	36,554
	251,522

	2.3
	Cooperating IA (UNEP) agreed funding (US $)
	461,696
	0
	0
	440,301
	0
	0
	155,983
	1,057,980

	2.4
	Support costs for Cooperating IA (US $)
	55,150
	0
	0
	52,595
	0
	0
	18,633
	126,378

	3.1
	Total agreed funding (US $)
	2,019,488
	0
	0
	1,953,488
	0
	0
	678,187
	4,651,163

	3.2
	Total support costs (US $)
	164,195
	0
	0
	158,518
	0
	0
	55,187
	377,900

	3.3
	Total agreed costs (US $)
	2,183,683
	0
	0
	2,112,006
	0
	0
	733,374
	5,029,063

	4.1.1
	Deductions of HFCs under this Agreement (CO2-eq tonnes)
	1,438,128

	4.1.2
	Deductions of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The Viet Nam National Focal Point for the Implementation of the Montreal Protocol, which is the Country’s national ozone unit (NOU) under the Department of Climate Change (DCC) in the Ministry of Agriculture and Environment (MAE), is responsible for managing and coordinating the Country’s overall Montreal Protocol implementation programme, including all phase-down activities and measures controlling Annex F substances (HFCs). The management and implementation of this Agreement will be undertaken by the Plan’s project management unit (PMU) which falls under the direct authority of the NOU in the DCC.
The MAE, through the PMU and the NOU, will collaborate and coordinate with the Ministry of Industry and Trade (MOIT) and the Department of Customs (DOC) to implement the import/control system for HFCs; review annual HFC import/export license applications; and establish and publish the annual import quotas for HFCs for the period 2024 through 2029.
In order to assist the MAE in monitoring and evaluating the progress of implementation of this Agreement, the PMU and the NOU will:
(a) Update the NOU’s management information system (MIS) that captures and tracks all relevant and required data on the importation of Montreal Protocol-controlled substances on an annual basis;
(b) Update the data on the actual amount of imported HFCs;
(c) Monitor and report, in cooperation with the DOC, any incidents of illegal import of HFCs;
(d) Monitor the progress of HFC phase-down on the demand side;
(e) Maintain a project MIS on HFC consumption and related activities;
(f) Compile periodic progress reports of the Plan implementation and HFC phase-down achievements for sharing with the MAE, the MOIT, and the Ministry of Finance (MOF);
(g) Prepare Tranche Implementation Reports and Plans according to the schedule set forth in Appendix 2-A;
(h) Prepare other monitoring reports as required by the MAE or other Government authorities and by Executive Committee decision, in coordination with the Lead IA; and
(i) Carry out safety and technical reviews of all relevant activities undertaken under the Plan.
The MAE, along with its Government partner agencies (MOIT and MOF), will be responsible for the sustainability of consumption reduction targets achieved through this Agreement; reviewing the PMU reports and data; and instituting control and policy measures which facilitate HFC control and reductions according to the Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(a) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required;
Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $6.47 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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Annex XXXVI
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF ZIMBABWE
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Zimbabwe (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 761,510 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
(a) Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNEP has agreed to be the lead implementing agency (the “Lead IA”) and UNDP and the Government of France have agreed to be the cooperating implementing agencies (the “Cooperating IAs”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the evaluation work programme of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IAs taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IAs will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IAs are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IAs with the fees set out in rows 2.2, 2.4 and 2.6 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IAs to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IAs with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption
(CO2-eq tonnes)

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2018*
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	1,210,624
	1,210,624
	1,210,624
	1,210,624
	1,210,624
	1,089,561
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	21.9
	21.9
	21.9
	21.9
	26.3
	37.1
	n/a

	
	
	CO2‑eq tonnes
	n/a
	945,654
	945,654
	945,654
	945,654
	892,463
	761,510
	n/a

	2.1
	Lead IA (UNEP) agreed funding (US $)
	0
	151,500
	0
	0
	106,500
	0
	54,000
	312,000

	2.2
	Support costs for Lead IA (US $)
	0
	19,695
	0
	0
	13,845
	0
	7,020
	40,560

	2.3
	Cooperating IA (UNDP) agreed funding (US $)
	326,954
	90,000
	0
	0
	0
	0
	30,000
	446,954

	2.4
	Support costs for Cooperating IA (US $)
	22,887
	11,700
	0
	0
	0
	0
	3,900
	38,487

	2.5
	Cooperating IA (France) agreed funding (US $)
	100,000
	0
	0
	0
	0
	0
	0
	100,000

	2.6
	Support costs for Cooperating IA (US $)
	13,000
	0
	0
	0
	0
	0
	0
	13,000

	3.1
	Total agreed funding (US $)
	426,954
	241,500
	0
	0
	106,500
	0
	84,000
	858,954

	3.2
	Total support costs (US $)
	35,887
	31,395
	0
	0
	13,845
	0
	10,920
	92,047

	3.3
	Total agreed costs (US $)
	462,841
	272,895
	0
	0
	120,345
	0
	94,920
	951,001

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	449,114

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	20,735

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


* Approved at the 82nd meeting to phase out 14.50 mt (20,735 CO2‑eq tonnes) of HFC-134a in the manufacturing of domestic refrigerators at Capri (decision 82/81).
APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. Overall monitoring will be provided by the Ministry of Environment, Climate and Wildlife, through the national ozone unit (NOU), with assistance from the Lead IA. The NOU will submit annual progress reports of status of implementation of the Plan to the Lead IA.
1. Consumption will be monitored and determined from the official data on the import and export of substances as registered by the relevant Government departments. The NOU will compile and report the following data and information each year on or before the relevant deadlines:
(a) Reports on the consumption of the substances to be submitted to the Ozone Secretariat in line with Article 7 of the Montreal Protocol; and
(b) Reports on country programme data to be submitted to the Secretariat of the Multilateral Fund.
Monitoring of development of the Plan and verification of the achievement of the performance targets will be assigned to an independent local company or to independent local consultant(s) by the Lead IA. The company or consultant(s) responsible for verification will have full access to relevant technical and financial information related to the implementation of the Plan.
The Ministry of Environment, Climate and Wildlife will be responsible for the sustainability of consumption reduction targets achieved through this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IAs;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(a) Coordinating the activities of the Cooperating IAs and ensuring the appropriate sequence of activities;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IAs, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required;
Reaching consensus with the Cooperating IAs on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IAs will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IAs, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $3.66 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently confiscated, destroyed, exported, or returned to the country of origin.
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