| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/98/8 6 June 2026 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-eighth Meeting

Montreal, 22–26 June 2026

Item 7(a) of the provisional agenda

UPDATE ON THE STATUS OF IMPLEMENTATION OF THE 2026–2028 CONSOLIDATED BUSINESS PLAN OF THE MULTILATERAL FUND

- Introduction

# This document consists of:

## Part I:	An update on the status of the implementation of the 2026–2028 business plan

## Part II:	Resource allocation for the 2024–2026 triennium

Recommendation

## Update on the status of the implementation of the 2026–2028 business plan

# At its 97th meeting, the Executive Committee endorsed the 2026–2028 consolidated business plan of the Multilateral Fund. In response to decision 97/24, the Secretariat adjusted the consolidated 2026‍‍‍‍–2028 business plan, as shown in table 1.

Table 1. Resource allocation of the adjusted 2026–2028 consolidated business plan of the Multilateral Fund (US $)*

| Description | 2026 | 2027 | 2028 | Total (2026–2028) |
| --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 81,321,701 | 46,942,784 | 22,231,140 | 150,495,625 |
| HCFC production phase-out management plan (HPPMP) stage III | 0 | 23,540,000 | 0 | 23,540,000 |
| HPMP stage II – preparation (PRP) | 22,600 | 0 | 0 | 22,600 |
| HPMP stage II | 522,553 | 2,151,622 | 537,636 | 3,211,812 |
| HPMP stage III – PRP | 148,250 | 42,800 | 0 | 191,050 |
| HPMP stage III | 8,481,202 | 2,576,742 | 22,460,846 | 33,518,791 |
| HPMP stage IV | 3,841,000 | 5,537,000 | 0 | 9,378,000 |
| HPMP – energy efficiency (decision 89/6) | 1,964,908 | 288,540 | 0 | 2,253,448 |
| HPMP verification** | 588,600 | 588,600 | 588,600 | 1,765,800 |
| HCFC activities subtotal | 96,890,815 | 81,668,088 | 45,818,223 | 224,377,126 |
| HFC activities |  |  |  |  |
| Approved Kigali HFC implementation plans (KIPs) | 16,411,575 | 34,304,922 | 4,198,691 | 54,915,188 |
| Approved HFC-23 emission control | 572,433 | 552,371 | 509,571 | 1,634,375 |
| KIP stage I – PRP | 3,087,475 | 937,617 | 0 | 4,025,091 |
| KIP stage I | 14,312,115 | 15,901,762 | 29,068,084 | 59,281,962 |
| KIP stage I – investment | 0 | 339,000 | 0 | 339,000 |
| HFC investment | 941,600 | 0 | 2,140,000 | 3,081,600 |
| HFC-23 investment | 0 | 8,000,000 | 0 | 8,000,000 |
| KIP verification | 1,406,100 | 0 | 0 | 1,406,100 |
| HFC activities subtotal | 36,731,297 | 60,035,672 | 35,916,346 | 132,683,316 |
| Other activities |  |  |  |  |
| Pilot project for energy efficiency (decision 91/65) – PRP | 153,500 | 0 | 0 | 153,500 |
| Pilot project for energy efficiency (decision 91/65) | 9,380,000 | 6,149,000 | 0 | 15,529,000 |
| Energy efficiency (decision 94/60) – PRP | 53,500 | 0 | 0 | 53,500 |
| Energy efficiency (decision 94/60) | 11,770,000 | 0 | 0 | 11,770,000 |
| Energy-efficiency revolving fund (decision 95/87) | 42,800,000 | 0 | 0 | 42,800,000 |
| Other activities subtotal | 64,157,000 | 6,149,000 | 0 | 70,306,000 |
| Standard activities |  |  |  |  |
| Institutional strengthening (IS) | 19,593,580 | 19,545,691 | 5,717,815 | 44,857,085 |
| Compliance Assistance Programme (CAP) | 12,377,638 | 12,748,967 | 13,131,436 | 38,258,042 |
| Core unit | 6,059,037 | 6,101,450 | 6,144,160 | 18,304,646 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 8,262,303 | 8,192,234 | 8,280,544 | 24,735,081 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |
| Standard activities subtotal | 46,792,557 | 47,088,342 | 33,773,955 | 127,654,854 |
| Total | 244,571,669 | 194,941,102 | 115,508,524 | 555,021,296 |

* Including agency support costs where applicable.

** Funding for the preparation of HPMP verification reports for low-volume-consuming countries is approved by the Executive Committee on an annual basis.

Status of implementation of the 2026 business plan

# Table 2 sets out the submissions by agency to the 98th meeting (as at 5 June 2026), and the balance of funds from projects in the 2026 business plans.

Table 2. 2026 consolidated business plan, projects recommended to the 98th meeting, and balance (US $)*

| Budget items | Total value in business plan | Activities recommended to the 98th meeting | Balance (above)/below |
| --- | --- | --- | --- |
| Bilateral agencies | 8,436,137 | 2,929,807 | 5,506,330 |
| UNDP | 59,066,819 | 30,625,618 | 28,441,201 |
| UNEP | 45,012,265 | 7,698,472 | 37,313,793 |
| UNIDO | 50,309,903 | 17,169,603 | 33,140,300 |
| World Bank | 28,223,442 | 14,453,684 | 13,769,758 |
| HPMP verification** | 554,700 | 468,300 | 86,400 |
| KIP verification | 1,406,100 | 1,346,100 | 60,000 |
| Energy-efficiency revolving fund (decision 95/87)*** | 42,800,000 | 51,360,000 | (8,560,000) |
| Subtotal (agencies) | 235,809,366 | 126,051,584 | 109,757,782 |
| Secretariat/Executive Committee/Monitoring and Evaluation (excluding Canadian counterpart) | 8,262,303 | 0 | 8,262,303 |
| Treasurer | 500,000 | 0 | 500,000 |
| Subtotal (standard costs) | 8,762,303 | 0 | 8,762,303 |
| Total | 244,571,669 | 126,051,584 | 118,520,085 |

* Including core unit costs.

** In addition, Germany’s business plan included US $33,900 for the HPMP verification report of Papua New Guinea in line with decision 96/26.

*** The Executive Committee will select two projects under this funding window.

# The value of project proposals recommended to the 98th meeting of US $126,051,584 is US $19,272,763 above its value in the 2026 business plan and includes US $7,658,529 associated with project proposals not included in the 2026 business plan.

# The value of HFC-related activities recommended to the 98th meeting is US $27,129,471, of which US $3,667,556 is associated with project proposals not included in the 2026 business plan.

# The value of projects recommended to the 98th meeting under the funding window for pilot projects for energy efficiency pursuant to decision 91/65 is US $1,058,872. Taking into account approvals from the 92nd to the 97th meetings of US $13,630,372, and the values recommended to the 98th meeting, the remaining funding available under this funding window is US $5,310,756.

# The value of projects recommended to the 98th meeting under the funding window for energy efficiency pursuant to decision 94/60 is US $13,575,558. Taking into account approvals from the 95th to the 97th meetings of US $22,033,800, and the values recommended to the 98th meeting, the remaining funding available under this funding window is US $64,390,642.

# The value of three projects recommended to the 98th meeting under the funding window for the energy-efficiency revolving fund for end-users pursuant to decision 95/87 is US $51,360,000. The Executive Committee will select two projects amounting to US $42.8 million under this funding window. In addition, US $2,132,510 is recommended to the 98th meeting for three technical assistance projects that are not included under this funding window.

# Forward commitments

# The total amount for existing forward commitments for multi-year agreements (MYAs) for the period 2026 to 2033 is US $331.06 million, assuming that the funding requests of MYAs submitted to the 98th meeting will be approved in principle, as shown in table 3.

Table 3. Forward commitments (2026–2033) (US $000)

| Description | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approved in principle | 102,883 | 79,336 | 32,161 | 17,591 | 24,069 | 576 | 0 | 0 | 256,616 |
| Submitted to 98th meeting | 26,024 | 1,208 | 26,312 | 623 | 17,767 | 185 | 0 | 2,326 | 74,446 |
| Total | 128,907 | 80,544 | 58,473 | 18,214 | 41,836 | 762 | 0 | 2,326 | 331,062 |

II.	Resource allocation for the 2024–2026 triennium

# The resources approved by the Parties to the Montreal Protocol for the 2024–2026 triennium amount to US $965,000,000. Taking into account the approvals in 2024 and 2025 and the 2026 business plans of US $244,571,669, the estimated resources available at the end of 2026 is US $390,263,094.

Table 4. Resource allocation for the 2024–2026 triennium

| Description | Amount (US $) |
| --- | --- |
| Total budget for the 2024–2026 triennium | 965,000,000 |
| 2024 approvals including Secretariat/Executive Committee/Monitoring and Evaluation/Treasurer | 183,180,780 |
| 2025 approvals including Secretariat/Executive Committee/Monitoring and Evaluation/Treasurer | 146,984,457 |
| 2026 business plans including Secretariat/Executive Committee/Monitoring and Evaluation/Treasurer | 244,571,669 |
| Estimated resources available at the end of 2026 | 390,263,094 |

# Recommendation

# The Executive Committee may wish to note:

## The update on the status of implementation of the 2026–2028 consolidated business plan of the Multilateral Fund contained in document UNEP/OzL.Pro/ExCom/98/8; and

## That the total value of activities recommended to the 98th meeting amounts to US $126,051,584 (including US $27,129,471 for HFC-related activities; US $1,058,872 for pilot projects for energy efficiency pursuant to decision 91/65; US $13,575,558 for energy-efficiency projects pursuant to decision 94/60; and US $53,492,510 (including US $51,360,000 for investment and US $2,132,510 for technical assistance projects) for the energy-efficiency revolving fund for end-users pursuant to decision 95/87), of which US $7,658,529 is associated with project proposals not included in the 2026 business plan.

UNEP/OzL.Pro/ExCom/98/1

Two energy-efficiency projects under decision 89/6 for Angola (UNDP) and Bosnia and Herzegovina (UNIDO); three technical assistance projects under the energy-efficiency revolving fund for the global region (UNDP), Grenada (World Bank) and Thailand (World Bank); stage II of the HPMPs for Bolivia (Plurinational State of) (UNEP and UNIDO), Ecuador (UNIDO), Saint Kitts and Nevis (UNIDO) and South Sudan (UNDP and UNEP); stage III of the HPMP for Tunisia (Italy); stage IV of the HPMP for Nigeria (the United Kingdom of Great Britain and Northern Ireland);  stage I of KIPs for Bolivia (Plurinational State of) (UNEP and UNIDO), Brazil (the United Kingdom of Great Britain and Northern Ireland) and Nigeria (UNIDO); two investment projects for stage I of KIPs for Bolivia (Plurinational State of) (UNIDO) and Ecuador (UNIDO); three project preparation activities for stage I of KIPs for Haiti (UNDP) and  Saint Kitts and Nevis (UNEP and UNIDO); and one preparation activity for a KIP investment project for India (UNDP).

Decision XXXV/1