| EP |  | ### الأمم المتحدة |  |
| --- | --- | --- | --- |
| Distr. GENERAL UNEP/OzL.Pro/ExCom/95/4 19 November 2024 ARABIC ORIGINAL: ENGLISH | #### برنامج #### الأمم المتحدة #### للبيئة |  |  |

اللجنــة التنفيـذيــــة للصنــدوق المــتعــدد الأطـــراف

لتنفيـــذ بروتوكـول مونتريــال

الاجتماع الخامس والتسعون

مونتريال، 4 - 8 ديسمبر/ كانون الاول 2024

البند 4(ب) من جدول الأعمال المؤقت

تقرير عن الأرصدة وتوافر الموارد

مقدمـــة

- تعرض هذه الوثيقة موجزاً للتعديلات المالية التي أشارت إليها الوكالات المنفذة والوكالات الثنائية على النحو الذي وافقت عليه الأمانة. وهي تتضمن بيانات إحصائية من جميع المشاريع التي احتفظت بأرصدتها لأكثر من 12 شهراً بعد الانتهاء من المشروع، على النحو المطلوب بموجب المقرَّرين 28/7 و56/2(ج). وتتناول الوثيقة الأرصدة التي يتعين إعادتها مقابل المشاريع على سبيل المتابعة للمقرَّرات ذات الصلة (المشار إليها باسم ’’مشاريع صادر بها مقررات‘‘ في هذه الوثيقة) وتحويلات المشاريع. وهي تشير كذلك إلى مستوى الموارد المتاحة للجنة التنفيذية نقداً على النحو المسجل في وثيقة حالة المساهمات والمصروفات، على النحو المطلوب بموجب المقرَّر 41/92(ب)، وتقدم توصية في هذا الصدد. وترد في المرفقين الأول والثاني المبالغ التي تحتفظ بها الوكالات المنفذة والوكالات الثنائية للمشاريع المكتملة، ومشاريع المساهمات الطوعية الإضافية. ويعرض المرفق الثالث الأموال التي أعادتها الوكالات المنفذة والوكالات الثنائية من المشاريع المكتملة والمشاريع الإضافية القائمة على المساهمات الطوعية.

الأموال التي يتعين إعادتها إلى الاجتماع الخامس والتسعين

- يبلغ مجموع الأموال التي يتعين إعادتها 3,337,269 دولاراً أمريكياً، تتألف من 3,334,669 دولاراً أمريكياً من الوكالات المنفذة و2,600 دولار أميركي من الوكالات الثنائية من المشاريع المكتملة والمشاريع الإضافية القائمة على المساهمات الطوعية، على النحو الموضح في الجدولين 1 و2.

الجدول 1. الأموال التي يتعين إعادتها من الوكالات المنفّذة إلى الاجتماع الخامس والتسعين (بالدولار الأميركي)

| الوكالة | تكلفة المشروع | تكلفة دعم الوكالة | التكلفة الإجمالية |
| --- | --- | --- | --- |
| اليوئنديبي | 49,738 | 3,589 | 53,327 |
| اليونيب* | 1,795,410 | 143,021 | 1,938,431 |
| اليونيدو | 567,175 | 41,415 | 608,590 |
| البنك الدولي | 620,456 | 113,865 | 734,321 |
| المجموع | 3,032,779 | 301,890 | 3,334,669 |

* تشمل الأموال المعادة من اليونيب 401,361 دولاراً أمريكياً، مضافاً إليها مبلغ 27,217 دولاراً أمريكياً ، لثلاثة مشاريع سيجري تحويلها على النحو المشار إليه في الجدول 5.

| الوكالة | تكلفة المشروع | تكلفة دعم الوكالة | المجموع |
| --- | --- | --- | --- |
| اليابان | 2,301 | 299 | 2,600 |

الجدول ٢. المبالغ التي يتعلين إعادتها من الوكالات الثنائية إلى الاجتماع الخامس والتسعين (بالدولار الأمريكي)

الأرصدة المحتفظ بها لدى الوكالات التنفيذية والوكالات الثنائية

- يبلغ إجمالي المبالغ المحتفظ بها 6,417,445 دولاراً أمريكياً (6,413,350 دولار أمريكي من قبل الوكالات التنفيذية و4,096 دولار أمريكي من قبل إحدى الوكالات الثنائية)، على النحو المبيَّن في الجدولين 3 و4.

الجدول 3. أرصدة المشاريع المكتملة والمشاريع الصادر بها مقرَّرات ومشاريع المساهمات الطوعية التي تحتفظ بها الوكالات المنفذة (بما في ذلك تكاليف دعم الوكالة)

| سنة الإنجاز | اليوئنديبي |  | اليونيدو |  | المجموع |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | العدد | دولار أمريكي | العدد | دولار أمريكي | العدد | دولار أمريكي |
| مشروعات مضى على إنجازها أكثر من عامين |  |  |  |  |  |  |
| 2020 | 1 | 40,434 | 0 | 0 | 1 | 40,434 |
| 2021 | 2 | 8,518 | 4 | 2,315,225 | 6 | 2,323,743 |
| 1 يناير إلى 31 أكتوبر 2022 | 2 | 13,091 | 2 | 24,101 | 4 | 37,192 |
| المجموع الفرعي | 5 | 62,043 | 6 | 2,339,326 | 11 | 2,401,369 |
| مشروعات مضى على إنجازها أقل من عامين |  |  |  |  |  |  |
| 1 نوفمبر إلى 31 ديسمبر 2022 | 3 | 102,335 | 5 | 95,212 | 8 | 197,547 |
| 2023 | 31 | 2,670,188 | 22 | 1,048,301 | 53 | 3,718,489 |
| المجموع الفرعي | 34 | 2,772,523 | 27 | 1,143,513 | 61 | 3,916,036 |
| المجموع | 39 | 2,834,566 | 33 | 3,482,839 | 72 | 6,317,405 |
| مشروعات المساهمات الطوعية الإضافية |  |  |  |  |  |  |
|  | 0 | 0 | 3 | 95,945 | 3 | 95,945 |
| المجموع الكلي | 39 | 2,834,566 | 36 | 3,578,784 | 75 | 6,413,350 |

الجدول 4. الرصيد المتبقي لمشروع منجز تحتفظ به إحدى الوكالات الثنائية

| الوكالة | رمز المشروع | سنة الإنجاز | رصيد الإلتزامات (دولار أمريكي) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | رصيد المشروع |  | رصيد تكلفة دعم الوكالة | المجموع |
| إسبانيا | MEX/PHA/81/TAS/190 | 2023 |  | 3,674 | 421 | 4,096 |

نقل المشروعات

- وفقاً للمقرَّر 93/14(ج)، سيتم نقل الأرصدة المتبقية للمشاريع التالية في إطار خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية في أفغانستان من اليونيب إلى اليونيدو:

  - AFG/PHA/85/TAS/27 (المرحلة الأولى، الشريحة الرابعة) - 28,453 دولاراً أمريكياً بالإضافة إلى تكاليف دعم الوكالة البالغة 3,699 دولاراً أمريكياً. وسوف ينطوي النقل إلى اليونيدو على تكاليف دعم أقل للوكالة تبلغ 2,561 دولاراً أمريكياً؛

  - ) AFG/PHA/85/TAS/29 المرحلة الثانية، الشريحة الأولى) - 180,908 دولاراً أمريكياً بالإضافة إلى تكاليف دعم الوكالة البالغة 23,518 دولاراً أمريكياً. وسوف ينطوي النقل إلى اليونيدو على تكاليف دعم أقل للوكالة تبلغ 16,282 دولاراً أمريكياً.

- بالإضافة إلى ذلك، طلبت أفغانستان تحويل الأموال اللازمة لتمديد مشروع التعزيز المؤسسي (المرحلة العاشرة) من اليونيب إلى اليونيدو على النحو المبين أدناه:

  - AFG/SEV/87/INS/31- 192,000 دولار أمريكي ولا توجد تكاليف دعم من جانب الوكالة. وسوف يستلزم التحويل إلى اليونيدو تكاليف دعم للوكالة أعلى قدرها 13,440 دولاراً أمريكياً.

- وترد في الجدول 5 معلومات مفصلة عن الأرصدة التي يتعين تحويلها. وقد ترغب اللجنة التنفيذية في الموافقة على هذه الطلبات.

الجدول 5. أرصدة المشروعات لأفغانستان التي يتعين تحويلها

| عنوان المشروع | رقم المشروع | الإعادة |  |  | النقل |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | إلى الصندوق المتعدد الأطراف |  |  | إلى الوكالة |  |  |
|  |  | من | رصيد | تكاليف دعم الوكالة | إلى | رصيد | تكاليف دعم الوكالة |
| المرحلتان الأولى والثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية | AFG/PHA/85/TAS/27 | اليونيب | 28,453 | 3,699 | اليونيدو | 28,453 | 2,561 |
|  | AFG/PHA/85/TAS/29 | اليونيب | 180,908 | 23,518 | اليونيدو | 180,908 | 16,282 |
| تمديد مشروع التعزيز المؤسسي | AFG/SEV/87/INS/31 | اليونيب | 192,000 | - | اليونيدو | 192,000 | 13,440 |
| المجموع |  |  | 401,361 | 27,217 |  | 401,361 | 32,283 |

توافر الموارد

- تشير الوثيقة المتعلقة بحالة المساهمات والمصروفات إلى وجود رصيد متاح قدره 577,336,286 دولاراً أمريكياً اعتباراً من 23 أكتوبر/تشرين الأول 2024. ويبلغ إجمالي الرصيد الذي أعادته الوكالات المنفذة والوكالات الثنائية إلى الاجتماع الخامس والتسعين 2,908,691 دولار أمريكي، باستثناء 428,578 دولار أمريكي أعادها برنامج الأمم المتحدة للبيئة لتحويلها إلى اليونيدو. وبالتالي، فإن إجمالي مستوى الموارد المتاحة للموافقة عليها في الاجتماع الخامس والتسعين يبلغ 580,244,977 دولاراً أمريكياً.

تعليقات الأمانــــة

- ذكّرت الأمانة الوكالات المنفذة بأنه ينبغي إعادة أرصدة المشاريع المكتملة منذ عام واحد أو أكثر، ومشاريع المساهمات الطوعية الإضافية، إلى الصندوق المتعدد الأطراف في أقرب وقت ممكن.

- وبالنظر إلى أن إجمالي مستوى التمويل للمشاريع والأنشطة المقدمة إلى الاجتماع الخامس والتسعين يبلغ 135,939,008 دولارات أمريكية، فهناك موارد كافية متاحة للموافقة في هذا الاجتماع.

التوصيـــــــة

- قد ترغب اللجنة التنفيذية فيما يلي:

- أن تحيط علماً بما يلي:

  - التقرير المتعلق بالأرصدة وتوافر الموارد الوارد في الوثيقة UNEP/OzL.Pro/ExCom/95/4؛

  - أن صافي مستوى الأموال التي تقوم الوكالات المنفذة بإعادتها في الاجتماع الخامس والتسعين يبلغ 2,906,091 دولاراً أمريكياً ويتألف من مبلغ 49,738 دولاراً أمريكياً بالإضافة إلى تكاليف دعم الوكالة البالغة 3,589 دولاراً أمريكياً من اليوئنديبي؛ و1,394,049 دولاراً أمريكياً بالإضافة إلى تكاليف دعم الوكالة البالغة 115,804 دولارات أمريكية من اليونيب؛ و567,175 دولاراً أمريكياً بالإضافة إلى تكاليف دعم الوكالة البالغة 41,415 دولاراً أمريكياً من اليونيدو؛ و620,456 دولاراً أمريكياً بالإضافة إلى تكاليف دعم الوكالة البالغة 113,865 دولاراً أمريكياً من البنك الدولي.

  - أن اليوئنديبي كان يحتفظ بأرصدة قدرها 62,043 دولاراً أمريكياً، بما في ذلك تكاليف دعم الوكالة، لخمسة مشاريع اكتملت قبل أكثر من عامين؛

  - أن اليونيدو كانت تحتفظ بأرصدة قدرها 2,339,326 دولاراً أمريكياً، بما في ذلك تكاليف دعم الوكالة، لستة مشاريع مكتملة منذ أكثر من عامين سابقين؛ و95,945 دولاراً أمريكياً، بما في ذلك تكاليف دعم الوكالة، لثلاثة مشاريع ممولة باستخدام المساهمات الطوعية الإضافية التي قدمتها مجموعة من البلدان المانحة لتمويل أنشطة البدء السريع لتنفيذ التخفيض التدريجي للمواد الهيدروفلوروكربونية؛

  - أن اليونيب يعيد في الاجتماع الخامس والتسعين الأرصدة من المرحلتين الأولى والثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية ومشروع التعزيز المؤسسي في أفغانستان بمبلغ 401,361 دولاراً أمريكياً، بالإضافة إلى تكاليف دعم الوكالة البالغة 27,217 دولاراً أمريكياً، وتتألف هذه الأرصدة من:

- 28,453 دولاراً أمريكياً، بالإضافة إلى تكاليف دعم الوكالة البالغة 3,699 دولاراً أمريكياً من الشريحة الرابعة من المرحلة الأولى من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (AFG/PHA/85/TAS/27)؛

- 180,908 دولارات أمريكية، بالإضافة إلى تكاليف دعم الوكالة البالغة 23,518 دولاراً أمريكياً من الشريحة الأولى من المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (AFG/PHA/85/TAS/29)؛

- 192,000 دولار أمريكي من تمديد مشروع التعزيز المؤسسي (المرحلة العاشرة) (AFG/SEV/87/INS/31)؛

  - أن حكومة اليابان تعيد مبلغاً قدره 2,600 دولار أمريكي، بما في ذلك تكاليف الدعم لمشروع واحد؛

- أن تطلب:

- الى اليوئنديبي واليونيدو المضي قدماً في الصرف أو إلغاء الالتزامات للمشاريع المكتملة قبل أكثر من عامين، وإعادة الأرصدة في الاجتماع السادس والتسعين؛

- الى اليوئنديبي واليونيدو المضي قدماً في الصرف أو إلغاء الالتزامات للمشاريع المكتملة قبل أكثر من عامين، وإعادة الأرصدة في الاجتماع السادس والتسعين

- 3))	إلى اليونيدو أن تشرع في صرف أو إعادة أرصدة المشاريع الممولة باستخدام المساهمات الطوعية الإضافية في الاجتماع السادس والتسعين؛

- 4))	أن يحول أمين الخزانة في الاجتماع الخامس والتسعين الأموال المعادة للمشاريع المشار إليها في الفقرة الفرعية (أ)(5) أعلاه إلى اليونيدو لتنفيذها، بمبلغ 401,361 دولاراً أمريكياً، بالإضافة إلى تكاليف دعم الوكالة البالغة 32,283 دولاراً أمريكياً، وتتألف من الآتي:

- (أ) 	28,453 دولاراً أمريكياً، بالإضافة إلى تكاليف دعم الوكالة البالغة 2,561 دولاراً أمريكياً من الشريحة الرابعة من المرحلة الأولى من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية ( (AFG/PHA/85/TAS/27؛

- (ب)	 180,908 دولارات أمريكية، بالإضافة إلى تكاليف دعم الوكالة البالغة 16,282 دولاراً أمريكياً من الشريحة الأولى من المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (AFG/PHA/85/TAS/29)؛

- (ج)	 192,000 دولار أمريكي، بالإضافة إلى تكاليف دعم الوكالة البالغة 13,440 دولاراً أمريكياً من تمديد مشروع التعزيز المؤسسي (المرحلة العاشرة) (AFG/SEV/87/INS/31)؛

- 5))	أن يقوم أمين الخزانة بمتابعة الأمر مع حكومة اليابان بشأن إعادة مبلغ 2,600 دولار أمريكي نقدًا وفقًا للفقرة الفرعية (أ) (6) أعلاه.

Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AND BILATERAL AGENCIES FOR COMPLETED PROJECTS

| Code | Project title | Date completed (Actual) | Approved funding plus adjustments as of 31 Dec 2023 (US $) | Funds disbursed as of 95th meeting (US $) | Balances committed as per 95th meeting (US $) | Balances not-committed as per 95th meeting (US $) | Support cost on balances committed and not committed as per 95th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| ANG/PHA/79/INV/19 | HCFC phase-out management plan (stage II, first tranche) | Aug-22 | 450,000 | 443,189 | 6,811 |  | 477 |  |  |  |
| BRA/PHA/88/PRP/330 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | Dec-23 | 40,000 | 31,233 | 8,767 |  | 614 |  |  |  |
| BZE/SEV/85/TAS/37 | Enabling activities for HFC phase-down | Oct-22 | 55,000 | 49,576 | 5,424 |  | 380 |  |  |  |
| COL/SEV/88/INS/115 | Extension of institutional strengthening project (phase XIII: 12/2021-11/2023) | Dec-23 | 352,768 | 328,161 | 24,607 |  | 1,723 |  |  |  |
| COS/SEV/88/INS/64 | Extension of institutional strengthening project (phase XIV: 1/2022-12/2023) | Dec-23 | 179,857 | 170,446 | 9,411 |  | 659 |  |  |  |
| EGY/PHA/79/TAS/132 | HCFC phase-out management plan (stage II, first tranche) (project management and monitoring) | Dec-22 | 75,000 | 67,871 | 7,129 |  | 499 |  |  |  |
| EGY/PHA/84/INV/144 | HCFC phase-out management plan (stage II, second tranche) (extruded polystyrene foam sector) | Dec-23 | 1,761,750 | 1,471,691 | 290,059 |  | 20,304 |  |  |  |
| GHA/KIP/87/PRP/51 | Preparation of Kigali HFC implementation plan | Aug-23 | 130,000 | 81,220 | 48,780 |  | 3,415 |  |  |  |
| GHA/PHA/87/INV/50 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 459,820 | 442,121 | 17,699 |  | 1,239 |  |  |  |
| HAI/SEV/84/TAS/23 | Enabling activities for HFC phase-down | Dec-21 | 95,000 | 90,311 | 4,689 |  | 328 |  |  |  |
| IDS/PHA/76/TAS/210 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Dec-23 | 2,203,114 | 1,829,259 | 373,855 |  | 26,170 |  |  |  |
| IDS/PHA/87/PRP/216 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | Dec-23 | 90,000 | 65,168 | 24,832 |  | 1,738 |  |  |  |
| IND/PHA/87/PRP/487 | Preparation of HCFC phase-out management plan (stage III) (refrigeration sector) | Aug-23 | 150,000 | 89,924 | 60,076 |  | 4,205 |  |  |  |
| IRA/PHA/90/INV/262 | HCFC phase-out management plan (stage II, fourth tranche) (PMU) | Dec-23 | 92,000 | 69,877 | 22,123 |  | 1,549 |  |  |  |
| IRA/PHA/92/INV/264 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | Dec-23 | 93,017 | 0 | 93,017 |  | 6,511 |  |  |  |
| IRA/PHA/92/INV/265 | HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration sector) | Dec-23 | 145,255 | 0 | 145,255 |  | 10,168 |  |  |  |
| IRA/SEV/86/INS/249 | Extension of the institutional strengthening project (phase XIII: 4/2021-3/2023) | May-23 | 222,094 | 178,036 | 44,058 |  | 3,084 |  |  |  |
| KAM/KIP/88/PRP/40 | Preparation of Kigali HFC implementation plan | Dec-23 | 35,000 | 19,678 | 15,322 |  | 1,073 |  |  |  |
| KYR/KIP/87/PRP/45 | Preparation of Kigali HFC implementation plan | Aug-23 | 91,000 | 74,690 | 16,310 |  | 1,142 |  |  |  |
| KYR/PHA/90/TAS/47 | Verification report on the implementation of stage II of the HCFC phase-out management plan | Jul-23 | 30,000 | 0 | 30,000 |  | 2,700 |  |  |  |
| LAO/PHA/86/INV/38 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 107,000 | 86,720 | 20,280 |  | 1,825 |  |  |  |
| LEB/SEV/86/INS/96 | Extension of the institutional strengthening project (phase XII: 4/2021-3/2023) | Dec-23 | 198,515 | 157,610 | 40,905 |  | 2,863 |  |  |  |
| MAL/PHA/84/INV/191 | HCFC phase-out management plan (stage II, second tranche) (polyurethane foam sector) | Dec-23 | 1,703,922 | 1,651,948 | 51,974 |  | 3,638 |  |  |  |
| MAL/PHA/84/TAS/186 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | Dec-23 | 627,053 | 174,875 | 452,178 |  | 31,653 |  |  |  |
| MAL/PHA/88/INV/193 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector and management and coordination) | Dec-23 | 154,900 | 39,789 | 115,111 |  | 8,058 |  |  |  |
| MAL/SEV/88/INS/192 | Extension of institutional strengthening project (phase XIV: 1/2022-12/2023) | Dec-23 | 357,760 | 296,772 | 60,988 |  | 4,269 |  |  |  |
| MEX/KIP/87/PRP/195 | Preparation of Kigali HFC implementation plan | Aug-23 | 85,000 | 62,950 | 22,050 |  | 1,544 |  |  |  |
| NIR/PHA/81/TAS/148 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Dec-22 | 1,077,113 | 1,063,456 | 13,657 |  | 956 |  |  |  |
| NIR/PHA/81/TAS/150 | HCFC phase-out management plan (stage II, first tranche) (project management and coordination) | Dec-22 | 165,000 | 90,146 | 74,854 |  | 5,240 |  |  |  |
| NIR/PHA/88/INV/162 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | Dec-23 | 977,407 | 962,333 | 15,074 |  | 1,055 |  |  |  |
| PAN/PHA/83/PRP/49 | Preparation of a HCFC phase-out management plan (stage III) | Jun-21 | 60,000 | 56,728 | 3,272 |  | 229 |  |  |  |
| PAR/KIP/87/PRP/42 | Preparation of Kigali HFC implementation plan | Aug-23 | 170,000 | 154,838 | 15,162 |  | 1,061 |  |  |  |
| PER/KIP/87/PRP/59 | Preparation of Kigali HFC implementation plan | Sep-23 | 190,000 | 167,346 | 22,654 |  | 1,586 |  |  |  |
| PER/PHA/85/INV/57 | HCFC phase-out management plan (stage II, second tranche) | Jun-23 | 233,400 | 194,591 | 38,809 |  | 2,717 |  |  |  |
| SWA/KIP/87/PRP/33 | Preparation of Kigali HFC implementation plan | Aug-23 | 30,000 | 3,000 | 27,000 |  | 1,890 |  |  |  |
| TRI/PHA/86/INV/38 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 498,756 | 413,693 | 85,063 |  | 5,954 |  |  |  |
| TRI/SEV/88/INS/41 | Extension of the institutional strengthening project (phase XI: 12/2021-12/2023) | Dec-23 | 85,000 | 82,010 | 2,990 |  | 209 |  |  |  |
| URU/PHA/77/INV/67 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Dec-20 | 100,000 | 62,211 | 37,789 |  | 2,645 |  |  |  |
| URU/PHA/82/INV/72 | HCFC phase-out management plan (stage II, second tranche) (foam sector) | Dec-23 | 422,889 | 122,736 | 300,153 |  | 21,011 |  |  | 94/13(a)(iii) |
| TOTAL UNDP |  |  |  |  | 2,648,187 |  | 186,379 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| ALG/SEV/84/TAS/83 | Enabling activities for HFC phase-down | Jun-22 | 150,000 | 142,499 | 7,501 |  | 525 | 1 | 96 |  |
| BKF/PHA/84/PRP/41 | Preparation of a HCFC phase-out management plan (stage II) | Dec-23 | 20,000 | 19,207 | 793 |  | 55 | 1 | 96 |  |
| CMR/KIP/88/PRP/49 | Preparation of Kigali HFC implementation plan | Dec-23 | 190,000 | 188,245 | 1,755 |  | 123 | 1 | 96 |  |
| CPR/PHA/88/INV/607 | HCFC phase-out management plan (stage II, fourth tranche) (extruded polystyrene foam sector plan) | Dec-23 | 4,400,000 | 3,960,000 | 440,000 |  | 30,800 | 1 | 96 |  |
| GAB/PHA/79/INV/34 | HCFC phase-out management plan (stage I, third tranche) | Dec-22 | 119,900 | 60,409 | 59,491 |  | 5,354 | 1 | 96 |  |
| GUA/PHA/91/TAS/61 | Verification report on the implementation of stage II of the HCFC phase-out management plan | Dec-23 | 30,000 | 29,899 | 101 |  | 9 | 1 | 96 |  |
| GUI/PHA/86/PRP/37 | Preparation of a HCFC phase-out management plan (stage II) | Dec-23 | 10,000 | 9,999 | 1 |  | 0 | n.a. | 96 |  |
| IRQ/PHA/58/INV/09 | National phase-out plan (first tranche) | Jun-21 | 4,353,530 | 2,398,765 | 1,954,765 |  | 146,607 | 1 | 96 | 71/11(b), 73/8(c), 75/10(b)(i) and 79/7(c) |
| IRQ/PHA/74/INV/23 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Dec-21 | 230,000 | 66,856 | 163,144 |  | 12,236 | 1 | 96 |  |
| IVC/PHA/84/INV/45 | HCFC phase-out management plan (stage I, third tranche) | Dec-22 | 460,000 | 449,046 | 10,954 |  | 767 | 1 | 96 | 90/32(a) |
| JOR/PHA/77/INV/101 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Dec-23 | 227,686 | 227,444 | 242 |  | 17 | 1 | 96 |  |
| JOR/PHA/84/TAS/107 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector, project management and coordination) | Dec-23 | 294,122 | 280,486 | 13,636 |  | 954 | 1 | 96 |  |
| LEB/REF/88/PRP/99 | Project preparation for HFC-related project in the manufacturing sector at Lematic Industries to convert the production of residential air-conditioning from R-410A to R-290 | Dec-23 | 30,000 | 24,155 | 5,845 |  | 409 | 1 | 96 |  |
| LIB/PHA/75/INV/36 | HCFC phase-out management plan (stage I, first tranche) (foam sector) | Dec-23 | 943,094 | 713,112 | 229,982 |  | 16,099 | 1 | 96 | 93/23(c) |
| LIB/SEV/85/INS/44 | Renewal of the institutional strengthening project (phase VI: 7/2020-6/2022) | Jun-23 | 174,164 | 166,234 | 7,930 |  | 555 | 1 | 96 |  |
| MDN/SEV/88/INS/48 | Extension of the institutional strengthening project (phase VII: 12/2021-11/2023) | Dec-23 | 169,404 | 158,932 | 10,472 |  | 733 | 1 | 96 |  |
| MEX/PHA/73/INV/174 | HCFC phase-out management plan (stage II, first tranche) (cleaning agent phase-out in refrigeration servicing sector) | Jun-23 | 673,009 | 672,892 | 117 |  | 8 | 1 | 96 |  |
| MEX/PHA/81/INV/189 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) | Dec-23 | 2,139,719 | 2,142,290 | -2,571 |  | -180 | n.a. | 96 |  |
| MOZ/PHA/66/INV/23 | HCFC phase-out management plan (stage I, first tranche) | Dec-22 | 75,000 | 72,133 | 2,867 |  | 258 | 1 | 96 |  |
| MOZ/PHA/83/INV/31 | HCFC phase-out management plan (stage I, third and fourth tranches) | Jun-23 | 85,000 | 75,322 | 9,678 |  | 871 | 1 | 96 |  |
| NER/PHA/84/INV/39 | HCFC phase-out management plan (stage I, second tranche) | Dec-22 | 90,000 | 76,492 | 13,508 |  | 946 | 1 | 96 |  |
| NER/PHA/88/INV/41 | HCFC phase-out management plan (stage I, third tranche) | Dec-22 | 20,000 | 19,002 | 998 |  | 70 | 1 | 96 |  |
| NIC/PHA/86/INV/40 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 100,092 | 98,549 | 1,543 |  | 108 | 1 | 96 |  |
| PHI/PHA/83/INV/104 | HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector) | Dec-23 | 537,856 | 345,899 | 191,957 |  | 13,436 | 1 | 96 | 87/19(c) |
| PHI/PHA/83/TAS/105 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Dec-23 | 273,894 | 233,872 | 40,022 |  | 2,802 | 1 | 96 | 87/19(c) |
| PHI/PHA/88/PRP/108 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | Dec-23 | 70,000 | 69,762 | 238 |  | 17 | 1 | 96 |  |
| SEN/PHA/85/INV/41 | HCFC phase-out management plan (stage I, third tranche) | Dec-21 | 50,000 | 18,910 | 31,090 |  | 2,332 | 1 | 96 |  |
| SEN/PHA/85/PRP/43 | Preparation of a HCFC phase-out management plan (stage II) | Jun-22 | 20,000 | 4,977 | 15,023 |  | 1,052 | 1 | 96 |  |
| SOA/PHA/91/INV/16 | HCFC phase-out management plan (stage I, fifth tranche) (refrigeration servicing, custom training and monitoring) | Dec-23 | 178,760 | 157,305 | 21,455 |  | 1,502 | 1 | 96 | 94/9(b) |
| SOM/PHA/88/INV/16 | HCFC phase-out management plan (stage I, third tranche) | Jun-23 | 40,000 | 34,494 | 5,506 |  | 385 | 1 | 96 | 88/40(a) |
| SYR/REF/62/INV/103 | Phase-out of HCFC-22 and HCFC-141b from the manufacture of unitary air-conditioning equipment and rigid polyurethane insulation panels at Al Hafez Group | Dec-21 | 1,465,361 | 1,460,663 | 4,698 |  | 352 | 1 | 96 |  |
| TKM/PHA/86/INV/17 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 165,000 | 164,864 | 137 |  | 10 | 1 | 96 |  |
| ZAM/PHA/77/INV/33 | HCFC phase-out management plan (stage I, third tranche) | Jun-23 | 70,000 | 69,311 | 689 |  | 62 | 1 | 96 |  |
| TOTAL UNIDO |  |  |  |  | 3,243,565 |  | 239,274 |  |  |  |
| SPAIN |  |  |  |  |  |  |  |  |  |  |
| MEX/PHA/81/TAS/190 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) | Dec-23 | 1,070,000 | 1,066,326 | 3,674 |  | 421 |  |  |  |
| TOTAL SPAIN |  |  |  |  | 3,674 |  | 421 |  |  |  |

Annex II

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS

| CODE | Project title | Approved funding plus adjustments as of 31 December 2023 (US $) | Funds disbursed as of 95th meeting (US $) | Balances committed as per 95th meeting (US $) | Balances not- committed as per 95th meeting (US $) | Support cost on balances committed and not-committed as per 95th meeting (US $) | Why any balances could not be returned? | When they could be returned? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNIDO |  |  |  |  |  |  |  |  |
| ARG/REF/81/INV/01+ | Conversion project for replacement of HFC-134a with isobutane (R-600a)/propane (R-290)-based refrigerant in the manufacture of domestic and commercial refrigeration equipment at Briket, Bambi and Mabe-Kronen | 1,840,755 | 1,597,406 | 2,622 |  | 184 | 1 | 96 |
| ARG/SEV/81/TAS/02+ | Enabling activities for HFC phase-down | 250,000 | 164,539 | 85,461 |  | 5,982 | 1 | 96 |
| VEN/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 250,000 | 248,415 | 1,585 |  | 111 | 1 | 96 |
| TOTAL UNIDO |  |  |  | 89,668 |  | 6,277 |  |  |

Annex III

DETAILS ON COMPLETED, BY DECISIONS AND ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AND BILATERAL AGENCIES

| Code |  | Project title |  |  | Project costs returned (US $) | Agency support costs (US $) |  | Total (US $) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |
| ANG/PHA/84/TAS/22 |  | Verification report on the implementation of the HCFC phase-out management plan |  |  | 411 | 37 |  | 448 |
| BGD/SEV/81/TAS/52 |  | Enabling activities for HFC phase-down |  |  | 10,751 | 753 |  | 11,504 |
| CHI/SEV/87/INS/204 |  | Extension of the institutional strengthening project (phase XIV: 7/2021-6/2023) |  |  | 574 | 40 |  | 614 |
| CUB/PHA/82/PRP/61 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 2,087 | 146 |  | 2,233 |
| DOM/PHA/83/PRP/68 |  | Preparation of a HCFC phase-out management plan (stage III) |  |  | 3,290 | 230 |  | 3,520 |
| FIJ/PHA/86/INV/38 |  | HCFC phase-out management plan (stage I, fourth tranche) |  |  | 4,942 | 445 |  | 5,387 |
| IDS/PHA/76/INV/211 |  | HCFC phase-out management plan (stage II, first tranche) (firefighting sector) |  |  | 14,922 | 1,045 |  | 15,967 |
| IND/SEV/88/INS/491 |  | Extension of institutional strengthening project (phase XIII: 12/2021-11/2023) |  |  | 2,941 | 206 |  | 3,147 |
| JAM/PHA/81/PRP/38 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 6,499 | 455 |  | 6,954 |
| SRL/SEV/86/INS/57 |  | Extension of the institutional strengthening project (phase XIII: 1/2021-12/2022) |  |  | 3,221 | 225 |  | 3,446 |
| TRI/PHA/82/PRP/36 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 100 | 7 |  | 107 |
| Total completed projects |  |  |  |  | 49,738 | 3,589 |  | 53,327 |
| TOTAL UNDP |  |  |  |  | 49,738 | 3,589 |  | 53,327 |
| UNEP |  |  |  |  |  |  |  |  |
| AFG/PHA/85/TAS/27 |  | HCFC phase-out management plan (stage I, fourth tranche) |  |  | 28,453 | 3,699 |  | 32,151 |
| AFG/PHA/85/TAS/29 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 180,908 | 23,518 |  | 204,426 |
| AFG/SEV/87/INS/31 |  | Extension of institutional strengthening project (phase X: 1/2022-12/2023) |  |  | 192,000 | 0 |  | 192,000 |
| ALB/KIP/87/PRP/44 |  | Preparation of Kigali HFC implementation plan |  |  | 1,633 | 212 |  | 1,846 |
| ALB/PHA/85/TAS/42 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 1,346 | 175 |  | 1,521 |
| ASP/PHA/85/TAS/62 |  | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) |  |  | 9,702 | 1,261 |  | 10,964 |
| BAH/PHA/88/TAS/40 |  | HCFC phase-out management plan (stage II, first tranche) (servicing sector) |  |  | 73 | 9 |  | 82 |
| BAH/PHA/88/TAS/42 |  | HCFC phase-out management plan (stage II, first tranche) (PMU) |  |  | 49 | 6 |  | 55 |
| BDI/PHA/86/TAS/41 |  | Verification report on the implementation of stage I of the HCFC phase-out management plan |  |  | 205 | 27 |  | 232 |
| BHA/PHA/88/TAS/31 |  | HCFC phase-out management plan (stage I, fourth tranche) |  |  | -4,504 | -585 |  | -5,089 |
| BKF/SEV/87/INS/45 |  | Extension of the institutional strengthening project (phase XIV: 7/2021-6/2023) |  |  | 1 | 0 |  | 1 |
| BOT/PHA/82/TAS/22 |  | HCFC phase-out management plan (stage I, second tranche) |  |  | -181 | -23 |  | -204 |
| BOT/PHA/88/TAS/28 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 205 | 27 |  | 232 |
| CHI/KIP/88/PRP/208 |  | Preparation of Kigali HFC implementation plan |  |  | 12,675 | 1,648 |  | 14,323 |
| CHI/PHA/76/TAS/191 |  | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) |  |  | 15,183 | 1,974 |  | 17,157 |
| CHI/PHA/85/TAS/199 |  | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) |  |  | 567 | 74 |  | 641 |
| COI/PHA/84/PRP/30 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 26 | 3 |  | 29 |
| COL/PHA/84/TAS/107 |  | HCFC phase-out management plan (stage II, third tranche) (technical assistance in policies formulation and implementation) |  |  | 26,575 | 3,455 |  | 30,029 |
| COL/PHA/88/TAS/112 |  | HCFC phase-out management plan (stage II, fourth tranche) |  |  | 447 | 58 |  | 505 |
| GAB/PHA/84/PRP/39 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 485 | 63 |  | 548 |
| GAB/SEV/87/INS/40 |  | Extension of the institutional strengthening project (phase XI: 7/2021-6/2023) |  |  | 50 | 0 |  | 50 |
| GAM/PHA/88/TAS/43 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 205 | 27 |  | 232 |
| GBS/SEV/87/INS/28 |  | Extension of the institutional strengthening project (phase VII: 7/2021-6/2023) |  |  | 16 | 0 |  | 16 |
| GHA/KIP/87/PRP/53 |  | Preparation of Kigali HFC implementation plan |  |  | 410 | 53 |  | 463 |
| GHA/PHA/87/TAS/52 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 459 | 60 |  | 519 |
| GLO/SEV/91/TAS/361 |  | Compliance Assistance Programme: 2023 budget |  |  | 1,192,987 | 95,439 |  | 1,288,426 |
| GUI/PHA/85/TAS/33 |  | HCFC phase-out management plan (stage I, third tranche) |  |  | 205 | 27 |  | 232 |
| GUI/PHA/86/PRP/38 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 7,880 | 1,024 |  | 8,904 |
| GUY/PHA/86/TAS/34 |  | Verification report on the implementation of the HCFC phase-out management plan |  |  | 9,850 | 1,281 |  | 11,131 |
| HON/PHA/86/TAS/52 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 240 | 31 |  | 271 |
| IVC/PHA/84/PRP/46 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 463 | 60 |  | 523 |
| MEX/KIP/87/PRP/197 |  | Preparation of Kigali HFC implementation plan |  |  | 2,168 | 282 |  | 2,450 |
| MEX/PHA/90/TAS/201 |  | HCFC phase-out management plan (stage II, fourth tranche) |  |  | 3,377 | 439 |  | 3,816 |
| MLW/KIP/88/PRP/50 |  | Preparation of Kigali HFC implementation plan |  |  | 460 | 60 |  | 520 |
| MLW/PHA/91/TAS/53 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 205 | 27 |  | 232 |
| NIC/PHA/88/TAS/46 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 6,071 | 789 |  | 6,860 |
| NIR/KIP/87/PRP/157 |  | Preparation of Kigali HFC implementation plan |  |  | 430 | 56 |  | 486 |
| PAK/SEV/81/TAS/97 |  | Enabling activities for HFC phase-down |  |  | 2,580 | 181 |  | 2,761 |
| PER/PHA/85/TAS/58 |  | HCFC phase-out management plan (stage II, second tranche) |  |  | 3,823 | 497 |  | 4,320 |
| PHI/SEV/87/INS/107 |  | Extension of institutional strengthening project (phase XIII: 1/2022-12/2023) |  |  | 2,908 | 0 |  | 2,908 |
| STK/PHA/82/TAS/22 |  | Verification report on the implementation of the HCFC phase-out management plan |  |  | 982 | 128 |  | 1,110 |
| STP/PHA/81/PRP/28 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 8 | 1 |  | 9 |
| SUR/PHA/81/TAS/26 |  | HCFC phase-out management plan (stage I, third tranche) |  |  | 1,250 | 163 |  | 1,413 |
| SUR/PHA/83/PRP/29 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 4,950 | 644 |  | 5,594 |
| YEM/SEV/73/INS/43 |  | Extension of the institutional strengthening project (phase VIII: 1/2015-12/2016) |  |  | 14 | 0 |  | 14 |
| ZAM/PHA/91/TAS/45 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 205 | 27 |  | 232 |
| ZIM/PHA/88/TAS/64 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 205 | 27 |  | 232 |
| Total completed projects |  |  |  |  | 1,708,250 | 136,920 |  | 1,845,170 |
| ANG/SEV/80/TAS/01+ |  | Enabling activities for HFC phase-down |  |  | (1,750) | (123) |  | (1,873) |
| BRU/SEV/82/TAS/01+ |  | Enabling activities for HFC phase-down |  |  | 30,188 | 2,113 |  | 32,301 |
| DMI/SEV/80/TAS/01+ |  | Enabling activities for HFC phase-down |  |  | 10,000 | 700 |  | 10,700 |
| NAU/SEV/81/TAS/01+ |  | Enabling activities for HFC phase-down |  |  | (8,278) | (579) |  | (8,857) |
| STL/SEV/80/TAS/01+ |  | Enabling activities for HFC phase-down |  |  | 38,000 | 2,660 |  | 40,660 |
| SYR/SEV/83/TAS/01+ |  | Enabling activities for HFC phase-down |  |  | 19,000 | 1,330 |  | 20,330 |
| Total “additional voluntary contributions” projects |  |  |  |  | 87,160 | 6,101 |  | 93,261 |
| TOTAL UNEP |  |  |  |  | 1,795,410 | 143,021 |  | 1,938,431 |
| UNIDO |  |  |  |  |  |  |  |  |
| AFG/PHA/77/INV/20 |  | HCFC phase-out management plan (stage I, second tranche) |  |  | 512 | 46 |  | 558 |
| ALB/PHA/85/INV/41 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 108 | 9 |  | 117 |
| ARG/PHA/79/INV/180 |  | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) |  |  | 3,200 | 224 |  | 3,424 |
| ARG/PHA/80/TAS/185 |  | HCFC phase-out management plan (stage II, first tranche) (management and coordination) |  |  | 2,911 | 204 |  | 3,115 |
| BHE/PHA/86/TAS/38 |  | Verification report on implementation of stage I of the HCFC phase-out management plan |  |  | 9,094 | 818 |  | 9,912 |
| BOL/KIP/87/PRP/52 |  | Preparation of Kigali HFC implementation plan |  |  | 4,594 | 321 |  | 4,915 |
| BOT/PHA/75/INV/18 |  | HCFC phase-out management plan (stage I, first tranche) |  |  | 9,859 | 690 |  | 10,549 |
| BOT/PHA/82/INV/21 |  | HCFC phase-out management plan (stage I, second tranche) |  |  | 29,918 | 2,094 |  | 32,013 |
| CHI/PHA/76/TAS/189 |  | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) |  |  | 173 | 12 |  | 185 |
| CHI/PHA/81/TAS/196 |  | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) |  |  | 3,923 | 274 |  | 4,197 |
| CHI/PHA/85/TAS/200 |  | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) |  |  | 2,123 | 149 |  | 2,272 |
| ECU/KIP/87/PRP/76 |  | Preparation of Kigali HFC implementation plan |  |  | 5,810 | 407 |  | 6,217 |
| ECU/PHA/86/INV/75 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 8,363 | 586 |  | 8,949 |
| ECU/SEV/87/INS/77 |  | Extension of institutional strengthening project (phase VII: 7/2019-6/2021) |  |  | 974 | 68 |  | 1,042 |
| EGY/PHA/84/TAS/145 |  | HCFC phase-out management plan (stage II, second tranche) (air-conditioning sector) |  |  | 3,494 | 245 |  | 3,738 |
| GLO/REF/80/DEM/344 |  | Global chiller replacement project (Argentina) |  |  | 253,768 | 19,033 |  | 272,801 |
| HON/PHA/86/INV/50 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 879 | 61 |  | 941 |
| KUW/PHA/66/INV/21 |  | HCFC phase-out management plan (stage I, first tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Company) |  |  | 10,247 | 769 |  | 11,016 |
| KUW/PHA/74/INV/24 |  | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector phase-out: Kuwait polyurethane Industry Co.; Kirby Building Systems, technical assistance to spray foam users and other small users) |  |  | 7,558 | 529 |  | 8,088 |
| KUW/PHA/74/INV/25 |  | HCFC phase-out management plan (stage I, second tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Company) |  |  | 429 | 30 |  | 460 |
| KUW/PHA/88/INV/45 |  | HCFC phase-out management plan (stage I, fourth tranche) (extruded polystyrene foam sector phase-out) |  |  | 72,516 | 5,076 |  | 77,592 |
| LIB/FOA/82/PRP/41 |  | Preparation for HCFC phase-out investment activities (stage II) (foam sector) |  |  | 436 | 31 |  | 467 |
| LIB/PHA/75/INV/37 |  | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) |  |  | 12,538 | 878 |  | 13,416 |
| MAG/PHA/84/PRP/33 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 1,023 | 72 |  | 1,094 |
| MEX/PHA/77/INV/183 |  | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) |  |  | 199 | 14 |  | 213 |
| MEX/PRO/86/INV/194 |  | Control and phase-out of HFC-23 emissions in production of HCFC-22 at Quimobasicos |  |  | 301 | 21 |  | 322 |
| MLW/KIP/88/PRP/51 |  | Preparation of Kigali HFC implementation plan |  |  | 1,878 | 131 |  | 2,009 |
| MLW/PHA/85/INV/48 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 4,748 | 427 |  | 5,175 |
| MOG/PHA/88/TAS/18 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 4,410 | 397 |  | 4,807 |
| NIC/KIP/87/PRP/45 |  | Preparation of Kigali HFC implementation plan |  |  | 1,615 | 113 |  | 1,728 |
| NIR/PHA/83/PRP/153 |  | Preparation of a HCFC phase-out management plan (stage III) |  |  | 762 | 53 |  | 815 |
| OMA/SEV/86/INS/42 |  | Renewal of institutional strengthening support (phase VIII: 12/2020-11/2022) |  |  | 8,339 | 584 |  | 8,923 |
| PAK/FOA/84/INV/103 |  | Phase-out of HCFC-142b/HCFC-22 from the manufacturing of extruded polystyrene at Symobl Industries, Lahore |  |  | 1,100 | 77 |  | 1,177 |
| RWA/PHA/86/INV/35 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 711 | 64 |  | 775 |
| SOA/FOA/67/INV/03 |  | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) |  |  | 8,098 | 567 |  | 8,665 |
| SOA/PHA/76/INV/10 |  | HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector plan) |  |  | 3,398 | 238 |  | 3,636 |
| SOA/PHA/83/TAS/13 |  | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, custom training and monitoring) |  |  | 1,455 | 102 |  | 1,557 |
| SOM/PHA/77/INV/12 |  | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) |  |  | 2,662 | 186 |  | 2,849 |
| SYR/KIP/88/PRP/109 |  | Preparation of Kigali HFC implementation plan |  |  | 3,210 | 225 |  | 3,435 |
| TKM/PHA/88/TAS/19 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 81 | 7 |  | 89 |
| TUR/SEV/84/INS/110 |  | Extension of institutional strengthening project (phase IX: 12/2019-11/2021) |  |  | 24,482 | 1,713 |  | 26,195 |
| Total completed projects |  |  |  |  | 511,900 | 37,546 |  | 549,446 |
| MOR/SEV/81/TAS/01+ |  | Enabling activities for HFC phase-down |  |  | 55,275 | 3,869 |  | 59,144 |
| Total “additional voluntary contributions” projects |  |  |  |  | 55,275 | 3,869 |  | 59,144 |
| TOTAL UNIDO |  |  |  |  | 567,175 | 41,415 |  | 608,590 |
| WORLD BANK |  |  |  |  |  |  |  |  |
| GLO/SEV/91/TAS/362 |  | Core unit budget (2023) |  |  |  | 70,433 |  | 70,433 |
| IDS/PHA/88/INV/218 |  | HCFC phase-out management plan (stage II, third tranche) (foam sector) |  |  | 14,628 | 1,024 |  | 15,652 |
| VIE/EEF/93/PRP/89 |  | EE project at an AC enterprise will not go forward |  |  | 30,000 | 2,100 |  | 32,100 |
| VIE/PHA/91/INV/82 |  | Savings after closing the Stage II HPMP. Slightly adjusted after WB-Viet Nam project financial closure (with $269 more disbursed than reported in the 2023 PR). |  |  | 575,828 | 40,308 |  | 616,136 |
| Total completed projects |  |  |  |  | 620,456 | 113,865 |  | 734,321 |
| Total WORLD BANK |  |  |  |  | 620,456 | 113,865 |  | 734,321 |
| JAPAN |  |  |  |  |  |  |  |  |
| VIE/PHA/87/INV/79 |  | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) |  |  | 2,301 | 299 |  | 2,600 |
| TOTAL JAPAN |  |  |  |  | 2,301 | 299 |  | 2,600 |

UNEP/OzL.Pro/ExCom/95/1

تستند البيانات المعروضة إلى نموذج الإبلاغ الذي تم إعداده عملاً بالمقرر 31/2.

UNEP/OzL.Pro/ExCom/95/3

انظر الوثيقة UNEP/OzL.Pro/ExCom/95/20 بشأن المشروعات ذات متطلبات الإبلاغ المحددة ودون مسائل معلقة.

انظر الرسالة المؤرخة 8 يوليه/تموز 2024 الموجهة من الوكالة الوطنية لحماية البيئة في أفغانستان، وانظر أيضاً الوثيقة UNEP/OzL.Pro/ExCom/95/37 المتعلقة بالتعديلات على برنامج عمل اليونيدو لعام 2024.

لا يشمل هذا المبلغ الأموال التي أعادها اليونيب بمبلغ 401,361 دولاراً أمريكياً، بالإضافة إلى تكاليف دعم الوكالة البالغة 27,217 دولاراً أمريكياً، لثلاثة مشاريع سيتم تحويلها إلى اليونيدو على النحو المبين في الجدول 5.

Outstanding obligations to be paid, funds will be returned with next balance list.

Outstanding obligations to be paid, funds will be returned with next balance list.