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INFORME SOBRE SALDOS Y DISPONIBILIDAD DE RECURSOS 


Introducción
1. El presente documento resume los ajustes financieros indicados por los organismos bilaterales y de ejecución, según lo acordado por la Secretaría. Según lo dispuesto en las decisiones 28/7 y 56/2 c), se incluyen datos estadísticos[footnoteRef:3] sobre todo proyecto con saldos a su haber a los 12 o más meses de terminado e informa los saldos a reintegrar contra proyectos en virtud de decisiones del Comité Ejecutivo (en el presente documento, “por decisión”) y de proyectos transferidos. Conforme a la decisión 41/92 b), indica además el nivel presupuestario en efectivo a disposición del Comité según el informe Situación de las contribuciones y los desembolsos[footnoteRef:4], así como una recomendación. Los montos que obran en poder de los organismos de ejecución para los proyectos terminados y financiados por contribuciones voluntarias adicionales se incluyen en el anexo I y el anexo II, respectivamente. En el anexo III se presentan los fondos reintegrados por los organismos de ejecución por concepto de proyectos terminados, de contribuciones voluntarias adicionales y de proyectos por decisión. [3: Los datos presentados se basan en el formato de presentación de informes que se ha elaborado en respuesta a la decisión 31/2.]  [4: UNEP/OzL.Pro/ExCom/98/3] 

Fondos a reintegrar a la 98ª reunión
2. Los fondos totales que han de devolver los organismos de ejecución ascienden a USD 1.417.152 provenientes de proyectos terminados, financiados por contribuciones voluntarias adicionales y por decisión, tal y como se muestra en el cuadro 1.
Cuadro1. Fondos que han de reintegrar los organismos de ejecución a la 98ª reunión (USD)
	Organismo
	Costo del proyecto
	Gastos de apoyo
	Costo total

	PNUD
	105.125
	7.918
	113.043

	PNUMA
	594.160
	42.303
	636.463

	ONUDI
	620.860
	46.786
	667.646

	Total
	1.320.145
	97.007
	1.417.152


Fondos en poder los organismos de ejecución
3. El total de fondos en poder de los organismos de ejecución asciende a USD 5.125.184, tal y como se muestra en el cuadro 2. 
Cuadro 2. Saldos de proyectos terminados y proyectos financiados con contribuciones voluntarias adicionales en poder de los organismos de ejecución (incluidos gastos de apoyo)
	Año de terminación
	PNUD
	ONUDI
	Total

	 
	Cantidad
	USD
	Cantidad
	USD
	Cantidad
	USD

	Proyectos terminados hace más de dos años

	2021
	0
	0
	1
	-367
	1
	-367

	[bookmark: RANGE!A6]2022
	2
	56.723
	5
	99.526
	7
	156.249

	2023
	7
	629.753
	5
	468.332
	12
	1.098.085

	1 de ene. a 
30 de abr. 2024
	0
	0
	0
	0
	0
	0

	Subtotal
	9
	        686.476 
	11
	        567.491 
	20
	  1.253.967 

	Proyectos terminados hace menos de dos años 

	1 de may. a 
31 de dic. 2024
	21
	3.381.616
	12
	398.199
	33
	3.779.815

	Subtotal
	21
	     3.381.616
	12
	        398.199
	33
	  3.779.815 

	[bookmark: RANGE!A13]Total
	30
	     4.068.092
	23
	        965.690
	53
	  5.033.782 

	Proyecto financiado con contribuciones voluntarias adicionales 

	 
	0
	0
	1
	          91,402 
	1
	91,402

	Total general
	30
	     4.068.092
	24
	     1.057.092
	54
	5.125.184 




Disponibilidad de recursos 
4. Para el trienio 2024-2026, las Partes del Fondo Multilateral aprobaron un presupuesto de USD 965.000.000 (decisión XXXV/1). A fecha 15 de mayo de 2026, el documento Situación de las contribuciones y los desembolsos muestra que el saldo disponible asciende a USD 652.281.816. El saldo total que los organismos de ejecución reintegran a la 98ª reunión asciende a la suma de USD 1.417.152. En consecuencia, el nivel total de recursos disponibles para aprobación en la 98ª reunión asciende a la suma de USD 653.698.968.
Observaciones de la Secretaría
5. La Secretaría recordó a los organismos de ejecución que los saldos por concepto de proyectos terminados hace un año o más, así como los proyectos por decisión y los financiados por contribuciones voluntarias adicionales deben reintegrarse sin demora al Fondo Multilateral.
6. Teniendo en cuenta que el nivel total de financiación para los proyectos y actividades presentados a la 98ª reunión asciende a USD 155.293.564[footnoteRef:5], se dispone de recursos suficientes para las aprobaciones en la 98ª reunión.  [5: A fecha 4 de mayo de 2026] 

Recomendación
7. El Comité Ejecutivo podrá estimar oportuno:
 a)	Tomar nota de lo siguiente:
i) El informe sobre saldos y disponibilidad de recursos que recoge el documento UNEP/OzL.Pro/ExCom/98/4;
ii) Que el nivel neto de fondos que los organismos de ejecución reintegran a la 98ª reunión asciende a USD 1.417.152, cifra consistente en USD 105.125, más gastos de apoyo de USD 7.918 que reintegra el PNUD; USD 594.160, más gastos de apoyo de USD 42.303 que reintegra el PNUMA, y USD 620.860, más gastos de apoyo de USD 46.786 que reintegra la ONUDI;
iii) Que el PNUD mantiene a su haber un saldo de USD 686.476, incluyendo gastos de apoyo, por concepto de nueve proyectos terminados hace más de dos años;
iv) Que la ONUDI mantiene a su haber un saldo de USD 567.491, incluyendo gastos de apoyo, por concepto de 11 proyectos terminados hace más de dos años, y de USD 91.402, incluyendo gastos de apoyo, por concepto de un proyecto financiado con cargo a las contribuciones voluntarias adicionales; 
 b)	Solicitar al PNUD y a la ONUDI:	
i) Proceder al desembolso o cancelación de los fondos comprometidos que no se precisaron para proyectos terminados y reintegrar los saldos respectivos a la 99ª reunión; 
ii) Proceder al desembolso o cancelación de los fondos comprometidos para proyectos terminados hace más de dos años y reintegrar los saldos respectivos a la 99ª reunión; y
 c)	Solicitar a la ONUDI que proceda al desembolso o reintegro en la 99ª reunión de los saldos del proyecto financiado por contribuciones voluntarias adicionales.
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Los documentos previos al período de sesiones del Comité Ejecutivo del Fondo Multilateral para la Aplicación del Protocolo de Montreal no van en perjuicio de las decisiones que el Comité pudiera adoptar después de la emisión de los mismos.
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AnnexI
COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR COMPLETED PROJECTS

	Code
	Project Title
	Date Completed (Actual)
	Approved funding plus adjustments as of 
31 December 2024 
(US $)
	Funds disbursed as of
 98th meeting 
(US $)
	 Balances committed as per 98th meeting 
(US $)
	 Balances not-committed as per 98th meeting 
(US $)
	 Support cost on balances committed and not committed as per 
98th meeting (US $)
	Why any balances could not be returned?
	When they could be returned?
	Project subject to decision

	UNDP
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	BGD/PHA/90/INV/59
	HCFC phase-out management plan (stage II, second tranche) (air-conditioning sector)
	Dec-24
	1,967,866
	1,678,655
	289,211
	0
	20,245
	 
	 
	 

	BZE/PHA/87/INV/40
	HCFC phase-out management plan (stage II, first tranche)
	Dec-24
	73,854
	41,316
	32,538
	0
	2,928
	 
	 
	 

	COS/KIP/87/PRP/63
	Preparation of Kigali HFC implementation plan
	Dec-24
	170,000
	163,390
	6,610
	0
	463
	 
	 
	 

	CUB/KIP/87/PRP/65
	Preparation of Kigali HFC implementation plan
	Aug-24
	170,000
	154,279
	15,721
	0
	1,100
	 
	 
	 

	DOM/KIP/87/PRP/73
	Preparation of Kigali HFC implementation plan
	Aug-24
	190,000
	174,370
	15,630
	0
	1,094
	 
	 
	 

	EGY/PHA/79/TAS/132
	HCFC phase-out management plan (stage II, first tranche) (project management and monitoring)
	Dec-22
	75,000
	39,629
	35,371
	0
	2,476
	 
	 
	 

	EGY/PHA/84/INV/144
	HCFC phase-out management plan (stage II, second tranche) (extruded polystyrene foam sector)
	Dec-23
	1,761,750
	1,627,929
	133,821
	0
	9,368
	 
	 
	 

	ELS/PHA/87/INV/43
	HCFC phase-out management plan (stage II, first tranche)
	Dec-24
	169,000
	66,702
	102,298
	0
	7,161
	 
	 
	 

	GHA/KIP/87/PRP/51
	Preparation of Kigali HFC implementation plan
	Aug-23
	130,000
	126,468
	3,532
	0
	247
	 
	 
	 

	GRN/KIP/88/PRP/28
	Preparation of Kigali HFC implementation plan
	Dec-24
	40,000
	14,163
	25,837
	0
	1,809
	 
	 
	 

	HAI/SEV/90/INS/25
	Extension of the institutional strengthening project (phase V: 7/2022-6/2024)
	Dec-24
	128,000
	119,478
	8,522
	0
	597
	 
	 
	 

	IDS/PHA/81/INV/213
	HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector)
	Dec-24
	753,500
	158,983
	594,517
	0
	41,616
	 
	 
	 

	IDS/PHA/87/PRP/216
	Preparation of HCFC phase-out management plan (stage III) (Overarching)
	Dec-23
	90,000
	87,245
	2,755
	0
	193
	 
	 
	 

	IDS/PHA/88/INV/217
	HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector)
	Dec-24
	627,086
	0
	627,086
	0
	43,896
	 
	 
	 

	IDS/PHA/92/INV/220
	HCFC phase-out management plan (stage II, fourth tranche)
	Dec-24
	433,300
	0
	433,300
	0
	30,331
	 
	 
	 

	IND/PHA/86/TAS/482
	HCFC phase-out management plan (stage II, third tranche) (project management and monitoring)
	Dec-24
	800,000
	0
	800,000
	0
	56,000
	 
	 
	 

	IRA/PHA/86/INV/243
	HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration sector)
	Dec-24
	576,090
	551,597
	24,493
	0
	1,714
	 
	 
	 

	IRA/PHA/90/INV/262
	HCFC phase-out management plan (stage II, fourth tranche) (PMU)
	Dec-23
	92,000
	69,877
	22,123
	0
	1,549
	 
	 
	 

	IRA/PHA/92/INV/264
	HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector)
	Dec-23
	93,017
	0
	93,017
	0
	6,511
	 
	 
	 

	IRA/PHA/92/INV/265
	HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration sector)
	Dec-23
	145,255
	0
	145,255
	0
	10,168
	 
	 
	 

	MDV/KIP/87/PRP/36
	Preparation of Kigali HFC implementation plan
	Dec-24
	35,000
	22,026
	12,974
	0
	908
	 
	 
	 

	NIR/KIP/87/PRP/156
	Preparation of Kigali HFC implementation plan
	Dec-24
	137,000
	124,331
	12,669
	0
	887
	 
	 
	 

	NIR/PHA/81/TAS/150
	HCFC phase-out management plan (stage II, first tranche) (project management and coordination)
	Dec-22
	165,000
	147,359
	17,641
	0
	1,235
	 
	 
	 

	NIR/PHA/88/INV/163
	HCFC phase-out management plan (stage II, second tranche) (project management and coordination)
	Dec-24
	75,000
	41,581
	33,419
	0
	2,339
	 
	 
	 

	SRL/SEV/91/INS/61
	Extension of the institutional strengthening project (phase XIV: 1/2023-12/2024)
	Dec-24
	236,796
	234,222
	2,574
	0
	180
	 
	 
	 

	TRI/KIP/87/PRP/40
	Preparation of Kigali HFC implementation plan
	Dec-24
	190,000
	145,057
	44,943
	0
	3,146
	 
	 
	 

	TRI/PHA/86/INV/38
	HCFC phase-out management plan (stage II, first tranche)
	Dec-23
	498,756
	310,706
	188,050
	0
	13,164
	 
	 
	 

	URU/KIP/87/PRP/77
	Preparation of Kigali HFC implementation plan
	Dec-24
	190,000
	160,103
	29,897
	0
	2,093
	 
	 
	 

	URU/PHA/86/INV/76
	HCFC phase-out management plan (stage III, first tranche)
	Dec-24
	350,601
	313,973
	36,628
	0
	2,564
	 
	 
	 

	ZIM/KIP/91/PRP/66
	Preparation of a Kigali HFC implementation plan
	Dec-24
	51,000
	40,086
	10,914
	0
	764
	 
	 
	 

	Total UNDP
	 
	 
	10,414,871
	6,613,525
	3,801,346
	0
	266,746
	 
	 
	 

	UNIDO
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	BOL/PHA/87/INV/50
	HCFC phase-out management plan (stage II, first tranche)
	Aug-24
	141,009
	128,910
	12,099
	0
	847
	 
	 
	 

	BRA/PHA/82/INV/320
	HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration and air-conditioning sector)
	Dec-24
	2,647,057
	1,613,586
	289,368
	0
	20,256
	 
	 
	 

	CMR/KIP/88/PRP/49
	Preparation of Kigali HFC implementation plan
	Dec-23
	190,000
	188,394
	1,606
	0
	112
	 
	 
	 

	CPR/PHA/88/INV/607
	HCFC phase-out management plan (stage II, fourth tranche) (extruded polystyrene foam sector plan)
	Dec-23
	4,400,000
	4,405,665
	-5,665
	0
	-397
	 
	 
	 

	GAB/PHA/79/INV/34
	HCFC phase-out management plan (stage I, third tranche)
	Dec-22
	119,900
	60,409
	59,491
	0
	5,354
	 
	 
	 

	GAM/KIP/90/PRP/44
	Preparation of a Kigali HFC implementation plan
	Dec-24
	39,000
	36,622
	2,378
	0
	166
	 
	 
	 

	IVC/PHA/84/PRP/47
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-24
	20,000
	16,024
	3,976
	0
	278
	 
	 
	 

	JOR/PHA/84/TAS/107
	HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector, project management and coordination)
	Dec-23
	294,122
	90,153
	203,969
	0
	14,277
	 
	 
	 

	LIB/PHA/75/INV/36
	HCFC phase-out management plan (stage I, first tranche) (foam sector)
	Dec-23
	1,690,627
	713,112
	229,982
	0
	16,099
	 
	 
	 

	LIB/SEV/85/INS/44
	Renewal of the institutional strengthening project (phase VI: 7/2020-6/2022)
	Jun-23
	174,164
	166,361
	7,803
	0
	546
	 
	 
	 

	MEX/PHA/90/INV/200
	HCFC phase-out management plan (stage II, fourth tranche) (cleaning agent phase-out in refrigeration servicing sector and project implementation and monitoring)
	Dec-24
	1,612,350
	1,612,260
	90
	0
	6
	 
	 
	 

	MEX/PHA/92/INV/206
	HCFC phase-out management plan (stage II, fifth tranche)
	Dec-24
	450,600
	448,181
	2,419
	0
	169
	 
	 
	 

	MOZ/PHA/66/INV/23
	HCFC phase-out management plan (stage I, first tranche)
	Dec-22
	75,000
	72,133
	2,867
	0
	258
	 
	 
	 

	NER/PHA/84/INV/39
	HCFC phase-out management plan (stage I, second tranche)
	Dec-22
	90,000
	76,492
	13,508
	0
	946
	 
	 
	 

	NER/PHA/88/INV/41
	HCFC phase-out management plan (stage I, third tranche)
	Dec-22
	20,000
	19,002
	998
	0
	70
	 
	 
	 

	SAU/REF/86/PRP/35
	Preparation of a HCFC phase-out management plan (stage II) (air-conditioning)
	Dec-24
	150,000
	141,442
	8,558
	0
	599
	 
	 
	 

	SEN/PHA/85/INV/41
	HCFC phase-out management plan (stage I, third tranche)
	Dec-21
	50,000
	50,341
	-341
	0
	-26
	 
	 
	 

	SEN/PHA/85/PRP/43
	Preparation of a HCFC phase-out management plan (stage II)
	Jun-22
	20,000
	5,015
	14,985
	0
	1,049
	 
	 
	 

	SIL/KIP/88/PRP/43
	Preparation of Kigali HFC implementation plan
	Dec-24
	39,000
	39,014
	-14
	0
	-1
	 
	 
	 

	SIL/PHA/87/INV/40
	HCFC phase-out management plan (stage II, first tranche)
	Dec-24
	117,000
	92,734
	24,266
	0
	2,184
	 
	 
	 

	SOM/PHA/88/PRP/17
	Preparation of HCFC phase-out management plan (stage II) (Overarching)
	Dec-24
	60,000
	57,244
	2,756
	0
	193
	 
	 
	 

	TUR/KIP/90/PRP/113
	Preparation of a Kigali HFC implementation plan
	Dec-24
	120,000
	108,720
	11,280
	0
	790
	 
	 
	 

	VEN/PHA/91/INV/137
	HCFC phase-out management plan (stage II, second tranche) (servicing sector)
	Dec-24
	261,444
	246,924
	14,520
	0
	1,016
	 
	 
	 

	Total UNIDO 
	 
	 
	12,781,273
	10,388,738
	900,899
	0
	64,791
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Annex II
COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS
	CODE
	Project title
	Approved funding plus adjustments as of 
31 December 2025 (US $) 
	Funds disbursed as of 
98thmeeting (US $)
	Balances committed as per 
98thmeeting (US $)
	Balances not- committed as per 
98thmeeting (US $)
	Support cost on balances committed and not-committed as per 
98th meeting
(US $) 
	Why any balances could not be returned?
	When they could be returned?

	UNIDO

	ARG/SEV/81/TAS/02+ 
	Enabling activities for HFC phase-down
	250,000

	164,578

	85,422
	
	5,980
	
	

	TOTAL UNIDO
	
	
	
	85,422
	
	5,980
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AnnexIII
DETAILSONCOMPLETED, ADDITIONAL VOLUNTARY CONTRIBUTIONS ANDBY‑DECISIONSPROJECTSWITHRETURNEDBALANCESFROMIMPLEMENTINGAGENCIES

	Code
	Project title
	Project costs returned 
(US$)
	Agency support costs returned 
(US$)
	Total
(US$) 

	UNDP
	 
	 
	 
	 

	COL/KIP/87/PRP/110
	Preparation of Kigali HFC implementation plan
	75
	5
	80

	COL/PHA/88/INV/111
	HCFC phase-out management plan (stage II, fourth tranche)
	2,712
	190
	2,902

	COL/SEV/88/INS/115
	Extension of institutional strengthening project (phase XIII: 12/2021-11/2023)
	802
	56
	858

	COS/PHA/91/TAS/66
	Verification report on the implementation of stage II of the HCFC phase-out management plan
	3,841
	346
	4,187

	GHA/SEV/91/INS/54
	Extension of the institutional strengthening project (phase XV: 1/2023-12/2024)
	4
	0
	4

	HAI/PHA/91/PRP/26
	Preparation of HCFC phase-out management plan (stage II) (Overarching)
	7,233
	506
	7,739

	IDS/SEV/90/INS/219
	Extension of institutional strengthening project (phase XIII: 7/2022-6/2024)
	2
	0
	2

	IND/KIP/92/PRP/505
	Preparation of a KIP investment project in the refrigeration manufacturing sector for Mech Air Industries
	28,499
	1,995
	30,494

	KAM/KIP/88/PRP/40
	Preparation of Kigali HFC implementation plan
	10,027
	702
	10,729

	LAO/KIP/87/PRP/39
	Preparation of Kigali HFC implementation plan
	297
	21
	318

	LAO/PHA/86/INV/38
	HCFC phase-out management plan (stage II, first tranche)
	254
	23
	277

	LEB/KIP/87/PRP/98
	Preparation of Kigali HFC implementation plan
	3,886
	272
	4,158

	LEB/SEV/86/INS/96
	Extension of the institutional strengthening project (phase XII: 4/2021-3/2023)
	2,233
	156
	2,389

	MAL/PHA/87/PRP/189
	Preparation of HCFC phase-out management plan (stage III) (Overarching)
	3,946
	276
	4,222

	MEX/FOA/90/PRP/198
	Preparation for HFC investment projects in the foam sector
	3,935
	275
	4,210

	MEX/KIP/87/PRP/195
	Preparation of Kigali HFC implementation plan
	3,883
	272
	4,155

	MEX/REF/92/INV/204
	Conversion of the manufacturing of commercial refrigerators from HFC-134a to propane (R-290) at the enterprise Friocima
	23,922
	2,153
	26,075

	PAK/SEV/87/INS/108
	Extension of the institutional strengthening project (phase XI: 7/2021-6/2023)
	1,257
	88
	1,345

	PAN/KIP/87/PRP/53
	Preparation of Kigali HFC implementation plan
	82
	6
	88

	PAR/KIP/87/PRP/42
	Preparation of Kigali HFC implementation plan
	-65
	-5
	-70

	SRL/KIP/87/PRP/59
	Preparation of Kigali HFC implementation plan
	-154
	-11
	-165

	SWA/KIP/87/PRP/33
	Preparation of Kigali HFC implementation plan
	284
	20
	304

	Total completed projects
	96,955
	7,346
	104,301

	FIJ/SEV/80/TAS/01+
	Enabling activities for HFC phase-down
	8,170
	572
	8,742

	Total “additional voluntary contributions” projects
	8,170
	572
	8,742

	Total UNDP 
	 
	105,125
	7,918
	113,043

	UNEP
	 
	 
	 
	 

	CKI/SEV/88/INS/18
	Extension of the institutional strengthening project (phase VIII: 7/2022-6/2024)
	5,000
	0
	5,000

	ELS/PHA/87/TAS/42
	HCFC phase-out management plan (stage II, first tranche)
	1,419
	184
	1,603

	GLO/SEV/93/TAS/368
	Compliance Assistance Programme: 2024 budget
	468,485
	37,479
	505,964

	GUA/SEV/88/INS/60
	Renewal of the institutional strengthening project (phase IX: 12/2021-11-2023)
	13,315
	0
	13,315

	IND/PHA/86/TAS/483
	HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector plan)
	7,246
	878
	8,124

	KYR/SEV/91/INS/48
	Extension of the institutional strengthening project (phase XI: 1/2023-12/2024)
	4,602
	0
	4,602

	NIC/PHA/92/TAS/47
	HCFC phase-out management plan (stage II, second tranche)
	26,312
	3,421
	29,733

	NIC/SEV/92/INS/51
	Renewal of institutional strengthening project (phase XI: 7/2023-6/2026)
	65,161
	0
	65,161

	PAK/PHA/88/TAS/109
	HCFC phase-out management plan (stage II, third tranche)
	2,539
	330
	2,869

	SEN/KIP/87/PRP/44
	Preparation of Kigali HFC implementation plan
	81
	11
	92

	Total completed projects
	594,160
	42,303
	636,463

	Total UNEP 
	 
	594,160
	42,303
	636,463

	UNIDO
	 
	 
	 
	 

	BAH/PHA/93/INV/46
	HCFC phase-out management plan (stage II, second tranche)
	108
	8
	116

	BRA/PHA/75/INV/311
	HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration and air-conditioning sector)
	1,699
	119
	1,818

	BRA/PHA/88/INV/327
	HCFC phase-out management plan (stage II, fifth tranche) (commercial refrigeration and air-conditioning sector)
	23,994
	1,680
	25,674

	CPR/PHA/75/INV/564
	HCFC phase-out management plan (stage I, fifth tranche) (room air-conditioner manufacturing sector plan)
	-5,665
	-5,385
	-11,050

	GUA/KIP/94/PRP/69
	Preparation of a Kigali HFC implementation plan (stage I)
	216
	15
	231

	HON/KIP/90/PRP/55
	Preparation of a Kigali HFC implementation plan
	34
	2
	36

	JOR/PHA/92/PRP/115
	Preparation of HCFC phase-out management plan (stage III) (Overarching)
	15
	1
	16

	MEX/PHA/92/INV/205
	Destruction of emissions of HFC-23 generated in the production of HCFC-22 in Quimobasicos (second tranche)
	32
	2
	34

	MOR/KIP/92/PRP/79
	Preparation of a KIP investment project in the refrigeration manufacturing sector for MANAR
	471
	33
	504

	NIC/PHA/86/INV/40
	HCFC phase-out management plan (stage II, first tranche)
	1,505
	105
	1,610

	PAK/PHA/76/INV/94
	HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector)
	16,483
	1,154
	17,637

	PAK/PHA/83/INV/102
	HCFC phase-out management plan (stage II, second tranche) (polyurethane foam sector)
	43,813
	3,067
	46,880

	PAK/PHA/83/TAS/100
	HCFC phase-out management plan (stage II, second tranche) (project management unit)
	34,237
	2,397
	36,634

	PAK/PHA/90/INV/110
	HCFC phase-out management plan (stage II, fourth tranche) (domestic air-conditioner manufacturing sector)
	1,882
	131
	2,013

	PHI/PHA/83/INV/104
	HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector)
	188,014
	13,160
	201,174

	PHI/PHA/83/TAS/105
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector)
	38,932
	2,726
	41,658

	PRC/KIP/91/PRP/38
	Preparation of a Kigali HFC implementation plan
	1,196
	84
	1,280

	RWA/KIP/88/PRP/38
	Preparation of Kigali HFC implementation plan
	6,238
	440
	6,678

	SOA/PHA/91/INV/16
	HCFC phase-out management plan (stage I, fifth tranche) (refrigeration servicing, custom training and monitoring)
	21,481
	1,503
	22,984

	Total completed projects
	374,685
	21,242
	395,927

	IRQ/PHA/74/INV/23
	HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector)
	8,064
	605
	8,669

	NIC/EEF/92/TAS/49
	HCFC phase-out management plan (stage II, second tranche) (energy efficiency - related activities under decision 89/6)
	23,618
	1,653
	25,271

	NIC/KIP/93/INV/57
	Kigali HFC implementation plan (stage I, first tranche)
	137,870
	17,923
	155,793

	NIC/PHA/92/INV/48
	HCFC phase-out management plan (stage II, second tranche)
	56,623
	3,963
	60,586

	PAK/PHA/90/INV/111
	HCFC phase-out management plan (stage III, first tranche) (foam sector)
	20,000
	1,400
	21,400

	Total "by-decision" projects
	246,175
	25,544
	271,719

	Total UNIDO  
	620,860
	46,786
	667,646
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