| NATIONS UNIES |  | EP |
| --- | --- | --- |
|  | Programme des Nations Unies pour l’environnement | Distr. GÉNÉRALE UNEP/OzL.Pro/ExCom/93/23 6 décembre 2023 FRANÇAIS ORIGINAL: ANGLAIS |

COMITÉ EXÉCUTIF 
  DU FONDS MULTILATÉRAL AUX FINS 
  D’APPLICATION DU PROTOCOLE DE MONTRÉAL
Quatre-vingt-treizième réunion

Montréal, 15 – 19 décembre 2023

Point 8(a) de l’ordre du jour provisoire

MISE À JOUR SUR L’ÉTAT DE LA MISE EN ŒUVRE DU PLAN D’ACTIVITÉS GÉNÉRAL DU FONDS MULTILATÉRAL POUR LA PÉRIODE 2023–2025

- Introduction

# Le présent document se compose des sections suivantes :

## I.	Mise à jour sur l’état de la mise en œuvre du plan d’activités de 2023–2025

## II.	Répartition des ressources pour le triennat 2021–2023

III.	Recommandation

## I.	Mise à jour sur l’état de la mise en œuvre du plan d’activités de 2023–2025

# À sa 91e réunion, le Comité exécutif a entériné le plan d’activités général du Fonds multilatéral pour 2023–2025. En réponse à la décision 91/31, le Secrétariat a ajusté le plan d’activités général pour 2023–2025, comme indiqué dans le tableau 1.

Tableau 1. Répartition des ressources du plan d’activités général rectifié du Fonds multilatéral pour 2023–2025 ($ US)*

| Description | 2023 | 2024 | 2025 | Total |
| --- | --- | --- | --- | --- |
| Activités liées aux HCFC |  |  |  |  |
| Plans de gestion de l’élimination des HCFC (PGEH) approuvés | 60 280 861 | 56 111 450 | 43 084 350 | 159 476 661 |
| Préparation de projet (PRP) des PGEH – phase II | 200 480 | 77 600 | 0 | 278 080 |
| PGEH phase II | 2 937 082 | 5 199 804 | 3 462 199 | 11 599 085 |
| PGEH phase II – investissement | 0 | 248 532 | 0 | 248 532 |
| PRP des PGEH – phase III | 290 100 | 92 750 | 0 | 382 850 |
| PGEH phase III | 14 794 713 | 10 344 520 | 20 526 731 | 45 665 964 |
| PRP des PGEH – phase IV | 90 000 | 0 | 0 | 90 000 |
| PGEH phase IV | 0 | 0 | 2 093 000 | 2 093 000 |
| PGEH – efficacité énergétique | 3 258 494 | 2 672 980 | 3 379 420 | 9 310 894 |
| Vérification des PGEH** | 588 600 | 588 600 | 588 600 | 1 765 800 |
| Total partiel des activités liées aux HCFC | 82 440 330 | 75 336 236 | 73 134 299 | 230 910 865 |
| Activités liées aux HFC |  |  |  |  |
| Activités de facilitation de la réduction progressive des HFC | 53 500 | 160 500 | 0 | 214 000 |
| Plans de mise en œuvre de l’Amendement de Kigali pour les HFC (KIP) – PRP | 3 945 431 | 2 567 011 | 144 560 | 6 657 002 |
| KIP | 27 299 967 | 21 437 607 | 245 413 | 48 982 987 |
| PRP des KIP – investissement | 129 000 | 0 | 0 | 129 000 |
| KIP – investissement | 321 000 | 8 963 616 | 0 | 9 284 616 |
| PRP pour le contrôle des émissions de HFC-23 | 43 000 | 0 | 0 | 43 000 |
| Contrôle des émissions de HFC-23 | 0 | 8 000 000 | 0 | 8 000 000 |
| HFC – assistance technique | 0 | 678 000 | 0 | 678 000 |
| Total partiel des activités liées aux HFC | 31 791 898 | 41 806 734 | 389 973 | 73 988 605 |
| Projet pilote sur l’efficacité énergétique |  |  |  |  |
| Projet pilote sur l’efficacité énergétique | 20 000 000 | 0 | 0 | 20 000 000 |
| Total partiel du projet pilote sur l’efficacité énergétique | 20 000 000 | 0 | 0 | 20 000 000 |
| Activités normalisées |  |  |  |  |
| Renforcement des institutions (RI) | 27 860 444 | 16 639 896 | 0 | 44 500 341 |
| Programme d’aide à la conformité (PAC) | 11 445 002 | 11 788 350 | 12 142 003 | 35 375 355 |
| Coûts de base | 5 969 740 | 6 011 529 | 6 053 610 | 18 034 878 |
| Coûts associés au Secrétariat, au Comité exécutif et aux activités de surveillance et d’évaluation, moins la contrepartie canadienne | 7 237 326 | 7 202 023 | 6 816 624 | 21 255 973 |
| Trésorier | 500 000 | 500 000 | 500 000 | 1 500 000 |
| Total partiel des activités normalisées | 53 012 512 | 42 141 798 | 25 512 237 | 120 666 547 |
| Total global | 187 244 740 | 159 284 767 | 99 036 509 | 445 566 017 |
| Australie | 0 | 0 | 152 497 | 152 497 |
| Autriche | 783 667 | 0 | 0 | 783 667 |
| France | 671 075 | 0 | 0 | 671 075 |
| Allemagne | 1 349 869 | 3 705 721 | 1 028 250 | 6 083 840 |
| Japon | 67 800 | 0 | 0 | 67 800 |
| PNUD | 62 425 117 | 54 216 500 | 29 064 016 | 145 705 634 |
| PNUE | 40 325 066 | 36 674 895 | 22 071 085 | 99 071 046 |
| ONUDI | 38 767 526 | 29 078 890 | 29 553 746 | 97 400 162 |
| Banque mondiale | 14 528 694 | 27 318 138 | 9 261 691 | 51 108 523 |
| Vérification des PGEH** | 588 600 | 588 600 | 588 600 | 1 765 800 |
| Projet pilote sur l’efficacité énergétique | 20 000 000 | 0 | 0 | 20 000 000 |
| Coûts associés au Secrétariat, au Comité exécutif et aux activités de surveillance et d’évaluation, moins la contrepartie canadienne | 7 237 326 | 7 202 023 | 6 816 624 | 21 255 973 |
| Trésorier | 500 000 | 500 000 | 500 000 | 1 500 000 |

* Y compris les coûts d’appui d’agence, le cas échéant.

** Le financement pour la préparation des rapports de vérification des PGEH pour les pays à faible volume de consommation est approuvé par le Comité exécutif sur une base annuelle.

I.1	État de la mise en œuvre du plan d’activités de 2023

# Le montant total du plan d’activités de 2023 s’élève à 187 244 740 $ US. Sur cette somme, 29 253 988 $ US ont été approuvés à la 92e réunion. En outre, des activités d’une valeur de 108 304 705 $ US seront examinées à la 93e réunion. Si les demandes de fonds pour les propositions de projets soumises sont toutes approuvées, il restera un solde de 49 686 047 $ US qui sera disponible pour le plan d’activités de 2023, comme indiqué dans le tableau 2.

Tableau 2. Plan d’activités général de 2023, approbations à la 92e réunion, projet recommandé à la 93e réunion et solde ($ US)*

| Postes budgétaires | Montant total figurant dans le plan d’activités | Approbations à la 92e réunion | Activités recommandées à la 93e réunion | Solde (au-dessus)/au-dessous |
| --- | --- | --- | --- | --- |
| Agences bilatérales | 2 872 411 | 687 988 | 1 657 265 | 527 158 |
| PNUD | 62 425 117 | 10 211 836 | 28 591 500 | 23 621 781 |
| PNUE | 40 325 066 | 6 644 731 | 22 767 524 | 10 912 811 |
| ONUDI | 38 767 526 | 8 419 645 | 24 134 585 | 6 213 296 |
| Banque mondiale | 14 528 694 | 2 681 989 | 15 997 224 | (4 150 519) |
| Vérification des PGEH | 588 600 | 573 900 | 0 | 14 700 |
| Projet pilote sur l’efficacité énergétique | 20 000 000 | 33 900 | 7 419 281 | 12 546 819 |
| Total partiel (agences) | 179 507 414 | 29 253 988 | 100 567 379 | 49 686 047 |
| Secrétariat, Comité exécutif, surveillance et évaluation (hormis la contrepartie canadienne) | 7 237 326 | 0 | 7 237 326 | 0 |
| Trésorier | 500 000 | 0 | 500 000 | 0 |
| Total partiel (coûts normalisés) | 7 737 326 | 0 | 7 737 326 | 0 |
| Total | 187 244 740 | 29 253 988 | 108 304 705 | 49 686 047 |

* Incluant les coûts de base.

# Le montant des propositions de projets recommandées à la 93e réunion, s’élevant à 100 567 379 $ US, est supérieur de 16 578 316 $ US à leur valeur dans le plan d’activités de 2023, dont 12 521 905 $ US sont liés aux propositions de projets non incluses dans le plan d’activités de 2023.

# Le montant des activités liées aux HFC recommandées à la 93e réunion est de 23 789 140 $ US, dont 3 182 574 $ US sont liés à des propositions de projets non incluses dans le plan d’activités de 2023. L’annexe I au présent document indique les projets liés aux HFC soumis par les agences bilatérales et les agences d’exécution à la 93e réunion.

# Le montant des projets recommandés au titre de la fenêtre de financement dédiée aux projets pilotes sur l’efficacité énergétique conformément à la décision 91/65 s’élève à 7 419 281 $ US. En tenant compte des approbations obtenues à la 92e réunion, d’un montant de 33 900 $ US, et des montants recommandés à la 93e réunion, les fonds encore disponibles au titre de cette fenêtre de financement sont de 12 546 819 $ US. L’annexe II au présent document indique les projets pilotes soumis par les agences bilatérales et les agences d’exécution à la 93e réunion conformément à la décision 91/65.

# Le montant des projets recommandés au titre de la fenêtre de financement pour la préparation des inventaires nationaux des banques de déchets de substances réglementées dans le cadre de la décision 91/66 est de 3 222 500 $ US ; il n’est pas inclus dans le plan d’activités de 2023. L’annexe III au présent document présente les activités de préparation de projets soumises par les agences bilatérales et les agences d’exécution à la 93e réunion conformément à la décision 91/66.

# En outre, concernant la décision 91/66, le paragraphe (c)(iii) impose que les projets bénéficiant de la fenêtre de financement mentionnée ci-dessus soient soumis à l’examen du Comité exécutif à partir de la 93e réunion et jusqu’à la 97e réunion (inclusive), étant entendu qu’ils seront inclus dans les plans d’activités correspondants avant leur approbation. Lors des délibérations avec les agences durant les réunions de réseau, les agences ont informé le Secrétariat du fait que les pays visés à l’article 5 avaient besoin de plus de temps pour comprendre les différents aspects de la gestion des substances réglementées indésirables et attendaient davantage d’informations de la part des agences au cours des réunions de réseau avant d’accepter d’inclure ces activités dans leurs plans d’activités respectifs ; ceci a pris plus de temps que prévu. D’après les nouvelles contributions et les consultations qui se sont tenues durant ces derniers mois, y compris pendant la trente-cinquième réunion des Parties en octobre 2023, les pays ont exprimé leur envie de soumettre des projets au titre de cette fenêtre de financement. Afin de faciliter la soumission de projets en lien avec la préparation des inventaires des banques de substances réglementées usagées ou indésirables, le Comité exécutif, à titre exceptionnel, pourrait souhaiter autoriser les agences bilatérales et les agences d’exécution à soumettre en 2024 des activités de préparation de projet au titre de la fenêtre de financement établie conformément à la décision 91/66, même lorsque ces activités ne sont pas incluses dans les plans d’activités.

# Des propositions de projets d’une valeur de 54 097 185 $ US qui étaient incluses dans le plan d’activités de 2023 n’ont pas été soumises à la 93e réunion. Ces propositions ont été incluses dans le plan d’activités général du Fonds multilatéral pour 2024–2026.

# I.2	Engagements à terme

# Le montant total des engagements à terme actuellement en vigueur pour des accords pluriannuels (APA) sur la période de 2023 à 2031 est de 314,16 millions de $ US, en supposant que les demandes de financement soumises à la 93e réunion soient approuvées en principe, comme indiqué dans le tableau 3.

Tableau 3. Engagements à terme (2023–2031) (milliers de $ US)

| Description | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approuvés en principe | 68 086 | 53 334 | 51 015 | 42 781 | 10 187 | 5 852 | 4 733 | 8 163 | 57 | 244 207 |
| Soumis à la 93e réunion | 27 918 | 0 | 10 122 | 14 050 | 10 623 | 24 | 5 528 | 1 683 | 0 | 69 949 |
| Total | 96 005 | 53 334 | 61 137 | 56 831 | 20 811 | 5 876 | 10 261 | 9 846 | 57 | 314 156 |

# II.	Répartition des ressources pour le triennat 2021–2023

# Au 8 novembre 2023, le solde à la disposition du Fonds multilatéral s’élevait à 277 322 098 $ US, avec des contributions impayées de 52 864 962 $ US pour le triennat 2021–2023, dont 23 281 488 $ US qui ne devraient pas être perçues. À compter du 8 novembre 2023, les intérêts potentiels à courir et la perte potentielle due au mécanisme de taux de change fixe (FERM) sont estimés respectivement à 5 849 812 $ US et 753 989 $ US. De plus, les fonds restitués pour les projets achevés et les intérêts restitués à la 93e réunion s’élèvent respectivement à 4 669 316 $ US et 505 720 $ US. En conséquence, le financement total disponible pour de nouvelles allocations à la 93e réunion s’élève à 317 176 431 $ US.

# Étant donné le montant du financement recommandé pour les projets soumis à la 93e réunion, d’un montant de 100 567 379 $ US, et étant donné le budget du Secrétariat, s’élevant à 7 737 326 $ US, les ressources disponibles à l’issue du triennat 2021–2023 seront de 208 871 726 $ US. De plus, la cinquième Réunion extraordinaire des Parties a également noté que 246 millions de $ US, correspondant au solde des fonds versés au Fonds multilatéral au cours du triennat 2018–2020, seront utilisés après 2023 pour appuyer la mise en œuvre du Protocole de Montréal (décision Ex.V/1). Par conséquent, les ressources totales disponibles pour le triennat 2024–2026 sont de 454 871 726 $ US, comme indiqué dans le tableau 4.

Tableau 4. Répartition des ressources pour le triennat 2021–2023 ($ US)

| Description |  | Montant ($ US) |
| --- | --- | --- |
| Fonds disponibles |  |  |
| Solde disponible à compter du 8 novembre 2023 | (a) | 277 322 098 |
| Contributions impayées pour 2021 à 2023 | (b) | 52 864 962 |
| Contributions impayées qui ne devraient pas être perçues | (c) | (23 281 488) |
| Potentiels intérêts courus à compter du 8 novembre 2023 | (d) | 5 849 812 |
| Potentielle perte due au FERM à compter du 8 novembre 2023 | (e) | (753 989) |
| Fonds restitués à la 93e réunion | (f) | 4 669 316 |
| Intérêts restitués à la 93e réunion | (g) | 505 720 |
| Financement total disponible | (h = a+b+c+d+e+f+g) | 317 176 431 |
| Dépenses |  |  |
| Projets recommandés à la 93e réunion | (i) | 100 567 379 |
| Secrétariat / Comité exécutif / Suivi / Trésorier | (j) | 7 737 326 |
| Dépenses totales | (k = i+j) | 108 304 705 |
| Ressources disponibles à la fin de 2023 | (l = h-k) | 208 871 726 |
| Report de solde du triennat 2018–2020 à utiliser après 2023 | (m) | 246 000 000 |
| Ressources totales disponibles pour le triennat 2024–2026 | (n= l+m) | 454 871 726 |

# III.	Recommandation

# Le Comité exécutif pourrait souhaiter :

## Prendre note :

### De la mise à jour sur l’état de la mise en œuvre du plan d’activités général du Fonds multilatéral pour la période 2023–2025, présentée dans le document UNEP/OzL.Pro/ExCom/93/23 ;

### Du fait que le montant totale des activités demandées à la 93e réunion s’élève à 100 567 379 $ US (dont 23 789 140 $ US pour les activités liées aux HFC, 7 419 281 $ US pour les projets pilotes sur l’efficacité énergétique et 3 222 500 $ US pour la préparation des inventaires nationaux des banques de déchets de substances réglementées), parmi lesquels 12 521 905 $ US correspondent aux propositions de projet non incluses dans le plan d’activités de 2023 ; et

## Autoriser, à titre exceptionnel, les agences bilatérales et les agences d’exécution à soumettre, durant l’année 2024, des projets pour la préparation d’inventaires nationaux des banques de déchets de substances réglementées au titre de la fenêtre de financement établie conformément à la décision 91/66, même lorsque ces projets ne sont pas inclus dans les plans d’activités des agences.

Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 93RD MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Albania | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 50,000 | 6,500 |
| Albania | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 129,390 | 9,057 |
| Bolivia (Plurinational State of) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 40,500 | 5,265 |
| Bolivia (Plurinational State of) | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 153,500 | 10,745 |
| Brazil | Germany | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 40,000 | 5,200 |
| Brazil | UNDP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 126,500 | 8,855 |
| Brazil | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 63,500 | 4,445 |
| Cambodia | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 123,810 | 11,143 |
| Cambodia | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 126,300 | 16,419 |
| Chile | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 752,607 | 52,683 |
| Chile | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 123,900 | 16,107 |
| Colombia | UNDP | PRP | KIP | Preparation of a KIP investment project in the air-conditioning manufacturing sector | 50,000 | 3,500 |
| Colombia | UNDP | PRP | KIP | Preparation of a KIP investment project in the refrigeration manufacturing sector | 150,000 | 10,500 |
| Congo (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 13,750 | 1,788 |
| Congo (the) | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 67,750 | 6,098 |
| Cuba | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 145,455 | 10,182 |
| Cuba | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 14,545 | 1,018 |
| Dominican Republic (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 120,774 | 15,701 |
| Dominican Republic (the) | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 50,050 | 4,505 |
| Dominican Republic (the) | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 320,935 | 22,465 |
| Dominican Republic (the) | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 44,171 | 3,092 |
| Ecuador | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 292,600 | 20,482 |
| Egypt | UNDP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 40,000 | 2,800 |
| Egypt | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 180,000 | 12,600 |
| Eritrea | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 91,000 | 11,830 |
| Eritrea | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 39,000 | 2,730 |
| Georgia | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 130,000 | 16,900 |
| Ghana | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 125,000 | 11,250 |
| Ghana | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 51,000 | 6,630 |
| Ghana | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 7,500 | 675 |
| Ghana | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 4,500 | 585 |
| Grenada | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 29,670 | 2,670 |
| Grenada | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 42,830 | 5,568 |
| India | UNDP | INV | KIP | Conversion from R-407C and R-410A to HFC-32 in the manufacturing of light commercial air-conditioning packaged and ducted air-conditioning units at Voltas Limited | 422,561 | 29,579 |
| India | UNDP | INV | KIP | Conversion of the manufacturing of commercial refrigeration appliances at Rockwell Industries Limited from HFC-134a to propane (R-290) | 423,765 | 29,664 |
| India | UNDP | INV | KIP | Demonstration/conversion from R-404A and R-407C to CO2 transcritical heat pump technology in the food processing and cold storage refrigeration equipment manufacturing sector at Mech Air Industries | 322,452 | 22,572 |
| India | UNDP | PRP | KIP | Preparation of a demonstration project in the manufacture of compressors for mobile air-conditioning manufacturing sector | 30,000 | 2,100 |
| Jordan | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 2,540,680 | 177,848 |
| Kenya | Germany | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 95,000 | 12,350 |
| Kenya | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 95,000 | 12,350 |
| Kyrgyzstan | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 51,000 | 4,590 |
| Kyrgyzstan | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 30,000 | 3,900 |
| Lebanon | UNDP | PRP | PHA | Preparation of a KIP investment project in the refrigeration manufacturing sector | 70,000 | 4,900 |
| Malawi | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 39,000 | 5,070 |
| Malawi | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 29,000 | 2,610 |
| Malaysia | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 3,042,912 | 213,004 |
| Mali | UNDP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 35,000 | 2,450 |
| Mali | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 135,000 | 17,550 |
| Mexico | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring) | 79,905 | 5,593 |
| Mexico | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring) | 12,695 | 1,574 |
| Mexico | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring) | 283,418 | 19,839 |
| Mexico | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (foam sector plan) | 888,833 | 62,218 |
| Mexico | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 465,000 | 32,550 |
| Mexico | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 215,100 | 26,669 |
| Mexico | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 4,801,972 | 336,138 |
| Mongolia | ONUDI | PRP | KIP | Preparation of a KIP investment project in the foam sector | 80,000 | 5,600 |
| Nicaragua | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 40,000 | 5,200 |
| Nicaragua | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 159,000 | 14,310 |
| Niger (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I) | 15,000 | 1,950 |
| Niger (the) | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I) | 35,000 | 850 |
| North Macedonia | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 103,555 | 9,320 |
| Panama | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 331,100 | 23,177 |
| Peru | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 283,140 | 19,820 |
| Republic of Moldova (the) | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 130,000 | 16,900 |
| Saint Vincent and the Grenadines | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 70,000 | 9,100 |
| Saint Vincent and the Grenadines | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 30,000 | 2,100 |
| Sri Lanka | UNDP | PRP | KIP | Preparation of a KIP investment project in the refrigeration manufacturing sector | 80,000 | 5,600 |
| Thailand | IBRD | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 220,000 | 15,400 |
| Trinidad and Tobago | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 496,973 | 34,788 |
| Trinidad and Tobago | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 46,276 | 3,239 |
| Turkmenistan | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 106,000 | 7,420 |
| Turkmenistan | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 10,000 | 700 |
| Viet Nam | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (manufacturing sector) | 289,220 | 20,245 |
| Viet Nam | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 119,265 | 8,349 |
| Viet Nam | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 35,533 | 4,244 |
| Viet Nam | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 984,000 | 68,880 |
| Viet Nam | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 426,163 | 50,906 |
| Viet Nam | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (technical assistance and policy) | 165,307 | 11,571 |

Annex II

Pilot projects for energy efficiency (decision 91/65) 
SUBMITTED TO THE 93RD MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Bolivia (Plurinational State of) | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 96,000 | 8,640 |
| Chile | UNDP | PRP | EEF | Preparation of a pilot project for the use of R-744 (carbon dioxide) as an alternative refrigerant in heat pumps in industrial refrigeration (decision 91/65) | 30,000 | 2,100 |
| China | UNIDO | DEM | EEF | Demonstration project of replacing HFC-134a with R-744 in the field of electric vehicles (decision 91/65) | 1,371,500 | 96,005 |
| Ecuador | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 190,000 | 17,100 |
| Egypt | UNIDO | DEM | EEF | Energy efficiency pilot project in the refrigeration and air-conditioning sector (decision 91/65) | 285,000 | 19,950 |
| India | Germany | DEM | EEF | Design and development of a pilot scale energy-efficient rotary compressor along with microchannel heat exchanger compatible with R-290 technology at Godrej & Boyce Mfg. Ltd., for use in manufacturing of room air conditioners (decision 91/65) | 1,853,795 | 213,918 |
| India | UNDP | DEM | EEF | Conversion of the manufacturing of commercial refrigeration appliances at Rockwell Industries Limited from HFC-134a to propane (R-290) (technical assistance to enhance the energy efficiency of the converted equipment) (decision 91/65) | 150,000 | 13,500 |
| Kenya | Germany | PRP | EEF | Preparation for a pilot project on energy efficiency (decision 91/65) | 30,000 | 3,900 |
| Kyrgyzstan | UNEP | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 206,000 | 26,780 |
| Malaysia | IBRD | PRP | EEF | Preparation for a pilot project on energy efficiency in stand-alone commercial refrigeration sector (decision 91/65) | 30,000 | 2,100 |
| Mexico | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 938,620 | 65,703 |
| Nicaragua | UNEP | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 30,000 | 3,900 |
| Nicaragua | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 66,000 | 5,940 |
| Nigeria | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 145,000 | 13,050 |
| South Africa | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 1,120,000 | 78,400 |
| Togo | Germany | PRP | EEF | Project preparation for energy efficiency-related activities (decision 91/65) | 30,000 | 3,900 |
| Turkmenistan | UNIDO | DEM | EEF | Pilot project for maintaining and enhancing energy efficiency of replacement technologies and equipment (decision 91/65) | 142,000 | 12,780 |
| Viet Nam | IBRD | PRP | EEF | Preparation for a pilot project on energy efficiency in the air-conditioning sector (decision 91/65) | 30,000 | 2,100 |
| Global | UNDP | PRP | EEF | Preparation for a pilot project for digital monitoring and management tools to enhance energy efficiency and reduce emission of greenhouse gases in the space cooling and cold chain sectors in Colombia, Lebanon, Panama, Sri Lanka, and Trinidad and Tobago | 80,000 | 5,600 |

Annex III

Project preparation for national inventories of banks 
of waste-controlled substances (decision 91/66) 
SUBMITTED TO THE 93RD MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Albania | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Armenia | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Benin | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Bolivia (Plurinational State of) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 35,000 | 4,550 |
| Bolivia (Plurinational State of) | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 55,000 | 3,850 |
| Burkina Faso | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Burundi | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Cameroon | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Costa Rica | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Cuba | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Dominican Republic (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Ecuador | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Egypt | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| El Salvador | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Guatemala | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 35,000 | 4,550 |
| Guatemala | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 55,000 | 3,850 |
| Honduras | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 35,000 | 4,550 |
| Honduras | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 55,000 | 3,850 |
| Jamaica | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Kenya | Germany | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Liberia | Germany | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Mexico | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Montenegro | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 4,900 |
| Namibia | Germany | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Nicaragua | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 35,000 | 4,550 |
| Nicaragua | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 55,000 | 3,850 |
| North Macedonia | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 5,600 |
| Peru | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Republic of Moldova (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Seychelles | Germany | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Togo | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Trinidad and Tobago | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Turkmenistan | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Uruguay | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Venezuela (Bolivarian Republic of) | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Viet Nam | IBRD | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Yemen | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 13,000 |

UNEP/OzL.Pro/ExCom/93/1

Phase II des PGEH pour la Bolivie (État plurinational de) (PNUE et ONUDI), l’Équateur (ONUDI), le Guatemala (PNUE et ONUDI), le Mozambique (PNUE) et la Macédoine du Nord (ONUDI) ; phase III des PGEH pour le Viet Nam (Banque mondiale) ; une préparation de projet pour la phase III des PGEH pour le Pérou (PNUD) ; une préparation de projet pour un projet d’investissement dans le cadre du PGEH pour la Thaïlande (Banque mondiale) ; une préparation de projet pour un projet de démonstration pour l’Inde (PNUD) ; préparation de cinq KIP pour des projets d’investissement pour la Colombie (2) (PNUD), le Liban (PNUD), la Mongolie (ONUDI) et le Sri Lanka (PNUD) ; préparation de huit projets pour la phase I des KIP pour le Brésil (Allemagne, PNUD et ONUDI), le Kenya (Allemagne), le Mali (PNUD et PNUE) et Saint-Vincent-et-les Grenadines (PNUE et ONUDI) ; trois projets d’investissement en lien avec les HFC pour l’Inde (PNUD) ; 12 projets sur l’efficacité énergétique au titre de la décision 89/6 pour l’Albanie (ONUDI), le Bénin (ONUDI), la Bolivie (État plurinational de) (PNUE et ONUDI), l’Équateur (ONUDI), la Grenade (ONUDI), le Guatemala (PNUE et ONUDI), le Lesotho (Allemagne), le Libéria (Allemagne), la Namibie (Allemagne) et les Seychelles (Allemagne) ; phase I des KIP pour la Bolivie (État plurinational de) (PNUE), le Congo (PNUE et ONUDI), la République dominicaine (PNUE et ONUDI), le Kirghizistan (PNUD), le Nicaragua (PNUE), le Niger (PNUE et ONUDI) et le Pérou (PNUD) ; projet de renforcement des institutions pour la Bolivie (État plurinational de) (PNUE) ; et préparation de 37 projets pour des inventaires nationaux des banques de déchets de substances réglementées au titre de la décision 91/66 conformément à l’annexe III.

Ces activités incluent : 104 activités liées aux HCFC pour 40 pays (32,37 millions de $ US), 49 activités liées aux HFC pour 34 pays (12,26 millions de $ US) et 28 activités de renforcement des institutions (9,47 millions de $ US).

UNEP/OzL.Pro/ExCom/93/25.

UNEP/OzL.Pro/ExCom/93/3.

UNEP/OzL.Pro/ExCom/93/4 et UNEP/OzL.Pro/ExCom/93/95.

UNEP/OzL.Pro/ExCom/93/6 et UNEP/OzL.Pro/ExCom/93/47.