| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/93/19 20 November 2023 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-third Meeting

Montreal, 15-19 December 2023

Item 7(a)(vi) of the provisional agenda

PROGRESS REPORT OF THE WORLD BANK AS AT 31 DECEMBER 2022

Introduction

# This document presents the progress report of the World Bank as at 31 December 2022.

# The progress report of the World Bank includes the status of implementation of projects, including five HFC-related projects that have been funded under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment.

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2022, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs which are measured in CO2-eq tonnes.

# This document consists of the following sections:

## I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2022 and cumulative since 1991 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs). It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee.

## II.	Projects approved for Annex F substances (HFCs) under the additional voluntary contributions for fast-start support for HFC phase-down.

III.	Recommendation.

I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund

I.1	Progress in implementation of projects for 2022 and cumulative since 1991

# As of 31 December 2022, the Executive Committee had approved US $1.32 billion in projects for the World Bank, consisting of US $1.19 billion for the implementation of investment and non-investment projects and US $124.96 million for agency support costs, as shown in table 1.

# Table 1. Approved funding by sector for the World Bank as at 31 December 2022

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 22,984,030 |
| Destruction | 400,000 |
| Foam | 136,059,064 |
| Halon | 70,221,038 |
| HFC phase-down plan | 665,000 |
| Fumigants | 5,837,887 |
| Multiple sectors | 2,341,168 |
| Other | 5,059,360 |
| Phase-out plan | 212,206,926 |
| Process agent | 114,342,497 |
| Production | 400,893,496 |
| Refrigeration | 180,259,970 |
| Several | 29,413,466 |
| Solvents | 10,237,394 |
| Sterilant | 661,227 |
| Sub-total | 1,191,582,522 |
| Agency support costs | 124,964,722 |
| Total | 1,316,547,244 |

# In 2022, eight new projects and activities were approved. This level of funding is expected to result in the phase-out of 313,381 ODP tonnes of consumption and production of controlled substances. Annex I shows the status of project implementation per country in 2022.

# Table 2 shows the status of project implementation including fund disbursement per project type as at 31 December 2022. Annex II presents analytical information per year since 1991.

Table 2. Status of project implementation by type as at 31 December 2022

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 29 | 29 | 100 | 1,627,732 | 1,627,732 | 0 | 100 |
| Demonstration | 8 | 8 | 100 | 6,172,901 | 6,172,901 | 0 | 100 |
| Institutional strengthening (IS) | 51 | 48 | 94 | 10,013,716 | 9,413,540 | 600,176 | 94 |
| Investment | 640 | 627 | 98 | 1,132,361,745 | 1,101,261,445 | 31,100,300 | 97 |
| Project preparation | 299 | 291 | 97 | 27,443,320 | 26,765,291 | 678,029 | 98 |
| Technical assistance | 76 | 74 | 97 | 13,657,342 | 13,095,419 | 561,923 | 96 |
| Training | 4 | 4 | 100 | 305,766 | 305,766 | 0 | 100 |
| Total | 1,107 | 1,081 | 98 | 1,191,582,522 | 1,158,642,094 | 32,940,428 | 97 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

# Implementation of projects and activities by the World Bank for 2022 and cumulative since 1991 up to 31 December 2022, is summarized as follows:

## Phase-out: In 2022, zero ODP tonnes of consumption of controlled substances were phased out and an additional 98.2 ODP tonnes of consumption and 5,947 ODP tonnes of production of controlled substances were approved for phase-out. Since 1991, 148,230 ODP tonnes of consumption of controlled substances and 187,996 ODP tonnes of production of controlled substances had been phased out, of an expected total of 313,381 ODP tonnes from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2022, US $7.82 million was disbursed and US $8.70 million was planned for disbursement based on the 2021 progress report, representing a rate of disbursement of 90 per cent of that planned. Cumulatively, US $1.16 billion had been disbursed out of the total US $1.19 billion approved for disbursement (excluding agency support costs), representing a rate of disbursement of 97 per cent. In 2022, US $23.59 million was approved for implementation;

## Cost-effectiveness (in ODP): Since 1991, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $5.45/kg and for the production sector was US $4.78/kg. The average cost-effectiveness of investment projects per ODP tonne was US $3.22/kg for completed projects and US $7.03/kg for ongoing projects;

## Number of projects completed: In 2022, two projects were completed. Since 1991, 1,081 projects of the 1,107 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 98 per cent;

## Speed of delivery – investment projects: In 2022, one investment project was completed with a duration of 69 months after its approval. Since 1991, the average time for completion of investment projects has been 40 months after their approval. First disbursements under these projects occurred, on average, 24 months after they had been approved;

## Speed of delivery – non-investment projects: In 2022, one non-investment project was completed with a duration of 13 months after its approval. Since 1991, the average time for completion of non-investment projects has been 35 months after their approval. First disbursements under these projects occurred, on average, 22 months after they had been approved;

## Project preparation: Of the 299 project preparation activities approved by the end of 2022, 291 have been completed, leaving eight ongoing activities. The World Bank did not complete any preparation activities in 2022;

## Implementation delays: A total of 26 projects were under implementation at the end of 2022, experiencing, on average, a delay of 11 months. Four of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation, and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2022, five MYAs for HCFC phase-out management plans (HPMPs) and one HCFC production phase-out management plan (HPPMP) were under implementation. Since 1991, 40 MYAs have been approved and 34 MYAs have been completed, representing a completion rate of 85 per cent.

# Table 3 summarized progress made by the World Bank since 1991.

## Table 3. Progress made by the World Bank since 1991

| Phase out achieved |  | Disbursement (US $) | Average CE (US$/kg) |  | Number of projects |  | Speed of delivery for completion (months) |  | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes* | CO2-eq tonnes |  | Consump- tion | Produc- tion | Approved | Completed | Investment | Non- investment |  | Approved | Completed |
| 336,226 | 0 | 1,158,642,094 | 5.45 | 4.78 | 1,107 | 1,081 | 40 | 35 | 11 | 40 | 34 |

*Consumption and production

HFC-related projects

# As of 31 December 2022, the Executive Committee had approved five HFC preparation projects under regular contributions amounting to US $665,000 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 5 to 9.

Table 4. HFC-related projects approved under regular contributions

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Project preparation | 5 | 0 | 0 | 665,000 | 141,971 | 523,029 | 21 |

* Excludes agency support costs.

# Of the total cumulative funding approved of US $665,000, US $141,971 had been disbursed, representing a disbursement rate of 21 per cent. The five ongoing preparation activities are expected to be completed in 2023 and 2024.

I.2	Issues identified in project implementation in 2022

# Further to the review process, several issues were discussed and satisfactorily addressed, except for issues on four projects related to components of MYAs, classified as projects with implementation delays that are subject to procedures for project cancellation, in line with decision 84/45(c). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 94th meeting.

# Details of progress in implementation of projects associated with the HPMPs for China (polyurethane foam sector plan) and Viet Nam have been submitted to the 93rd meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. Outstanding issues for the remaining ongoing projects not included in annex III to the present document, and requests for extension of dates of completion, are addressed below.

# Of the 15 ongoing projects, excluding IS and project preparation, seven projects have revised planned dates of completion since the 2021 progress report.

# In line with decision 82/11(b), the World Bank has requested the extension of the duration of three projects, as shown in table 5.

Table 5. Projects for which an extension of the completion dates has been requested

| Country/ project code | Project title | Disburse-ment (%) | Status/issues | Original date of completion | Date of completion requested |
| --- | --- | --- | --- | --- | --- |
| Jordan JOR/PHA/77/INV/99 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | 86 | Additional time required for completing the procurement and distribution of low-global-warming-potential pre-blended polyol to foam enterprises; these activities were delayed due to challenges related to the COVID-19 pandemic and supply challenges due to small quantities needed in the country. | Dec-23 | Dec-24 |
| Jordan JOR/PHA/84/INV/108 | HCFC phase-out management plan (stage II, second tranche) (polyurethane foam sector, project management and coordination) | 27 |  |  |  |
| Jordan JOR/PHA/88/PRP/110 | HCFC phase-out management plan (stage II, third tranche) | 0 |  |  |  |

Gender mainstreaming

# The World Bank reported that in 2022, two countries were reporting on gender mainstreaming: China (stage II of the HPMP (polyurethane rigid foam sector plan) and HPPMP); and Malaysia (preparation of the Kigali HFC implementation plan (KIP)).

# For the projects in China, gender balance in meetings and activities is now being tracked. In the training organised by the Foreign Environmental Cooperation Centre in China on stage II sub-project implementation, about 50 per cent of the participants were women. Further, 40 per cent of individuals in charge of each sub-project at the enterprise level are women. In the case of Malaysia, data on the number of female employees is collected during the KIP surveys.

II.	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down

# As of 31 December 2022, the Executive Committee had approved five HFC-related projects under the additional voluntary contributions amounting to US $960,180 (excluding agency support costs). A summary of the status of these projects is presented in table 6.

# Table 6. Status of approved HFC-related projects as of the end of 2022

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment*** | 1 | 1 | 100 | 183,514 | 183,514 | 0 | 100 |
| Project preparation | 1 | 1 | 100 | 30,000 | 30,000 | 0 | 100 |
| Enabling activities | 3 | 3 | 100 | 746,666 | 744,080 | 2,586 | 99.7 |
| Total | 5 | 5 | 100 | 960,180 | 957,594 | 2,586 | 99.7 |

* Excludes transferred projects.

** Excludes agency support costs.

*** 8.8 mt (12,555 CO2-eq tonnes) of HFCs was approved and phased out.

# As of the end of 2022, all five activities approved had been completed.

# Of the total cumulative funding approved of US $960,180, US $957,594 had been disbursed, representing a disbursement rate of 99.7 per cent.

III.	Recommendation

# The Executive Committee may wish:

## To note the progress report of the World Bank as at 31 December 2022 contained in document UNEP/OzL.Pro/ExCom/93/19;

## To approve the extension, to 31 December 2024, of the completion date of stage II of the HCFC phase‑out management plan for Jordan (first tranche (polyurethane foam sector) (JOR/PHA/77/INV/99), second tranche (polyurethane foam sector, project management and coordination) (JOR/PHA/84/INV/108) and third tranche (JOR/PHA/88/PRP/110)), to allow for completion of the remaining ongoing activities as reflected in table 5 of document UNEP/OzL.Pro/ExCom/93/19; and

## To approve the recommendations related to ongoing projects with specific issues contained in annex III to the present document.

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR THE WORLD BANK

PER COUNTRY FOR 2022

# Table 1 of annex I presents the status of project implementation by country for 2022 in achieved phased out, planned and achieved disbursements and project completion.

Table 1. Status of project implementation by the World Bank for 2022

| Country | Phased out in 2022 (ODP tonnes)* | Phased out in 2022 (CO2-eq tonnes)* | Estimated funds disbursed in 2022 (US$) | Funds disbursed in 2022 (US$) | Percentage of funds disbursed over estimation in 2022 | Percentage of planned projects completed in 2022** |
| --- | --- | --- | --- | --- | --- | --- |
| China | 0 | 0 | 5,000,000 | 5,800,000 | 116 | 50 |
| Indonesia | 0 | 0 | 600,000 | 275,491 | 46 | 0 |
| Jordan | 0 | 0 | 404,600 | 360,777 | 89 | 0 |
| Malaysia | 0 | 0 | 140,000 | 100,896 | 72 |  |
| Thailand | 0 | 0 | 1,148,175 | 409,875 | 36 | 0 |
| Viet Nam | 0 | 0 | 1,408,859 | 873,487 | 62 | 0 |
| Global*** |  |  |  |  |  | 100 |
| Grand total | 0 | 0 | 8,701,634 | 7,820,526 | 90 | 20 |

* No phase-out in 2022.

** For projects that were planned to be completed in 2022.

*** 2022 core unit.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR THE WORLD BANK

PER YEAR AS AT 31 DECEMBER 2022

# Table 1 of annex II presents an overview of the status of project implementation by year. All projects and activities approved between 1991 and 2015, and 2017, have now been completed.

Table 1. Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1991 | 42 | 42 | 100 | 5,429,404 | 5,429,404 | 0 | 100 |
| 1992 | 76 | 76 | 100 | 28,047,705 | 28,047,705 | 0 | 100 |
| 1993 | 79 | 79 | 100 | 42,538,405 | 42,538,405 | 0 | 100 |
| 1994 | 91 | 91 | 100 | 41,081,267 | 41,081,267 | 0 | 100 |
| 1995 | 112 | 112 | 100 | 47,224,186 | 47,224,186 | 0 | 100 |
| 1996 | 55 | 55 | 100 | 29,319,479 | 29,319,479 | 0 | 100 |
| 1997 | 95 | 95 | 100 | 56,173,102 | 56,173,103 | -1 | 100 |
| 1998 | 59 | 59 | 100 | 35,959,418 | 35,959,417 | 1 | 100 |
| 1999 | 73 | 73 | 100 | 64,173,138 | 64,173,138 | 0 | 100 |
| 2000 | 67 | 67 | 100 | 36,982,134 | 36,982,133 | 1 | 100 |
| 2001 | 29 | 29 | 100 | 55,212,853 | 55,212,854 | -1 | 100 |
| 2002 | 32 | 32 | 100 | 64,357,778 | 64,357,778 | 0 | 100 |
| 2003 | 24 | 24 | 100 | 72,734,119 | 72,734,119 | 0 | 100 |
| 2004 | 29 | 29 | 100 | 77,111,770 | 77,111,770 | 0 | 100 |
| 2005 | 28 | 28 | 100 | 68,592,865 | 68,592,865 | 0 | 100 |
| 2006 | 22 | 22 | 100 | 64,473,260 | 64,473,260 | 0 | 100 |
| 2007 | 25 | 25 | 100 | 66,005,270 | 66,005,270 | 0 | 100 |
| 2008 | 28 | 28 | 100 | 39,934,666 | 39,934,666 | 0 | 100 |
| 2009 | 22 | 22 | 100 | 25,529,554 | 25,529,554 | 0 | 100 |
| 2010 | 16 | 16 | 100 | 1,148,623 | 1,148,623 | 0 | 100 |
| 2011 | 10 | 10 | 100 | 44,201,956 | 44,201,956 | 0 | 100 |
| 2012 | 10 | 10 | 100 | 11,698,145 | 11,698,145 | 0 | 100 |
| 2013 | 7 | 7 | 100 | 43,736,999 | 43,736,999 | 0 | 100 |
| 2014 | 13 | 13 | 100 | 28,336,509 | 28,336,509 | 0 | 100 |
| 2015 | 13 | 13 | 100 | 62,990,648 | 62,990,648 | 0 | 100 |
| 2016 | 18 | 17 | 94 | 12,601,632 | 12,527,501 | 74,131 | 99 |
| 2017 | 3 | 3 | 100 | 1,651,291 | 1,651,291 | 0 | 100 |
| 2018 | 7 | 1 | 14 | 26,408,870 | 24,797,653 | 1,611,217 | 94 |
| 2019 | 3 | 1 | 33 | 2,579,179 | 1,655,518 | 923,661 | 64 |
| 2020 | 2 | 1 | 50 | 2,067,012 | 2,067,012 | 0 | 100 |
| 2021 | 9 | 1 | 11 | 9,687,863 | 2,949,865 | 6,737,998 | 30 |
| 2022 | 8 | 0 | 0 | 23,593,422 | 0 | 23,593,422 | 0 |
| Total | 1,107 | 1,081 | 98 | 1,191,582,522 | 1,158,642,094 | 32,940,428 | 97 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

Annex III

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR THE WORLD BANK

| Country/project code | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- |
| Indonesia IDS/PHA/81/INV/214 | HCFC phase-out management plan (stage II, second tranche) (foam sector) | 80 | 12 months delays | To request the World Bank to report to the 94th meeting on this project with implementation delays |
| Jordan JOR/PHA/77/INV/99 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | 86 | 12 months delays | To request the World Bank to report to the 94th meeting on this project with implementation delays |
| Thailand THA/PHA/82/INV/179 | HCFC phase-out management plan (stage II, first tranche) (spray foam sector) | 6 | 12 months delays | To request the World Bank to report to the 94th meeting on this project with implementation delays |
| Thailand THA/PHA/82/TAS/177 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector and project management unit) | 31 | 12 months delays | To request the World Bank to report to the 94th meeting on this project with implementation delays |

UNEP/OzL.Pro/ExCom/93/1

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database that is available upon request.

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 93rd meeting.

Ongoing projects are all projects that were under implementation as at 31 December 2022. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

In line with decision 84/12(b), a detailed progress report providing an overview of the objectives, status of implementation, key findings and lessons learned, the amounts of HFC phased out where applicable, the level of funds approved and disbursed and potential challenges in completing the projects and activities, is presented in the consolidated progress report (UNEP/OzL.Pro/ExCom/93/14).

All the controlled substances under these projects were ozone-depleting substances.

All the controlled substances under these projects were ozone-depleting substances.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61).

UNEP/OzL.Pro/ExCom/93/47

UNEP/OzL.Pro/ExCom/93/93

Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.

The Executive Committee requested bilateral and implementing agencies to provide a brief report on key gender mainstreaming results achieved as part of their annual progress reports, as of 2023, on the basis of the information available to them (decision 90/48(d)).

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.