| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/96/14 8 May 2025 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-sixth Meeting

Montreal, 26-30 May 2025

Item 8(a) of the provisional agenda

UPDATE ON THE STATUS OF IMPLEMENTATION OF THE 2025–2027 CONSOLIDATED BUSINESS PLAN OF THE MULTILATERAL FUND

- Introduction

# This document consists of:

## Part I:	An update on the status of the implementation of the 2025–2027 business plan

## Part II:	Resource allocation for the 2024–2026 triennium

Recommendation

## UPDATE ON THE STATUS OF THE IMPLEMENTATION OF THE 2025–‍2027 BUSINESS PLAN

# At its 95th meeting, the Executive Committee endorsed the 2025–2027 consolidated business plan of the Multilateral Fund. In response to decision 95/27, the Secretariat adjusted the consolidated 2025–‍2027 business plan, as shown in table 1.

Table 1. Resource allocation of the adjusted 2025–2027 consolidated business plan of the Multilateral Fund (US $)*

| Description | 2025 | 2026 | 2027 | Total |
| --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 56,520,741 | 67,316,489 | 33,313,171 | 157,150,401 |
| HPMP stage II – preparation | 110,900 | 0 | 0 | 110,900 |
| HPMP stage II | 1,913,851 | 1,690,836 | 775,205 | 4,379,892 |
| HPMP stage III – preparation | 318,340 | 42,800 | 0 | 361,140 |
| HPMP stage III | 9,221,502 | 6,720,339 | 22,499,633 | 38,441,474 |
| HPMP stage IV | 0 | 3,691,000 | 5,537,000 | 9,228,000 |
| HCFC production phase-out management plan (HPPMP) stage III – preparation | 321,000 | 0 | 0 | 321,000 |
| HPPMP stage III | 0 | 0 | 23,540,000 | 23,540,000 |
| HPMP verification** | 588,600 | 588,600 | 588,600 | 1,765,800 |
| HPMP – energy efficiency (decision 89/6) | 3,328,995 | 558,112 | 76,000 | 3,963,107 |
| HCFC activities subtotal | 72,323,929 | 80,608,176 | 86,329,609 | 239,261,714 |
| HFC activities |  |  |  |  |
| Approved Kigali HFC implementation plans (KIPs) | 10,127,716 | 6,689,529 | 25,853,153 | 42,670,398 |
| Approved HFC-23 emission control | 519,900 | 584,100 | 552,371 | 1,656,371 |
| Enabling activities for HFC phase-down | 428,000 | 0 | 0 | 428,000 |
| Kigali HFC implementation plan for the production sector stage I – preparation | 321,000 | 0 | 0 | 321,000 |
| KIP stage I – preparation | 3,378,021 | 926,893 | 100,000 | 4,404,913 |
| KIP stage I | 24,739,456 | 16,818,239 | 39,876,189 | 81,433,885 |
| KIP stage I – investment | 0 | 339,000 | 0 | 339,000 |
| HFC investment preparation | 85,600 | 0 | 0 | 85,600 |
| HFC investment | 0 | 96,000 | 0 | 96,000 |
| HFC demonstration | 650,000 | 0 | 0 | 650,000 |
| HFC-23 investment | 0 | 8,000,000 | 0 | 8,000,000 |
| HFC – technical assistance | 678,000 | 0 | 0 | 678,000 |
| HFC activities subtotal | 40,927,693 | 33,453,761 | 66,381,713 | 140,763,167 |
| Other activities |  |  |  |  |
| Energy efficiency manufacturing (decision 94/60) | 2,354,000 | 4,280,000 | 0 | 6,634,000 |
| Pilot demonstration project for energy efficiency (decision 91/65) | 5,370,000 | 0 | 0 | 5,370,000 |
| Pilot investment project for energy efficiency (decision 91/65) | 1,880,000 | 0 | 0 | 1,880,000 |
| National inventories of banks of waste-controlled substances preparation (decision 91/66) | 3,346,247 | 0 | 0 | 3,346,247 |
| Other activities subtotal | 12,950,247 | 4,280,000 | 0 | 17,230,247 |
| Standard activities |  |  |  |  |
| Compliance Assistance Programme (CAP) | 12,113,777 | 12,310,330 | 12,679,640 | 37,103,747 |
| Core unit | 6,641,293 | 6,083,582 | 6,126,167 | 18,851,043 |
| Institutional strengthening (IS) | 5,898,152 | 22,008,918 | 17,095,016 | 45,002,085 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 8,221,543 | 7,905,673 | 7,974,726 | 24,101,942 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |
| Standard activities subtotal | 33,374,765 | 48,808,503 | 44,375,549 | 126,558,817 |
| Total | 159,576,633 | 167,150,440 | 197,086,872 | 523,813,945 |
| By agency |  |  |  |  |
| Australia | 463,113 | 0 | 105,090 | 568,203 |
| France | 671,075 | 0 | 0 | 671,075 |
| Germany | 1,191,480 | 5,769,916 | 1,675,197 | 8,636,593 |
| United Kingdom of Great Britain and Northern Ireland (the) | 533,900 | 0 | 0 | 533,900 |
| UNDP | 37,604,225 | 62,114,178 | 46,675,877 | 146,394,281 |
| UNEP | 38,121,523 | 35,574,374 | 30,739,664 | 104,435,561 |
| UNIDO | 48,279,677 | 41,880,004 | 58,533,404 | 148,693,084 |
| World Bank | 23,401,497 | 12,817,695 | 50,294,313 | 86,513,506 |
| HPMP verification** | 588,600 | 588,600 | 588,600 | 1,765,800 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 8,221,543 | 7,905,673 | 7,974,726 | 24,101,942 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |

* Including agency support costs where applicable.

** Funding for the preparation of HPMP verification reports for low-volume-consuming countries is approved by the Executive Committee on an annual basis.

Status of implementation of the 2025 business plan

# Table 2 sets out the submissions by agency to the 96th meeting (as at 8 May 2025), and the balance of funds from projects in the 2025 business plans.

Table 2. 2025 consolidated business plan, project recommended to the 96th meeting, and balance (US $)*

| Budget items | Total value in business plan | Activities recommended to the 96th meeting | Balance (above)/below |
| --- | --- | --- | --- |
| Bilateral agencies | 2,859,568 | 444,025 | 2,415,543 |
| UNDP | 37,604,225 | 8,705,734 | 28,898,491 |
| UNEP | 38,121,523 | 5,563,715 | 32,557,808 |
| UNIDO | 48,279,677 | 18,000,378 | 30,279,299 |
| World Bank | 23,401,497 | 4,846,181 | 18,555,316 |
| HPMP verification | 588,600 | 402,000 | 186,600 |
| Subtotal (agencies) | 150,855,090 | 37,962,033 | 112,893,057 |
| Secretariat/Executive Committee/Monitoring and Evaluation (excluding Canadian counterpart) | 8,221,543 | 0 | 8,221,543 |
| Treasurer | 500,000 | 0 | 500,000 |
| Subtotal (standard costs) | 8,721,543 | 0 | 8,721,543 |
| Total | 159,576,633 | 37,962,033 | 121,614,600 |

* Including core unit costs.

# The value of project proposals recommended to the 96th meeting of US $37,962,033 is US $15,159,456 above its value in the 2025 business plan and includes US $1,837,242 associated with project proposals not included in the 2025 business plan.

# The value of HFC-related activities recommended to the 96th meeting is US $20,289,897 of which US $85,600 is associated with project proposals not included in the 2025 business plan. Annex I to the present document lists HFC-related projects submitted by bilateral and implementing agencies to the 96th meeting.

# The value of projects recommended under the funding window for pilot projects for energy efficiency pursuant to decision 91/65 is US $1,713,080. Taking into account approvals at the 92nd, 93rd, 94th and 95th meetings of US $8,670,409, and the values recommended to the 96th meeting, the remaining funding available under this funding window is US $9,616,511. Annex II to the present document lists the pilot projects submitted by bilateral and implementing agencies to the 96th meeting pursuant to decision 91/65.

# The value of projects recommended under the funding window for energy efficiency pursuant to decision 94/60 is US $87,740. Taking into account approvals at the 95th meeting of US $688,747, the remaining funding available under this funding window is US $99,223,513. Annex III to the present document lists the projects submitted by bilateral and implementing agencies to the 96th meeting pursuant to decision 94/60.

# The value of projects submitted for the preparation of energy-efficiency end-user projects using a revolving fund mechanism pursuant to decision 95/87 is US $642,000. Annex IV to the present document lists the projects submitted by bilateral and implementing agencies to the 96th meeting pursuant to decision 95/87.

# The value of projects recommended under the funding window for the preparation of national inventories of banks of waste-controlled substances pursuant to decision 91/66 is US $1,124,000 including US $293,800 that is not included in the 2025 business plan. Annex V to the present document lists the project preparation activities submitted by bilateral and implementing agencies to the 96th meeting pursuant to decision 91/66.

# Forward commitments

# The total amount for existing forward commitments for multi-year agreements (MYAs) for the period 2025 to 2032 is US $247.72 million, assuming that the funding requests of MYAs submitted to the 96th meeting will be approved in principle, as shown in table 3.

Table 3. Forward commitments (2025–2032) (US $000)

| Description | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approved in principle | 57,604 | 68,062 | 33,865 | 20,353 | 8,176 | 17,702 | 165 | 0 | 205,929 |
| Submitted to 96th meeting | 21,815 | 0 | 7,444 | 4,980 | 4,665 | 2,370 | 0 | 520 | 41,794 |
| Total | 79,419 | 68,062 | 41,309 | 25,333 | 12,841 | 20,072 | 165 | 520 | 247,723 |

## II.	 RESOURCE ALLOCATION FOR THE 2024-2026 TRIENNIUM

# The resources approved by the Parties to the Montreal Protocol for the 2024–2026 triennium amount to US $965,000,000. Of this amount, US $183,996,211 had been allocated to activities approved in 2024, with US $781,003,789 remaining for 2025 and 2026.

# The value of the activities recommended to the 96th meeting, the remaining activities in the business plan and the operation of the Secretariat/Executive Committee/Monitoring and Evaluation, and Treasurer for the period 2025 and 2026, amounts to US $341,886,529, and is below the resources available by US $439,117,260 as shown in table 4.

Table 4. Resource allocation for the 2024-2026 triennium (US $)

|  | 2024 | 2025 | 2026 | Total |
| --- | --- | --- | --- | --- |
| Resource allocation for the 2024–2026 triennium* (a) | 181,000,000 | 392,000,000 | 392,000,000 | 965,000,000 |
| Project costs |  |  |  |  |
| 94th meeting approvals | 61,332,445 | 0 | 0 | 61,332,445 |
| 95th meeting approvals | 114,322,558 | 0 | 0 | 114,322,558 |
| 96th meeting recommended | 0 | 37,962,033 | 0 | 37,962,033 |
| Remaining business plans values | 0 | 128,052,513 | 158,744,767 | 286,797,280 |
| Sub-total project costs (b) | 175,655,003 | 166,014,546 | 158,744,767 | 500,414,316 |
| Recurrent costs |  |  |  |  |
| Secretariat/Executive Committee/Monitoring and Evaluation | 7,841,208 | 8,221,543 | 7,905,673 | 23,968,424 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |
| Subtotal recurrent costs (c) | 8,341,208 | 8,721,543 | 8,405,673 | 25,468,424 |
| Total costs (d) = (b) + (c) | 183,996,211 | 174,736,089 | 167,150,440 | 525,882,740 |
| Balance (e) = (a) – (d) | -2,996,211 | 217,263,911 | 224,849,560 | 439,117,260 |

*Resource allocation adopted at the 94th meeting for the 2024–2026 triennium (decision 94/15).

# Recommendation

# The Executive Committee may wish to note:

## The update on the status of implementation of the 2025–2027 consolidated business plan of the Multilateral Fund contained in document UNEP/OzL.Pro/ExCom/96/14; and

## That the total value of activities recommended to the 96th meeting amounts to US $37,962,033 (including US $20,289,897 for HFC-related activities; US $1,713,080 for pilot projects for energy efficiency pursuant to decision 91/65; US $87,740 for energy efficiency projects pursuant to decision 94/60; US $642,000 as submitted for the preparation of energy-efficiency end-user projects using a revolving fund mechanism pursuant to decision 95/87; and US $1,124,000 for the preparation of national inventories of banks of waste-controlled substances pursuant to decision 91/66), of which US $1,837,242 is associated with project proposals not included in the 2025 business plan.

Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 96TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Bosnia and Herzegovina | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 216,000 | 28,080 |
| Central African Republic (the) | UNEP | TAS | SEV | Enabling activities for HFC phase-down | 150,000 | 10,500 |
| Egypt | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 492,700 | 34,489 |
| Egypt | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 1,367,000 | 95,690 |
| Egypt | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (commercial refrigeration manufacturing) | 502,202 | 35,154 |
| Egypt | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (domestic refrigeration manufacturing) | 4,552,856 | 318,700 |
| Egypt | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 133,547 | 9,348 |
| Egypt | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 711,476 | 49,803 |
| Egypt | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PU foam) | 225,420 | 15,779 |
| Egypt | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (residential AC) | 1,948,253 | 136,378 |
| Egypt | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (XPS foam) | 853,021 | 59,711 |
| Georgia | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 67,000 | 8,710 |
| Georgia | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 137,500 | 17,875 |
| Guinea | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 222,400 | 28,912 |
| Guinea | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 189,000 | 13,230 |
| Indonesia | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 3,170,609 | 221,943 |
| Lebanon | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 357,250 | 25,008 |
| Lebanon | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (AC manufacturing - Lematic Industries) | 355,850 | 24,910 |
| Lebanon | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (conversion of SMEs and micro-SMEs) | 1,100,192 | 77,013 |
| Lebanon | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 56,500 | 3,955 |
| Mexico | UNIDO | INV | PRO | Control and phase-out of HFC-23 emissions in the production of HCFC-22 at Quimobásicos (fourth tranche) | 317,500 | 22,225 |
| Morocco | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 488,500 | 34,195 |
| Morocco | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 48,850 | 3,420 |
| Philippines (the) | UNDP | PRP | KIP | Project preparation for PU foam manufacturing sector plan | 80,000 | 5,600 |
| Republic of Moldova (the) | UNEP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 95,500 | 12,415 |
| Sri Lanka | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 84,176 | 5,892 |
| Sri Lanka | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 46,000 | 5,980 |
| Sri Lanka | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 21,290 | 1,490 |
| Sri Lanka | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (RAC manufacturing) | 95,745 | 6,702 |
| Global | UNEP | TAS | SEV | Twinning of national ozone officers and national energy-efficiency policymakers to support Kigali Amendment (phase II) | 793,200 | 97,252 |

Annex II

Pilot projects for energy efficiency PURSUANT TO decision 91/65 
SUBMITTED TO THE 96TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Chile | UNDP | INV | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (decision 91/65) | 720,000 | 50,400 |
| Cuba | UNDP | INV | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (decision 91/65) | 360,000 | 25,200 |
| Egypt | UNIDO | PRP | EEF | Preparation of a project to enhance energy efficiency of cooling technologies in data centres (decision 91/65) | 30,000 | 2,100 |
| Ghana | UNDP | PRP | EEF | Preparation of a pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (decision 91/65) | 30,000 | 2,100 |
| Guatemala | UNIDO | INV | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (decision 91/65) | 151,000 | 13,590 |
| North Macedonia | UNIDO | TAS | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (decision 91/65) | 241,000 | 21,690 |
| North Macedonia | UNIDO | PRP | EEF | Preparation of a project to enhance energy efficiency of cooling technologies in data centres (decision 91/65) | 30,000 | 2,100 |
| Rwanda | United Kingdom of Great Britain and Northern Ireland (the) | PRP | EEF | Preparation of a pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (decision 91/65) | 30,000 | 3,900 |

Annex III

projects for energy efficiency PURSUANT TO decision 94/60
SUBMITTED TO THE 96TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Argentina | UNIDO | PRP | EEF | Preparation of a project to enhance energy efficiency in the context of HFC phase-down in the air-conditioning sector (decision 94/60) | 42,000 | 2,940 |
| Indonesia | IBRD | PRP | EEF | Preparation of a project to enhance energy efficiency in the context of HFC phase-down in domestic refrigeration manufacturing sector (decision 94/60) | 40,000 | 2,800 |

Annex IV

PREPARATION OF energy-efficiency END-USER projectS PURSUANT TO

decision 95/87 SUBMITTED TO THE 96TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Grenada | IBRD | PRP | EEF | Preparation of energy-efficiency end-user projects using a revolving fund mechanism (decision 95/87) | 100,000 | 7,000 |
| Mexico | IBRD | PRP | EEF | Preparation of energy-efficiency end-user projects using a revolving fund mechanism (decision 95/87) | 100,000 | 7,000 |
| Thailand | IBRD | PRP | EEF | Preparation of energy-efficiency end-user projects using a revolving fund mechanism (decision 95/87) | 100,000 | 7,000 |
| Türkiye | IBRD | PRP | EEF | Preparation of energy-efficiency end-user projects using a revolving fund mechanism (decision 95/87) | 100,000 | 7,000 |
| Global | UNDP | PRP | EEF | Preparation of energy-efficiency end-user projects using a revolving fund mechanism in Colombia, Ghana and Jordan (decision 95/87) | 200,000 | 14,000 |

Annex V

Project preparation for national inventories of banks 
of waste-controlled substances PURSUANT TO decision 91/66 
SUBMITTED TO THE 96TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Barbados | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Dominica | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Ethiopia | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Georgia | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Ghana | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Iraq | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 13,000 |
| Oman | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Rwanda | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Saint Kitts and Nevis | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| South Africa | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Suriname | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| United Republic of Tanzania (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |

UNEP/OzL.Pro/ExCom/96/1

One project preparation for a KIP investment project for the Philippines (UNDP); four energy efficiency projects under decision 89/6 for Barbados (UNDP), Fiji (UNEP), Georgia (UNDP) and Haiti (UNDP); two IS projects for Brazil (UNDP) and Maldives (UNEP); and three project preparation activities for national inventories of banks of waste-controlled substances under decision 91/66 for Barbados (UNEP), Ghana (UNEP) and Oman (UNEP).

Decision 95/87 allows a maximum of five preparatory projects, each with US $100,000, plus agency support costs.

Decision XXXV/1