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	INFORME SOBRE SALDOS Y DISPONIBILIDAD DE RECURSOS


Introducción
1. El presente documento resume los ajustes financieros indicados por los organismos bilaterales y de ejecución en acuerdo con la Secretaría. De conformidad con las decisiones 28/7 y 56/2 c), incluye datos estadísticos[footnoteRef:2] sobre todo proyecto con saldos a su haber durante 12 o más meses de terminado. El documento informa sobre saldos a reintegrar según lo dispuesto en las correspondientes decisiones (en el presente documento, denominados proyectos “según decisión”). Indica el nivel de recursos en efectivo de que dispone el Comité Ejecutivo según el documento Situación de las contribuciones y los desembolsos,[footnoteRef:3] conforme a la decisión 41/92 b), y presenta una recomendación. [2:  Basados en el formato de presentación de informes elaborado de conformidad con la decisión 31/2.]  [3: UNEP/OzL.Pro/ExCom/88/3.

] 

2. El presente documento contiene además los siguientes cuatro anexos:
Anexo I	Montos que obran en poder de los organismos de ejecución y bilaterales por concepto de proyectos terminados
Anexo II 	Montos que obran en poder de los organismos de ejecución y bilaterales por concepto de proyectos según decisión
Anexo III 	Montos que obran en poder de los organismos de ejecución y bilaterales por concepto de proyectos financiados por contribuciones adicionales
Anexo IV	Fondos reintegrados por los organismos de ejecución y bilaterales por concepto de proyectos terminados, según decisión, y financiados por contribuciones adicionales
Los Anexos I, II y III explican el motivo de las demoras en el desembolso de fondos comprometidos o en el reintegro de aquellos no comprometidos.
Fondos a reintegrar a la 88ª reunión
El total a reintegrar por concepto de proyectos terminados, según decisión, y financiados por contribuciones adicionales asciende a la suma de 6.322.577 $EUA (2.339 $EUA por parte de organismos bilaterales y 6.320.238 $EUA por parte de organismos de ejecución).
Fondos a reintegrar por parte de organismos de ejecución

Según se muestra en el Cuadro 1, el total de fondos a reintegrar por parte de los organismos de ejecución asciende a la suma de 6.320.238 $EUA.
Cuadro 1. Fondos a reintegrar a la 88ª reunión por parte de organismos de ejecución ($EUA)
	Organismo
	Costos de proyecto
	Gastos de apoyo
	Total

	PNUD
	2.261.506
	168.607
	2.430.113

	PNUMA
	3.165.404
	241.892
	3.407.296

	ONUDI
	36.947
	2.678
	39.625

	Banco Mundial
	0
	443.204
	443.204

	Total
	5.463.857
	856.381
	6.320.238



El Cuadro 2 muestra los saldos retenidos por organismos de ejecución por concepto de proyectos terminados, según decisión, y financiados por contribuciones voluntarias adicionales.
Cuadro 2. Saldos retenidos por organismos de ejecución por concepto de proyectos terminados, según decisión y financiados por contribuciones voluntarias adicionales (incluye gastos de apoyo)
	Año de término
	PNUD
	PNUMA
	ONUDI
	Total

	
	Cantidad
	($EUA)
	Cantidad
	($EUA)
	Cantidad
	($EUA)
	Cantidad
	($EUA)

	Proyectos terminados hace más de dos años

	2017
	1
	21.740
	0
	0
	0
	0
	1
	21.740

	2018
	1
	1.787
	0
	0
	0
	0
	1
	1.787

	1º ene. al 31 oct. 2019
	1
	2.246
	0
	0
	0
	0
	1
	2.246

	Subtotal
	3
	25.773
	0
	0
	0
	0
	3
	25.773

	Proyectos terminados hace menos de dos años

	1º nov. al 31 dic. 2019
	13
	842.341
	0
	0
	0
	0
	13
	842.341

	2020
	20
	3.218.499
	2
	18.257
	11
	1.235.473
	33
	4.472.229

	Subtotal
	33
	4.060.840
	2
	18.257
	11 
	1.235.473
	46
	5.314.570

	Total 
	36
	4.086.613
	2
	18.257
	11
	1.235.473
	49
	5.340.343

	Proyectos según decisión (en curso)

	
	1
	135.001
	2
	116.344
	0
	0
	3
	251.345

	Contribuciones voluntarias adicionales

	
	3
	22.223
	0
	0
	0
	0
	3
	22.223

	Total general
	40
	4.243.837
	4
	134.601
	11
	1.235.473
	55
	5.613.911



Fondos a reintegrar por parte de organismos bilaterales

El total de fondos a reintegrar por parte de los organismos bilaterales asciende a la suma de 2.339 $EUA, cifra consistente en 2.070 $EUA más gastos de apoyo de 269 $EUA para Australia.
Japón mantuvo un saldo a su haber de 18.080 $EUA, cifra que incluye gastos de apoyo, por concepto de un proyecto terminado durante el año 2020.
Disponibilidad de recursos
El documento Situación de las contribuciones y los desembolsos muestra al 12 de octubre de 2021 un saldo disponible de 385.240.783 $EUA. El total reintegrado a la 88ª reunión por los organismos bilaterales y de ejecución asciende a la suma de 6.322.577 $EUA. En consecuencia, el nivel total de recursos disponibles para aprobación durante la 88ª reunión asciende a la cifra de 391.563.360 $EUA.
Observaciones de la Secretaría
La Secretaría recordó a los organismos bilaterales y de ejecución que los saldos provenientes de proyectos según decisión y de proyectos terminados hace un año o más deben ser reintegrados al Fondo Multilateral a la brevedad.
Al 18 de octubre de 2021, el nivel total de recursos disponibles para proyectos y actividades que se presenta a la 88ª reunión asciende a la suma de 81.490.200 $EUA, cifra que se estima como suficiente para solventar las aprobaciones previstas durante la 88ª reunión.
Recomendaciones

El Comité Ejecutivo podrá estimar oportuno:
Tomar nota de:

i) El informe sobre saldos y disponibilidad de recursos recogido en el documento UNEP/OzL.Pro/ExCom/88/4;
ii) Que el nivel neto de fondos reintegrados a la 88ª reunión por organismos de ejecución asciende a 6.320.238 $EUA, cifra consistente en 2.261.506 $EUA más gastos de apoyo de 168.607 $EUA del PNUD; 3.165.404 $EUA más gastos de apoyo de 241.892 $EUA del PNUMA; 36.947 $EUA más gastos de apoyo de 2.678 $EUA de la ONUDI, y gastos de apoyo de 443.204 $EUA del Banco Mundial;
iii) Que el PNUD mantenía a su haber saldos de 25.773 $EUA, incluyendo gastos de apoyo, por concepto de tres proyectos terminados hace más de dos años, y de 22.223 $EUA, incluyendo gastos de apoyo, por concepto de tres proyectos financiados por contribuciones voluntarias adicionales para actividades de apoyo a la reducción de los HFC que ya fueron terminadas;
iv) Que el PNUMA mantenía a su haber saldos de 116.344 $EUA, incluyendo gastos de apoyo, por concepto de dos proyectos terminados “según decisión del Comité Ejecutivo”;
v) Que el nivel neto de fondos que el Gobierno de Australia debe reintegrar a la 88ª reunión asciende a la suma de 2.070 $EUA más gastos de apoyo de 269 $EUA;
Solicitar:
A los organismos bilaterales y de ejecución, proceder al desembolso o bien a la cancelación de los fondos comprometidos y no comprometidos que ya no se precisen para proyectos terminados o para aquellos terminados “por decisión del Comité Ejecutivo”, y reintegrar los respectivos saldos a la 90ª reunión;
Al PNUD, proceder al desembolso o cancelación de sus compromisos respecto de los restantes tres proyectos terminados hace más de dos años, y reintegrar los saldos a la 90ª reunión;
Al PNUD, reintegrar a la 90ª reunión el saldo de tres proyectos terminados que fueron financiados con contribuciones voluntarias adicionales;
Al PNUMA, reintegrar a la 90ª reunión el saldo de dos proyectos terminados “por decisión del Comité Ejecutivo”, según lo dispuesto en la decisión 86/16 f) i); y
A Tesorería, consultar al Gobierno de Australia respecto del reintegro en efectivo de la suma de 2.339 $EUA mencionada en el párrafo a) v) anterior.
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Los documentos previos al período de sesiones del Comité Ejecutivo del Fondo Multilateral para la Aplicación del Protocolo de Montreal no van en perjuicio de las decisiones que el Comité pudiera adoptar después de la emisión de los mismos.
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Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES AND BILATERAL AGENCIES FOR COMPLETED PROJECTS
		
	Code
	Project title
	Date completed (Actual)
	Approved funding plus adjustments as of 31 December 2020(US $)
	Funds disbursed as of 88th meeting (US $)
	Balances committed as per 88th meeting (US $)
	Balances not-committed as per 88th meeting (US $)
	Support cost on balances committed and not committed as per 88th meeting (US $)
	Why any balances could not be returned?
	When they could be returned?
	Project subject to decision

	UNDP

	BHU/PHA/76/TAS/26
	HCFC phase-out management plan (third tranche)
	Nov-19
	57,000
	56,359
	641
	
	58
	
	
	

	BRU/PHA/82/INV/23
	HCFC phase-out management plan (stage I, third tranche)
	Dec-20
	33,000
	26,549
	6,451
	
	581
	
	
	

	COS/PHA/81/PRP/58
	Preparation of a HCFC phase-out management plan (stage II)
	Mar-20
	40,000
	38,883
	1,117
	
	78
	
	
	

	COS/PHA/83/INV/59
	HCFC phase-out management plan (stage I, fifth tranche)
	Dec-20
	56,000
	49,952
	6,048
	
	454
	
	
	

	COS/SEV/80/INS/56
	Extension of institutional strengthening project (phase XII: 1/2018-12/2019)
	Dec-19
	179,857
	174,459
	5,398
	
	378
	
	
	

	CUB/PHA/82/TAS/60
	Verification report on the implementation of the HCFC phase-out management plan
	Dec-20
	30,000
	22,236
	7,764
	
	699
	
	
	

	EGY/PHA/68/INV/117
	HCFC phase-out management plan (stage I, second tranche) (phase-out of HCFC-141b in the polyurethane foam sector)
	Dec-19
	2,000,000
	1,896,153
	103,847
	
	7,789
	
	
	

	EGY/PHA/82/INV/139
	HCFC phase-out management plan (stage I, third tranche) (phase-out of HCFC-141b in the polyurethane foam sector)
	Dec-19
	716,400
	530,037
	186,363
	
	13,977
	
	
	

	FIJ/PHA/73/INV/27
	HCFC phase-out management plan (stage I, second tranche)
	Jun-17
	37,900
	17,955
	19,945
	
	1,795
	
	
	

	FIJ/PHA/77/INV/31
	HCFC phase-out management plan (stage I, third tranche)
	Dec-19
	59,850
	55,584
	4,266
	
	384
	
	
	

	FIJ/PHA/82/TAS/35
	Verification report on the implementation of the HCFC phase-out management plan
	Dec-20
	30,000
	3,718
	26,282
	
	2,365
	
	
	

	GHA/PHA/81/INV/46
	HCFC phase-out management plan (stage I, fifth tranche)
	Dec-20
	125,000
	105,139
	19,861
	
	1,490
	
	
	

	GHA/PHA/81/PRP/44
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-20
	60,000
	49,389
	10,611
	
	743
	
	
	

	GHA/SEV/82/INS/47
	Extension of the institutional strengthening project (phase XIII: 1/2018-12/2020)
	Dec-20
	178,048
	177,391
	657
	
	46
	
	
	

	GUY/PHA/75/INV/28
	HCFC phase-out management plan (stage II, first tranche)
	Dec-19
	159,750
	111,244
	48,506
	
	3,396
	
	
	

	IDS/PHA/71/TAS/200
	HCFC phase-out management plan (project management and coordination) (stage I, second tranche)
	Jun-20
	201,674
	42,383
	159,291
	
	11,947
	
	
	

	IDS/PHA/76/INV/208
	HCFC phase-out management plan (stage I, third tranche) (refrigeration and air-conditioning sector)
	Jun-20
	512,190
	244,358
	267,832
	
	20,087
	
	
	

	IDS/SEV/80/INS/212
	Extension of institutional strengthening project (phase XI: 1/2018-12/2019)
	Dec-19
	347,194
	343,303
	3,891
	
	272
	
	
	

	IND/SEV/76/INS/467
	Extension of institutional strengthening project (phase X: 4/2016-3/2018)
	Dec-19
	477,734
	477,682
	52
	
	4
	
	
	

	KYR/PHA/81/INV/40
	HCFC phase-out management plan (stage II, second tranche)
	Dec-20
	175,000
	108,104
	66,896
	
	4,683
	
	
	

	MEX/PHA/71/INV/168
	HCFC phase-out management plan (stage I, third tranche) (foam sector plan for systems houses and local customers)
	Dec-19
	3,800,000
	3,388,171
	411,829
	
	30,887
	
	
	

	MEX/REF/81/INV/187
	Conversion of domestic refrigeration manufacturing facility from HFC-134a to isobutane as a refrigerant and conversion of compressors manufacturing facility from HFC-134a-based to isobutane-based at Mabe Mexico
	Nov-20
	2,115,012
	2,110,680
	4,332
	
	303
	
	
	

	MLI/PHA/76/INV/38
	HCFC phase-out management plan (stage I, third tranche)
	Dec-19
	92,000
	77,893
	14,107
	
	1,058
	
	
	

	NEP/PHA/75/INV/35
	HCFC phase-out management plan (stage I, second tranche)
	Dec-19
	33,600
	30,916
	2,684
	
	242
	
	
	

	PAR/PHA/74/INV/34
	HCFC phase-out management plan (stage I, second tranche)
	Dec-19
	131,500
	129,642
	1,858
	
	139
	
	
	

	SRL/PHA/82/PRP/52
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-20
	40,000
	29,919
	10,081
	
	706
	
	
	

	SRL/PHA/82/TAS/51
	Verification report on the implementation of the HCFC phase-out management plan
	Dec-20
	30,000
	23,657
	6,343
	
	571
	
	
	

	SRL/SEV/82/INS/53
	Extension of the institutional strengthening project (phase XII: 1/2019-12/2020)
	Dec-20
	171,592
	136,511
	35,081
	
	2,456
	
	
	

	URU/PHA/77/INV/67
	HCFC phase-out management plan (stage II, first tranche) (foam sector)
	Dec-20
	100,000
	38,101
	61,899
	
	4,333
	
	
	

	URU/PHA/77/TAS/69
	HCFC phase-out management plan (stage II, first tranche) (implementation and monitoring)
	Dec-18
	35,800
	34,130
	1,670
	
	117
	
	
	

	URU/SEV/80/INS/70
	Extension of institutional strengthening project (phase XII: 1/2018-12/2019)
	Dec-19
	193,024
	192,729
	295
	
	21
	
	
	

	VEN/SEV/77/INS/135
	Renewal of institutional strengthening project (phase XIII: 1/2017-12/2018)
	Mar-19
	365,414
	363,315
	2,099
	
	147
	
	
	

	ZIM/PHA/83/PRP/58
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-20
	20,000
	11,435
	8,565
	
	600
	
	
	

	TOTAL UNDP
	
	
	
	
	3,807,156
	
	279,457
	
	
	

	UNEP

	LAO/PHA/74/TAS/27
	HCFC phase-out management plan (stage I, second tranche)
	Dec-20
	97,875
	 86,875 
	
	 11,000 
	 1,430 
	UNEP is working on financial closure of the project.
	ExCom 90
	

	UGA/PHA/82/PRP/24
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-20
	20,000
	 14,844 
	
	 5,156 
	 670 
	Once project is financially completed
	ExCom 89
	

	TOTAL UNEP
	
	
	
	
	
	 16,157
	 2,100
	
	
	

	UNIDO[footnoteRef:4] [4:  2: Financial completion initiated; 3: Financial completion being initiated; 4: Financial completion to be initiated after settlement of all pending issues; 5: Project is ongoing; 6: Funds were not transferred.] 


	JOR/REF/81/INV/103
	Conversion of large commercial unitary roof top air-conditioning units of up to 400kW manufacturing facility from HFC (R134a, R407c, R410a) to propane R290 as refrigerant at Petra Engineering Industries Co.
	Jun-20
	1,637,610
	1,524,521
	113,089
	
	7,917
	3
	90
	

	MOG/PHA/84/TAS/14
	Verification report on the implementation of the HCFC phase-out management plan
	Dec-20
	30,000
	24,091
	5,909
	
	532
	3
	90
	

	NER/PHA/82/TAS/34
	Verification report on the implementation of the HCFC phase-out management plan
	Dec-20
	30,000
	29,658
	342
	
	31
	3
	90
	

	PAK/PHA/76/TAS/95
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector)
	Dec-20
	190,000
	180,077
	9,923
	
	695
	3
	90
	

	QAT/PHA/73/PRP/21
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-20
	40,000
	39,629
	372
	
	26
	3
	90
	

	RWA/PHA/77/INV/27
	HCFC phase-out management plan (stage I, third tranche)
	Dec-20
	55,000
	54,664
	336
	
	30
	3
	90
	

	SAU/PHA/72/INV/21
	HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan)
	Dec-20
	2,693,674
	2,080,492
	613,182
	
	42,923
	3
	90
	86/17(i)(i)

	SAU/REF/76/DEM/28
	Demonstration project on promoting HFO-based low-global warming potential refrigerants for air-conditioning sector in high ambient temperatures
	Dec-20
	1,300,000
	903,494
	396,506
	
	27,755
	3
	90
	83/33(c) and 85/17(c) 

	SIL/PHA/76/INV/31
	HCFC phase-out management plan (stage I, third tranche)
	Dec-20
	50,000
	48,855
	1,145
	
	103
	2
	90
	

	SOA/PHA/67/TAS/04
	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring)
	Dec-20
	110,005
	103,224
	6,782
	
	474
	2
	90
	

	SOA/PHA/71/INV/05
	HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan)
	Dec-19
	2,042,620
	2,035,702
	6,918
	
	484
	3
	90
	

	TOTAL UNIDO
	
	
	
	
	1,154,504
	
	80,969
	
	
	

	JAPAN
	
	
	
	
	
	
	
	
	
	

	CPR/PHA/77/TAS/582

	HCFC phase-out management plan (stage II, first tranche) (refrigeration and air-conditioning servicing sector plan and enabling component)
	Dec-20

	80,000

	64,000

	16,000

	
	2,080

	
	
	

	TOTAL JAPAN
	
	
	
	
	16,000
	
	2,080
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Annex II
COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR BY-DECISIONS PROJECTS
	Code
	Project title
	Financial date of completion per decision
	Approved funding plus adjustments as of 31 December 2020 (US $)
	Funds disbursed as of
88th meeting (US $)
	Balances committed as per 88th meeting (US $)
	Balances not- committed as per 88th meeting (US $)
	Support cost on balances committed and not-committed as per 88th meeting (US $)
	Why any balances could not be returned?
	When they could be returned?
	Project subject to decision

	UNDP

	BRA/DES/72/DEM/305 
	Pilot demonstration project on ODS waste management and disposal 
	Dec-23 
	1,490,600 
	1,364,430
	126,179
	
	8,832
	
	
	79/18(c)(i) and 81/24(e)(ii) 

	TOTAL UNDP
	
	
	
	
	126,179
	
	8,832
	
	
	

	UNEP

	SAU/PHA/68/TAS/16
	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring)
	87th meeting
	233,674
	182,206
	32,350
	
	4,007
	
	
	86/16(f)(i)

	SAU/PHA/77/TAS/32
	HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, custom training and monitoring)
	87th meeting
	130,400
	50,589
	71,170
	
	8,817
	
	
	86/16(f)(i)

	TOTAL UNEP
	
	
	
	
	103,520
	
	12,824
	
	
	



UNEP/OzL.Pro/ExCom/88/4
Annex II
UNEP/OzL.Pro/ExCom/88/4
Annex II


1
Annex III
COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL CONTRIBUTIONS PROJECTS
	CODE
	Project title
	Approved funding plus adjustments as of 31 December 2020 (US $) 
	Funds disbursed as of 
88th meeting (US $)
	Balances committed as per 88th meeting (US $)
	Balances not- committed as per 88th meeting (US $)
	Support cost on balances committed and not-committed as per 88th meeting (US $) 
	Why any balances could not be returned?
	When they could be returned?

	COS/SEV/80/TAS/01
	Enabling activities for HFC phase-down
	150,000
	144,830
	5,170
	
	362
	
	

	JAM/SEV/80/TAS/01
	Enabling activities for HFC phase-down
	150,000
	145,083
	4,917
	
	344
	
	

	TRI/SEV/80/TAS/01
	Enabling activities for HFC phase-down
	150,000
	139,318
	10,682
	
	748
	
	

	TOTAL UNDP
	
	
	
	20,769
	
	1,454
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Annex IV

DETAILS ON COMPLETED PROJECTS, BY-DECISION AND PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES AND BILATERAL AGENCIES

	Code
	Project title
	Project costs returned (US $)
	Agency support costs (US $)
	Total (US $)

	ARM/PHA/84/TAS/23
	Verification report on the implementation of the HCFC phase-out management plan
	370
	33
	403

	BRA/PHA/74/INV/307
	HCFC phase-out management plan (stage I, fourth tranche) (foam sector plan)
	1,020,974
	76,573
	1,097,547

	BRA/PHA/75/INV/315
	HCFC phase-out management plan (stage I, fifth tranche) (foam sector)
	1,032,897
	77,468
	1,110,365

	COL/PHA/75/TAS/92
	HCFC phase-out management plan (stage II, first tranche) (technical assistance in policies formulation and implementation)
	5
	0
	5

	COS/REF/76/DEM/55
	Demonstration of the application of an ammonia/carbon dioxide refrigeration system in replacement of HCFC-22 for the medium-sized producer and retail store of Premezclas Industriales S.A.
	697
	49
	746

	COS/SEV/75/INS/53
	Extension of institutional strengthening project 
(phase XI: 1/2016-12/2017)
	198
	14
	212

	CUB/SEV/75/INS/54
	Extension of institutional strengthening project 
(phase X: 1/2016-12/2017)
	1
	0
	1

	DOM/REF/81/INV/63
	Conversion of a commercial refrigerator manufacturing line at Fábrica de Refrigeradores Comerciales, SRL (FARCO) from HFC-134a and R-404A to propane (R-290) as refrigerant
	24
	2
	26

	DRC/PHA/80/INV/45
	HCFC phase-out management plan (stage I, third tranche)
	476
	43
	519

	EGY/FOA/76/DEM/129
	Demonstration of low-cost options for the conversion to non-ODS technologies in polyurethane foams at very small users
	190,799
	13,356
	204,155

	EGY/PHA/74/PRP/126
	Preparation of a HCFC phase-out management plan (stage II)
	11,860
	830
	12,690

	ELS/PHA/77/INV/34
	HCFC phase-out management plan (stage I, third tranche)
	1,052
	79
	1,131

	IDS/PHA/71/INV/199
	HCFC phase-out management plan (air conditioning sector plan) (stage I, second tranche)
	380
	29
	409

	IDS/SEV/75/INS/206
	Extension of institutional strengthening project (phase X: 1/2016-12/2017)
	29
	2
	31

	IND/PHA/75/INV/463
	CTC phase-out plan for the consumption and production sectors: 2009 annual programme
	48
	4
	52

	IND/SEV/72/INS/457
	Extension of institutional strengthening project (phase X: 4/2014-3/2016)
	182
	13
	195

	MDV/PHA/69/INV/24
	HCFC phase-out management plan (second tranche)
	3
	0
	3

	NIR/PHA/75/INV/143
	HCFC phase-out management plan (stage I, fifth tranche) (foam sector and refrigeration servicing)
	1,511
	113
	1624

	[bookmark: _Hlk5787459]Total completed projects
	
	2,261,506
	168,607
	2,430,113

	TOTAL UNDP
	
	2,261,506
	168,607
	2,430,113

	AFG/PHA/82/PRP/24
	Preparation of a HCFC phase-out management plan (stage II)
	273
	35
	308

	AFG/SEV/80/INS/23
	Extension of institutional strengthening project (phase VIII: 1/2018-12/2019)
	5,754
	0
	5,754

	BEN/SEV/80/INS/35
	Renewal of institutional strengthening project (phase X: 1/2018-12/2019)
	2,663
	0
	2,663

	BKF/PHA/84/TAS/40
	Verification report on the implementation of the HCFC phase-out management plan
	710
	92
	802

	BZE/PHA/82/TAS/35
	Verification report on the implementation of the HCFC phase-out management plan
	9,800
	1,274
	11,074

	CHI/PHA/76/TAS/193
	HCFC phase-out management plan (stage I, fourth and fifth tranches)
	507
	66
	573

	CKI/SEV/77/INS/13
	Extension of the institutional strengthening project (phase VI: 1/2017-12/2018)
	5,000
	0
	5,000

	ECU/PHA/76/TAS/64
	HCFC phase-out management plan (stage I, third tranche)
	14,590
	1,897
	16,487

	ECU/PHA/82/PRP/67
	Preparation of a HCFC phase-out management plan (stage II)
	9,900
	1,287
	11,187

	ECU/PHA/82/TAS/69
	HCFC phase-out management plan (stage I, fourth tranche)
	1,235
	161
	1,396

	ECU/PHA/85/TAS/73
	HCFC phase-out management plan (stage I, fifth tranche)
	10,000
	1,300
	11,300

	ECU/PHA/86/TAS/74
	HCFC phase-out management plan (stage II, first tranche)
	24,000
	3,120
	27,120

	ECU/SEV/83/INS/71
	Extension of institutional strengthening project (phase VII: 7/2019-6/2021)
	226,305
	0
	226,305

	ELS/PHA/65/TAS/28
	HCFC phase-out management plan (stage I, first tranche)
	6,531
	229
	6,760

	ERI/PHA/82/TAS/17
	Verification report on the implementation of the HCFC phase-out management plan
	982
	128
	1,110

	FSM/SEV/77/INS/12
	Renewal of institutional strengthening project (phase VI: 1/2017-12/2018)
	969
	0
	969

	GAM/PHA/82/TAS/36
	Verification report on the implementation of the HCFC phase-out management plan
	1,096
	142
	1,238

	GBS/PHA/71/TAS/17
	HCFC phase-out management plan (stage I, second tranche)
	22,921
	2,980
	25,901

	GLO/SEV/82/TAS/347
	Compliance Assistance Programme: 2019 budget
	10,677
	854
	11,531

	GLO/SEV/84/TAS/350
	Compliance Assistance Programme: 2020 budget
	2,611,540
	208,923
	2,820,463

	GUA/PHA/82/PRP/54
	Preparation of a HCFC phase-out management plan (stage II)
	1,828
	238
	2,066

	HAI/PHA/68/TAS/18
	HCFC phase-out management plan (stage I, first tranche)
	20,109
	2,614
	22,723

	HON/PHA/82/PRP/46
	Preparation of a HCFC phase-out management plan (stage II)
	9,706
	1,262
	10,968

	IRQ/PHA/65/TAS/17
	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector)
	4,734
	582
	5,316

	IRQ/PHA/73/PRP/21
	Preparation of a HCFC phase-out management plan (stage II)
	6,886
	895
	7,781

	LAO/PHA/82/TAS/32
	Verification report on the implementation of the HCFC phase-out management plan
	5,780
	751
	6,531

	MAG/PHA/82/TAS/31
	Verification report on the implementation of the HCFC phase-out management plan
	1,076
	140
	1,216

	MDV/SEV/81/INS/33
	Extension of the institutional strengthening project (phase X: 12/2018-11/2020)
	10,000
	0
	10,000

	MLW/PHA/82/TAS/44
	Verification report on the implementation of the HCFC phase-out management plan
	1,547
	201
	1,748

	MOL/SEV/77/INS/36
	Extension of the institutional strengthening project (phase IX: 1/2017-12/2018)
	18,617
	0
	18,617

	MON/PHA/82/PRP/27
	Preparation of a HCFC phase-out management plan (stage II)
	4,850
	631
	5,481

	MON/PHA/82/TAS/28
	Verification report on the implementation of the HCFC phase-out management plan
	1,967
	256
	2,223

	NEP/PHA/82/TAS/39
	Verification report on the implementation of the HCFC phase-out management plan
	4,744
	617
	5,361

	NIC/PHA/74/TAS/31
	HCFC phase-out management plan (stage I, second tranche)
	3,072
	399
	3,471

	NIC/PHA/83/PRP/38
	Preparation of a HCFC phase-out management plan (stage II)
	4,850
	631
	5,481

	PAR/SEV/77/INS/36
	Extension of institutional strengthening project (phase VIII: 1/2017-12/2018)
	4,938
	0
	4,938

	SAM/PHA/82/TAS/22
	Verification report on the implementation of the HCFC phase-out management plan
	2,519
	327
	2,846

	SOI/PHA/82/TAS/15
	Verification report on the implementation of the HCFC phase-out management plan
	7,926
	1,030
	8,956

	STV/PHA/77/TAS/24
	Verification report on the implementation of the HCFC phase-out management plan
	14,738
	1,916
	16,654

	SYR/PHA/83/PRP/105
	Preparation of a HCFC phase-out management plan (stage II)
	17,375
	2,259
	19,634

	TON/PHA/82/TAS/14
	Verification report on the implementation of the HCFC phase-out management plan
	5,589
	727
	6,316

	TTR/PHA/82/TAS/14
	Verification report on the implementation of the HCFC phase-out management plan
	5,623
	731
	6,354

	UGA/PHA/77/TAS/21
	HCFC phase-out management plan (stage I, second tranche)
	3,500
	455
	3,955

	UGA/PHA/82/TAS/25
	Verification report on the implementation of the HCFC phase-out management plan
	380
	49
	429

	URT/PHA/82/TAS/38
	Verification report on the implementation of the HCFC phase-out management plan
	485
	63
	548

	ZAM/PHA/82/TAS/35
	Verification report on the implementation of the HCFC phase-out management plan
	529
	69
	598

	Total completed projects
	
	3,128,821
	239,331
	3,368,152

	MON/SEV/80/TAS/01
	Enabling activities for HFC phase-down
	2,134
	149
	2,283

	TTR/SEV/80/TAS/01
	Enabling activities for HFC phase-down
	25,000
	1,750
	26,750

	ZIM/SEV/80/TAS/01
	Enabling activities for HFC phase-down
	9,449
	661
	10,110

	Total “additional voluntary contributions” projects
	
	36,583
	2,561
	39,143

	TOTAL UNEP
	
	3,165,404
	241,892
	3,407,296

	ARG/PHA/79/TAS/181
	HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector)
	1,298
	91
	1,389

	BOL/PHA/82/PRP/47
	Preparation of a HCFC phase-out management plan (stage II)
	26
	2
	28

	EGY/ARS/50/INV/92
	Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs)
	681
	51
	732

	EGY/SEV/81/INS/138
	Extension of the institutional strengthening project (phase XII: 1/2019-12/2020)
	1,253
	88
	1,341

	GAB/PHA/62/INV/27
	HCFC phase-out management plan (stage I, first tranche)
	42
	4
	46

	GLO/REF/76/DEM/333
	Demonstration project on refrigerant quality, containment and introduction of low-global warming potential alternatives (Eastern Africa and Caribbean regions)
	3,212
	225
	3,437

	GUA/PHA/84/TAS/56
	Verification report on the implementation of the HCFC phase-out management plan
	3,403
	306
	3,709

	HON/PHA/84/TAS/49
	Verification report on the implementation of the HCFC phase-out management plan
	285
	26
	311

	SAU/PHA/68/INV/17
	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring)
	6,628
	464
	7,092

	SAU/PHA/68/INV/19
	HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan)
	215
	15
	230

	SEN/PHA/65/INV/31
	HCFC phase-out management plan (stage I, first tranche)
	521
	39
	560

	SEN/PHA/77/INV/36
	HCFC phase-out management plan (stage I, second tranche)
	1,988
	149
	2,137

	SOM/PHA/77/TAS/13
	HCFC phase-out management plan (stage I, second tranche) (additional security)
	8,172
	572
	8,744

	TKM/PHA/76/INV/12
	HCFC phase-out management plan (stage I, third tranche)
	91
	7
	98

	UGA/PHA/82/PRP/23
	Preparation of a HCFC phase-out management plan (stage II)
	26
	2
	28

	Total completed projects
	
	27,841
	2,040
	29,881

	SAU/PHA/68/INV/17

	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring)
	6,628
	464
	7,092

	Total “by decision” projects
	
	6,628
	464
	7,092

	ARM/SEV/80/TAS/01
	Enabling activities for HFC phase-down
	361
	26
	387

	LEB/REF/80/PRP/01
	Project preparation for HFC-related projects in the manufacturing sector at Lematic Industries to gain experience in ICCs and IOCs associated with the phase-down of HFCs in domestic refrigeration
	2,106
	147
	2,253

	TUN/SEV/80/TAS/02
	Enabling activities for HFC phase-down
	10
	1
	11

	Total “additional voluntary contributions” projects
	
	2,478
	174
	2,652

	TOTAL UNIDO
	
	36,947
	2,678
	39,625

	GLO/SEV/84/TAS/351

	Core unit budget (2020)

	0
	443,204

	443,204


	TOTAL WORLD BANK
	
	
	443,204
	443,204

	IDS/PHA/64/TAS/196
	HCFC phase-out management plan (technical assistance for refrigerant management) (stage I, first tranche)
	2,070

	269

	2,339

	TOTAL AUSTRALIA
	
	2,070
	269
	2,339
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