| NACIONES UNIDAS |  | EP |
| --- | --- | --- |
|  | Programa de las Naciones Unidas para el Medio Ambiente | Distr. GENERAL UNEP/OzL.Pro/ExCom/88/4 21 de octubre de 2021 ESPAÑOL ORIGINAL: INGLÉS |

COMITÉ EJECUTIVO DEL FONDO MULTILATERAL
 PARA LA APLICACIÓN DEL
 PROTOCOLO DE MONTREAL
Octogésima octava Reunión

Montreal, 15-19 de noviembre de 2021

# INFORME SOBRE SALDOS Y DISPONIBILIDAD DE RECURSOS

# Introducción

- El presente documento resume los ajustes financieros indicados por los organismos bilaterales y de ejecución en acuerdo con la Secretaría. De conformidad con las decisiones 28/7 y 56/2 c), incluye datos estadísticos sobre todo proyecto con saldos a su haber durante 12 o más meses de terminado. El documento informa sobre saldos a reintegrar según lo dispuesto en las correspondientes decisiones (en el presente documento, denominados proyectos “según decisión”). Indica el nivel de recursos en efectivo de que dispone el Comité Ejecutivo según el documento Situación de las contribuciones y los desembolsos, conforme a la decisión 41/92 b), y presenta una recomendación.

- El presente documento contiene además los siguientes cuatro anexos:

Anexo I	Montos que obran en poder de los organismos de ejecución y bilaterales por concepto de proyectos terminados

Anexo II 	Montos que obran en poder de los organismos de ejecución y bilaterales por concepto de proyectos según decisión

Anexo III 	Montos que obran en poder de los organismos de ejecución y bilaterales por concepto de proyectos financiados por contribuciones adicionales

Anexo IV	Fondos reintegrados por los organismos de ejecución y bilaterales por concepto de proyectos terminados, según decisión, y financiados por contribuciones adicionales

# Los Anexos I, II y III explican el motivo de las demoras en el desembolso de fondos comprometidos o en el reintegro de aquellos no comprometidos.

Fondos a reintegrar a la 88ª reunión

# El total a reintegrar por concepto de proyectos terminados, según decisión, y financiados por contribuciones adicionales asciende a la suma de 6.322.577 $EUA (2.339 $EUA por parte de organismos bilaterales y 6.320.238 $EUA por parte de organismos de ejecución).

Fondos a reintegrar por parte de organismos de ejecución

# Según se muestra en el Cuadro 1, el total de fondos a reintegrar por parte de los organismos de ejecución asciende a la suma de 6.320.238 $EUA.

# Cuadro 1. Fondos a reintegrar a la 88ª reunión por parte de organismos de ejecución ($EUA)

| Organismo | Costos de proyecto | Gastos de apoyo | Total |
| --- | --- | --- | --- |
| PNUD | 2.261.506 | 168.607 | 2.430.113 |
| PNUMA | 3.165.404 | 241.892 | 3.407.296 |
| ONUDI | 36.947 | 2.678 | 39.625 |
| Banco Mundial | 0 | 443.204 | 443.204 |
| Total | 5.463.857 | 856.381 | 6.320.238 |

# El Cuadro 2 muestra los saldos retenidos por organismos de ejecución por concepto de proyectos terminados, según decisión, y financiados por contribuciones voluntarias adicionales.

Cuadro 2. Saldos retenidos por organismos de ejecución por concepto de proyectos terminados, según decisión y financiados por contribuciones voluntarias adicionales (incluye gastos de apoyo)

| Año de término | PNUD |  | PNUMA |  | ONUDI |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Cantidad | ($EUA) | Cantidad | ($EUA) | Cantidad | ($EUA) | Cantidad | ($EUA) |
| Proyectos terminados hace más de dos años |  |  |  |  |  |  |  |  |
| 2017 | 1 | 21.740 | 0 | 0 | 0 | 0 | 1 | 21.740 |
| 2018 | 1 | 1.787 | 0 | 0 | 0 | 0 | 1 | 1.787 |
| 1º ene. al 31 oct. 2019 | 1 | 2.246 | 0 | 0 | 0 | 0 | 1 | 2.246 |
| Subtotal | 3 | 25.773 | 0 | 0 | 0 | 0 | 3 | 25.773 |
| Proyectos terminados hace menos de dos años |  |  |  |  |  |  |  |  |
| 1º nov. al 31 dic. 2019 | 13 | 842.341 | 0 | 0 | 0 | 0 | 13 | 842.341 |
| 2020 | 20 | 3.218.499 | 2 | 18.257 | 11 | 1.235.473 | 33 | 4.472.229 |
| Subtotal | 33 | 4.060.840 | 2 | 18.257 | 11 | 1.235.473 | 46 | 5.314.570 |
| Total | 36 | 4.086.613 | 2 | 18.257 | 11 | 1.235.473 | 49 | 5.340.343 |
| Proyectos según decisión (en curso) |  |  |  |  |  |  |  |  |
|  | 1 | 135.001 | 2 | 116.344 | 0 | 0 | 3 | 251.345 |
| Contribuciones voluntarias adicionales |  |  |  |  |  |  |  |  |
|  | 3 | 22.223 | 0 | 0 | 0 | 0 | 3 | 22.223 |
| Total general | 40 | 4.243.837 | 4 | 134.601 | 11 | 1.235.473 | 55 | 5.613.911 |

Fondos a reintegrar por parte de organismos bilaterales

# El total de fondos a reintegrar por parte de los organismos bilaterales asciende a la suma de 2.339 $EUA, cifra consistente en 2.070 $EUA más gastos de apoyo de 269 $EUA para Australia.

# Japón mantuvo un saldo a su haber de 18.080 $EUA, cifra que incluye gastos de apoyo, por concepto de un proyecto terminado durante el año 2020.

Disponibilidad de recursos

# El documento Situación de las contribuciones y los desembolsos muestra al 12 de octubre de 2021 un saldo disponible de 385.240.783 $EUA. El total reintegrado a la 88ª reunión por los organismos bilaterales y de ejecución asciende a la suma de 6.322.577 $EUA. En consecuencia, el nivel total de recursos disponibles para aprobación durante la 88ª reunión asciende a la cifra de 391.563.360 $EUA.

Observaciones de la Secretaría

# La Secretaría recordó a los organismos bilaterales y de ejecución que los saldos provenientes de proyectos según decisión y de proyectos terminados hace un año o más deben ser reintegrados al Fondo Multilateral a la brevedad.

# Al 18 de octubre de 2021, el nivel total de recursos disponibles para proyectos y actividades que se presenta a la 88ª reunión asciende a la suma de 81.490.200 $EUA, cifra que se estima como suficiente para solventar las aprobaciones previstas durante la 88ª reunión.

Recomendaciones

# El Comité Ejecutivo podrá estimar oportuno:

## Tomar nota de:

- El informe sobre saldos y disponibilidad de recursos recogido en el documento UNEP/OzL.Pro/ExCom/88/4;

- Que el nivel neto de fondos reintegrados a la 88ª reunión por organismos de ejecución asciende a 6.320.238 $EUA, cifra consistente en 2.261.506 $EUA más gastos de apoyo de 168.607 $EUA del PNUD; 3.165.404 $EUA más gastos de apoyo de 241.892 $EUA del PNUMA; 36.947 $EUA más gastos de apoyo de 2.678 $EUA de la ONUDI, y gastos de apoyo de 443.204 $EUA del Banco Mundial;

- Que el PNUD mantenía a su haber saldos de 25.773 $EUA, incluyendo gastos de apoyo, por concepto de tres proyectos terminados hace más de dos años, y de 22.223 $EUA, incluyendo gastos de apoyo, por concepto de tres proyectos financiados por contribuciones voluntarias adicionales para actividades de apoyo a la reducción de los HFC que ya fueron terminadas;

- Que el PNUMA mantenía a su haber saldos de 116.344 $EUA, incluyendo gastos de apoyo, por concepto de dos proyectos terminados “según decisión del Comité Ejecutivo”;

- Que el nivel neto de fondos que el Gobierno de Australia debe reintegrar a la 88ª reunión asciende a la suma de 2.070 $EUA más gastos de apoyo de 269 $EUA;

## Solicitar:

### A los organismos bilaterales y de ejecución, proceder al desembolso o bien a la cancelación de los fondos comprometidos y no comprometidos que ya no se precisen para proyectos terminados o para aquellos terminados “por decisión del Comité Ejecutivo”, y reintegrar los respectivos saldos a la 90ª reunión;

### Al PNUD, proceder al desembolso o cancelación de sus compromisos respecto de los restantes tres proyectos terminados hace más de dos años, y reintegrar los saldos a la 90ª reunión;

### Al PNUD, reintegrar a la 90ª reunión el saldo de tres proyectos terminados que fueron financiados con contribuciones voluntarias adicionales;

### Al PNUMA, reintegrar a la 90ª reunión el saldo de dos proyectos terminados “por decisión del Comité Ejecutivo”, según lo dispuesto en la decisión 86/16 f) i); y

### A Tesorería, consultar al Gobierno de Australia respecto del reintegro en efectivo de la suma de 2.339 $EUA mencionada en el párrafo a) v) anterior.

Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES AND BILATERAL AGENCIES FOR COMPLETED PROJECTS

| Code | Project title | Date completed (Actual) | Approved funding plus adjustments as of 31 December 2020(US $) | Funds disbursed as of 88th meeting (US $) | Balances committed as per 88th meeting (US $) | Balances not-committed as per 88th meeting (US $) | Support cost on balances committed and not committed as per 88th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| BHU/PHA/76/TAS/26 | HCFC phase-out management plan (third tranche) | Nov-19 | 57,000 | 56,359 | 641 |  | 58 |  |  |  |
| BRU/PHA/82/INV/23 | HCFC phase-out management plan (stage I, third tranche) | Dec-20 | 33,000 | 26,549 | 6,451 |  | 581 |  |  |  |
| COS/PHA/81/PRP/58 | Preparation of a HCFC phase-out management plan (stage II) | Mar-20 | 40,000 | 38,883 | 1,117 |  | 78 |  |  |  |
| COS/PHA/83/INV/59 | HCFC phase-out management plan (stage I, fifth tranche) | Dec-20 | 56,000 | 49,952 | 6,048 |  | 454 |  |  |  |
| COS/SEV/80/INS/56 | Extension of institutional strengthening project (phase XII: 1/2018-12/2019) | Dec-19 | 179,857 | 174,459 | 5,398 |  | 378 |  |  |  |
| CUB/PHA/82/TAS/60 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 22,236 | 7,764 |  | 699 |  |  |  |
| EGY/PHA/68/INV/117 | HCFC phase-out management plan (stage I, second tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | Dec-19 | 2,000,000 | 1,896,153 | 103,847 |  | 7,789 |  |  |  |
| EGY/PHA/82/INV/139 | HCFC phase-out management plan (stage I, third tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | Dec-19 | 716,400 | 530,037 | 186,363 |  | 13,977 |  |  |  |
| FIJ/PHA/73/INV/27 | HCFC phase-out management plan (stage I, second tranche) | Jun-17 | 37,900 | 17,955 | 19,945 |  | 1,795 |  |  |  |
| FIJ/PHA/77/INV/31 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 59,850 | 55,584 | 4,266 |  | 384 |  |  |  |
| FIJ/PHA/82/TAS/35 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 3,718 | 26,282 |  | 2,365 |  |  |  |
| GHA/PHA/81/INV/46 | HCFC phase-out management plan (stage I, fifth tranche) | Dec-20 | 125,000 | 105,139 | 19,861 |  | 1,490 |  |  |  |
| GHA/PHA/81/PRP/44 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 60,000 | 49,389 | 10,611 |  | 743 |  |  |  |
| GHA/SEV/82/INS/47 | Extension of the institutional strengthening project (phase XIII: 1/2018-12/2020) | Dec-20 | 178,048 | 177,391 | 657 |  | 46 |  |  |  |
| GUY/PHA/75/INV/28 | HCFC phase-out management plan (stage II, first tranche) | Dec-19 | 159,750 | 111,244 | 48,506 |  | 3,396 |  |  |  |
| IDS/PHA/71/TAS/200 | HCFC phase-out management plan (project management and coordination) (stage I, second tranche) | Jun-20 | 201,674 | 42,383 | 159,291 |  | 11,947 |  |  |  |
| IDS/PHA/76/INV/208 | HCFC phase-out management plan (stage I, third tranche) (refrigeration and air-conditioning sector) | Jun-20 | 512,190 | 244,358 | 267,832 |  | 20,087 |  |  |  |
| IDS/SEV/80/INS/212 | Extension of institutional strengthening project (phase XI: 1/2018-12/2019) | Dec-19 | 347,194 | 343,303 | 3,891 |  | 272 |  |  |  |
| IND/SEV/76/INS/467 | Extension of institutional strengthening project (phase X: 4/2016-3/2018) | Dec-19 | 477,734 | 477,682 | 52 |  | 4 |  |  |  |
| KYR/PHA/81/INV/40 | HCFC phase-out management plan (stage II, second tranche) | Dec-20 | 175,000 | 108,104 | 66,896 |  | 4,683 |  |  |  |
| MEX/PHA/71/INV/168 | HCFC phase-out management plan (stage I, third tranche) (foam sector plan for systems houses and local customers) | Dec-19 | 3,800,000 | 3,388,171 | 411,829 |  | 30,887 |  |  |  |
| MEX/REF/81/INV/187 | Conversion of domestic refrigeration manufacturing facility from HFC-134a to isobutane as a refrigerant and conversion of compressors manufacturing facility from HFC-134a-based to isobutane-based at Mabe Mexico | Nov-20 | 2,115,012 | 2,110,680 | 4,332 |  | 303 |  |  |  |
| MLI/PHA/76/INV/38 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 92,000 | 77,893 | 14,107 |  | 1,058 |  |  |  |
| NEP/PHA/75/INV/35 | HCFC phase-out management plan (stage I, second tranche) | Dec-19 | 33,600 | 30,916 | 2,684 |  | 242 |  |  |  |
| PAR/PHA/74/INV/34 | HCFC phase-out management plan (stage I, second tranche) | Dec-19 | 131,500 | 129,642 | 1,858 |  | 139 |  |  |  |
| SRL/PHA/82/PRP/52 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 40,000 | 29,919 | 10,081 |  | 706 |  |  |  |
| SRL/PHA/82/TAS/51 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 23,657 | 6,343 |  | 571 |  |  |  |
| SRL/SEV/82/INS/53 | Extension of the institutional strengthening project (phase XII: 1/2019-12/2020) | Dec-20 | 171,592 | 136,511 | 35,081 |  | 2,456 |  |  |  |
| URU/PHA/77/INV/67 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Dec-20 | 100,000 | 38,101 | 61,899 |  | 4,333 |  |  |  |
| URU/PHA/77/TAS/69 | HCFC phase-out management plan (stage II, first tranche) (implementation and monitoring) | Dec-18 | 35,800 | 34,130 | 1,670 |  | 117 |  |  |  |
| URU/SEV/80/INS/70 | Extension of institutional strengthening project (phase XII: 1/2018-12/2019) | Dec-19 | 193,024 | 192,729 | 295 |  | 21 |  |  |  |
| VEN/SEV/77/INS/135 | Renewal of institutional strengthening project (phase XIII: 1/2017-12/2018) | Mar-19 | 365,414 | 363,315 | 2,099 |  | 147 |  |  |  |
| ZIM/PHA/83/PRP/58 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 20,000 | 11,435 | 8,565 |  | 600 |  |  |  |
| TOTAL UNDP |  |  |  |  | 3,807,156 |  | 279,457 |  |  |  |
| UNEP |  |  |  |  |  |  |  |  |  |  |
| LAO/PHA/74/TAS/27 | HCFC phase-out management plan (stage I, second tranche) | Dec-20 | 97,875 | 86,875 |  | 11,000 | 1,430 | UNEP is working on financial closure of the project. | ExCom 90 |  |
| UGA/PHA/82/PRP/24 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 20,000 | 14,844 |  | 5,156 | 670 | Once project is financially completed | ExCom 89 |  |
| TOTAL UNEP |  |  |  |  |  | 16,157 | 2,100 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| JOR/REF/81/INV/103 | Conversion of large commercial unitary roof top air-conditioning units of up to 400kW manufacturing facility from HFC (R134a, R407c, R410a) to propane R290 as refrigerant at Petra Engineering Industries Co. | Jun-20 | 1,637,610 | 1,524,521 | 113,089 |  | 7,917 | 3 | 90 |  |
| MOG/PHA/84/TAS/14 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 24,091 | 5,909 |  | 532 | 3 | 90 |  |
| NER/PHA/82/TAS/34 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 29,658 | 342 |  | 31 | 3 | 90 |  |
| PAK/PHA/76/TAS/95 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Dec-20 | 190,000 | 180,077 | 9,923 |  | 695 | 3 | 90 |  |
| QAT/PHA/73/PRP/21 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 40,000 | 39,629 | 372 |  | 26 | 3 | 90 |  |
| RWA/PHA/77/INV/27 | HCFC phase-out management plan (stage I, third tranche) | Dec-20 | 55,000 | 54,664 | 336 |  | 30 | 3 | 90 |  |
| SAU/PHA/72/INV/21 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Dec-20 | 2,693,674 | 2,080,492 | 613,182 |  | 42,923 | 3 | 90 | 86/17(i)(i) |
| SAU/REF/76/DEM/28 | Demonstration project on promoting HFO-based low-global warming potential refrigerants for air-conditioning sector in high ambient temperatures | Dec-20 | 1,300,000 | 903,494 | 396,506 |  | 27,755 | 3 | 90 | 83/33(c) and 85/17(c) |
| SIL/PHA/76/INV/31 | HCFC phase-out management plan (stage I, third tranche) | Dec-20 | 50,000 | 48,855 | 1,145 |  | 103 | 2 | 90 |  |
| SOA/PHA/67/TAS/04 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | Dec-20 | 110,005 | 103,224 | 6,782 |  | 474 | 2 | 90 |  |
| SOA/PHA/71/INV/05 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Dec-19 | 2,042,620 | 2,035,702 | 6,918 |  | 484 | 3 | 90 |  |
| TOTAL UNIDO |  |  |  |  | 1,154,504 |  | 80,969 |  |  |  |
| JAPAN |  |  |  |  |  |  |  |  |  |  |
| CPR/PHA/77/TAS/582 | HCFC phase-out management plan (stage II, first tranche) (refrigeration and air-conditioning servicing sector plan and enabling component) | Dec-20 | 80,000 | 64,000 | 16,000 |  | 2,080 |  |  |  |
| TOTAL JAPAN |  |  |  |  | 16,000 |  | 2,080 |  |  |  |

Annex II

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR BY-DECISIONS PROJECTS

| Code | Project title | Financial date of completion per decision | Approved funding plus adjustments as of 31 December 2020 (US $) | Funds disbursed as of 88th meeting (US $) | Balances committed as per 88th meeting (US $) | Balances not- committed as per 88th meeting (US $) | Support cost on balances committed and not-committed as per 88th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| BRA/DES/72/DEM/305 | Pilot demonstration project on ODS waste management and disposal | Dec-23 | 1,490,600 | 1,364,430 | 126,179 |  | 8,832 |  |  | 79/18(c)(i) and 81/24(e)(ii) |
| TOTAL UNDP |  |  |  |  | 126,179 |  | 8,832 |  |  |  |
| UNEP |  |  |  |  |  |  |  |  |  |  |
| SAU/PHA/68/TAS/16 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | 87th meeting | 233,674 | 182,206 | 32,350 |  | 4,007 |  |  | 86/16(f)(i) |
| SAU/PHA/77/TAS/32 | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, custom training and monitoring) | 87th meeting | 130,400 | 50,589 | 71,170 |  | 8,817 |  |  | 86/16(f)(i) |
| TOTAL UNEP |  |  |  |  | 103,520 |  | 12,824 |  |  |  |

Annex III

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL CONTRIBUTIONS PROJECTS

| CODE | Project title | Approved funding plus adjustments as of 31 December 2020 (US $) | Funds disbursed as of 88th meeting (US $) | Balances committed as per 88th meeting (US $) | Balances not- committed as per 88th meeting (US $) | Support cost on balances committed and not-committed as per 88th meeting (US $) | Why any balances could not be returned? | When they could be returned? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COS/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 150,000 | 144,830 | 5,170 |  | 362 |  |  |
| JAM/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 150,000 | 145,083 | 4,917 |  | 344 |  |  |
| TRI/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 150,000 | 139,318 | 10,682 |  | 748 |  |  |
| TOTAL UNDP |  |  |  | 20,769 |  | 1,454 |  |  |

Annex IV

DETAILS ON COMPLETED PROJECTS, BY-DECISION AND PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES AND BILATERAL AGENCIES

| Code | Project title | Project costs returned (US $) | Agency support costs (US $) | Total (US $) |
| --- | --- | --- | --- | --- |
| ARM/PHA/84/TAS/23 | Verification report on the implementation of the HCFC phase-out management plan | 370 | 33 | 403 |
| BRA/PHA/74/INV/307 | HCFC phase-out management plan (stage I, fourth tranche) (foam sector plan) | 1,020,974 | 76,573 | 1,097,547 |
| BRA/PHA/75/INV/315 | HCFC phase-out management plan (stage I, fifth tranche) (foam sector) | 1,032,897 | 77,468 | 1,110,365 |
| COL/PHA/75/TAS/92 | HCFC phase-out management plan (stage II, first tranche) (technical assistance in policies formulation and implementation) | 5 | 0 | 5 |
| COS/REF/76/DEM/55 | Demonstration of the application of an ammonia/carbon dioxide refrigeration system in replacement of HCFC-22 for the medium-sized producer and retail store of Premezclas Industriales S.A. | 697 | 49 | 746 |
| COS/SEV/75/INS/53 | Extension of institutional strengthening project (phase XI: 1/2016-12/2017) | 198 | 14 | 212 |
| CUB/SEV/75/INS/54 | Extension of institutional strengthening project (phase X: 1/2016-12/2017) | 1 | 0 | 1 |
| DOM/REF/81/INV/63 | Conversion of a commercial refrigerator manufacturing line at Fábrica de Refrigeradores Comerciales, SRL (FARCO) from HFC-134a and R-404A to propane (R-290) as refrigerant | 24 | 2 | 26 |
| DRC/PHA/80/INV/45 | HCFC phase-out management plan (stage I, third tranche) | 476 | 43 | 519 |
| EGY/FOA/76/DEM/129 | Demonstration of low-cost options for the conversion to non-ODS technologies in polyurethane foams at very small users | 190,799 | 13,356 | 204,155 |
| EGY/PHA/74/PRP/126 | Preparation of a HCFC phase-out management plan (stage II) | 11,860 | 830 | 12,690 |
| ELS/PHA/77/INV/34 | HCFC phase-out management plan (stage I, third tranche) | 1,052 | 79 | 1,131 |
| IDS/PHA/71/INV/199 | HCFC phase-out management plan (air conditioning sector plan) (stage I, second tranche) | 380 | 29 | 409 |
| IDS/SEV/75/INS/206 | Extension of institutional strengthening project (phase X: 1/2016-12/2017) | 29 | 2 | 31 |
| IND/PHA/75/INV/463 | CTC phase-out plan for the consumption and production sectors: 2009 annual programme | 48 | 4 | 52 |
| IND/SEV/72/INS/457 | Extension of institutional strengthening project (phase X: 4/2014-3/2016) | 182 | 13 | 195 |
| MDV/PHA/69/INV/24 | HCFC phase-out management plan (second tranche) | 3 | 0 | 3 |
| NIR/PHA/75/INV/143 | HCFC phase-out management plan (stage I, fifth tranche) (foam sector and refrigeration servicing) | 1,511 | 113 | 1624 |
| Total completed projects |  | 2,261,506 | 168,607 | 2,430,113 |
| TOTAL UNDP |  | 2,261,506 | 168,607 | 2,430,113 |
| AFG/PHA/82/PRP/24 | Preparation of a HCFC phase-out management plan (stage II) | 273 | 35 | 308 |
| AFG/SEV/80/INS/23 | Extension of institutional strengthening project (phase VIII: 1/2018-12/2019) | 5,754 | 0 | 5,754 |
| BEN/SEV/80/INS/35 | Renewal of institutional strengthening project (phase X: 1/2018-12/2019) | 2,663 | 0 | 2,663 |
| BKF/PHA/84/TAS/40 | Verification report on the implementation of the HCFC phase-out management plan | 710 | 92 | 802 |
| BZE/PHA/82/TAS/35 | Verification report on the implementation of the HCFC phase-out management plan | 9,800 | 1,274 | 11,074 |
| CHI/PHA/76/TAS/193 | HCFC phase-out management plan (stage I, fourth and fifth tranches) | 507 | 66 | 573 |
| CKI/SEV/77/INS/13 | Extension of the institutional strengthening project (phase VI: 1/2017-12/2018) | 5,000 | 0 | 5,000 |
| ECU/PHA/76/TAS/64 | HCFC phase-out management plan (stage I, third tranche) | 14,590 | 1,897 | 16,487 |
| ECU/PHA/82/PRP/67 | Preparation of a HCFC phase-out management plan (stage II) | 9,900 | 1,287 | 11,187 |
| ECU/PHA/82/TAS/69 | HCFC phase-out management plan (stage I, fourth tranche) | 1,235 | 161 | 1,396 |
| ECU/PHA/85/TAS/73 | HCFC phase-out management plan (stage I, fifth tranche) | 10,000 | 1,300 | 11,300 |
| ECU/PHA/86/TAS/74 | HCFC phase-out management plan (stage II, first tranche) | 24,000 | 3,120 | 27,120 |
| ECU/SEV/83/INS/71 | Extension of institutional strengthening project (phase VII: 7/2019-6/2021) | 226,305 | 0 | 226,305 |
| ELS/PHA/65/TAS/28 | HCFC phase-out management plan (stage I, first tranche) | 6,531 | 229 | 6,760 |
| ERI/PHA/82/TAS/17 | Verification report on the implementation of the HCFC phase-out management plan | 982 | 128 | 1,110 |
| FSM/SEV/77/INS/12 | Renewal of institutional strengthening project (phase VI: 1/2017-12/2018) | 969 | 0 | 969 |
| GAM/PHA/82/TAS/36 | Verification report on the implementation of the HCFC phase-out management plan | 1,096 | 142 | 1,238 |
| GBS/PHA/71/TAS/17 | HCFC phase-out management plan (stage I, second tranche) | 22,921 | 2,980 | 25,901 |
| GLO/SEV/82/TAS/347 | Compliance Assistance Programme: 2019 budget | 10,677 | 854 | 11,531 |
| GLO/SEV/84/TAS/350 | Compliance Assistance Programme: 2020 budget | 2,611,540 | 208,923 | 2,820,463 |
| GUA/PHA/82/PRP/54 | Preparation of a HCFC phase-out management plan (stage II) | 1,828 | 238 | 2,066 |
| HAI/PHA/68/TAS/18 | HCFC phase-out management plan (stage I, first tranche) | 20,109 | 2,614 | 22,723 |
| HON/PHA/82/PRP/46 | Preparation of a HCFC phase-out management plan (stage II) | 9,706 | 1,262 | 10,968 |
| IRQ/PHA/65/TAS/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 4,734 | 582 | 5,316 |
| IRQ/PHA/73/PRP/21 | Preparation of a HCFC phase-out management plan (stage II) | 6,886 | 895 | 7,781 |
| LAO/PHA/82/TAS/32 | Verification report on the implementation of the HCFC phase-out management plan | 5,780 | 751 | 6,531 |
| MAG/PHA/82/TAS/31 | Verification report on the implementation of the HCFC phase-out management plan | 1,076 | 140 | 1,216 |
| MDV/SEV/81/INS/33 | Extension of the institutional strengthening project (phase X: 12/2018-11/2020) | 10,000 | 0 | 10,000 |
| MLW/PHA/82/TAS/44 | Verification report on the implementation of the HCFC phase-out management plan | 1,547 | 201 | 1,748 |
| MOL/SEV/77/INS/36 | Extension of the institutional strengthening project (phase IX: 1/2017-12/2018) | 18,617 | 0 | 18,617 |
| MON/PHA/82/PRP/27 | Preparation of a HCFC phase-out management plan (stage II) | 4,850 | 631 | 5,481 |
| MON/PHA/82/TAS/28 | Verification report on the implementation of the HCFC phase-out management plan | 1,967 | 256 | 2,223 |
| NEP/PHA/82/TAS/39 | Verification report on the implementation of the HCFC phase-out management plan | 4,744 | 617 | 5,361 |
| NIC/PHA/74/TAS/31 | HCFC phase-out management plan (stage I, second tranche) | 3,072 | 399 | 3,471 |
| NIC/PHA/83/PRP/38 | Preparation of a HCFC phase-out management plan (stage II) | 4,850 | 631 | 5,481 |
| PAR/SEV/77/INS/36 | Extension of institutional strengthening project (phase VIII: 1/2017-12/2018) | 4,938 | 0 | 4,938 |
| SAM/PHA/82/TAS/22 | Verification report on the implementation of the HCFC phase-out management plan | 2,519 | 327 | 2,846 |
| SOI/PHA/82/TAS/15 | Verification report on the implementation of the HCFC phase-out management plan | 7,926 | 1,030 | 8,956 |
| STV/PHA/77/TAS/24 | Verification report on the implementation of the HCFC phase-out management plan | 14,738 | 1,916 | 16,654 |
| SYR/PHA/83/PRP/105 | Preparation of a HCFC phase-out management plan (stage II) | 17,375 | 2,259 | 19,634 |
| TON/PHA/82/TAS/14 | Verification report on the implementation of the HCFC phase-out management plan | 5,589 | 727 | 6,316 |
| TTR/PHA/82/TAS/14 | Verification report on the implementation of the HCFC phase-out management plan | 5,623 | 731 | 6,354 |
| UGA/PHA/77/TAS/21 | HCFC phase-out management plan (stage I, second tranche) | 3,500 | 455 | 3,955 |
| UGA/PHA/82/TAS/25 | Verification report on the implementation of the HCFC phase-out management plan | 380 | 49 | 429 |
| URT/PHA/82/TAS/38 | Verification report on the implementation of the HCFC phase-out management plan | 485 | 63 | 548 |
| ZAM/PHA/82/TAS/35 | Verification report on the implementation of the HCFC phase-out management plan | 529 | 69 | 598 |
| Total completed projects |  | 3,128,821 | 239,331 | 3,368,152 |
| MON/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 2,134 | 149 | 2,283 |
| TTR/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 25,000 | 1,750 | 26,750 |
| ZIM/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 9,449 | 661 | 10,110 |
| Total “additional voluntary contributions” projects |  | 36,583 | 2,561 | 39,143 |
| TOTAL UNEP |  | 3,165,404 | 241,892 | 3,407,296 |
| ARG/PHA/79/TAS/181 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | 1,298 | 91 | 1,389 |
| BOL/PHA/82/PRP/47 | Preparation of a HCFC phase-out management plan (stage II) | 26 | 2 | 28 |
| EGY/ARS/50/INV/92 | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | 681 | 51 | 732 |
| EGY/SEV/81/INS/138 | Extension of the institutional strengthening project (phase XII: 1/2019-12/2020) | 1,253 | 88 | 1,341 |
| GAB/PHA/62/INV/27 | HCFC phase-out management plan (stage I, first tranche) | 42 | 4 | 46 |
| GLO/REF/76/DEM/333 | Demonstration project on refrigerant quality, containment and introduction of low-global warming potential alternatives (Eastern Africa and Caribbean regions) | 3,212 | 225 | 3,437 |
| GUA/PHA/84/TAS/56 | Verification report on the implementation of the HCFC phase-out management plan | 3,403 | 306 | 3,709 |
| HON/PHA/84/TAS/49 | Verification report on the implementation of the HCFC phase-out management plan | 285 | 26 | 311 |
| SAU/PHA/68/INV/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | 6,628 | 464 | 7,092 |
| SAU/PHA/68/INV/19 | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | 215 | 15 | 230 |
| SEN/PHA/65/INV/31 | HCFC phase-out management plan (stage I, first tranche) | 521 | 39 | 560 |
| SEN/PHA/77/INV/36 | HCFC phase-out management plan (stage I, second tranche) | 1,988 | 149 | 2,137 |
| SOM/PHA/77/TAS/13 | HCFC phase-out management plan (stage I, second tranche) (additional security) | 8,172 | 572 | 8,744 |
| TKM/PHA/76/INV/12 | HCFC phase-out management plan (stage I, third tranche) | 91 | 7 | 98 |
| UGA/PHA/82/PRP/23 | Preparation of a HCFC phase-out management plan (stage II) | 26 | 2 | 28 |
| Total completed projects |  | 27,841 | 2,040 | 29,881 |
| SAU/PHA/68/INV/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | 6,628 | 464 | 7,092 |
| Total “by decision” projects |  | 6,628 | 464 | 7,092 |
| ARM/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 361 | 26 | 387 |
| LEB/REF/80/PRP/01 | Project preparation for HFC-related projects in the manufacturing sector at Lematic Industries to gain experience in ICCs and IOCs associated with the phase-down of HFCs in domestic refrigeration | 2,106 | 147 | 2,253 |
| TUN/SEV/80/TAS/02 | Enabling activities for HFC phase-down | 10 | 1 | 11 |
| Total “additional voluntary contributions” projects |  | 2,478 | 174 | 2,652 |
| TOTAL UNIDO |  | 36,947 | 2,678 | 39,625 |
| GLO/SEV/84/TAS/351 | Core unit budget (2020) | 0 | 443,204 | 443,204 |
| TOTAL WORLD BANK |  |  | 443,204 | 443,204 |
| IDS/PHA/64/TAS/196 | HCFC phase-out management plan (technical assistance for refrigerant management) (stage I, first tranche) | 2,070 | 269 | 2,339 |
| TOTAL AUSTRALIA |  | 2,070 | 269 | 2,339 |

Debido a la pandemia del coronavirus, en los meses de noviembre y diciembre de 2021 se realizarán reuniones telemáticas y un proceso de aprobación entre sesiones.

Basados en el formato de presentación de informes elaborado de conformidad con la decisión 31/2.

UNEP/OzL.Pro/ExCom/88/3.

2: Financial completion initiated; 3: Financial completion being initiated; 4: Financial completion to be initiated after settlement of all pending issues; 5: Project is ongoing; 6: Funds were not transferred.