| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/95/82 19 November 2024 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-fifth Meeting

Montreal, 4-8 December 2024

Item 9(d) of the provisional agenda

PROJECT PROPOSAL: ZIMBABWE

This document consists of the comments and recommendation of the Secretariat on the following project proposal:

Phase-down

| - Kigali HFC implementation plan (stage I, first tranche) | UNEP and UNDP | Individual consideration |
| --- | --- | --- |

PROJECT EVALUATION SHEET – MULTI-YEAR PROJECTS

Zimbabwe

| PROJECT TITLE | AGENCY |
| --- | --- |
| Kigali HFC implementation plan (stage I) | UNEP (lead), UNDP |

| LATEST ARTICLE 7 DATA (Annex F) | Year: 2023 | 378.40 mt | 842,264 CO2-eq tonnes |
| --- | --- | --- | --- |

| SECTORAL HFC CONSUMPTION DATA (CO2-eq tonnes) AND ACTIVITIES |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Aerosol | Foam | Fire-fighting | AC and refrigeration |  |  |  | Solvent | Other |
|  |  |  |  | Manufacturing |  |  | Servicing |  |  |
|  |  |  |  | Refrigeration | AC | Other |  |  |  |
| Latest CP report (2023) |  |  | 4,444 | 35,049 |  |  | 802,771 |  |  |
| KIP stage I activities as agreed (Y/N) |  |  | N | N |  |  | Y |  |  |

| Average 2020-2022 HFC consumption in servicing | 345.77 mt | 800,084 CO2-eq tonnes |
| --- | --- | --- |

| BASELINE CONSUMPTION DATA (CO2-eq tonnes) | 2020 | 2021 | 2022 | Average 2020-2022 |
| --- | --- | --- | --- | --- |
| HFC annual consumption | 1,009,387 | 733,188 | 795,792 | 846,122 |
| HCFC baseline (65%) |  |  |  | 364,502 |
| HFC baseline |  |  |  | 1,210,624 |

| HFC CONSUMPTION ELIGIBLE FOR FUNDING |  |
| --- | --- |
| Starting point for sustained aggregate reductions | TBD |
| Previously approved HFC phase-down investment projects | Yes |
| Aggregate reductions from previously approved projects (CO2-eq tonnes) | 20,735 |

| PROJECT DATA AS AGREED |  |  | 2024* | 2025 | 2026 | 2027 | 2028 | 2029 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Consumption (CO2-eq tonnes) | Montreal Protocol limits |  | 1,210,624 | 1,210,624 | 1,210,624 | 1,210,624 | 1,210,624 | 1,089,561 | n/a |
|  | Maximum allowable |  | 945,654 | 945,654 | 945,654 | 945,654 | 892,463 | 761,510 | n/a |
|  | Maximum allowable (%) |  | 78 | 78 | 78 | 78 | 74 | 63 | n/a |
| Amounts recommended in principle (US $) | UNEP | Project costs | 151,500 | 0 | 0 | 106,500 | 0 | 54,000 | 312,000 |
|  |  | Support costs | 19,695 | 0 | 0 | 13,845 | 0 | 7,020 | 40,560 |
|  | UNDP | Project costs | 90,000 | 0 | 0 | 0 | 0 | 30,000 | 120,000 |
|  |  | Support costs | 11,700 | 0 | 0 | 0 | 0 | 3,900 | 15,600 |
|  | Total project costs |  | 241,500 | 0 | 0 | 106,500 | 0 | 84,000 | 432,000 |
|  | Total support costs |  | 31,395 | 0 | 0 | 13,845 | 0 | 10,920 | 56,160 |
|  | Total funds |  | 272,895 | 0 | 0 | 120,345 | 0 | 94,920 | 488,160 |

* Recommended for approval at the present meeting

| Reduction from remaining consumption eligible for funding in CO2-eq tonnes | 469,849* |
| --- | --- |

* Includes the reduction of 20,735 CO2-eq tonnes from previously approved projects

| Secretariat's recommendation: | Individual consideration |
| --- | --- |

PROJECT DESCRIPTION

# The present document contains the following sections:

- Summary of the proposal as submitted

- Background: Implementation status of the country’s HCFC phase-out management plan and previous HFC-related projects

- HFC consumption: Overview of the country’s HFC consumption levels, trends, and sectoral uses

- Stage I of the Kigali HFC implementation plan, as submitted: Overarching strategy and plan of implementation for the first tranche

- Secretariat’s comments, including the agreed cost of activities

- Recommendation

# I.	Summary of the proposal as submitted

# On behalf of the Government of Zimbabwe, UNEP as the lead implementing agency has submitted a request for stage I of the Kigali HFC implementation plan (KIP), at a total cost of US $406,800, consisting of US $240,000, plus agency support costs of US $31,200 for UNEP and US $120,000, plus agency support costs of US $15,600 for UNDP, as originally submitted.

# The implementation of stage I of the KIP will assist the Government of Zimbabwe in meeting the target of 10 per cent reduction from its HFC baseline consumption by 1 January 2029.

# The first tranche of stage I of the KIP being requested at this meeting amounts to US $238,430, consisting of US $121,000, plus agency support costs of US $15,730 for UNEP and US $90,000, plus agency support costs of US $11,700 for UNDP, as originally submitted, for the period of January 2025 to December 2027.

II.	Background

# Status of implementation of the HCFC phase-out management plan

# Table 1 presents information on the HCFC phase-out management plan (HPMP) in Zimbabwe as of November 2024.

Table 1. HPMP implementation status for Zimbabwe

|  | Stage I | Stage II |
| --- | --- | --- |
| Meetings when HPMP was approved/updated | 65th/71st | 86th/92nd |
| Reduction from baseline | 35% by 2020 | 100% by 2030 |
| Total project cost (US $) | 1,038,818 | 1,160,000 |
| Date of completion (actual/planned) | 31 December 2021 | 31 December 2031 |

# Status of implementation of previous HFC-related activities

# Table 2 presents an overview of activities implemented in Zimbabwe in the context of the Kigali Amendment that have been funded by the Multilateral Fund.

# Table 2. Previously approved HFC-related activities in Zimbabwe

| Approval meeting | Project title | Implementing agency | Cost (US $) | Date of completion |
| --- | --- | --- | --- | --- |
| 74th | Survey of ODS alternatives | UNEP | 70,000 | Aug 2017 |
| 80th | Enabling activities for HFC phase-down | UNEP | 150,000 | Dec 2019 |
| 82nd | Conversion from HFC-134a to isobutane in the manufacture of domestic refrigerators at Capri | UNDP/France | 426,954 | Jun 2025* |

# * The project was originally expected to be completed in June 2023.

# The conversion of the domestic refrigerator manufacturing line at Capri has been delayed due to the COVIC-19 pandemic and the delayed delivery of equipment. All civil and structural works have been completed for the modification of the two manufacturing lines for freezers and refrigerators, respectively, including storage areas for the R-600a. Equipment was procured from Galileo, Italy and delivered in December 2023. With the assistance of the international expert from Galileo, equipment installation and commissioning have been planned; and installation of pipes is underway. The remaining activities to be implemented include training of personnel on safety aspects and safety audits. It is expected that the project will be completed by March 2025. A request for extension of project completion to June 2025 is being requested.

# III.	HFC consumption overview

# HFC consumption levels

# Zimbabwe only imports HFCs for use in the refrigeration manufacturing, refrigeration and air-conditioning (RAC) servicing, and firefighting sectors. The most consumed substances in 2023 were R-404A (37.0 per cent of total HFC consumption in CO2-equivalent (CO2-eq) tonnes), R-410A (28.7 per cent), and HFC-134a (18.7 per cent), followed by other HFCs (15.6 per cent). Table 3 presents the country’s HFC consumption as reported to the Ozone Secretariat under Article 7 of the Montreal Protocol.

# Table 3. HFC consumption in Zimbabwe (2019–2023 Article 7 data)

| HFC | GWP | 2019 | 2020 |  | 2021 |  | 2022 |  | 2023 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Metric tonnes (mt) |  |  |  |  |  |  |  |  |  |
| HFC-32 | 675 | 0.20 |  | 0.34 |  | 2.18 |  | 22.41 | 31.54 |
| HFC-125 | 3,500 | 0.00 |  | 0.57 |  | 0.57 |  | 0.00 | 0.00 |
| HFC-134a | 1,430 | 293.07 |  | 116.37 |  | 122.25 |  | 110.04 | 109.97 |
| HFC-227ea | 3,220 | 2.50 |  | 0.00 |  | 0.23 |  | 20.25 | 1.38 |
| R-404A | 3,922 | 79.04 |  | 84.01 |  | 62.15 |  | 58.89 | 79.53 |
| R-407C | 1,774 | 36.60 |  | 66.93 |  | 32.68 |  | 27.50 | 24.51 |
| R-410A | 2,088 | 91.57 |  | 96.20 |  | 107.35 |  | 96.34 | 115.94 |
| R-507A | 3,985 | 7.78 |  | 48.12 |  | 7.12 |  | 19.39 | 15.53 |
| R-508B | 6,808 | 0.01 |  | 0.00 |  | 0.00 |  | 0.00 | 0.00 |
| Total (mt) |  | 510.77 |  | 412.54 |  | 334.53 |  | 354.82 | 378.40 |
| CO2-eq tonnes |  |  |  |  |  |  |  |  |  |
| HFC-32 | 675 | 135 |  | 230 |  | 1,472 |  | 15,127 | 21,290 |
| HFC-125 | 3,500 | 0 |  | 1,995 |  | 1,995 |  | 0 | 0 |
| HFC-134a | 1,430 | 419,090 |  | 166,409 |  | 174,818 |  | 157,357 | 157,257 |
| HFC-227ea | 3,220 | 8,050 |  | 0 |  | 741 |  | 65,205 | 4,444 |
| R-404A | 3,922 | 309,963 |  | 329,454 |  | 243,727 |  | 230,943 | 311,885 |
| R-407C | 1,774 | 64,923 |  | 118,724 |  | 57,969 |  | 48,781 | 43,477 |
| R-410A | 2,088 | 191,152 |  | 200,818 |  | 224,093 |  | 201,110 | 242,025 |
| R-507A | 3,985 | 31,003 |  | 191,758 |  | 28,373 |  | 77,269 | 61,887 |
| R-508B | 6,808 | 68 |  | 0 |  | 0 |  | 0 | 0 |
| Total (CO2-eq tonnes) |  | 1,024,385 |  | 1,009,387 |  | 733,188 |  | 795,792 | 842,264 |

Established HFC baseline

# The Government of Zimbabwe reported the Article 7 data for 2020-2022. The country’s HFC consumption baseline was established at 1,210,624 CO2-eq tonnes by adding 65 per cent of its HCFC baseline (expressed in CO2-eq tonnes) to its average HFC consumption in 2020-2022, as shown in table 4.

# Table 4. HFC baseline calculation for Zimbabwe (CO2-eq tonnes)

| Baseline calculation components | 2020 | 2021 | 2022 |
| --- | --- | --- | --- |
| HFC annual consumption | 1,009,387 | 733,188 | 795,792 |
| HFC average consumption in 2020-2022 | 846,122 |  |  |
| HCFC baseline (65%) | 364,502 |  |  |
| HFC baseline | 1,210,624 |  |  |

Country programme implementation report

# The sectoral HFC consumption data provided by the Government of Zimbabwe in its country programme (CP) implementation report for 2023 is consistent with the data reported under Article 7 of the Montreal Protocol.

# HFC consumption trends

# HFC consumption decreased by 35 per cent from 2019 to 2021 due to the COVID-19 pandemic and economic slowdown, as well as potential stockpiling in 2019 due to anticipated controls on HFCs. However, HFC consumption has been increasing in 2022 and 2023, and this trend is expected to continue under a business-as-usual scenario with ongoing economic development.

# HFC consumption by sector

# HFCs are mainly used for RAC servicing (95 per cent in mt and CO2-eq tonnes) with the remaining amounts used in domestic and commercial refrigeration equipment manufacturing (4.8 per cent in mt and 4.2 per cent in CO2-eq tonnes) and in firefighting equipment servicing (less than 1 per cent).

# In the RAC servicing sector, HFCs are used in commercial, industrial and transport refrigeration (37.7 per cent in mt and 51.4 per cent in CO2-eq tonnes), followed by residential and commercial air-conditioning (AC) and chillers (45.5 per cent in mt and 36.4 per cent in CO2-eq tonnes), residential refrigeration equipment servicing (8.6 per cent in mt and 5.5 per cent in CO2-eq tonnes), and mobile air-conditioning (MAC) (2.4 per cent in mt and 1.5 per cent in CO2-eq tonnes), as shown in tables 5 and 6.

# Table 5. HFC consumption in Zimbabwe by sector in mt (2023)

| Sectors |  | HFC-134a | HFC-32 | HFC-227ea | R-404A | R-407C | R-410A | R-507A | Total | Share of total (%) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Manufacturing and assembly |  |  |  |  |  |  |  |  |  |  |
| Domestic refrigeration |  | 9.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 9.00 | 2.4 |
| Commercial refrigeration |  | 5.50 | 0.00 | 0.00 | 3.65 | 0.00 | 0.00 | 0.00 | 9.15 | 2.4 |
| MAC |  | 2.75 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 2.75 | 0.7 |
| Subtotal for manufacturing/assembly |  | 17.25 | 0.00 | 0.00 | 3.65 | 0.00 | 0.00 | 0.00 | 20.90 | 5.5 |
| Refrigeration and AC servicing |  |  |  |  |  |  |  |  |  |  |
| Domestic refrigeration |  | 32.40 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 32.40 | 8.6 |
| Commercial refrigeration | Stand-alone units | 13.35 | 0.00 | 0.00 | 3.90 | 0.00 | 0.00 | 0.00 | 17.25 | 4.6 |
|  | Condenser units (simplex) | 28.95 | 0.00 | 0.00 | 38.18 | 0.00 | 0.00 | 8.67 | 75.80 | 20.0 |
|  | Centralized systems | 0.00 | 0.00 | 0.00 | 22.60 | 0.00 | 0.00 | 5.33 | 27.93 | 7.4 |
| Industrial refrigeration |  | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 1.53 | 1.53 | 0.4 |
| Transport refrigeration |  | 8.90 | 0.00 | 0.00 | 11.2 | 0.00 | 0.00 | 0.00 | 20.10 | 5.3 |
| Residential AC |  | 0.00 | 10.13 | 0.00 | 0.00 | 0.00 | 28.84 | 0.00 | 38.97 | 10.3 |
| Packaged AC units |  | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 24.70 | 0.00 | 24.70 | 6.5 |
| Chiller AC units |  | 0.00 | 0.00 | 0.00 | 0.00 | 15.00 | 30.00 | 0.00 | 45.00 | 11.9 |
| Commercial AC |  | 0.00 | 21.41 | 0.00 | 0.00 | 9.51 | 32.40 | 0.00 | 63.32 | 16.7 |
| MAC |  | 9.12 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 9.12 | 2.4 |
| Subtotal for servicing |  | 92.72 | 31.54 | 0.00 | 75.88 | 24.51 | 115.94 | 15.53 | 356.12 | 94.1 |
| Firefighting servicing |  | 0.00 | 0.00 | 1.38 | 0.00 | 0.00 | 0.00 | 0.00 | 1.38 | 0.4 |
| Total |  | 109.97 | 31.54 | 1.38 | 79.53 | 24.51 | 115.94 | 15.53 | 378.40 | 100.0 |

# Table 6. HFC consumption in Zimbabwe by sector in CO2-eq tonnes (2023)

| Sectors |  | HFC-134a | HFC-32 | HFC-227ea | R-404A | R-407C | R-410A | R-507A | Total | Share of total (%) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Manufacturing and assembly |  |  |  |  |  |  |  |  |  |  |
| Domestic refrigeration |  | 12,870 | 0 | 0 | 0 | 0 | 0 | 0 | 12,870 | 1.5 |
| Commercial refrigeration |  | 7,865 | 0 | 0 | 14,314 | 0 | 0 | 0 | 22,179 | 2.6 |
| MAC |  | 3,933 | 0 | 0 | 0 | 0 | 0 | 0 | 3,933 | 0.5 |
| Subtotal for manufacturing/assembly |  | 24,668 | 0 | 0 | 14,314 | 0 | 0 | 0 | 38,981 | 4.6 |
| Refrigeration and AC servicing |  |  |  |  |  |  |  |  |  |  |
| Domestic refrigeration |  | 46,332 | 0 | 0 | 0 | 0 | 0 | 0 | 46,332 | 5.5 |
| Commercial refrigeration | Stand-alone units | 19,091 | 0 | 0 | 15,294 | 0 | 0 | 0 | 34,385 | 4.1 |
|  | Condenser units (simplex) | 41,399 | 0 | 0 | 149,727 | 0 | 0 | 34,550 | 225,675 | 26.8 |
|  | Centralized systems | 0 | 0 | 0 | 88,628 | 0 | 0 | 21,240 | 109,868 | 13.0 |
| Industrial refrigeration |  | 0 | 0 | 0 | 0 | 0 | 0 | 6,097 | 6,097 | 0.7 |
| Transport refrigeration |  | 12,727 | 0 | 0 | 43,922 | 0 | 0 | 0 | 56,649 | 6.7 |
| Residential AC |  | 0 | 6,838 | 0 | 0 | 0 | 60,204 | 0 | 67,041 | 8.0 |
| Packaged AC units |  | 0 | 0 | 0 | 0 | 0 | 51,561 | 0 | 51,561 | 6.1 |
| Chiller AC units |  | 0 | 0 | 0 | 0 | 26,608 | 62,625 | 0 | 89,233 | 10.6 |
| Commercial AC |  | 0 | 14,452 | 0 | 0 | 16,869 | 67,635 | 0 | 98,956 | 11.7 |
| MAC |  | 13,042 | 0 | 0 | 0 | 0 | 0 | 0 | 13,042 | 1.5 |
| Subtotal for servicing |  | 132,590 | 21,290 | 0 | 297,571 | 43,477 | 242,025 | 61,887 | 798,839 | 94.8 |
| Firefighting servicing |  | 0 | 0 | 4,444 | 0 | 0 | 0 | 0 | 4,444 | 0.5 |
| Total |  | 157,257 | 21,290 | 4,444 | 311,885 | 43,477 | 242,025 | 61,887 | 842,264 | 100.0 |

# Manufacturing and assembly sectors

# The manufacturing sector in Zimbabwe consists of enterprises that manufacture domestic and commercial refrigeration equipment. Most of the refrigeration manufacturing enterprises in Zimbabwe are from the informal sector and with low HFC consumption, thereby making them ineligible for funding due to the cost threshold under the guidelines. R-134a is the major refrigerant used in the manufacture of domestic refrigeration appliances such as single and double-door upright fridges, deep freezers, and water coolers and dispensers. There are two enterprises, Capri and Imperial, that manufacture domestic refrigerators. At the 82nd meeting, the Executive Committee approved a demonstration project for Capri to convert one manufacturing line for domestic refrigerator from R-134a to R-600a. The project is delayed and is expected to be completed by June 2025.

# The commercial refrigeration manufacturing subsector consists of many small enterprises spread across the country consuming R-134a, R-404A and R-507A. R-134a is used in manufacturing small to medium-sized refrigeration appliances where R-290 has just been introduced; for example, the enterprise Imperial is assembling R-290-based bottle coolers. R-404A is mainly used in the manufacturing of medium to large-sized appliances such as cold rooms, chillers and freezers, and in mid- and low-temperature applications. Except for Capri, other enterprises with small consumption also use HFCs to manufacture or assemble commercial equipment. The very low HFC consumption by these enterprises render them ineligible for funding, as the project cost would exceed the cost-effective threshold. Alternative refrigerants for the sector include R-600a, R-717, R-744 and R-290.

# Refrigeration and air-conditioning servicing sector

# There are approximately 6,700 technicians (including 1,785 women) and 1,950 workshops consuming HFCs in Zimbabwe. The formal sector comprises of 70 per cent (4,690) technicians and has well-equipped workshops; 30 per cent of the technicians are from the informal sector that do not have defined workshops and proper tools, and normally service small RAC units as domestic fridges. Most technicians in the formal sector are formally trained. Zimbabwe has seven Government-owned colleges, two privately owned, and several enterprises that train refrigeration technicians. Under the HPMP, training was provided to 2,500 technicians, of which 1,700 were trained in hydrocarbons. A mandatory certification of RAC technicians has been implemented and a total of 286 technicians have been certified.

# Domestic, commercial, industrial and transport refrigeration servicing

# The domestic refrigeration sector accounts for 8.6 per cent in mt and 4.2 per cent in CO2-eq tonnes of the total HFC consumption in the country. R-134a is the dominant refrigerant used for servicing various domestic refrigeration appliances, including single and double-door upright fridges, deep freezers, and water coolers and dispensers. Although a substantial number of appliances in the sector are still charged with HFC-134a, the majority of the imports are hydrocarbon-based appliances.

# The commercial refrigeration subsector has the highest use of HFCs in the country, accounting for 33.2 per cent in mt and 36.4 per cent in CO2-eq tonnes of total HFC consumption in the country. The main HFCs used are R-404A, HFC-134a and R-507A, in servicing stand-alone equipment, condensing units, and large centralized systems. R-134a is used in servicing small to medium-sized commercial refrigeration appliances and R-404A in servicing medium to large-sized appliances such as cold rooms, chillers and freezers, and in mid and low-temperature applications. The use of R-134a and R-404A has been increasing.

# The industrial refrigeration subsector only consumes a small amount of HFC-407C in industrial processing plants in replacing HCFC-22. R-717 is also used for servicing industrial refrigeration appliances in the food storage and processing industries such as dairy, fish and meat processing. In transport refrigeration, R-134a is used for servicing railway wagons and R-404A is used for servicing refrigerated trucks which are imported from South Africa.

Residential and commercial air-conditioning servicing

# The stationary AC sector consumes 45.5 per cent of the total HFCs in Zimbabwe. R-410A is the most common refrigerant, accounting for 67 per cent of the subsector’s consumption in mt, followed by HFC-32 at 18 per cent and R-407C at 14 per cent. This subsector includes residential AC, packaged AC, commercial AC, and chillers. The demand for AC units in Zimbabwe is increasing due to rising ambient temperatures. Most imported AC units are pre-charged with R-410A, with capacities ranging from 9,000 to 72,000 BTUs. While the import of R-32-based AC units is growing, their higher price remains a barrier.

Mobile air-conditioning servicing

# HFC-134a is the primary refrigerant used in the MAC sector, with negligible use of HFO-1234yf in the latest vehicle models. Over one million vehicles are imported annually, pre-charged with HFC-134a. The Government has also implemented restrictions on importing vehicles that are ten years or older; this has promoted the import of HFO-1234yf-based vehicles. However, the lack of training on handling HFO-1234yf refrigerant has limited its use among service technicians, hindering its widespread adoption in the MAC sector. There are two assembly plants in Zimbabwe that use HFC-134a in the assembly of vehicles, neither of which currently use HFO-1234yf.

Firefighting

# In the firefighting sector, HFC-227ea (FM-200) and HFC-125 are the primary HFCs used as fire suppressants in fixed flooding systems for large-scale applications, such as thermal power stations and telecommunication facilities, as replacements for Halon 1301. It is estimated that over 5 mt of HFC-227ea are installed in fire suppression systems across the country. Imported HFC-227ea is primarily used for servicing these installed systems. Additionally, some HFC-125 is imported by petroleum processing enterprises for use as a fire suppressant at refueling stations nationwide. However, due to the high global warming potential (GWP) of HFC-125, these enterprises are being discouraged from using this suppressant.

# IV.	Stage I of the Kigali HFC implementation plan as submitted

Institutional, policy and regulatory framework

# The Ministry of Environment, Climate, and Wildlife is the national body responsible for overseeing the implementation of the Montreal Protocol. The national ozone unit (NOU) within the Ministry is responsible for the operational aspects of implementing the Protocol. The Government has revised the Environmental Management Regulations of 2023, gazetted as Statutory Instrument 49 of 2023, to control ODS and greenhouse gases, including HFCs. These revised regulations include a mandatory licensing and quota system for the import and export of HFCs and HFC-based equipment. National quotas for HFCs will align with the country’s obligations for HFC phase-down under the Montreal Protocol.

# The revised regulations include provisions for mandatory certification for RAC technicians. Uncertified personnel are prohibited from servicing, repairing, installing, commissioning, or decommissioning RAC appliances. To combat illegal trade, the regulations control all transit shipments of controlled substances by requiring transit permits. Additionally, the regulations have adopted the 2022 World Customs Organization (WCO) Harmonized System (HS) codes for HCFCs and HFCs to better differentiate individual HFCs.

# The Ministry of Energy and Power Development coordinated the development of the National Renewable Energy Policy and the National Energy Efficiency Policy, with involvement from the NOU. The Standards Association of Zimbabwe adopted the Minimum Energy Performance Standards (MEPS) for RAC appliances in March 2024. The National Energy Efficiency Policy, which aims to improve energy efficiency, is set to be launched in 2024.

# Phase-down strategy for stage I of the Kigali HFC implementation plan

# Overarching strategy

# The Government of Zimbabwe has proposed a three-stage approach to reduce HFCs in line with the Montreal Protocol phase-down schedule: stage I (2024-2029), stage II (2030-2040), and stage III (2040-2045). In stage I, Zimbabwe aims to freeze its HFC consumption at the baseline level by 2024 and achieve a 10 per cent reduction from this baseline by 2029. Stage I of the KIP will be implemented in an integrated manner with stage II of the HPMP to optimize the impact.

# Proposed reductions

Table 7. HFC consumption forecast under unconstrained scenario, Montreal Protocol limits and proposed HFC reductions under stage I (CO2-eq tonnes)

|  | 2023* | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| HFC consumption forecast (annual growth rate of 6 per cent**) | 842,264 | 892,463 | 945,654 | 1,002,015 | 1,061,735 | 1,125,014 | 1,192,065 |
| Montreal Protocol HFC consumption limits | 842,264 | 1,210,624 | 1,210,624 | 1,210,624 | 1,210,624 | 1,210,624 | 1,089,562 |
| Proposed HFC consumption under the KIP | - | 1,210,624 | 1,210,624 | 1,210,624 | 1,210,624 | 1,210,624 | 1,089,562 |
| Proposed reduction in HFC consumption from baseline (%) | - | 0 | 0 | 0 | 0 | 0 | 10 |

* As per Article 7 data.

** Growth calculated based on average growth rate of 2020, 2022 and 2023 because 2021 data is not representative.

# Proposed activities

# The following activities are planned for stage I of the KIP:

## Policies and regulatory framework: awareness-raising and training activities for 150 enforcement officers on updated ODS and HFC regulations; awareness-raising campaigns for importers and end users on the updated regulations; integrating HFC licensing and quota system into customs single window system software; development of labelling requirements to include restrictions on the GWP value of refrigerants and an enforcement procedure for implementing MEPS in the RAC sector, and development of MEPS for other potential sectors (MAC and commercial refrigeration equipment) based on assessment; training of 500 customs and enforcement officers in HFC import control (250 women); strengthening record keeping; and market monitoring and survey to prevent illegal trade (UNEP) (US $115,000);

## Strengthening the RAC sector, including supports to the RAC industry association; updating the code of practice and training curriculum for RAC technicians; 10 training sessions for 250 technicians (80 women) in good servicing practices, refrigerant recovery and recycling, and servicing with alternative technologies in commercial and industrial refrigeration and transport refrigeration as well as MAC subsectors; and five awareness-raising workshops for 100 end users in large commercial and industrial refrigeration sectors on the benefits of low-GWP and energy-efficiency technologies (UNEP) (US $105,000);

## Technical assistance and five sensitization workshops for 75 end users and small and medium-sized enterprise (SME) assemblers on good servicing and installation procedures as well as safety aspects with low-GWP, high energy efficiency technology options in commercial and industrial refrigeration subsectors, cost analysis, and long-term economic approach to the technology selection to support decision-making in adopting low-GWP technologies; provision of tools and equipment (leak detector for CO2, NH3 and R-290, test meters, vacuum pumps, Lokring, pipe cutter, CO2 manifold gauge, etc.) for improving installation and servicing practices with low-GWP technologies; and training of 100 RAC technicians in using the tools (UNDP) (US $55,000);

## Technology demonstration of R-290-based split AC units, including procurement of 350 split AC units; installing them in Government institutions in 10 provinces to demonstrate the Government’s commitment to R-290 technology; training technicians on installation; monitoring energy efficiency performance of the units; coordinating refrigerant recovery and disposal of dismantled units; coordinating the importation of R-290 refrigerant for servicing; and conducting five awareness-raising sessions for 100 end users to disseminate information on the demonstration project (UNDP) (US $45,000); and

## Refrigerant recovery and recycling in the MAC sector: conducting six training sessions for 60 technicians on refrigerant recovery and recycling in the MAC sector with tools; designating a focal point at each workshop for refrigerant recovery, recycling and transportation of unwanted refrigerant to a destruction facility; and procurement of five refrigerant recovery and recycling machines and cylinders (UNDP) (US $20,000).

Project implementation, coordination and monitoring

# Project coordination and monitoring is conducted by the NOU, the national ozone committee and the RAC associations at a total of US $20,000 for UNEP with the following breakdown: staff and consultants (US $13,000); monitoring travels (US $4,000); and workshops and meetings (US $3,000).

Gender policy implementation

# In line with gender mainstreaming policies of the Multilateral Fund and decision 92/40(b), gender mainstreaming will be incorporated into all steps of the implementation of stage I of the KIP. The Government of Zimbabwe has established several policies and strategies to support women’s empowerment and the advancement of gender equality, and a mechanism has been instituted to support their implementation. The Government of Zimbabwe recognizes the importance of gender equality and women’s involvement for the successful implementation of the KIP. During project preparation, a gender assessment was conducted, and gender mainstreaming baseline status was defined. Stage I of the KIP aims to promote gender equality and women’s involvement at all the levels of training and awareness-raising activities. A gender expert will be recruited to ensure that project staff and stakeholders will be sensitized to gender-related issues and have the knowledge of gender mainstreaming. The project has included a clear target that 55 per cent of the technicians to be trained in stage I will be women. Gender-disaggregated data will be collected.

Coordination of activities in the servicing sector under HCFC phase-out and HFC phase-down plans

# Stage I of the KIP will be implemented simultaneously with stage II of the HPMP. The activities planned under the KIP will be complementary to that in the HPMP. The implementation of the two multi-year agreements will be optimized to maximize the impact, as shown in annex II to the present document.

# Total cost of stage I of the Kigali HFC implementation plan

# Zimbabwe had an average HFC consumption of 367.30 mt during the baseline years including consumption in both the manufacturing and servicing sector. The budget for stage I has been proposed at US $360,000 (excluding agency support costs), in line with decision 92/37. No funding is requested for addressing the consumption in the manufacturing/assembly sector.

# The proposed activities and cost of stage I of the KIP are summarized in table 8.

Table 8. Proposed cost of activities to be implemented in stage I of the KIP for Zimbabwe

| Activity | Agency | Cost (US $) |
| --- | --- | --- |
| Regulatory framework and control mechanisms (US $115,000) |  |  |
| Awareness-raising and training activities for 150 enforcement officers on updated ODS and HFC regulations | UNEP | 20,000 |
| Awareness-raising campaigns on updated regulations for importers and end users | UNEP | 10,000 |
| Integrating HFC licensing and quota system into customs single window system software | UNEP | 5,000 |
| Developing, revising, and adopting standards and labelling of refrigerants | UNEP | 30,000 |
| Training of 500 customs and enforcement officers in HFC import control | UNEP | 30,000 |
| Strengthening record keeping by customs and reporting by enterprises | UNEP | 10,000 |
| Continuous market monitoring and surveys to prevent illegal trade | UNEP | 10,000 |
| Training of technicians and support to the industrial association (US $105,000) |  |  |
| Supporting the RAC industry association to formalize the sector | UNEP | 15,000 |
| Updating the code of practice and training curriculum of RAC technicians | UNEP | 20,000 |
| Training of 250 refrigeration technicians in good servicing practices | UNEP | 50,000 |
| Awareness-raising campaigns for 100 end users on the benefits of using low-GWP and energy-efficiency technologies | UNEP | 20,000 |
| Commercial and industrial refrigeration subsectors (US $55,000) |  |  |
| Technical assistance, awareness-raising campaign for 75 end users and SMEs | UNDP | 15,000 |
| Provision of tools and equipment for training on use of tools for installation with low-GWP technologies (CO2, NH3 and R-290) | UNDP | 40,000 |
| AC sector (US $45,000) |  |  |
| Demonstration of R-290 technology, supplying 350 units to end users | UNDP | 40,000 |
| Disseminating information on the demo project to 100 end users | UNDP | 5,000 |
| MAC subsector (US $20,000) |  |  |
| Training of 60 MAC technicians on handling HFO-1234yf and HFC-134a refrigerants; provision of 5 refrigerant recovery machines and cylinders | UNDP | 20,000 |
| Project coordination, implementation and reporting (US $20,000) |  |  |
| Coordination and management of KIP implementation | UNEP | 20,000 |
| Total |  | 360,000 |

# Implementation of the first tranche of stage I of the Kigali HFC implementation plan

# The first funding tranche of stage I of the KIP, in the total amount of US $211,000, will be implemented between January 2025 and December 2027 and will cover the activities listed in table 9.

# Table 9: Activities planned for the first tranche of stage I of the KIP for Zimbabwe

| Activity | Agency | Cost (US $) |
| --- | --- | --- |
| Regulatory framework and control mechanisms (US $64,000) |  |  |
| Awareness-raising and training activities for 150 enforcement officers on updated ODS and HFC regulations | UNEP | 20,000 |
| Awareness-raising campaigns on revised regulations to 50 importers and other key stakeholders | UNEP | 5,000 |
| Integrating HFC licensing and quota system into customs single window system software | UNEP | 5,000 |
| Developing, revising, and adopting standards and labelling of refrigerants | UNEP | 15,000 |
| Training of 200 customs and enforcement officers in HFC import control | UNEP | 12,500 |
| Strengthening record keeping by customs and reporting by enterprises | UNEP | 3,500 |
| Improving continuous market monitoring, including surveys | UNEP | 3,000 |
| Training of technicians and support to the industrial association (US $50,000) |  |  |
| Supporting the industry association to formalize the sector | UNEP | 5,000 |
| Updating the code of practice and training curriculum of RAC technicians | UNEP | 20,000 |
| Four workshops to train 100 refrigeration technicians in good servicing practices | UNEP | 17,500 |
| Awareness-raising campaigns to end users on the benefits of using low-GWP and energy-efficiency technologies | UNEP | 7,500 |
| Commercial and industrial refrigeration subsectors (US $37,500) |  |  |
| Awareness-raising campaign to 50 end users and SMEs | UNDP | 7,500 |
| Provision of tools and equipment for training on refrigeration | UNDP | 30,000 |
| AC sector (US $42,500) |  |  |
| Demonstration of R-290 technology, supplying 350 units to end users | UNDP | 40,000 |
| Disseminating information on the demo project to 100 end users | UNDP | 2,500 |
| MAC subsector (US $10,000) |  |  |
| Supply of five recovery units to workshops | UNDP | 10,000 |
| Project coordination, implementation and reporting (US $7,000) |  |  |
| Coordination and management of KIP implementation | UNEP | 7,000 |
| Total |  | 211,000 |

Project implementation, coordination and monitoring

# Project coordination and monitoring will be carried out by the NOU, the national ozone committee and the RAC associations, at a total of US $7,000, with the following breakdown: staff and consultants (US $4,500); monitoring travel (US $1,500); and workshops and meetings (US $1,000).

SECRETARIAT’S COMMENTS AND RECOMMENDATION

## V.	Comments

Institutional, policy and regulatory framework

HFC licensing and quota system

# In line with decision 87/50(g), UNEP has confirmed that Zimbabwe has an established and enforceable system of licensing and quotas for monitoring HFC imports/exports in place, effective as of January 2023. The Government issued HFC import quotas for 2024 and estimates quotas for 2025 at 985,532 CO2-eq tonnes, which is lower than the established baseline.

# The Secretariat discussed regulatory measures to promote the adoption of R-600a by other enterprises through the demonstration project at Capri and to support the sustainability of the HFC-134a phase-out in domestic refrigeration manufacturing. The Government agreed to implement a ban on the import of HFC-134a-based domestic refrigerators by January 2026. In addition, the enforcement of MEPS and labelling requirements will support the import of low-GWP products.

Technical and cost-related issues

# The Government proposes a 10 per cent reduction in HFC consumption from the baseline by 2029 in stage I of the KIP, in line with the Montreal Protocol phase-down schedule. The Secretariat noted that HFC consumption in 2023 is 30 per cent below the baseline and encouraged the Government to set ambitious yet achievable control targets to maximize environmental benefits. Upon discussion, the Government agreed to commit to a reduction of 10 per cent of the average HFC consumption in the baseline years, which is equal to a reduction of 37 per cent from the HFC baseline. The detailed control targets are presented in table 10 below. The Government of Zimbabwe will issue the quotas for 2025 taking into account the agreed maximum allowable targets for that year.

Table 10: Revised control targets for stage I of the KIP (CO2-eq tonnes)

| Particulars | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 |
| --- | --- | --- | --- | --- | --- | --- |
| Montreal Protocol reduction schedule of Annex F, Group I substances | 1,210,624 | 1,210,624 | 1,210,624 | 1,210,624 | 1,210,624 | 1,089,562 |
| Maximum allowable total consumption of Annex F, Group I substances | 945,654 | 945,654 | 945,654 | 945,654 | 892,463 | 761,510 |
| Percentage reduction in HFC consumption from the baseline (%) | 22 | 22 | 22 | 22 | 26 | 37 |

# In line with decision 92/37(b)(ii), the eligible funding for Zimbabwe to achieve a 37 per cent reduction from the baseline in stage I of the KIP is US $432,000 plus agency support costs.

# The Secretariat noted the delay in implementation of the conversion project at Capri and that the project is at its final stage of completion, and therefore recommends to the Executive Committee to extend the completion date to June 2025 to allow the implementation of the remaining activities.

# Regarding the demonstration project, the Secretariat noted that its purpose was to assess the safety-related issues and adaptability of R-290 domestic air-conditioners in Zimbabwe. Therefore, it was agreed to focus on demonstrating the technology. The total number of units was reduced from 350 to 50, and the monitoring of energy efficiency will be included. Co-funding will be provided for the installation of the equipment. UNDP will submit a final report on the implementation of this project, including the HFC phase-out and energy-efficiency gains achieved, once the project is completed, in line with decision 92/36(g).

Total project cost

# With the additional 20 per cent funding, activities for stage I of the KIP have been revised as summarized in table 11 (changes in funding and activity are in bold font).

Table 11. Revised cost of activities to be implemented in stage I of the KIP for Zimbabwe (US $)

| Activity | Agency | Cost |
| --- | --- | --- |
| Regulatory framework and control mechanisms (US $165,000) |  |  |
| Establishing and enforcing ODS/HFC regulations, including a ban on the import of domestic refrigerators using HFC-134a | UNEP | 20,000 |
| Awareness-raising campaigns on updated regulations for importers and end users | UNEP | 10,000 |
| Integrating HFC licensing and quota system into customs single window system software | UNEP | 5,000 |
| Developing, revising, and adopting standards and labelling of refrigerants | UNEP | 45,000 |
| Training of 750 customs and enforcement officers in HFC import control | UNEP | 45,000 |
| Strengthening record keeping by customs and reporting by enterprises | UNEP | 20,000 |
| Continuous market monitoring and surveys to prevent illegal trade | UNEP | 20,000 |
| Training of technicians and support to the industrial association (US $107,000) |  |  |
| Supporting the RAC industry association to formalize the sector | UNEP | 15,000 |
| Updating the code of practice and training curriculum of RAC technicians | UNEP | 22,000 |
| Training of 250 refrigeration technicians in good servicing practices | UNEP | 50,000 |
| Awareness-raising campaigns for 100 end users on the benefits of using low-GWP and energy-efficiency technologies | UNEP | 20,000 |
| Commercial and industrial refrigeration subsectors (US $55,000) |  |  |
| Technical assistance, awareness-raising campaign for 75 end users and SMEs | UNDP | 15,000 |
| Provision of tools and equipment for training on use of tools for installation with low-GWP technologies (CO2, NH3 and R-290) | UNDP | 40,000 |
| AC sector (US $45,000) |  |  |
| Demonstration of R-290 technology, including supplying 50 units to end users and monitoring energy efficiency | UNDP | 40,000 |
| Disseminating information on the demo project to 100 end users | UNDP | 5,000 |
| MAC subsector (US $20,000) |  |  |
| Training of 60 MAC technicians on handling HFO-1234yf and HFC-134a refrigerants; provision of five refrigerant recovery machines and cylinders to workshops | UNDP | 20,000 |
| Project coordination, implementation and reporting (US $40,000) |  |  |
| Coordination and management of KIP implementation | UNEP | 40,000 |
| Total |  | 432,000 |

# Stage I of the KIP will be implemented in three tranches. The schedule of HFC phase-down and HCFC phase-out commitments and of the KIP and HPMP tranches is presented in annex I to the present document.

# Implementation plan for the first tranche of the Kigali HFC implementation plan

# With the additional funding and revised implementation plan, the plan for the first tranche was adjusted as shown in table 12 (changes in funding and activity are in bold font).

# Table 12: Revised activities for the first tranche of stage I of the KIP for Zimbabwe

| Activity | Agency | Cost (US $) |
| --- | --- | --- |
| Regulatory framework and control mechanisms (US $83,000) |  |  |
| Establishing and enforcing ODS/HFC regulations, including a ban on the import of domestic refrigerators using HFC-134a | UNEP | 20,000 |
| Awareness-raising campaigns on revised regulations to 50 importers and other key stakeholders | UNEP | 5,000 |
| Integrating HFC licensing and quota system into customs single window system software | UNEP | 5,000 |
| Developing, revising, and adopting standards and labelling of refrigerants | UNEP | 22,500 |
| Training of 250 customs and enforcement officers in HFC import control | UNEP | 17,500 |
| Strengthening record keeping by customs and reporting by enterprises | UNEP | 7,000 |
| Improving continuous market monitoring, including surveys | UNEP | 6,000 |
| Training of technicians and support to the industrial association (US $54,500) |  |  |
| Supporting the industry association to formalize the sector | UNEP | 5,000 |
| Updating the code of practice and training curriculum of RAC technicians | UNEP | 22,000 |
| Four workshops to train 100 refrigeration technicians in good servicing practices | UNEP | 20,000 |
| Awareness-raising campaigns to end users on the benefits of using low-GWP and energy-efficiency technologies | UNEP | 7,500 |
| Commercial and industrial refrigeration subsectors (US $37,500) |  |  |
| Awareness-raising campaign to 50 end users and SMEs | UNDP | 7,500 |
| Provision of tools and equipment for training on refrigeration | UNDP | 30,000 |
| AC sector (US $42,500) |  |  |
| Demonstration of R-290 technology, including supplying 50 units to end users and monitoring energy efficiency | UNDP | 40,000 |
| Disseminating information on the demo project to 100 end users | UNDP | 2,500 |
| MAC subsector (US $10,000) |  |  |
| Provision of five refrigerant recovery machines and cylinders to workshops | UNDP | 10,000 |
| Project coordination, implementation and reporting (US $14,000) |  |  |
| Coordination and management of KIP implementation | UNEP | 14,000 |
| Total |  | 241,500 |

# Co-financing

# Stage I of the KIP includes the demonstration of R-290 AC units. The Government of Zimbabwe will co-finance the cost of installation at US $320 per unit for the demonstration project. The Government will continue to explore opportunities for co-financing during the implementation of the KIP.

# 2024-2026 business plan of the Multilateral Fund

# UNEP and UNDP are requesting US $432,000, plus agency support costs, for the implementation of stage I of the KIP for Zimbabwe. The total value of US $272,895, including agency support costs, requested for the period of 2024–2026, is US $114,800 above the amount in the business plan.

# Sustainability of the HFC phase-down and assessment of risks

# The Government of Zimbabwe has included in the KIP the development of a regulatory framework to ensure sustainability of HFC reduction, including a ban on the import of HFC-134a-based domestic refrigerators, enforcement of MEPS, and labelling requirements that incorporate the GWP of refrigerants. Frequent training of customs officers, support for training institutions, and awareness-raising activities planned under the KIP will continuously strengthen import control and capacity development in the refrigeration servicing sector, resulting in the sustained reduction of HFCs.

# The KIP includes a risk analysis, highlighting that the risks to sustainability and successful implementation of the KIP are mainly related to the availability and accessibility of low-GWP alternative technologies (including price, expertise and skills for adoption), as well as the illegal trade of refrigerants. These risks are considered high and have been addressed through enforcement of regulations, a technology demonstration project, and awareness-raising activities. Other risks, such as compliance with control targets, timely implementation of the KIP, and the increased demand for HFCs due to high leakage rates from domestic AC units, are considered medium-level risks. These will be mitigated through strict enforcement of the HFC licensing and quota system, continuous collaboration with key stakeholders in the RAC industry, the establishment of a project management team, and the training of RAC technicians. The project management team will coordinate implementation, monitor activities, and reporting progress.

Impact on the climate

# The activities proposed, including training in regulatory control of HFCs, support to the RAC servicing sector, training of technicians in good servicing practices, and the efforts to promote low-GWP alternatives through R-290 demonstration, indicate that the implementation of stage I of the KIP will reduce refrigerant emissions into the atmosphere, resulting in climate benefits. A calculation of the impact on the climate of the activities in the KIP indicates that by 2029, Zimbabwe will have reduced its emissions by approximately 835,548 CO2-eq tonnes of HFCs, calculated as the difference between the business-as-usual scenario and the HFC reduction scenario.

# Draft Agreement

# A draft Agreement between the Government of Zimbabwe and the Executive Committee for stage I of the KIP has not been prepared as the Agreement template is still under consideration by the Executive Committee.

# If the Executive Committee so wishes, the funds for stage I of the KIP for Zimbabwe could be approved in principle, and funds for the first tranche could be approved on the understanding that the Agreement would be prepared and presented at a future meeting, before the submission of the second tranche, and once the Agreement template has been approved.

# VI.	Recommendation

# The Executive Committee may wish to consider:

## Approving, in principle, stage I of the Kigali HFC implementation plan (KIP) for Zimbabwe for the period 2024-2029 to reduce HFC consumption by 10 per cent of the country’s average HFC consumption in the baseline years (or 37 per cent of the country’s baseline) by 2029, in the amount of US $488,160, consisting of US $312,000, plus agency support costs of US $40,560, for UNEP and US $120,000, plus agency support costs of US $15,600, for UNDP, as reflected in the schedule contained in annex I to the present document;

## Noting:

### That, in line with decision 82/81(b), stage I of the KIP included an additional US $462,841, consisting of US $326,954, plus agency support costs of US $22,887 for UNDP, and US $100,000, plus agency support costs of US $13,000 for the Government of France, related to the project approved at the 82nd meeting to phase out 14.50 mt (20,735 CO2-eq tonnes) in the conversion from HFC-134a to isobutane (R-600a) in the manufacture of domestic refrigerators at Capri;

### That the Government of Zimbabwe will establish its starting point for sustained aggregate reductions in HFC consumption based on guidance provided by the Executive Committee;

### That, once the cost guidelines for HFC phase-down are agreed by the Executive Committee, reductions from the country’s remaining HFC consumption eligible for funding will be determined in line with these guidelines;

### That the reductions from the country’s remaining HFC consumption eligible for funding referred to in subparagraph (b)(iii) above will be deducted from the starting point referred to in subparagraph (b)(ii);

### That the Government of Zimbabwe will put in place a ban on the import of HFC-134a-based domestic refrigerators by 1 January 2026;

### That, upon completion of the end-user project included in stage I of the KIP, UNDP will submit a final report on the implementation of this project, including the HFC phase-out and energy-efficiency gains achieved, in line with decision 92/36(g);

## Approving the first tranche of stage I of the KIP for Zimbabwe and the corresponding tranche implementation plan, in the amount of US $272,895, consisting of US $151,500, plus agency support costs of US $19,695, for UNEP and US $90,000, plus agency support costs of US $11,700, for UNDP;

## Requesting the Government of Zimbabwe, UNEP, UNDP and the Secretariat to finalize the draft Agreement between the Government of Zimbabwe and the Executive Committee for the reduction in consumption of HFCs, including the information contained in the annex referred to in subparagraph (a) above, and to submit it to a future meeting once the KIP Agreement template has been approved by the Executive Committee; and

## Approving the extension of the project referred to in subparagraph (b)(i) above to 30 June 2025, and requesting UNDP to submit a project completion report on said project to the 97th meeting.

Annex I

SCHEDULE OF HFC PHASE-DOWN AND HCFC PHASE-OUT COMMITMENTS AND FUNDING TRANCHES 
UNDER THE KIGALI HFC IMPLEMENTATION PLAN AND THE HCFC PHASE-OUT MANAGEMENT PLAN FOR ZIMBABWE

Kigali HFC implementation plan (stage I)

| Row | Particulars | 2018* | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Montreal Protocol reduction schedule of Annex F substances (CO2-eq tonnes) | n/a | 1,210,624 | 1,210,624 | 1,210,624 | 1,210,624 | 1,210,624 | 1,089,561 | n/a |
| 1.2 | Maximum allowable total consumption of Annex F substances (CO2-eq tonnes) | n/a | 945,654 | 945,654 | 945,654 | 945,654 | 892,463 | 761,510 | n/a |
| 2.1 | Lead IA (UNEP) agreed funding (US $) | 0 | 151,500 | 0 | 0 | 106,500 | 0 | 54,000 | 312,000 |
| 2.2 | Support costs for Lead IA (US $) | 0 | 19,695 | 0 | 0 | 13,845 | 0 | 7,020 | 40,560 |
| 2.3 | Cooperating IA (UNDP) agreed funding (US $) | 326,954 | 90,000 | 0 | 0 | 0 | 0 | 30,000 | 446,954 |
| 2.4 | Support costs for Cooperating IA (US $) | 22,887 | 11,700 | 0 | 0 | 0 | 0 | 3,900 | 38,487 |
| 2.5 | Cooperating IA (France) agreed funding (US $) | 100,000 | 0 | 0 | 0 | 0 | 0 | 0 | 100,000 |
| 2.6 | Support costs for Cooperating IA (US $) | 13,000 | 0 | 0 | 0 | 0 | 0 | 0 | 13,000 |
| 3.1 | Total agreed funding (US $) | 426,954 | 241,500 | 0 | 0 | 106,500 | 0 | 84,000 | 858,954 |
| 3.2 | Total support costs (US $) | 35,887 | 31,395 | 0 | 0 | 13,845 | 0 | 10,920 | 92,047 |
| 3.3 | Total agreed costs (US $) | 462,841 | 272,895 | 0 | 0 | 120,345 | 0 | 94,920 | 951,001 |

* Approved at the 82nd meeting to phase out 14.50 mt (20,735 CO2-eq tonnes) of HFC-134a for the conversion in the manufacture of domestic refrigerators at Capri (decision 82/81).

HCFC phase-out management plan from 2024 to 2030 (stage II)

| Row | Particulars | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Montreal Protocol reduction schedule of Annex C, Group I substances (ODP tonnes) | 11.57 | 5.78 | 5.78 | 5.78 | 5.78 | 5.78 | 0.00 | n/a |
| 1.2 | Maximum allowable total consumption of Annex C, Group I substances (ODP tonnes) | 11.57 | 5.78 | 5.78 | 5.78 | 5.78 | 5.78 | 0.00 | n/a |
| 2.1 | Lead IA (UNEP) agreed funding (US $) | 0 | 0 | 0 | 192,500 | 0 | 0 | 105,000 | 297,500 |
| 2.2 | Support costs for Lead IA (US $) | 0 | 0 | 0 | 23,591 | 0 | 0 | 12,868 | 36,459 |
| 2.3 | Cooperating IA (UNDP) agreed funding (US $) | 0 | 0 | 0 | 150,000 | 0 | 0 | 0 | 150,000 |
| 2.4 | Support costs for Cooperating IA (US $) | 0 | 0 | 0 | 10,500 | 0 | 0 | 0 | 10,500 |
| 3.1 | Total agreed funding (US $) | 0 | 0 | 0 | 342,500 | 0 | 0 | 105,000 | 447,500 |
| 3.2 | Total support costs (US $) | 0 | 0 | 0 | 34,091 | 0 | 0 | 12,868 | 46,959 |
| 3.3 | Total agreed costs (US $) | 0 | 0 | 0 | 376,591 | 0 | 0 | 117,868 | 494,459 |

Annex II

SIMULTANEOUS IMPLEMENTATION OF THE HCFC PHASE-OUT MANAGEMENT PLAN

AND THE KIGALI HFC IMPLEMENTATION PLAN IN ZIMBABWE

|  | HPMP – stage II |  | KIP – stage I |  | HPMP+KIP combined (US $) |
| --- | --- | --- | --- | --- | --- |
| Category of activity | Activity | Cost (US $) | Activity | Cost (US $) |  |
| Support for associations | Support to RAC Association to mobilise and coordinate technicians for training | 30,000 | Supporting the RAC industry association to formalize the sector | 15,000 | 45,000 |
| Provision of tools | Identifying needs and providing equipment and tools to strengthen seven training institutions; providing equipment and tools to the RAC Association to facilitate its role in the certification of technicians; establishing six refrigerant recovery and recycling centres to reduce HCFC consumption in the commercial and industrial refrigeration subsectors | 400,000 | Provision of tools and equipment for training on use of tools for installation with low-GWP technologies (CO2, NH3 and R-290) | 40,000 | 440,000 |
| Training of refrigeration technicians | Training 25 trainers and 1,000 refrigeration technicians in good servicing practices, in brazing competence and in the safe handling of flammable and toxic refrigerants | 150,000 | Training of 250 refrigeration technicians in good servicing practices | 50,000 | 200,000 |
| Training of MAC technicians |  |  | Training of 60 MAC technicians on handling HFO-1234yf and HFC-134a refrigerants; provision of 5 refrigerant recovery machines and cylinders | 20,000 | 20,000 |
| Development of codes of practice | Revising the training curriculum | 10,000 | Updating the code of practice and training curriculum of RAC technicians | 22,000 | 32,000 |
| Technology demonstration |  |  | Demonstration of R-290 technology and supplying 350 units to end users; and disseminating information on the demo project to 100 end users | 45,000 | 45,000 |
| Strengthening of licensing |  |  | Integrating HFC licensing and quota system into customs single window system software | 5,000 | 5,000 |
| Training of customs officers | Training 25 trainers and 1,000 customs and enforcement officers (including staff in tax, customs, revenue collection, and law enforcement department) in monitoring and controlling imports of HCFCs and identifying illegal trade; and conducting ongoing reviews and updates of the customs training curriculum to incorporate new issues into the customs training | 130,000 | Training of 500 customs and enforcement officers in HFC import control; ban on HFC-134a-based refrigerators; awareness-raising and training activities for 150 enforcement officers on updated ODS and HFC regulations; and awareness-raising campaigns on updated regulations for importers and end users | 75,000 | 205,000 |
| Strengthening of customs records |  |  | Strengthening record keeping by customs and reporting by enterprises through the training of 150 enforcement officers on registration of HFC imports and assessment and monitoring | 20,000 | 20,000 |
| Improving monitoring |  |  | Continuous market monitoring and surveys to prevent illegal trade | 20,000 | 20,000 |
| Certification of technicians | Developing standards and procedures, and continue implementing the certification of technicians in the RAC sector; stakeholder consultations and training on the certification process; conducting 10 awareness-raising campaigns and distributing certification procedures; and certifying 1,000 technicians | 120,000 |  |  | 120,000 |
| Standards and labelling | Developing technical standards for the safe handling of flammable and toxic refrigerants, as well as the standard for minimum energy efficiency in RAC equipment; stakeholder consultation, training and awareness-raising on the safety and energy efficiency standards; monitoring compliance in the implementation of safety and energy efficiency standards; supporting policy development on green procurement; and providing training for procurement officers on low-GWP, energy-efficient RAC equipment | 110,000 | Implementing MEPS and a labelling system to include a control on GWP of refrigerants | 45,000 | 155,000 |
| Awareness | Targeted awareness-raising activities for importers, distributors and end users on the need to move away from HCFCs and introduce alternative technologies | 30,000 | Awareness-raising campaigns for 100 end users on the benefits of using low-GWP and energy-efficiency technologies; and technical assistance and an awareness-raising campaign for 75 end users and SMEs | 35,000 | 65,000 |
| Coordination and monitoring | Project coordination and monitoring | 60,000 | Project coordination and monitoring | 40,000 | 100,000 |
| Total |  | 1,040,000 |  | 432,000 | 1,472,000 |
| Percentage of total (%) |  | 71 |  | 29 | 100 |

UNEP/OzL.Pro/ExCom/95/1

As per the letter of 14 August 2024 from the Ministry of Environment, Climate and Wildlife of Zimbabwe to the Secretariat.