| orryUNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/93/18 20 November 2023 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-third Meeting

Montreal, 15-19 December 2023

Item 7(a)(v) of the provisional agenda

PROGRESS REPORT OF UNIDO as at 31 december 2022

Introduction

# This document presents the progress report of UNIDO as at 31 December 2022.

# The progress report of UNIDO includes the status of implementation of projects, including 35 HFC-related projects that have been funded under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment.

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2022, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs which are measured in CO2-eq tonnes.

# This document consists of the following sections:

## I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2022 and cumulative since 1993 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs). It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee.

## II.	Projects approved for Annex F substances (HFCs) under the additional voluntary contributions for fast-start support for HFC phase-down.

III.	Recommendation.

I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund

I.1	Progress in implementation of projects for 2022 and cumulative since 1993

# As of 31 December 2022, the Executive Committee had approved US $1.02 billion in projects for UNIDO, consisting of US $895.88 million for the implementation of investment and non-investment projects, and US $119.22 million for agency support costs, as shown in table 1.

# Table 1. Approved funding by sector for UNIDO as at 31 December 2022

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 34,397,921 |
| Destruction | 3,805,540 |
| Foam | 89,066,904 |
| Halon | 1,780,369 |
| HFC phase-down plan | 4,194,000 |
| Fumigants | 78,028,741 |
| Multiple sectors | 139,440 |
| Other | 11,317,246 |
| Phase-out plan | 388,710,642 |
| Process agent | 6,337,359 |
| Production | 50,638,105 |
| Refrigeration | 182,310,825 |
| Several | 21,904,344 |
| Solvents | 23,247,443 |
| Sub-total | 895,878,878 |
| Agency support costs | 119,222,126 |
| Total | 1,015,101,004 |

# In 2022, 66 new projects and activities were approved. This level of funding is expected to result in the phase-out of 84,246 ODP tonnes of consumption and production and 226,432 CO2-eq tonnes of consumption of controlled substances. Annex I shows the status of project implementation per country in 2022.

# Table 2 shows the status of project implementation including fund disbursement per project type as at 31 December 2022. Annex II presents analytical information per year since 1993.

Table 2. Status of project implementation by type as at 31 December 2022

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 11 | 11 | 100 | 722,669 | 722,669 | 0 | 100 |
| Demonstration | 43 | 42 | 98 | 23,405,832 | 22,730,368 | 675,464 | 97 |
| Institutional strengthening (IS) | 102 | 83 | 81 | 17,306,395 | 14,307,697 | 2,998,698 | 83 |
| Investment | 1,000 | 879 | 88 | 801,373,629 | 723,710,037 | 77,663,592 | 90 |
| Project preparation | 597 | 534 | 89 | 27,274,254 | 23,312,172 | 3,962,082 | 85 |
| Technical assistance | 213 | 186 | 87 | 24,599,563 | 21,453,904 | 3,145,659 | 87 |
| Training | 23 | 23 | 100 | 1,196,535 | 1,196,535 | 0 | 100 |
| Total | 1,989 | 1,758 | 88 | 895,878,878 | 807,433,382 | 88,445,496 | 90 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

# Implementation of projects and activities by UNIDO for 2022 and cumulative since 1993 up to 31 December 2022, is summarized as follows:

## Phase-out: In 2022, 424.0 ODP tonnes of consumption of controlled substances were phased out and an additional 938.1 ODP tonnes of consumption of controlled substances were approved for phase-out. Since 1993, 64,672 ODP tonnes of consumption of controlled substances and 17,381 ODP tonnes of production of controlled substances had been phased out,  of an expected total of 84,246 ODP tonnes and 226,432 CO2-eq tonnes from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2022, US $22.29 million was disbursed and US $21.22 million was planned for disbursement based on the 2021 progress report, representing a rate of disbursement of 105 per cent of that planned. Cumulatively, US $807.43 million had been disbursed out of the total US $895.88 million approved for disbursement (excluding agency support costs), representing a rate of disbursement of 90 per cent. In 2022, US $20.32 million was approved for implementation;

## Cost-effectiveness (in ODP): Since 1993, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $11.52/kg and for all production sector activities (CFC and methyl bromide (MB)) was US $2.90/kg. The average cost-effectiveness of investment projects per ODP tonne was US $8.74/kg for completed projects and US $33.13/kg for ongoing projects;

## Number of projects completed: In 2022, 67 projects were completed. Since 1993, 1,758 projects of the 1,989 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 88 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2022 were completed on average 61 months after their approval. Since 1993, the average time for completion of investment projects has been 40 months after their approval. First disbursements under these projects occurred, on average, nine months after they had been approved;

## Speed of delivery – non-investment projects: Projects that were completed in 2022 were completed on average 45 months after their approval. Since 1993, the average time for completion of non-investment projects has been 36 months after their approval. First disbursements under these projects occurred, on average, nine months after they had been approved;

## Project preparation: Of the 597 project preparation activities approved by the end of 2022, 534 have been completed, leaving 63 ongoing activities. In 2022, 26 preparation activities have been completed;

## Implementation delays: A total of 231 projects were under implementation at the end of 2022, experiencing, on average, a delay of 15 months. Thirty-eight of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation, and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2022, two MYAs for the control and phase-out of HFC-23 emissions, 74 MYAs for HCFC phase-out management plans (HPMPs) and one Kigali HFC implementation plan (KIP) were under implementation. Since 1993, 208 MYAs have been approved and 131 MYAs have been completed, representing a completion rate of 63 per cent.

# Table 3 summarized progress made by UNIDO since 1993.

## Table 3: Progress made by UNIDO since 1993

| Phase out achieved |  | Disbursement (US $) | Average CE (US$/kg) |  | Number of projects |  | Speed of delivery for completion (months) |  | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes* | CO2-eq tonnes |  | Consump- tion | Produc- tion | Approved | Completed | Investment | Non- investment |  | Approved | Completed |
| 82,053 | 0 | 807,433,382 | 11.52 | 2.90 | 1,989 | 1,758 | 40 | 36 | 15 | 208 | 131 |

*Consumption and production

HFC-related projects

# As of 31 December 2022, the Executive Committee had approved 54 HFC-related projects (including five investment projects, 46 preparation projects and three enabling activities) under regular contributions amounting to US $8,699,914 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 5 to 9.

Table 4. HFC-related projects approved under regular contributions

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 5 | 0 | 0 | 3,996,404 | 2,445,970 | 1,550,434 | 61 |
| Project preparation | 46 | 4 | 9 | 4,303,510 | 1,121,060 | 3,182,450 | 26 |
| Technical assistance – Enabling activities | 3 | 3 | 100 | 400,000 | 359,057 | 40,943 | 90 |
| Total | 54 | 7 | 13 | 8,699,914 | 3,926,087 | 4,773,826 | 45 |

* Excludes agency support costs.

** 129.1 mt (226,432 CO2-eq tonnes) of HFCs was approved for phase-out.

# As of the end of 2022, of the 54 projects, four preparation projects and three enabling activities have been completed, leaving 47 ongoing.

# Of the five ongoing HFC investment projects, stage I of the KIP for the Niger (advance funding) was approved at the 91st meeting and is expected to be completed in 2025. The others, approved at the 81st, 86th, 87th and 91st meetings, are at various stages of implementation.

# Of the total cumulative funding approved of US $8,699,914 (excluding agency support costs), US $3,926,087 had been disbursed, representing a disbursement rate of 45 per cent.

I.2	Issues identified in project implementation in 2022

# Further to the review process, several issues were discussed and satisfactorily addressed, except for issues on 38 projects classified as projects with implementation delays (including 36 projects related to components of MYAs that are subject to procedures for project cancellation, in line with decision 84/45(c); one technical assistance project; and one investment project). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 94th meeting.

# In addition, issues have been identified regarding projects or tranches of MYAs for the phase-out of HCFCs. These issues are also presented in annex III. For each of these projects, a brief description on the status of implementation and the outstanding issues are presented and a recommendation is proposed for consideration by the Executive Committee.

# Details of progress in implementation of projects associated with the HPMPs for Bahrain, Bolivia (Plurinational State of), China (extruded polystyrene foam sector plan), Ecuador, the Gambia, Guatemala, Guinea, Morocco, North Macedonia, Oman, the Philippines, Qatar, Sierra Leone, Suriname, Türkiye, and Venezuela (Bolivarian Republic of), and reports on projects with specific reporting requirements associated with Argentina (HFC-23 by-product and global chiller replacement project), Côte d’Ivoire (HPMP) and Libya (HPMP), have been submitted to the 93rd meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. The issues relating to the HPMPs for Afghanistan, Algeria, Bosnia and Herzegovina, Botswana, Egypt, Iraq, Kuwait, and Senegal, tranches of which were due at the 93rd meeting but were not submitted, and for China (room air-conditioner manufacturing and heat pump water heaters sector plan) and the Islamic Republic of Iran, tranches of which were submitted but later withdrawn, are addressed in the document on tranche submission delays. Outstanding issues for the remaining ongoing projects not included in annex III to the present document, and requests for extension of dates of completion, are addressed below.

# Of the 149 ongoing projects, excluding IS and project preparation, 53 projects have revised planned dates of completion since the 2021 progress report.

# In line with decision 82/11(b), UNIDO has requested the extension of the duration of two projects, as shown in table 5.

Table 5. Projects for which an extension of the completion dates has been requested

| Country/ project code | Project title | Disburse-ment (%) | Status/issues | Original date of completion | Date of completion requested |
| --- | --- | --- | --- | --- | --- |
| Jordan JOR/PHA/91/INV/114 | HCFC phase-out management plan (stage II, third tranche) | 0 | Additional time required for completing procurement of identifiers and training of trainers in good servicing practices | Dec-23 | Dec-24 |
| Sudan (the) SUD/PHA/75/INV/38 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | 31 | Additional time required to complete equipment supply, installation and commissioning at Mina Factory and Target Steel | Dec-23 | Dec-24 |

# With regard to the HPMP for Myanmar, UNIDO informed the Secretariat that due to the political situation in the country, it is unable to communicate with the Government authorities and continue implementation. In consultation with the agency, it was agreed that the preparation of stage II of the HPMP (MYA/PHA/83/PRP/20) would be cancelled and the remaining balances would be returned in line with decision 28/7.

# Gender mainstreaming

# In 2022, UNIDO has implemented the Multilateral Fund operational policy on gender mainstreaming in 66 countries as part of projects approved since the 85th meeting. When preparing and submitting the project proposals, UNIDO tries to include to the extent possible activities that would address gender equality and women’s empowerment. The checklists and potential indicators included in the project guides are used for that purpose.

# UNIDO, as an organization, acknowledges the substantial positive impact of gender equality and women’s empowerment on sustained economic growth and the promotion of sustainable industrial development. These factors are instrumental in driving poverty reduction and fostering social integration. Consequently, the organization has instituted its own policy and strategy for gender mainstreaming with the goal of achieving tangible outcomes.

# The integration of gender mainstreaming into project implementation encompasses several key aspects starting from representation of women in project team constitution and recruitment process, participation of women in different capacity building and awareness raising activities and other project implementation monitoring and reporting processes.

# UNIDO is actively engaged in identifying potential female technicians and engineers who could pursue careers in this sector, offering tailored training programmes. The success of these initiatives varies from country to country. Additional information relating to country level activities is provided in section VI of UNIDO’s narrative attached to the present document.

# From the experiences garnered thus far, it is evident that there exists immense potential for advancing gender mainstreaming within the Montreal Protocol portfolio. In this regard, UNIDO stands prepared to continue implementing the Multilateral Fund operational policy on gender mainstreaming, incorporating gender mainstreaming activities within existing budgetary constraints, while also being ready to develop more comprehensive programmes within the stages of MYA projects, such as HPMPs or KIPs.

II.	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down

# As of 31 December 2022, the Executive Committee had approved 35 HFC-related projects under the additional voluntary contributions amounting to US $8,043,152 (excluding agency support costs). A summary of the status of these projects is presented in table 6.

# Table 6. Status of approved HFC-related projects as of the end of 2022

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 3 | 3 | 100 | 3,898,752 | 2,450,030 | 1,448,722 | 63 |
| Project preparation | 4 | 4 | 100 | 101,270 | 101,270 | 0 | 100 |
| Technical assistance – Enabling activities | 28 | 28 | 100 | 4,043,130 | 3,697,732 | 345,398 | 91 |
| Total | 35 | 35 | 100 | 8,043,152 | 6,249,032 | 1,794,120 | 78 |

* Excludes agency support costs.

** 189.4 mt (370,517 CO2-eq tonnes) of 286.0 mt (508,586 CO2-eq tonnes) of HFCs had been phased out.

# As of the end of 2022, all the 35 projects approved had been completed.

# Of the total cumulative funding approved of US $8,043,152, US $6,249,032 had been disbursed representing a disbursement rate of 78 per cent.

III.	Recommendation

# The Executive Committee may wish:

## To note the progress report of UNIDO as at 31 December 2022 contained in document UNEP/OzL.Pro/ExCom/93/18;

## To approve the extension, to 31 December 2024, of the completion dates of the HCFC phase-out management plans (HPMPs) for the countries listed below to allow for completion of the remaining ongoing activities as reflected in table 5 of document UNEP/OzL.Pro/ExCom/93/18:

### Jordan (stage II, third tranche) (JOR/PHA/91/INV/114); and

### Sudan (the) (stage II, first tranche) (foam sector) (SUD/PHA/75/INV/38);

## To cancel the preparation of stage II of the HPMP for Myanmar (MYA/PHA/83/PRP/20) and to request UNIDO to return the remaining balances in line with decision 28/7; and

## To approve the recommendations related to ongoing projects with specific issues contained in annex III to the present document.

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNIDO

PER COUNTRY FOR 2022

# Table 1 of annex I presents the status of project implementation by country for 2022 in achieved phased out, planned and achieved disbursements and project completion.

Table 1. Status of project implementation by UNIDO for 2022

| Country | Phased out in 2022 (ODP tonnes) | Phased out in 2022 (CO2-eq tonnes)* | Estimated funds disbursed in 2022 (US$) | Funds disbursed in 2022 (US$) | Percentage of funds disbursed over estimation in 2022 | Percentage of planned projects completed in 2022** |
| --- | --- | --- | --- | --- | --- | --- |
| Afghanistan | 0.0 | 0 | 3 | 9 | 316 | 0 |
| Albania | 0.0 | 0 | 79,400 | 47,792 | 60 |  |
| Algeria | 0.0 | 0 | 58,002 | 57,316 | 99 | 100 |
| Argentina | 17.1 | 0 | 800,804 | 760,557 | 95 |  |
| Armenia | 0.0 | 0 | 50,000 | 90,601 | 181 |  |
| Bahamas (the) | 0.0 | 0 | 28,400 | 10,038 | 35 | 100 |
| Bahrain | 0.0 | 0 | 79,001 | 38,744 | 49 | 100 |
| Benin | 0.1 | 0 | 600 | 4,703 | 784 | 100 |
| Bolivia (Plurinational State of) | 0.4 | 0 | 100,000 | 141,982 | 142 |  |
| Bosnia and Herzegovina | 0.6 | 0 | 93,280 | 50,712 | 54 | 100 |
| Botswana | 0.1 | 0 | 55,700 | 21,750 | 39 | 50 |
| Brazil | 6.1 | 0 | 194,000 | 295,297 | 152 |  |
| Burkina Faso | 0.0 | 0 | 11,500 | 7,816 | 68 | 0 |
| Burundi | 0.0 | 0 | 6,500 | 5,775 | 89 | 100 |
| Cameroon | 0.3 | 0 | 118,000 | 107,107 | 91 |  |
| Chad | 0.0 | 0 | 20,000 | 19,144 | 96 | 100 |
| Chile | 8.6 | 0 | 130,001 | 131,704 | 101 |  |
| China | 1.0 | 0 | 10,782,503 | 11,002,040 | 102 |  |
| Congo (the) | 0.0 | 0 | 2,600 | 0 | 0 | 100 |
| Cote d’Ivoire | 10.7 | 0 | 160,000 | 362,670 | 227 | 100 |
| Democratic People’s Republic of Korea (the) | 0.0 | 0 | 3 | 20,548 | 684,931 |  |
| Ecuador | 0.0 | 0 | 380,000 | 458,930 | 121 | 0 |
| Egypt | 11.3 | 0 | 1,071,302 | 807,371 | 75 | 50 |
| Equatorial Guinea | 0.0 | 0 | 1,000 | 0 | 0 | 0 |
| Eritrea | 0.0 | 0 | 1 | 12 | 1,182 |  |
| Ethiopia | 0.0 | 0 | 6,301 | 1,103 | 18 |  |
| Gabon | 4.9 | 0 | 35,000 | 5,149 | 15 | 50 |
| Gambia (the) | 0.0 | 0 | 23,001 | 1,424 | 6 |  |
| Grenada | 0.0 | 0 | 1 | 0 | 0 |  |
| Guatemala | 0.4 | 0 | 101,650 | 110,912 | 109 |  |
| Guinea | 0.0 | 0 | 16,000 | 4,273 | 27 | 100 |
| Guinea-Bissau | 0.0 | 0 | 3,000 | 0 | 0 | 0 |
| Honduras | 0.4 | 0 | 78,000 | 152,090 | 195 |  |
| Iran (Islamic Republic of) | 3.8 | 0 | 122,000 | 45,060 | 37 |  |
| Iraq | 0.0 | 0 | 856,501 | 314,883 | 37 |  |
| Jordan | 0.0 | 0 | 143,002 | 171,605 | 120 | 100 |
| Kuwait | 204.0 | 0 | 712,834 | 213,596 | 30 | 100 |
| Lebanon | 0.0 | 0 | 10,000 | 24,155 | 242 |  |
| Lesotho | 0.0 | 0 | 5,000 | 2,974 | 59 |  |
| Liberia | 0.0 | 0 | 7,000 | 6,933 | 99 | 100 |
| Libya | 2.7 | 0 | 265,000 | 201,783 | 76 | 25 |
| Madagascar | 0.0 | 0 | 24,000 | 23,517 | 98 | 100 |
| Malawi | 0.0 | 0 | 60,000 | 2,211 | 4 |  |
| Mauritania | 0.0 | 0 | 5,000 | 0 | 0 |  |
| Mexico | 18.1 | 0 | 584,300 | 1,384,363 | 237 | 0 |
| Montenegro | 0.1 | 0 | 91,802 | 68,017 | 74 |  |
| Morocco | 8.1 | 0 | 103,600 | 122,022 | 118 | 100 |
| Mozambique | 0.0 | 0 | 60,000 | 32,263 | 54 | 100 |
| Myanmar | 0.0 | 0 | 2 | 0 | 9 |  |
| Namibia | 0.0 | 0 | 20,000 | 29,567 | 148 |  |
| Nicaragua | 0.1 | 0 | 96,000 | 96,452 | 100 |  |
| Niger (the) | 1.1 | 0 | 163,001 | 227,803 | 140 | 100 |
| Nigeria | 0.0 | 0 | 16,250 | 8,766 | 54 |  |
| North Macedonia | 0.1 | 0 | 150,003 | 165,795 | 111 | 100 |
| Oman | 0.0 | 0 | 106,073 | 96,447 | 91 | 100 |
| Pakistan | 41.3 | 0 | 719,601 | 1,537,370 | 214 | 75 |
| Philippines (the) | 0.0 | 0 | 90,000 | 124,335 | 138 |  |
| Qatar | 0.0 | 0 | 80,001 | 58,233 | 73 |  |
| Rwanda | 0.0 | 0 | 55,001 | 4,629 | 8 |  |
| Saint Lucia | 0.0 | 0 | 20,001 | 51 | 0 |  |
| Saudi Arabia | 0.0 | 0 | 225,006 | 543,572 | 242 | 50 |
| Senegal | 0.0 | 0 | 53,000 | 12,262 | 23 | 100 |
| Serbia | 0.0 | 0 | 110,002 | 113,062 | 103 | 0 |
| Sierra Leone | 0.0 | 0 | 25,002 | 6,221 | 25 |  |
| Somalia | 0.0 | 0 | 83,000 | 66,701 | 80 | 50 |
| South Africa | 78.5 | 0 | 603,001 | 599,708 | 99 | 100 |
| Sudan (the) | 4.2 | 0 | 170,900 | 232,935 | 136 | 100 |
| Suriname | 0.0 | 0 | 1,501 | 8,500 | 566 | 100 |
| Syria | 0.0 | 0 | 153,201 | 197,467 | 129 | 100 |
| Togo | 0.0 | 0 | 11,900 | 7,447 | 63 | 100 |
| Tunisia | 0.0 | 0 | 205,001 | 221,899 | 108 | 0 |
| Türkiye | 0.0 | 0 | 147,000 | 175,017 | 119 | 0 |
| Turkmenistan | 0.0 | 0 | 93,000 | 83,474 | 90 | 0 |
| Uganda | 0.0 | 0 | 28,000 | 26,377 | 94 |  |
| United Republic of Tanzania (the) | 0.0 | 0 | 40,000 | 10,406 | 26 |  |
| Venezuela (Bolivarian Republic of) | 0.0 | 0 | 99,000 | 136,152 | 138 | 50 |
| Zambia | 0.0 | 0 | 35,001 | 40,026 | 114 | 0 |
| Global | 0.0 | 0 | 87,000 | 130,665 | 150 | 100 |
| Grand total | 424.0 | 0 | 21,222,040 | 22,292,292 | 105 | 72 |

* No phase-out in 2022 for HFC-related projects.

** For projects that were planned to be completed in 2022.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNIDO

PER YEAR AS AT 31 DECEMBER 2022

# Table 1 of annex II presents an overview of the status of project implementation by year. All projects and activities approved between 1993 and 2011, have now been completed.

Table 1. Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1993 | 22 | 22 | 100 | 11,815,540 | 11,815,540 | 0 | 100 |
| 1994 | 52 | 52 | 100 | 30,645,899 | 30,645,899 | 0 | 100 |
| 1995 | 59 | 59 | 100 | 25,662,092 | 25,662,092 | -1 | 100 |
| 1996 | 46 | 46 | 100 | 19,820,493 | 19,820,493 | 0 | 100 |
| 1997 | 130 | 130 | 100 | 42,083,037 | 42,083,038 | -1 | 100 |
| 1998 | 88 | 88 | 100 | 23,638,291 | 23,638,291 | 0 | 100 |
| 1999 | 123 | 123 | 100 | 34,140,324 | 34,140,324 | 0 | 100 |
| 2000 | 96 | 96 | 100 | 30,180,752 | 30,180,752 | 0 | 100 |
| 2001 | 119 | 119 | 100 | 24,700,254 | 24,700,255 | -1 | 100 |
| 2002 | 76 | 76 | 100 | 35,992,041 | 35,992,041 | 0 | 100 |
| 2003 | 49 | 49 | 100 | 29,997,305 | 29,997,305 | 0 | 100 |
| 2004 | 44 | 44 | 100 | 33,105,459 | 33,105,460 | -1 | 100 |
| 2005 | 74 | 74 | 100 | 52,035,808 | 52,035,806 | 2 | 100 |
| 2006 | 44 | 44 | 100 | 20,760,312 | 20,760,312 | 0 | 100 |
| 2007 | 42 | 42 | 100 | 24,186,740 | 24,186,740 | 0 | 100 |
| 2008 | 77 | 77 | 100 | 33,386,108 | 33,386,111 | -3 | 100 |
| 2009 | 70 | 70 | 100 | 15,345,924 | 15,054,995 | 290,929 | 98 |
| 2010 | 69 | 69 | 100 | 46,081,793 | 45,558,786 | 523,006 | 99 |
| 2011 | 71 | 71 | 100 | 76,542,461 | 76,542,380 | 81 | 100 |
| 2012 | 52 | 49 | 94 | 32,670,641 | 31,681,748 | 988,893 | 97 |
| 2013 | 37 | 36 | 97 | 31,117,693 | 31,086,604 | 31,089 | 100 |
| 2014 | 55 | 53 | 96 | 27,835,611 | 27,094,088 | 741,523 | 97 |
| 2015 | 83 | 75 | 90 | 37,085,970 | 32,640,253 | 4,445,716 | 88 |
| 2016 | 58 | 49 | 84 | 35,651,882 | 23,545,443 | 12,106,439 | 66 |
| 2017 | 28 | 24 | 86 | 16,417,092 | 14,442,589 | 1,974,503 | 88 |
| 2018 | 62 | 52 | 84 | 27,012,958 | 12,127,844 | 14,885,114 | 45 |
| 2019 | 66 | 35 | 53 | 19,210,508 | 7,432,234 | 11,778,274 | 39 |
| 2020 | 58 | 27 | 47 | 15,346,833 | 13,196,259 | 2,150,574 | 86 |
| 2021 | 73 | 7 | 10 | 23,091,580 | 4,531,688 | 18,559,892 | 20 |
| 2022 | 66 | 0 | 0 | 20,317,479 | 348,013 | 19,969,466 | 2 |
| Total | 1,989 | 1,758 | 88 | 895,878,878 | 807,433,382 | 88,445,496 | 90 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

Annex III

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR UNIDO

| Country/project code | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- |
| Afghanistan AFG/PHA/79/INV/22 | HCFC phase-out management plan (stage I, third tranche) | 14 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Afghanistan AFG/PHA/85/INV/28 | HCFC phase-out management plan (stage I, fourth tranche) | 0 | 12 and 18 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Afghanistan AFG/PHA/85/INV/30 | HCFC phase-out management plan (stage II, first tranche) | 3 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Algeria ALG/PHA/66/INV/76 | HCFC phase-out management plan (stage I, first tranche) (conversion from HCFC-22 in the manufacture of room air conditioners at Condor) | 64 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Algeria ALG/PHA/66/INV/77 | HCFC phase-out management plan (stage I, first tranche) (activities in the refrigeration servicing sector including phase-out of HCFC-141b used for flushing, and project monitoring) | 62 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Argentina ARG/PHA/84/INV/192 | HCFC phase-out management plan (stage II, second tranche) (foam sector) | 1 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Argentina ARG/PHA/84/TAS/193 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 10 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Bosnia and Herzegovina BHE/PHA/86/TAS/38 | Verification report on implementation of stage I of the HCFC phase-out management plan | 0 | 12 and 18 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Botswana BOT/PHA/82/INV/21 | HCFC phase-out management plan (stage I, second tranche) | 12 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Botswana BOT/PHA/86/INV/27 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Brazil BRA/PHA/75/INV/311 | HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration and air-conditioning sector) | 97 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Brazil BRA/PHA/75/TAS/308 | HCFC phase-out management plan (stage II, first tranche) (project monitoring) | 99 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Brazil BRA/PHA/82/INV/320 | HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration and air-conditioning sector) | 48 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Cameroon CMR/PHA/82/INV/45 | HCFC phase-out management plan (stage II, first tranche) | 47 | (i) 12 months delays (ii) Delay in implementation due to operational challenges | (i) To request UNIDO to report to the 94th meeting on this project with implementation delays (ii) To request UNIDO to submit a status report to the 94th meeting on implementation progress |
| Chile CHI/PHA/81/TAS/196 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 30 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| China CPR/PHA/77/INV/576 | HCFC phase-out management plan (stage II, first tranche) (room air-conditioner manufacturing and heat pump water heaters sector plan) | 30 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| China CPR/PHA/81/INV/588 | HCFC phase-out management plan (stage II, second tranche) (room air-conditioner manufacturing and heat pump water heaters sector plan) | 30 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| China CPR/PHA/88/INV/605 | HCFC phase-out management plan (stage II, third tranche) (room air-conditioning manufacturing and heat pump water heaters sector plan) | 0 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Egypt EGY/PHA/79/INV/133 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | 76 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Egypt EGY/PHA/84/INV/141 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector and project management unit) | 64 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Egypt EGY/PHA/84/INV/147 | HCFC phase-out management plan (stage II, second tranche) (residential air-conditioning manufacturing sector) | 26 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/77/INV/228 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | 65 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/84/INV/239 | HCFC phase-out management plan (stage II, second tranche) (foam sector) | 7 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/84/TAS/240 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 2 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Jordan JOR/PHA/77/INV/101 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 99 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Jordan JOR/REF/81/INV/103 | Conversion of large commercial unitary roof top air-conditioning units of up to 400kW manufacturing facility from HFC (R-134a, R-407c, R-410a) to propane R290 as refrigerant at Petra Engineering Industries Co. | 93 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Mexico MEX/PHA/73/INV/174 | HCFC phase-out management plan (stage II, first tranche) (cleaning agent phase-out in refrigeration servicing sector) | 100 | 12 months delays | Noting decision 77/8(j), to request UNIDO to report to the 94th meeting on this project with implementation delays |
| Mexico MEX/PHA/77/INV/183 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 100 | 12 months delays | Noting decision 77/8(j), to request UNIDO to report to the 94th meeting on this project with implementation delays |
| Mexico MEX/PHA/81/INV/189 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) | 32 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Mozambique MOZ/PHA/83/INV/31 | HCFC phase-out management plan (stage I, third and fourth tranches) | 27 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Pakistan PAK/PHA/76/INV/94 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | 77 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Pakistan PAK/PHA/83/INV/102 | HCFC phase-out management plan (stage II, second tranche) (polyurethane foam sector) | 39 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Pakistan PAK/PHA/83/INV/99 | HCFC phase-out management plan (stage II, second tranche) (domestic air-conditioning sector) | 55 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Pakistan PAK/PHA/83/TAS/100 | HCFC phase-out management plan (stage II, second tranche) (project management unit) | 53 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| South Africa SOA/FOA/67/INV/03 | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | 99 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| South Africa SOA/PHA/71/INV/06 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing, custom training and monitoring) | 96 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |
| Sudan (the) SUD/PHA/75/INV/38 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | 31 | (i) 12 months delays (ii) Implementation delayed due to political situation | (i) To request UNIDO to report to the 94th meeting on this project with implementation delays (ii) To request UNIDO to submit a status report to the 94th meeting on the status of implementation of activities |
| Sudan (the) SUD/PHA/88/INV/48 | HCFC phase-out management plan (stage III, first tranche) | 3 | Implementation delayed due to political situation | To request UNIDO to submit a status report to the 94th meeting on the status of implementation of activities |
| Zambia ZAM/PHA/77/INV/33 | HCFC phase-out management plan (stage I, third tranche) | 28 | 12 months delays | To request UNIDO to report to the 94th meeting on this project with implementation delays |

UNEP/OzL.Pro/ExCom/93/1

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database that is available upon request.

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 93rd meeting.

UNIDO became an implementing agency in 1993.

Ongoing projects are all projects that were under implementation as at 31 December 2022. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

In line with decision 84/12(b), a detailed progress report providing an overview of the objectives, status of implementation, key findings and lessons learned, the amounts of HFC phased out where applicable, the level of funds approved and disbursed and potential challenges in completing the projects and activities, is presented in the consolidated progress report (UNEP/OzL.Pro/ExCom/93/14).

Phase-out of ODS is expressed in ODP tonnes and of HFCs in CO2-eq tonnes.

No phase-out for HFC-related projects in 2022.

No phase-out so far for HFC-related projects.

Including 129.1 mt of HFC investment projects. Cost-effectiveness in CO2-eq. is not included due to the limited number of projects approved.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61).

UNEP/OzL.Pro/ExCom/93/41

UNEP/OzL.Pro/ExCom/93/43

UNEP/OzL.Pro/ExCom/93/47

UNEP/OzL.Pro/ExCom/93/52

UNEP/OzL.Pro/ExCom/93/54

UNEP/OzL.Pro/ExCom/93/57

UNEP/OzL.Pro/ExCom/93/58

UNEP/OzL.Pro/ExCom/93/72

UNEP/OzL.Pro/ExCom/93/78

UNEP/OzL.Pro/ExCom/93/79

UNEP/OzL.Pro/ExCom/93/82

UNEP/OzL.Pro/ExCom/93/83

UNEP/OzL.Pro/ExCom/93/86

UNEP/OzL.Pro/ExCom/93/88

UNEP/OzL.Pro/ExCom/93/90

UNEP/OzL.Pro/ExCom/93/92

UNEP/OzL.Pro/ExCom/93/20 or UNEP/OzL.Pro/ExCom/93/21

UNEP/OzL.Pro/ExCom/93/24

Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.

The Executive Committee requested bilateral and implementing agencies to provide a brief report on key gender mainstreaming results achieved as part of their annual progress reports, as of 2023, on the basis of the information available to them (decision 90/48(d)).

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.