| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/97/9 7 November 2025 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-seventh Meeting

Montreal, 1-5 December 2025

Item 6(a) of the provisional agenda

Evaluation of the performance of implementing agencies 
against their 2024 business plans

Introduction

# The present document consists of the following sections:

I.	Analysis of quantitative performance indicators. This section presents the quantitative evaluation of the performance of the implementing agencies with respect to the performance targets set in the 2024 business plans and progress and financial reports submitted to the 97th meeting; and a trend analysis for each of the eight performance indicators.

II.	Analysis of qualitative performance indicators. This section presents a qualitative assessment of the performance of bilateral and implementing agencies based on input received from national ozone unit (NOU) officers.

III.	Secretariat’s comments

IV.	Recommendation

# I.	Analysis of quantitative performance indicators

# Table 1 presents the approved targets, measures of progress towards achieving each target, and the number of targets achieved.

Table 1. 2024 performance indicator targets and achievement

| Item | UNDP |  |  |  | UNEP |  |  |  | UNIDO |  |  |  | World Bank |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Target | Agency achievement | Secretariat assessment | Met target | Target | Agency achievement | Secretariat assessment | Met target | Target | Agency achievement | Secretariat assessment | Met target | Target | Agency achievement | Secretariat assessment | Met target |
| Tranches approved* | 38 | 30 | 30 | No | 86 | 63 | 76 | No | 43 | 37 | 36 | No | 4 | 2 | 2 | No |
| Projects/activities approved | 33 | 29 | 29 | No | 119 | 153 | 122 | Yes | 56 | 18 | 40 | No | 4 | 4 | 4 | Yes |
| Funds disbursed (million US $) | 26.75 | 18.74 | 18.74 | No | 24.72 | 24.01 | 23.78 | No | 19.68 | 19.79 | 19.79 | Yes | 18.16 | 26.41 | 26.41 | Yes |
| ODS phase-out* | 271.84 | 260.0 | 260.0 | No | 198.99 | 177.7 | 173.8 | No | 468.43 | 456.7 | 456.7 | No | 5,446.1 | 7,876.9 | 5,443.7 | No |
| Project completion for activities | 45 | 41 | 41 | No | 81 | 82 | 82 | Yes | 64 | 34 | 33 | No | 1 | 6 | 6 | Yes |
| Speed of financial completion | 70% (48) | 48 | 48 | Yes | 12 months | 5.8 months | 5.9 months | Yes | 12 months after operational completion | 12 months | 11.6 months | Yes | 90% (7) | 57% (4) | 57% (4) | No |
| Timely submission of project completion reports | On time (1) | On time (6) | On time (2) | Yes | On time (5) | On time (11) | On time (11) | Yes | On time (4) | On time | On time (6) | Yes | 0 | 0 | 0 | N/A |
| Timely submission of progress reports | On time | On time | On time | Yes | On time | On time | On time | Yes | On time | On time | On time | Yes | On time | On time | On time | Yes |
| Number of targets achieved |  |  |  | 3/8 |  |  |  | 5/8 |  |  |  | 4/8 |  |  |  | 4/7 |

- * The targets of an agency would be reduced “if it could not submit a tranche owing to another cooperating agency or lead agency” or “if HPMP submitted for consideration by the Executive Committee was not approved as a result of factors beyond the control of the NOU and agency”.

Weighted assessment of performance

# Table 2 presents the outcome of the 2024 weighted assessment by performance indicator based on the Secretariat’s methodology.

Table 2. Weighted assessment of implementing agencies performance in 2024

| Item | Weight-ing | UNDP |  | UNEP |  | UNIDO |  | World Bank |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | % of target achieved | Points | % of target achieved | Points | % of target achieved | Points | % of target achieved* | Points |
| Tranches approved | 10 | 79 | 8 | 88 | 9 | 84 | 8 | 50 | 5 |
| Projects/activities approved | 10 | 88 | 9 | 103 | 10 | 71 | 7 | 100 | 10 |
| Funds disbursed | 15 | 70 | 11 | 96 | 14 | 101 | 15 | 145 | 15 |
| ODS phase-out | 25 | 96 | 24 | 87 | 22 | 97 | 24 | 100 | 25 |
| Project completion for activities | 20 | 91 | 18 | 101 | 20 | 52 | 10 | 600 | 20 |
| Speed of financial completion | 10 | 100 | 10 | 151 | 10 | 103 | 10 | 57 | 7 |
| Timely submission of project completion reports | 5 | 200 | 5 | 220 | 5 | 150 | 5 | N/A | N/A |
| Timely submission of progress reports | 5 | 100 | 5 | 100 | 5 | 100 | 5 | 100 | 7 |
| 2024 Assessment | 100 |  | 90 |  | 95 |  | 84 |  | 89 |

*For the World Bank, the weightings (5) for “Timely submission of project completion reports” has been prorated for other administrative indicators: “Speed of financial completion (3)” and “Timely submission of progress reports (2)”. Points earned are rounded to the nearest number.

# Analysis of other quantitative performance indicators

# In line with decision 41/93, annexes I and II present the historical analyses for investment and non-investment projects, respectively.

# Annex I shows that the target for ODS phased out was achieved by all agencies in 2024. The target for the amount of funds disbursed was achieved by UNDP and the World Bank, while UNIDO met 98 per cent. UNDP and UNIDO reached their targets for project completion reports, while the World Bank did not have project completion reports due in 2024. The speed of delivery and first disbursement in 2024 were similar to previous years reflecting the historical performance for all implementing agencies. The achievement of the target for value of projects approved increased for UNDP and UNIDO and decreased for the World Bank compared to 2023. The target for ODS to be phased out was achieved by the World Bank and was partially achieved by UNDP and UNIDO. The indicators “cost-effectiveness” and “cost of project preparation” are inconclusive with respect to any trend due to the differences in ODP of CFCs and HCFCs and the approval of MYAs instead of individual projects.

# Annex II shows that the target for the amount of funds disbursed was achieved by UNDP, UNEP and UNIDO; and the speed of delivery and first disbursement for 2024 were similar to previous years for all implementing agencies.

# II.	Analysis of qualitative performance indicators

# A total of 160 questionnaires received from the NOUs of 93 Article 5 countries to assess the qualitative performance of the bilateral and implementing agencies were processed.

# The questionnaire contains three main categories of questions, and an overall assessment of the agencies’ performance in each category must be provided.

# Table 3 presents a summary of the overall ratings provided by the NOUs for the three main categories. It should be noted that several NOUs did not provide overall ratings for one or more of the categories, although they did send responses to the individual questions that have been included in annex III to the present document. Table 3 shows that most of the overall ratings were satisfactory or above; only 13 ratings were below satisfactory.

# Table 3. Overall ratings for qualitative performance of bilateral and implementing agencies by category

| Category | Highly satisfactory | Satisfactory | Less satisfactory | Unsatisfactory |
| --- | --- | --- | --- | --- |
| Impact | 91 | 37 | 4 | 1 |
| Organization and cooperation | 73 | 31 | 3 | 1 |
| Technical assistance/training | 78 | 41 | 2 | 2 |

# In addition to the required overall ratings for the three main categories mentioned above, the questionnaire includes 31 individual questions. The NOUs provided 118 ratings below satisfactory for these questions, as detailed in annex III.

III.	Secretariat’s comments

# The implementing agencies have been informed of the results of the quantitative assessment of their performance for 2024, showing that all of them achieved 84 per cent or more of their targets.

# The Executive Committee may wish to note that the quantitative assessment of performance for 2024 had improved for two implementing agencies (UNDP and UNEP) compared to 2023.

# The Secretariat noted that 93 NOUs (as compared to 88 in 2023) submitted qualitative assessments. The Secretariat sent the assessments received from the NOUs to the respective bilateral and implementing agencies for their comments, with an emphasis on the 131 ratings below satisfactory (including 13 low ratings for the three main categories and 118 low ratings for the individual questions).

# Dialogues between the respective NOUs and bilateral and implementing agencies have been completed for all countries that identified issues in their qualitative assessments (i.e., ratings of “less satisfactory” or “unsatisfactory”); all agencies reported that a way forward was agreed during their dialogues with the respective NOUs, and in most cases, they have been able to resolve the issues identified in regard to the less than satisfactory ratings. In this regard, the Executive Committee may wish to note, with appreciation, the efforts undertaken by bilateral and implementing agencies to have open and constructive discussions with the respective NOUs about the areas in which their services were perceived to be less than satisfactory and that the outcome of their consultations with the NOUs concerned had also been satisfactory.

# IV.	Recommendation

# The Executive Committee may wish:

## To note:

### The evaluation of the performance of implementing agencies against their 2024 business plans, as contained in document UNEP/OzL.Pro/ExCom/97/9;

### That all implementing agencies had a quantitative assessment of their performance for 2024 of at least 84 on a scale of 100;

### That trend analysis indicated that the performance of implementing agencies had not improved for some indicators in 2024 compared with 2023;

### That quantitative performance in 2024 had improved for two implementing agencies (UNDP and UNEP) compared with 2023;

### With appreciation, the efforts undertaken by bilateral and implementing agencies to have open and constructive discussions with the respective national ozone units (NOUs) about the areas in which their services were perceived to be less than satisfactory and that the outcome of their consultations with the NOUs concerned had also been satisfactory; and

## To encourage NOUs to submit, on a yearly basis and in a timely manner, their assessments of the qualitative performance of the bilateral and implementing agencies assisting their governments, noting that 93 out of the 144 countries had submitted such assessments for 2024, compared with 88 in 2023.

Annex I

INVESTMENT PROJECT PERFORMANCE BY AGENCY

(2001-2024)

| UNDP | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODS phased out | 99% | 92% | 100% | 79% | 91% | 85% | 100% | 86% | 100% | N/A | 0% | 94% | 100% | 100% | 100% | 0% | 34% | 100% | 100% | 100% | 100% | 100% | 37% | 100% |
| Funds disbursed | 95% | 77% | 64% | 100% | 96% | 66% | 76% | 98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 97% | 97% | 100% | 100% | 100% | 100% | 100% | 64% | 100% |
| Project completion reports | 86% | 87% | 100% | 97% | 79% | 30% | 82% | 74% | 100% | 54% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |
| Distribution among countries | 63% | 58% | 38% | 72% | 44% | 75% | 64% | 66% | 83% | 51% | 79% | 94% | 81% | 68% | 85% | 90% | 60% | 88% | 80% | 69% | 76% | 67% | 77% | 82% |
| Value of projects approved | 100% | 99% | 65% | 73% | 82% | 83% | 77% | 100% | 100% | 38% | 87% | 100% | 87% | 89% | 91% | 100% | 80% | 79% | 85% | 81% | 80% | 78% | 57% | 84% |
| ODS to be phased out | 96% | 77% | 44% | 89% | 70% | 100% | 100% | 100% | 100% | 100% | 92% | 61% | 100% | 29% | 83% | 84% | 84% | 96% | 97% | 93% | 95% | 98% | 82% | 96% |
| Cost of project preparation (% of approvals) | 1.1% | 2.5% | 1.6% | 3.6% | 1.4% | 0.5% | 3.6% | 1.5% | 14.7% | 14.4% | 3.0% | 2.8% | 1.8% | 0.2% | 4.3% | 2.3% | 2.71% | 0.99% | 0.43% | 0.74% | 1.46% | 6.42% | 5.76% | 5.18% |
| Cost-effectiveness ($/kg) | 8.3 | 10.35 | 7.1 | 6.27 | 8.24 | 4.99 | 5.76 | 5.61 | 6.09 | 59.84 | 146.85 | 92.53 | 56.92 | 249.68 | 70.89 | 108.35 | 184.95 | 38.00 | 45.41 | 51.97 | 51.22 | 59.08 | 14.18 | 16.46 |
| Speed of first disbursement (months) | 12.84 | 12.8 | 12.8 | 12.91 | 12.9 | 13.0 | 13.1 | 13.2 | 13.4 | 13.6 | 13.7 | 13.7 | 13.7 | 13.7 | 13.7 | 13.6 | 13.5 | 13.6 | 13.6 | 13.6 | 13.6 | 13.6 | 13.7 | 13.7 |
| Speed of completion (months) | 33.6 | 32.7 | 32.4 | 32.41 | 32.9 | 33.6 | 33.9 | 33.8 | 33.9 | 34.2 | 34.6 | 34.9 | 34.9 | 35.2 | 35.1 | 34.4 | 35.6 | 35.7 | 35.8 | 35.7 | 35.8 | 35.9 | 35.8 | 35.9 |
| Net emissions due to delays (ODP tonnes) | 11,727 | 9,023 | 6,466 | 3,607 | 4,538 | 6,619 | 2,674 | 1,312 | 92 | 113 | 101 | 520 | 538 | 248 | 238 | -881 | 416.3 | 499.6 | 426.1 | 395.9 | 268.4 | 335.3 | 480.9 | 651.7 |
| UNIDO | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 |
| ODS phased out | 100% | 100% | 88% | 100% | 99% | 100% | 100% | 84% | 86% | 100% | 100% | 0% | 27% | 42% | 100% | 100% | 100% | 50% | 45% | 55% | 87% | 100% | 100% | 100% |
| Funds disbursed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 91% | 100% | 94% | 100% | 100% | 100% | 97% | 100% | 100% | 100% | 100% | 69% | 86% | 87% | 100% | 100% | 98% |
| Project completion reports | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 84% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |
| Distribution among countries | 89% | 73% | 78% | 67% | 79% | 69% | 75% | 82% | 61% | 81% | 83% | 100% | 72% | 67% | 100% | 76% | 54% | 64% | 75% | 74% | 52% | 62% | 66% | 75% |
| Value of projects approved | 99% | 97% | 68% | 82% | 100% | 100% | 92% | 100% | 59% | 78% | 100% | 79% | 88% | 64% | 93% | 71% | 73% | 57% | 73% | 85% | 52% | 90% | 77% | 100% |
| ODS to be phased out | 100% | 100% | 37% | 89% | 100% | 47% | 91% | 100% | 100% | 100% | 36% | 81% | 21% | 36% | 100% | 82% | 61% | 71% | 82% | 86% | 84% | 70% | 96% | 97% |
|  | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 |
| Cost of project preparation (% of approvals) | 2.7% | 3.3% | 3.6% | 2% | 0.9% | 1.8% | 2.1% | 1.3% | 11.9% | 5.7% | 2.7% | 3.9% | 1.1% | 1.3% | 1.8% | 3.6% | 2.6% | 0.4% | 2.4% | 2.8% | 3.2% | 8.71% | 8.82% | 4.50% |
| Cost-effectiveness ($/kg) | 5.67 | 7.28 | 9.79 | 3.58 | 3.10 | 7.13 | 6.51 | 9.34 | 3.26 | 22.58 | 187.59 | 35.34 | 186.02 | 79.01 | 56.02 | 65.50 | 53.61 | 22.83 | 119.38 | 20.96 | 27.80 | 17.48 | 11.09 | 11.19 |
| Speed of first disbursement (months) | 9.29 | 9.16 | 9.2 | 9.06 | 8.97 | 9.0 | 8.9 | 8.7 | 8.7 | 8.7 | 8.4 | 8.6 | 8.5 | 8.6 | 9.0 | 8.9 | 9.0 | 9.2 | 9.2 | 9.2 | 9.1 | 9.3 | 9.3 | 9.2 |
| Speed of completion (months) | 29.85 | 30.89 | 31.7 | 32.35 | 32.98 | 33.2 | 33.5 | 33.4 | 33.7 | 34.1 | 35.0 | 35.9 | 36.8 | 38.3 | 39.5 | 40.2 | 40.9 | 41.1 | 41.7 | 42.4 | 42.7 | 42.4 | 42.1 | 42.5 |
| Net emissions due to delays (ODP tonnes) | 5,727 | 5,960 | 3,503 | 13,035 | 1,481 | 3,864 | 4,470 | 3,431 | 6,970 | 8,918 | 14,583 | 17,144 | 8,805 | 9,939 | 13,389 | 6,906 | 8,054.8 | 7,971.7 | 3,372.1 | 8,137.3 | 9,458.7 | 8,112.8 | 7,797.6 | 870.5 |
| World Bank | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 |
| ODS phased out | 100% | 100% | 84% | 100% | 69% | 31% | 84% | 47% | 100% | 100% | 100% | 20% | 98% | 100% | 100% | 100% | 100% | 51% | 100% | 100% | 100% | N/A | 66% | 100% |
| Funds disbursed | 74% | 100% | 100% | 73% | 100% | 100% | 100% | 100% | 73% | 64% | 43% | 15% | 100% | 100% | 100% | 78% | 96% | 62% | 80% | 70% | 63% | 99% | 43% | 100% |
| Project completion reports | 74% | 100% | 84% | 84% | 100% | 84% | 74% | 69% | 25% | 20% | 85% | 10% | 100% | 24% | 24% | 8% | 33% | 11% | 45% | 26% | 77% | 90% | 100% | N/A |
| Distribution among countries | 67% | 79% | 65% | 71% | 93% | 79% | 92% | 77% | 67% | 50% | 57% | 100% | 67% | 50% | 33% | 100% | 50% | 60% | 100% | 33% | 60% | 75% | 100% | 40% |
| Value of projects approved | 92% | 100% | 82% | 94% | 83% | 87% | 83% | 93% | 98% | 3% | 93% | 29% | 93% | 72% | 100% | 39% | 29% | 95% | 46% | 26% | 77% | 80% | 100% | 90% |
| ODS to be phased out | 72% | 91% | 65% | 59% | 100% | 66% | 93% | 35% | 100% | 89% | 11% | 7% | 25% | 11% | 100% | 50% | 74% | 69% | 100% | 84% | 95% | 99% | 100% | 100% |
| Cost of project preparation (% of approvals) | 1.3% | 0.4% | 0.6% | 0.2% | 0.4% | 0.4% | 0.02% | 0.6% | 2.2% | 74.8% | 1.5% | 5.6% | 0.2% | 0.6% | 0.4% | 4.0% | 18.64% | 1.04% | 0.0% | 0.0% | 0.0% | 0.61% | 2.92% | 0.81% |
| Cost-effectiveness ($/kg) | 3.85 | 4.57 | 6.12 | 3.74 | 1.04 | 3.33 | 3.29 | 9.36 | 1.43 | 1.12 | 545.23 | 69.01 | 118.26 | 214.04 | 19.84 | 48.54 | 52.66 | 618.83 | 177.65 | 2.56 | 4.55 | 3.85 | 18.29 | 31.96 |
| Speed of first disbursement (months) | 25.33 | 26.28 | 26 | 26.02 | 25.7 | 25.3 | 25.0 | 24.8 | 24.8 | 24.6 | 24.6 | 24.7 | 24.6 | 24.6 | 24.6 | 24.6 | 24.5 | 24.4 | 24.5 | 24.4 | 24.4 | 24.4 | 24.3 | 24.2 |
| Speed of completion (months) | 40.09 | 41.35 | 41 | 40.88 | 40.7 | 40.3 | 40.2 | 39.8 | 39.8 | 40.2 | 40.2 | 40.2 | 40.3 | 40.8 | 40.8 | 40.8 | 41.0 | 40.1 | 41.2 | 41.2 | 41.2 | 41.3 | 41.2 | 41.2 |
| Net emissions due to delays (ODP tonnes) | 21,539 | 22,324 | 18,021 | 8,338 | 4,843 | 5,674 | 2,316 | 1,303 | 182 | 1,680 | 801 | 901 | 901 | 1,002 | 275 | 455 | 249.9 | 788.4 | 812.98 | 5.5 | 74.8 | 149.5 | 146.9 | 65.5 |

Annex II

NON-INVESTMENT PROJECT PERFORMANCE BY AGENCY

(2001-2024)

| UNDP | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Funds disbursed | 93% | 61% | 100% | 100% | 100% | 92% | 100% | 100% | 100% | 100% | 100% | 84% | 88% | 100% | 47% | 82% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |
| Speed until first disbursement (months) | 12 | 11.4 | 11 | 11.44 | 11.5 | 11.8 | 11.7 | 11.7 | 11.8 | 12.2 | 11.8 | 11.9 | 11.9 | 11.8 | 12.0 | 11.9 | 11.8 | 11.7 | 11.8 | 11.7 | 11.7 | 11.7 | 11.6 | 11.5 |
| Speed until project completion (months) | 36 | 34.7 | 35 | 35.36 | 35.4 | 36.6 | 37.3 | 37.1 | 37.3 | 37.7 | 37.1 | 37.4 | 37.2 | 36.7 | 36.3 | 36.0 | 36.8 | 36.2 | 36.1 | 36.0 | 36.0 | 35.7 | 35.7 | 35.6 |
| UNEP | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 |
| Funds disbursed | 93% | 93% | 99% | 54% | 54% | 51% | 49% | 64% | 69% | 60% | 63% | 55% | 47% | 61% | 44% | 91% | 100% | 81% | 85% | 75% | 85% | 85% | 82% | 100% |
| Speed until first disbursement (months) | 6.87 | 7.3 | 7.6 | 8.49 | 8.4 | 8.4 | 8.7 | 9.0 | 9.0 | 9.5 | 9.6 | 9.8 | 9.8 | 9.9 | 10.1 | 10.5 | 10.5 | 10.9 | 10.9 | 11.1 | 11.6 | 11.9 | 12.2 | 12.5 |
| Speed until project completion (months) | 29.66 | 30.4 | 31 | 31.8 | 32.4 | 32.9 | 33.2 | 33.6 | 32.9 | 33.9 | 34.3 | 34.4 | 34.7 | 35.3 | 35.3 | 36.1 | 36.7 | 36.7 | 36.8 | 36.8 | 36.7 | 36.6 | 36.9 | 37.4 |
| UNIDO | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 |
| Funds disbursed | 48% | 89% | 100% | 100% | 90% | 80% | 89% | 69% | 100% | 84% | 95% | 100% | 62% | 82% | 82% | 75% | 100% | 100% | 95% | 100% | 100% | 100% | 100% | 100% |
| Speed until first disbursement (months) | 9.15 | 9.85 | 9.4 | 9.34 | 8.9 | 9.8 | 10.2 | 10.6 | 10.4 | 10.4 | 10.3 | 10.3 | 10.2 | 10.1 | 10.0 | 10.1 | 10.4 | 10.3 | 10.0 | 9.8 | 9.8 | 9.7 | 9.6 | 9.5 |
| Speed until project completion (months) | 33.66 | 33.84 | 33.7 | 33.89 | 31.9 | 33.1 | 33.0 | 32.9 | 32.0 | 31.9 | 31.4 | 32.8 | 32.8 | 33.7 | 32.7 | 33.4 | 33.5 | 32.7 | 33.0 | 34.1 | 34.1 | 33.9 | 34.3 | 34.4 |
| World Bank | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 |
| Funds disbursed | 12% | 38% | 100% | 79% | 100% | 57% | 59% | 59% | 19% | 47% | 75% | 59% | 49% | 42% | 100% | 88% | 100% | 100% | 78% | 33% | 34% | 35% | 100% | 53% |
| Speed until first disbursement (months) | 11.95 | 12.05 | 13.7 | 14.58 | 13.6 | 14.6 | 14.3 | 14.4 | 14.4 | 14.9 | 14.6 | 15.1 | 14.7 | 14.0 | 14.1 | 14.8 | 16.8 | 16.8 | 16.6 | 16.9 | 17.0 | 17.0 | 17.0 | 17.0 |
| Speed until project completion (months) | 29.24 | 28.85 | 30 | 30.39 | 31 | 31.5 | 31.1 | 30.7 | 30.7 | 30.3 | 30.1 | 30.3 | 30.2 | 30.0 | 29.8 | 29.8 | 29.2 | 29.3 | 29.3 | 29.3 | 29.6 | 29.6 | 29.6 | 28.9 |

- Annex III

- QUALITATIVE ASSESSMENT OF THE IMPLEMENTING AGENCIES BY THE NATIONAL OZONE UNITS FOR 2024

| Category | Sub-category | Questions | Values | Australia | France | Germany | UNDP | UNEP | UNIDO | World Bank | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IMPACT | General | Has cooperation with the implementing agency substantially contributed and added value to your work or organization in managing compliance in your country? | Highly satisfactory | 1 | 1 | 7 | 16 | 55 | 28 | 1 | 109 |
|  |  |  | Satisfactory |  |  | 1 | 10 | 17 | 12 | 2 | 42 |
|  |  |  | Less satisfactory |  |  |  | 1 |  | 2 |  | 3 |
|  |  |  | Unsatisfactory |  |  |  |  |  |  |  |  |
|  |  | IMPACT (Overall Rating) | Highly satisfactory | 1 | 1 | 6 | 13 | 46 | 23 | 1 | 91 |
|  |  |  | Satisfactory |  |  | 2 | 11 | 13 | 9 | 2 | 37 |
|  |  |  | Less satisfactory |  |  |  | 1 |  | 3 |  | 4 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  |  |  | 1 |
|  |  | In the design and implementation of the project, has the implementing agency been striving to achieve sustainable results? | Highly satisfactory | 1 | 1 | 8 | 15 | 55 | 29 | 1 | 110 |
|  |  |  | Satisfactory |  |  |  | 12 | 16 | 11 | 2 | 41 |
|  |  |  | Less satisfactory |  |  |  |  |  | 2 |  | 2 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  |  |  | 1 |
| ORGANIZATION AND COOPERATION | General | Did cooperation with the staff of the implementing agency take place in an atmosphere of mutual understanding? | Highly satisfactory | 1 | 1 | 7 | 20 | 65 | 32 | 2 | 128 |
|  |  |  | Satisfactory |  |  | 1 | 9 | 8 | 7 | 1 | 26 |
|  |  |  | Less satisfactory |  |  |  | 2 |  | 5 |  | 7 |
|  |  |  | Unsatisfactory |  |  |  |  |  |  |  |  |
|  |  | Did the implementing agency clearly explain its work plan and division of tasks? | Highly satisfactory | 1 | 1 | 5 | 14 | 58 | 24 | 2 | 105 |
|  |  |  | Satisfactory |  |  | 3 | 13 | 15 | 18 | 1 | 50 |
|  |  |  | Less satisfactory |  |  |  | 3 |  | 2 |  | 5 |
|  |  |  | Unsatisfactory |  |  |  |  |  |  |  |  |
|  |  | Did the implementing agency sufficiently control and monitor the delivery of consultant services? | Highly satisfactory | 1 | 1 | 4 | 16 | 50 | 29 | 1 | 102 |
|  |  |  | Satisfactory |  |  | 4 | 11 | 20 | 14 | 2 | 51 |
|  |  |  | Less satisfactory |  |  |  |  |  |  |  |  |
|  |  |  | Unsatisfactory |  |  |  | 1 |  | 1 |  | 2 |
|  |  | Did the responsible staff of the implementing agency communicate sufficiently and help to avoid misunderstanding? | Highly satisfactory | 1 | 1 | 6 | 17 | 63 | 29 | 2 | 119 |
|  |  |  | Satisfactory |  |  | 2 | 9 | 10 | 9 | 1 | 31 |
|  |  |  | Less satisfactory |  |  |  | 4 |  | 6 |  | 10 |
|  |  |  | Unsatisfactory |  |  |  |  |  |  |  |  |
|  |  | Has the use of funds been directed effectively to reach the targets and was it agreed between the national ozone unit and the implementing agency? | Highly satisfactory | 1 | 1 | 6 | 18 | 63 | 30 | 2 | 121 |
|  |  |  | Satisfactory |  |  | 2 | 8 | 9 | 10 | 1 | 30 |
|  |  |  | Less satisfactory |  |  |  | 1 |  | 2 |  | 3 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  |  |  | 1 |
|  |  | If there was a lead agency for a multi-agency project, did it coordinate the activities of the other implementing agencies satisfactorily? | Highly satisfactory | 1 |  |  | 11 | 31 | 16 |  | 59 |
|  |  |  | Satisfactory |  | 1 | 2 | 5 | 15 | 11 | 1 | 35 |
|  |  |  | Less satisfactory |  |  |  | 2 | 1 | 1 |  | 4 |
|  |  |  | Unsatisfactory |  |  |  |  |  |  |  |  |
|  |  | ORGANIZATION AND COOPERATION (Overall Rating) | Highly satisfactory | 1 | 1 | 5 | 14 | 36 | 15 | 1 | 73 |
|  |  |  | Satisfactory |  |  | 2 | 11 | 8 | 9 | 1 | 31 |
|  |  |  | Less satisfactory |  |  |  |  |  | 3 |  | 3 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  |  |  | 1 |
|  |  | Was active involvement of the national ozone unit ensured in project Development? | Highly satisfactory | 1 | 1 | 8 | 18 | 54 | 33 | 2 | 117 |
|  |  |  | Satisfactory |  |  |  | 10 | 16 | 11 | 1 | 38 |
|  |  |  | Less satisfactory |  |  |  |  |  |  |  |  |
|  |  |  | Unsatisfactory |  |  |  | 1 |  |  |  | 1 |
|  |  | Was active involvement of the national ozone unit ensured in project Identification? | Highly satisfactory | 1 | 1 | 8 | 19 | 56 | 31 | 2 | 118 |
|  |  |  | Satisfactory |  |  |  | 9 | 14 | 13 | 1 | 37 |
|  |  |  | Less satisfactory |  |  |  |  |  |  |  |  |
|  |  |  | Unsatisfactory |  |  |  | 1 |  |  |  | 1 |
|  |  | Was active involvement of the national ozone unit ensured in project Implementation? | Highly satisfactory | 1 | 1 | 8 | 17 | 56 | 32 | 2 | 117 |
|  |  |  | Satisfactory |  |  |  | 9 | 13 | 11 | 1 | 34 |
|  |  |  | Less satisfactory |  |  |  |  |  |  |  |  |
|  |  |  | Unsatisfactory |  |  |  | 1 |  |  |  | 1 |
|  |  | Were the required services of the implementing agency delivered in time? | Highly satisfactory | 1 | 1 | 3 | 9 | 56 | 23 | 1 | 94 |
|  |  |  | Satisfactory |  |  | 5 | 17 | 16 | 16 | 2 | 56 |
|  |  |  | Less satisfactory |  |  |  | 3 | 1 | 5 |  | 9 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  |  |  | 1 |
| TECHNICAL ASSISTANCE/TRAINING | General | Did project partners receive sufficient technical advice and/or assistance in their decision-making on technology? | Highly satisfactory | 1 | 1 | 6 | 13 | 35 | 21 | 2 | 79 |
|  |  |  | Satisfactory |  |  | 1 | 11 | 26 | 17 | 1 | 56 |
|  |  |  | Less satisfactory |  |  |  | 1 | 1 | 3 |  | 5 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  |  |  | 1 |
|  |  | Did the agency give sufficient consideration to training aspects within funding limits? | Highly satisfactory | 1 | 1 | 7 | 14 | 51 | 30 | 1 | 105 |
|  |  |  | Satisfactory |  |  | 1 | 11 | 17 | 11 | 2 | 42 |
|  |  |  | Less satisfactory |  |  |  | 1 | 1 | 3 |  | 5 |
|  |  |  | Unsatisfactory |  |  |  |  |  |  |  |  |
|  |  | Do you feel that you have received sufficient support in building capacities for the national implementation of the project (within the funding limitations)? | Highly satisfactory | 1 | 1 | 6 | 14 | 47 | 24 | 1 | 94 |
|  |  |  | Satisfactory |  |  | 2 | 12 | 22 | 14 | 2 | 52 |
|  |  |  | Less satisfactory |  |  |  |  |  | 3 |  | 3 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  | 1 |  | 2 |
|  |  | Has the acquisition of services and equipment been successfully administered, contracted and its delivery monitored? | Highly satisfactory | 1 | 1 | 7 | 11 | 29 | 21 | 1 | 71 |
|  |  |  | Satisfactory |  |  | 1 | 13 | 26 | 16 | 2 | 58 |
|  |  |  | Less satisfactory |  |  |  | 1 |  |  |  | 1 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  | 1 |  | 2 |
|  |  | In case of need, was trouble-shooting by the agency quick and in direct response to your needs? | Highly satisfactory | 1 | 1 | 7 | 13 | 46 | 28 | 1 | 97 |
|  |  |  | Satisfactory |  |  | 1 | 12 | 19 | 7 | 2 | 41 |
|  |  |  | Less satisfactory |  |  |  | 1 |  | 2 |  | 3 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  | 2 |  | 3 |
|  |  | TECHNICAL ASSISTANCE/TRAINING (Overall Rating) | Highly satisfactory | 1 | 1 | 6 | 13 | 37 | 19 | 1 | 78 |
|  |  |  | Satisfactory |  |  | 1 | 11 | 15 | 12 | 2 | 41 |
|  |  |  | Less satisfactory |  |  |  |  |  | 2 |  | 2 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  | 1 |  | 2 |
|  |  | Was the selection and competence of consultants provided by the agency satisfactory? | Highly satisfactory | 1 | 1 | 5 | 15 | 45 | 25 | 2 | 94 |
|  |  |  | Satisfactory |  |  | 2 | 9 | 20 | 18 | 1 | 50 |
|  |  |  | Less satisfactory |  |  | 1 |  |  |  |  | 1 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  |  |  | 1 |
|  |  | Were project partners and stakeholders encouraged by the implementing agency to participate positively in decision-making and design of activities? | Highly satisfactory | 1 | 1 | 6 | 16 | 50 | 24 | 2 | 100 |
|  |  |  | Satisfactory |  |  | 2 | 9 | 18 | 16 | 1 | 46 |
|  |  |  | Less satisfactory |  |  |  |  |  | 2 |  | 2 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  |  |  | 1 |
|  | Investment projects | Has the agency been effective and met the expectations of stakeholders in providing technical advice, training and commissioning? | Highly satisfactory | 1 |  | 3 | 11 | 35 | 24 | 1 | 75 |
|  |  |  | Satisfactory |  | 1 | 4 | 11 | 15 | 9 |  | 40 |
|  |  |  | Less satisfactory |  |  |  | 1 |  | 1 |  | 2 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  | 1 |  | 2 |
|  |  | Has the agency been responsive in addressing any technical difficulties that may have been encountered subsequent to the provision of non-ODS technology? | Highly satisfactory | 1 | 1 | 4 | 10 | 25 | 19 | 1 | 61 |
|  |  |  | Satisfactory |  |  | 3 | 12 | 17 | 10 |  | 42 |
|  |  |  | Less satisfactory |  |  |  |  |  | 1 |  | 1 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  | 1 |  | 2 |
|  | National phase-out plans | Has support for the distribution of equipment been adequate? | Highly satisfactory | 1 | 1 | 6 | 12 | 33 | 20 | 1 | 74 |
|  |  |  | Satisfactory |  |  | 2 | 10 | 13 | 14 | 1 | 40 |
|  |  |  | Less satisfactory |  |  |  |  | 1 |  |  | 1 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  | 1 |  | 2 |
|  |  | Has support to identify policy issues related to implementation been adequate? | Highly satisfactory | 1 | 1 | 4 | 9 | 45 | 24 | 1 | 85 |
|  |  |  | Satisfactory |  |  | 2 | 9 | 22 | 12 | 2 | 47 |
|  |  |  | Less satisfactory |  |  |  | 1 |  | 1 |  | 2 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  | 1 |  | 2 |
|  |  | Has technical advice on equipment specifications been adequate? | Highly satisfactory | 1 | 1 | 7 | 10 | 31 | 25 |  | 75 |
|  |  |  | Satisfactory |  |  | 1 | 11 | 17 | 12 | 2 | 43 |
|  |  |  | Less satisfactory |  |  |  | 1 | 1 |  |  | 2 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  | 1 |  | 2 |
|  |  | Has the technical advice or training that was provided been effective? | Highly satisfactory | 1 |  | 5 | 12 | 50 | 26 | 1 | 95 |
|  |  |  | Satisfactory |  | 1 | 3 | 9 | 14 | 11 | 2 | 40 |
|  |  |  | Less satisfactory |  |  |  | 1 | 1 | 2 |  | 4 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  | 1 |  | 2 |
|  |  | Were proposed implementation strategies adequate? | Highly satisfactory | 1 |  | 5 | 15 | 51 | 25 | 2 | 99 |
|  |  |  | Satisfactory |  | 1 | 3 | 8 | 13 | 12 | 1 | 38 |
|  |  |  | Less satisfactory |  |  |  |  |  | 2 |  | 2 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  | 1 |  | 2 |
|  | Regulatory assistance projects | Were the regulations that were proposed by the agency Adapted to local circumstances? | Highly satisfactory | 1 |  | 2 | 10 | 40 | 20 |  | 73 |
|  |  |  | Satisfactory |  | 1 | 2 | 4 | 22 | 11 | 2 | 42 |
|  |  |  | Less satisfactory |  |  |  |  |  |  |  |  |
|  |  |  | Unsatisfactory |  |  |  | 1 |  |  |  | 1 |
|  |  | Were the regulations that were proposed by the agency Applicable? | Highly satisfactory | 1 | 1 | 3 | 10 | 47 | 15 |  | 77 |
|  |  |  | Satisfactory |  |  | 1 | 4 | 15 | 16 | 2 | 38 |
|  |  |  | Less satisfactory |  |  |  |  |  |  |  |  |
|  |  |  | Unsatisfactory |  |  |  | 1 |  |  |  | 1 |
|  |  | Were the regulations that were proposed by the agency Enforceable? | Highly satisfactory | 1 | 1 | 3 | 9 | 38 | 17 |  | 69 |
|  |  |  | Satisfactory |  |  | 1 | 5 | 23 | 14 | 2 | 45 |
|  |  |  | Less satisfactory |  |  |  |  |  |  |  |  |
|  |  |  | Unsatisfactory |  |  |  | 1 |  |  |  | 1 |
|  | Training projects | Was the quality of the training provided satisfactory? | Highly satisfactory | 1 | 1 | 5 | 14 | 48 | 27 | 2 | 98 |
|  |  |  | Satisfactory |  |  | 2 | 3 | 14 | 8 |  | 27 |
|  |  |  | Less satisfactory |  |  |  |  |  | 1 |  | 1 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  | 1 |  | 2 |
|  |  | Was the training designed so that those trained would be likely to use the skills taught? | Highly satisfactory | 1 | 1 | 5 | 14 | 42 | 25 | 1 | 89 |
|  |  |  | Satisfactory |  |  | 2 | 3 | 20 | 10 | 1 | 36 |
|  |  |  | Less satisfactory |  |  |  |  |  | 1 |  | 1 |
|  |  |  | Unsatisfactory |  |  |  | 1 |  | 1 |  | 2 |

UNEP/OzL.Pro/ExCom/97/1

Based on the performance indicators adopted in decision 41/93, as modified by decisions 47/51 and 71/28, and the targets that were adopted for the 2024 business plans in annexes X – XIII to the report of the 93rd meeting (UNEP/OzL.Pro/ExCom/93/105).

The Secretariat was requested to continue monitoring the investment and non-investment performance indicators on the basis of trend analysis in future evaluations of the performance of implementing agencies.

Investment projects include multi-year agreements (MYAs) that are so-designated by project code.

Only the “funds disbursed”, “speed of first disbursement” and “speed of project completion” indicators are applicable to non-investment projects.

Australia (1), France (1), Germany (8), UNDP (30), UNEP (73), UNIDO (44) and the World Bank (3).