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REPORT ON BALANCES AND AVAILABILITY OF RESOURCES



Introduction

1. This document presents a summary of financial adjustments indicated by the bilateral (BAs) and implementing agencies (IAs) as agreed by the Secretariat. It includes statistical data[footnoteRef:1] from all projects with balances that have been held for over 12-month following completion of the project, as required by decisions 28/7 and 56/2(c). It addresses balances to be returned against projects as a follow-up to decisions 70/7(b)(ii) and (iii) and 71/11(b) (referred to as “by-decision” projects in this document). It also indicates the level of resources available to the Executive Committee in cash and promissory notes as recorded in the status of contributions and disbursements document[footnoteRef:2], as required by decision 41/92(b). [1: The data presented are based on the reporting format that has been developed pursuant to decision 31/2.]  [2: UNEP/OzL.Pro/ExCom/77/3.] 



2. This document also contains the following three annexes:

Annex I	Amounts held by IAs and BAs for completed projects 

Annex II 	Amounts held by IAs and BAs for by-decision projects

Annex III	Fund returns by IAs and BAs from completed and by-decision projects






Funds to be returned 

3. The total funds to be returned to the 77th meeting amount to US $929,737 (i.e. US $66,266 by BAs and US $863,471 by IAs) from completed projects and by-decision projects. Annexes I and II include justifications submitted by the BAs and IAs on the delays in disbursing committed amounts or returning not-committed amounts.

Funds to be returned to the 77th meeting by IAs

4. The total funds to be returned by IAs amount to US $863,471 from completed and by-decision projects as shown in Table 1.

Table 1. Funds to be returned by IAs to the 77th meeting (US $)
	Agency
	Project 
	Agency support 
	Total 

	UNDP[footnoteRef:3] [3:  Includes UNDP adjustment of US $9,429 in project costs and US $707 for agency support costs returned by mistake to the 75th meeting for project MLI/PHA/63/INV/30.] 

	244,115
	18,478
	262,593

	UNEP[footnoteRef:4] [4:  Includes UNEP adjustment of US $25,677 in project costs and US $2,054 for agency support costs returned in error for the 2012 CAP project GLO/SEV/65/TAS/313, and the return of US $33,197, plus agency support costs of US $4,316 in accordance with decision 75/58(b) on stage I of the HPMP for the Democratic People’s Republic of Korea. 
Including the return of US $33,197 plus agency support costs of US $2,988 in accordance with decision 75/58(b) on stage I of the HPMP for the Democratic People’s Republic of Korea. ] 

	126,301
	17,643
	143,944

	UNIDO[footnoteRef:5] [5:  Includes refund of US $252 for agency support costs returned by mistake to the 74th meeting for project BHE/PHA/52/INV/22.] 

	42,829
	2,664
	45,493

	World Bank[footnoteRef:6] [6:  Return of 2015 core unit costs of US $411,441.] 

	0
	411,441
	411,441

	Total
	413,245
	450,226
	863,471



5. Table 2 presents information on completed projects and by-decision projects with balances that are still being withheld by the IAs. 

Table 2. Balances held by year of project completion by IAs (excluding agency support costs)
	Year completed
	UNDP
	UNEP
	UNIDO
	World Bank
	Total

	
	Number
	(US$)
	Number
	(US$)
	Number
	(US$)
	Number
	(US$)
	Number
	(US$)

	Projects completed over two years ago

	2013
	
	
	6
	90,035
	1
	137,311
	
	
	7
	227,346

	1 Jan to 
31 Oct 2014
	
	
	3
	48,783
	
	
	
	
	3
	48,783

	Sub-total
	0
	0
	9
	138,818
	1
	137,311
	0
	0
	10
	276,129

	Projects completed in less than two years ago

	1 Nov 2014 to 31 Dec 2014
	
	
	4

	226,537
	3
	17,295
	
	
	7
	243,382

	2015
	
	
	4
	97,260
	3
	496,698
	
	
	7
	593,958

	Sub-total
	
	
	8
	323,797
	6
	513,993
	
	
	14
	837,790

	Total completed
	0
	0
	17
	462,615
	7
	651,304
	0
	0
	24
	1,113,919

	By-decisions projects (on-going)

	
	0
	0
	1
	18,243
	0
	0
	
	
	1
	18,243

	Grand total 
	0
	0
	18
	480,858
	7
	651,304
	0
	0
	25
	1,132,162




Funds to be returned to the 77th meeting by BAs

6. The total funds to be returned by BAs amount to US $66,266 from completed projects as shown in Table 3.

Table 3. Funds to be returned by bilateral agencies to the 77th meeting (US $)
	Agency
	Project 
	Agency support
	Total 

	Italy
	59,486
	6,544
	66,030

	Japan
	209
	27
	236

	Total
	59,695
	6,571
	66,266



7. Table 4 presents the balances from completed projects that are being held by BAs.

Table 4. Balances held by bilateral agencies (US $)
	Year completed
	Germany
	Italy
	Japan
	Spain
	Total

	Closed projects
	
	
	
	
	

	2011
	0
	2,677
	
	
	2,677

	2012
	0
	4,594
	
	
	4,594

	2013
	0
	7,455
	
	
	7,455

	1 Jan 2014 to 
31 Oct 2014
	1,794
	0
	
	
	1,794

	Projects completed over 2 years ago
	1,794
	14,726
	0
	0
	16,520

	1 Nov 2014 to 
31 Dec 2014
	0
	18,328
	
	
	18,328

	Subtotal
	1,794
	33,054
	0
	0
	34,848

	Agency support costs
	195
	4,297
	
	15,600
	20,092

	Total completed projects
	1,989
	37,351
	0
	15,600
	54,940

	Ongoing projects including agency support costs
	149,090
	0
	0
	0
	149,090

	By-decision projects excluding agency support costs
	0
	0
	1,048,692
	0
	1,048,692

	Grand total
	151,079
	37,351
	1,048,692
	15,600
	1,252,722



8. With regard to balances held by BAs:

The Government of Germany is applying the not-committed balances of US $1,989 under one completed project, and of US $149,090 under two ongoing projects in line with decision 76/8(a)(iii)[footnoteRef:7], against its bilateral projects submitted to the 77th meeting if they were approved; [7:  That the Government of Germany would report on the possible transfer of the HCFC phase-out management plan (HPMP) for Afghanistan (stage I, first and second tranches) at the 77th meeting.
] 

The Government of Italy’s not-committed balances of US $17,327 of four completed projects will be returned in cash subject to update from the Government of Italy at the 77th meeting; 

The Government of Japan’s committed balances of US $1,048,692 of two by-decisions projects are pending futher consultation; and

[bookmark: _GoBack]The Government of Spain’s balances of two completed projects of US $15,600 in support costs would be offset against bilateral projects that would be submitted to a future meeting. 

Availability of resources

9. The status of contributions and disbursements indicates an available balance amounting to US $100,819,568 as at 28 October 2016. The total net balance returned by IAs, including agency support costs is US $863,471. The total level of resources available for approvals by the Executive Committee at its meeting, after taking into account the Fund’s balance and the total amount returned by IAs is US $101,683,039. 

Secretariat’s comments

10. During the Inter-agency coordination meeting[footnoteRef:8] the Secretariat reminded BAs and IAs that balances associated with completed and by-decisions projects should be returned to the Multilateral Fund no later than the 77th meeting. BAs and IAs committed to continue with their efforts to return funds as soon as possible and to provide an update to the 77th meeting with a view to returning additional balances. [8:  Montreal, 31 August - 1 September 2016.] 


11. Considering that the total level of funding for projects and activities as submitted to the 77th meeting, amounts to US $162,565,718 including agency support costs[footnoteRef:9], there are insufficient resources available for approvals at the 77th meeting. However, this information will be updated during the 77th meeting and will depend on the level of projects approvals at the 77th meeting particularly with respect to stage II of the HPMP for China.   [9:  As at 21 October 2016. ] 


Recommendations

12. The Executive Committee may wish:

(a) To note:

(i) The report on balances and availability of resources contained in document UNEP/OzL.Pro/ExCom/77/4;

(ii) That the net level of funds being returned to the 77th meeting by the implementing agencies was US $863,471, consisting of US $244,115, plus agency support costs of US $17,643 from UNDP; US $126,301, plus agency support costs of US $17,643 from UNEP; US $42,829, plus agency support costs of US $2,664 from UNIDO; and US $411,441 of agency support costs of  from the World Bank;

That the net level of funds being returned to the 77th meeting by the bilateral agencies was US $66,266, consisting of US $59,486, plus agency support costs of US $6,544 from the Government of Italy and US $209, plus agency support costs of US $27 from the Government of Japan; 

(iii) That UNEP had balances of US $138,818, excluding support costs for nine projects completed over two years previously;

(iv) That UNIDO had balances of US $137,311, excluding support costs for one projects completed over two years previously;

That the Government of Germany’s not-committed balances for one completed and two ongoing projects, totaling US $1,989 and US $149,090, including agency support costs, would be offset against bilateral projects submitted to the 77th meeting, if they were approved by the Executive Committee;

That the Government of Italy’s not-committed balances for four completed projects totaling US $17,327, including agency support costs, would be returned in cash subject to update from the Governement of Italy to the 
77th meeting; 

That the Government of Spain’s balances for two completed projects over two years totaling US $15,600 in agency support costs, would be offset against  bilateral projects that would be submitted to a future meeting;

(b) To request:

(i) Bilateral agencies and implementing agencies and with projects completed over two years previously to return the balances to the 78th meeting;

(ii) Bilateral and implementing agencies to disburse or to cancel commitments not needed for completed projects and project completed by-decision of the Executive Committee in order to return balances to the 78th meeting; and

(iii) UNEP to return not-committed balance to the 78th meeting.
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Annex I
COMMITTED AND NOT-COMMITTEED BALANCES HELD BY IMPLEMENTING AGENCIES AND BILATERAL AGENCIES FOR COMPLETED PROJECTS
	Code
	Project title
	Date completed (Actual)
	Approved funding plus adjustments as of 
31 December 2015 (US$)
	Funds disbursed as of 
77th meeting (US$)
	Balances committed as per 
77th meeting (US$)

	Balances 
not-committed as per 
77th  meeting (US$)
	Why any balances could not be returned?
	When they could be returned?
	Project subject to decision

	UNEP

	ALG/SEV/57/INS/69
	Extension of the institutional strengthening project (phase V)
	Jul-14
	257,400
	231,660
	25,740
	
	IS

	
	

	BOT/SEV/53/INS/10
	Extension of institutional strengthening project (phase III)
	Jul-14
	78,173
	60,130
	18,043
	
	IS
	
	

	CMR/SEV/65/INS/36
	Extension of institutional strengthening project (phase VIII: 1/2012-12/2013)
	Dec-13
	139,532
	133,657
	
	5,875
	IS
	Once all UNDP (inter office vouchers) IOVs are recorded
	

	COI/SEV/64/INS/20
	Extension of the institutional strengthening project (phase VII: 7/2011-6/2013)
	Jul-13
	60,000
	46,100
	13,900
	
	IS
	
	

	FIJ/SEV/67/INS/24
	Extension of the institutional strengthening project (phase VIII: 12/2012-11/2014)
	Dec-14
	60,000
	38,896
	21,104
	
	IS
	
	

	GAB/SEV/62/INS/28
	Extension of the institutional strengthening project (phase VII)
	Dec-13
	60,000
	49,574
	10,426
	
	IS
	
	

	GAM/SEV/67/INS/26
	Extension of the institutional strengthening project (phase VII: 8/2012-7/2014)
	Dec-14
	60,000
	38,061
	21,939
	
	IS
	
	

	GRN/SEV/67/INS/19
	Extension of the institutional strengthening project (phase IV: 8/2012-7/2014)
	Aug-15
	60,000
	36,000
	24,000
	
	IS

	
	

	MAR/SEV/53/INS/19
	Extension of the institutional strengthening project (phase III)
	Dec-14
	60,000
	46,505
	13,495
	
	IS

	
	

	MOL/SEV/67/INS/26
	Extension of the institutional strengthening project (phase VII: 7/2012-6/2014)
	Aug-15
	69,334
	61,050
	4,086
	4,198
	IS

	Awaiting recording of UNDP IOVs
	

	MOZ/PHA/59/TAS/18
	Terminal phase-out management plan (second tranche)
	Sep-13
	59,000
	40,000
	19,000
	
	
	
	71/11(b)

	QAT/PHA/53/TAS/10
	Terminal phase-out management plan (first tranche)
	Jul-14
	20,000
	15,000
	5,000
	
	
	
	70/7(b)(ii)a

	SEY/SEV/63/INS/18
	Extension of institutional strengthening project (phase V)
	Dec-13
	60,000
	46,500
	13,500
	
	IS

	
	

	STK/SEV/68/INS/18
	Extension of institutional strengthening project (phase V: 1/2013-12/2014)
	May-15
	60,000
	24,000
	36,000
	
	IS

	
	

	STP/SEV/63/INS/20
	Extension of the institutional strengthening project (phase III)
	Mar-13
	60,666
	33,332
	26,893
	441
	IS

	Once all UNDP IOVs are recorded
	

	VIE/SEV/68/INS/60
	Extension of the institutional strengthening project (phase IX: 7/2013-6/2015)
	Jun-15
	118,976
	90,000
	28,976
	
	IS

	
	

	YEM/SEV/68/INS/42
	Extension of the institutional strengthening project (phase VII: 1/2013-12/2014)
	Dec-14
	169,999
	0
	169,999
	
	IS

	Unable to transfer funds to Yemen since 2015 due to errors in banking details
	

	TOTAL UNEP
	 
	
	
	
	452,101
	10,514
	
	
	

	UNIDO

	AFR/REF/48/DEM/37
	Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan)
	Dec-14
	747,500
	735,058
	12,442
	
	4[footnoteRef:10] [10:  2: Financial completion iniated; 3: Financial completion being iniated;  4: Financial completion to be iniated after settlement of all pending issues; MY = Multiyear

] 

	79
	71/10(d)(i)

	ARG/PHA/47/INV/147
	National CFC phase-out plan: 2006 work programme 
	Dec-13
	1,850,000
	1,712,689
	137,311
	
	MY
	79
	70/7(b)(ii)a

	ARG/PHA/53/INV/152
	National CFC phase-out plan: 2008 work programme
	Dec-15
	1,167,350
	761,054
	406,296
	
	MY
	79
	70/7(b)(ii)a

	EUR/REF/47/DEM/06
	Demonstration project on the replacement of CFC centrifugal chillers (Croatia, Macedonia, Romania, and Serbia and Montenegro)
	Dec-15
	1,069,074
	1,035,502
	33,572
	
	4
	79
	71/10(b)(ii)

	GUA/FUM/59/INV/38
	National phase-out of methyl bromide (phase II, first tranche)
	Dec-15
	1,090,000
	1,033,170
	56,830
	
	MY
	79
	71/7(a)(iii)

	SUD/FUM/71/PRP/31
	Project preparation in the fumigants sector (post-harvest)
	Dec-14
	30,000
	28,547
	1,453
	
	3
	78
	

	TUN/FUM/71/PRP/55
	Project preparation in the fumigants sector (high moisture dates)
	Dec-14
	35,000
	31,600
	3,400
	
	4
	79
	

	TOTAL UNIDO

	 
	
	
	
	651,304
	
	
	
	

	GERMANY

	BOT/PHA/60/PRP/14
	Preparation of a HCFC phase-out management plan
	Mar-14
	150,000
	148,206
	
	1,794
	To be offset against future projects 
	
	

	AFG/PHA/63/INV/13
	HCFC phase-out management plan (stage I, first tranche)
	
	85,000
	37,062
	
	47,938
	To be offset against future projects
	
	

	AFG/PHA/72/INV/17
	HCFC phase-out management plan (stage I, second tranche)
	
	84,000
	0
	
	84,000
	To be offset against future projects
	
	

	TOTAL
	
	
	
	
	
	133,732
	
	
	

	ITALY

		CMR/FUM/52/INV/27
	Total phase-out of methyl bromide used in stored commodities fumigation
	Dec-11
	259,713
	257,036
	 
	2,677
	Italy to provide update at the 77th meeting for return in cash. 
	
	

	CRO/FOA/60/INV/35
	Phase-out of HCFC-141b from the manufacturing of polyurethane rigid and integral skin foams at Poly-Mix
	Dec-13
	210,000
	202,545
	 
	7,455
	Italy to provide update at the 77th meeting for return in cash
	
	

	GHA/PHA/67/INV/35
	HCFC phase-out management plan (stage I, second tranche)
	Dec-14
	60,000
	44,273
	15,727
	 
	
	
	

	MOR/FUM/56/INV/62
	Phase-out of methyl bromide used as a soil fumigant in the production of green beans and cucurbits (first tranche)
	Dec-14
	310,000
	307,399
	 
	2,601
	Italy to provide update at the 77th meeting for return in cash
	
	

	SEN/PHA/57/INV/28
	Terminal phase-out management plan for CFCs (second tranche)
	Dec-12
	135,000
	130,406
	 
	4,594
	Italy to provide update at the 77th meeting for return in cash
	
	

	TOTAL ITALY
	
	
	
	
	15,727
	17,327
	
	
	




	SPAIN
	
	
	
	
	
	
	Approved funding plus adjustments as of 31 Dec. 2015 (US$)  Support Cost
		Support Cost Disbursed as of 31 Dec.  2015 (US$)


	

	



	Support Cost Balance as of 31 December 2015 (US$)

	LAC/FUM/47/TAS/37
	Policy assistance to support the methyl bromide phase-out with special focus in Guatemala and Honduras
	Jul-07
	80,000
	80,000
	0
	0
	10,400
	0
	10,400

	PAR/FUM/47/TAS/15
	Technical assistance to phase-out the use of methyl bromide
	Jul-09
	40,000
	40,000
	0
	0
	5,200
	0
	5,200

	TOTAL SPAIN
	
	
	
	
	0
	0
	
	
	15,600
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				Annex II			
COMMITED AND NOT-COMMITED BALANCES HELD BY IMPLEMENTING AGENCIES AND BILATERAL AGENCIES FOR BY-DECISIONS PROJECTS

	Code
	Project title
	Financial date of completion per decision

	Approved funding plus adjustments as of 31 December 2015 (US$)


	Funds disbursed as of 
77th meeting (US$)
	Balances committed as per 77th meeting (US$)
	Balances not- committed as per 
77th meeting (US$)
	Why any balances could not be returned?
	When they could be returned?
	Project subject to decision

	UNEP

	KUW/PHA/52/TAS/10
	Terminal phase-out management plan for Annex A Group I substances (first tranche)
	Dec-13
	240,000
	221,757
	18,243
	
	
	
	70/7(b)(ii)a

	TOTAL UNEP
	
	
	
	
	18,243
	
	
	
	

	JAPAN
	
	
	
	
	
	
	
	
	

	AFR/REF/48/DEM/35
	Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan)
	Jun-16
	700,000
	464,951
	235,049
	
	
	
	71/10(d)(ii), 74/2(c)(iii) and 75/11(b)(ii)

	IND/PHA/45/INV/389
	CTC phase-out plan for the consumption and production sectors: 2005 annual programme
	Dec-13
	2,500,000
	1,686,357
	813,643
	
	
	
	70/7(b)(ii)c

	TOTAL JAPAN
	
	
	
	
	1,048,692
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Annex III

DETAILS ON COMPLETED PROJECTS AND BY-DECISION PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES

	Code
	Project Title
	Project costs returned (US$)
	Agency support costs (US$)
	Total
	Project subject to decision

	UNDP

	CPR/SOL/64/DEM/511
	Demonstration project for conversion from HCFC-141b based technology to iso-paraffin and siloxane (KC-6) technology for cleaning in the manufacture of medical devices at Zhejiang Kindly Medical Devices Co. Ltd.
	9
	1
	10
	

	FIJ/PHA/71/TAS/25
	Verification report for stage I of HCFC phase-out management plan
	10,501
	945
	11,446
	

	HAI/PHA/58/INV/14
	Terminal phase-out management plan for Annex A Group I substances (first tranche)
	757
	68
	825
	71/11(b)

	IND/ARS/56/INV/423
	Plan for phase-out of CFCs in the manufacture of pharmaceutical MDIs
	242,277
	18,171
	260,448
	

	MLI/PHA/63/INV/30
	HCFC phase-out management plan (stage I, first tranche)
	(9,429)
	(707)
	(262,593)
	

	TOTAL UNDP
	
	244,115
	18,478
	262,593
	

	UNEP

	ECU/FUM/65/TAS/56
	Technical assistance to eliminate the remaining consumption of methyl bromide to be in compliance with the total phase-out
	950
	124
	1,074
	

	GAB/PHA/57/TAS/24
	Terminal phase-out management plan (second tranche)
	48
	6
	54
	

	GLO/SEV/65/TAS/313
	Compliance Assistance Programme: 2012 budget
	-25,677
	-2,054
	-27,731
	

	GUA/FUM/59/TAS/39
	National phase-out of methyl bromide (phase II, first tranche)
	35,000
	4,550
	39,550
	71/7(a)(iii)

	HAI/SEV/61/INS/17
	Additional emergency assistance for institutional strengthening
	468
	0
	468
	

	KYR/PHA/72/PRP/31
	Preparation of a HCFC phase-out management plan (stage II)
	447
	58
	505
	

	NIC/PHA/60/TAS/25
	Terminal phase-out management plan for Annex A Group I substances (second tranche)
	7
	1
	8
	

	SAU/PHA/61/TAS/09
	National phase-out plan (second tranche)
	1,650
	215
	1,865
	71/11(b)

	YUG/PHA/62/TAS/39
	HCFC phase-out management plan (stage I, first tranche)
	970
	126
	1,096
	

	CHI/FUM/60/TAS/172
	National phase-out of methyl bromide, terminal project (first tranche)
	188
	24
	212

	

	DRK/PHA/73/TAS/58
	HCFC phase-out management plan (stage I, first tranche) (policy, and refrigeration servicing)
	33,197
	4,316
	37,512
	75/58(b)

	YEM/PHA/55/TAS/31
	National ODS phase-out plan (first tranche)
	79,053
	10,277
	89,330
	70/7(b)(ii)a, 73/8(c) and 75/10(b)(i)  

	TOTAL UNEP
	
	126,301
			17,643
	143,944
	

	UNIDO

	ALB/PHA/64/INV/22
	HCFC phase-out management plan (stage I, first tranche)
	989 
	89 
	1,078 
	

	ALG/PHA/58/INV/71
	National phase-out plan (second tranche)
	11 
	1 
	12 
	

	ALG/REF/26/INV/30
	Replacement of CFC-12 with HFC-134a for domestic refrigeration at Enapem
	0 
	1 
	1 
	

	ALG/SEV/21/PRP/20
	Project formulation of investment projects in the aerosol, foam and refrigeration sectors
	0 
	1 
	1 
	

	ANT/PHA/73/PRP/18
	National phase-out plan (second tranche)
National phase-out plan (second tranche)
Preparation of a HCFC phase-out management plan (stage II)
	(1)
	0 
	(1)
	

	ARG/PHA/50/INV/150
	National CFC phase-out plan: 2007 work programme
	14 
	1 
	15 
	70/7(b)(ii)a

	BHE/PHA/44/INV/21
	National ODS Phase-out Plan: second tranche
	0 
	1 
	1 
	70/7(b)(ii)a

	BHE/PHA/52/INV/22
	National ODS phase-out plan (third tranche)
	0 
	(252)
	(252)
	

	BHE/SEV/65/INS/25
	Extension of the institutional strengthening project (phase III: 3/2012-2/2014)
	1 
	0 
	1 
	

	CMR/FUM/50/PRP/25
	Project preparation for the total phase-out of methyl bromide in all remaining uses
	0 
	1 
	1 
	

	CPR/FOA/34/INV/375
	Phasing out CFC-11 with HCFC-141b at six companies Hongyu, Longan, Songliao, Tianyun, Xinyang and Yizheng) and phasing out CFC-11 by conversion to water blown technology at one company (Yinxian)
	0 
	1 
	1 
	

	CPR/PRO/56/INV/475
	Sector plan for methyl bromide production sector (second tranche)
	1,487 
	0 
	1,487 
	

	CPR/REF/22/INV/207
	Phasing out ODS at the refrigerator plant of Zerowatt Electric Appliances Group
	0 
	1 
	1 
	

	EGY/FUM/56/INV/98
	National phase-out of methyl bromide in horticulture and commodities fumigation except in date use
	19,618 
	1,472 
	21,090 
	

	ERI/PHA/63/INV/09
	Terminal phase-out management plan for CFCs (second tranche)
	79 
	8 
	87 
	71/11(b)

	GUA/PHA/64/INV/44
	HCFC phase-out management plan (stage I, first tranche)
	0 
	1 
	1 
	

	IRA/FUM/44/PRP/168
	Preparatory assistance in methyl bromide (soil fumigation in olive tree nurseries)
	0 
	1 
	1 
	

	IRA/REF/29/INV/53
	Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Sherkate Sanaayee Toulidy Bard Co.
	0 
	1 
	1 
	

	KEN/FUM/65/INV/52
	Technical assistance for the final elimination of methyl bromide in post harvest sector
	3,455 
	260 
	3,715 
	

	LIB/PHA/45/INV/25
	National CFC phase-out plan: 2nd tranche
	3,000 
	0 
	3,000 
	70/7(b)(ii)a

	LIB/PHA/63/PRP/32
	Preparation of a HCFC phase-out management plan (additional funding)
	13,395 
	1,005 
	14,400 
	

	LIB/SEV/59/INS/31
	Renewal of institutional strengthening project (phase II)
	0 
	1 
	1 
	

	MEX/ARS/72/PRP/169
	Preparation for HCFC phase-out investment activities (aerosol sector)
	279 
	19 
	298 
	

	MEX/FUM/60/INV/150
	National methyl bromide phase-out plan (second tranche)
	139 
	10 
	149 
	

	MEX/PHA/45/INV/123
	National CFC phase-out plan: 2nd tranche
	14 
	1 
	15 
	

	MEX/PHA/64/INV/160
	HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b as a cleaning agent in refrigeration servicing)
	6 
	0 
	6 
	

	MEX/PHA/64/TAS/158
	HCFC phase-out management plan (stage I, first tranche) (legislation customs training and monitoring)
	0 
	1 
	1 
	

	MOG/SEV/61/INS/07
	Institutional strengthening project (phase II)
	63 
	5 
	68 
	

	MOR/FOA/62/INV/67
	Conversion from HCFC-141b in the manufacture of polyurethane rigid insulation foam for domestic refrigerators at Manar
	(160)
	(12)
	(172)
	

	MOR/REF/25/INV/25
	Replacement of CFC-12 with HFC-134a for commercial refrigeration at Batinox
	0 
	1 
	1 
	

	MOZ/FUM/60/TAS/20
	Technical assistance for the elimination of controlled uses of methyl bromide in soil fumigation
	378 
	34 
	412 
	75/14(b)

	PER/PHA/65/INV/44
	Terminal phase-out management plan for Annex A Group I substances (first tranche)
	36 
	3 
	39 
	71/11(b)

	ROM/SOL/44/PRP/27
	Preparation of a terminal umbrella project to phase out CTC
	0 
	1 
	1 
	

	STL/PHA/64/INV/17
	HCFC phase-out management plan (stage I, first tranche)
	0 
	1 
	1 
	

	TKM/FUM/59/INV/06
	Technical assistance for the elimination of methyl bromide in post harvest sector
	27 
	3 
	30 
	

	URT/PHA/67/INV/30
	HCFC phase-out management plan (stage I, first tranche)
	(1)
	0 
	(1)
	

	VEN/FOA/29/INV/78
	Phasing out CFC-11 with HCFC-141b at Amerio Industrial S.A. in the production of rigid P.U. panels
	0 
	1 
	1 
	

	VEN/FOA/38/INV/96
	Phasing out CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid p.u. foams: Umbrella No. 2 project.
	0 
	1 
	1 
	

	YUG/PHA/60/INV/36
	National CFC phase-out plan (fourth and fifth tranches)
	0 
	1 
	1 
	71/11(b)

	TOTAL UNIDO

	
	42,829

	2,664

	45,493

	

	WORLD BANK


	GLO/SEV/73/TAS/326
	Core unit budget (2015)
	0
	411,441
	411,441
	

	TOTAL WORLD BANK
	
	
	411,441
	411,441
	

	ITALY

	IND/ARS/56/INV/424
	Plan for phase-out of CFCs in the manufacture of pharmaceutical MDIs
	59,486
	6,544
	66,030
	

	TOTAL ITALY
	
	
	
	
	

	JAPAN

	COL/FOA/60/DEM/75

	Demonstration project to validate the use of super-critical CO2 in the manufacture of sprayed polyurethane rigid foam
	209
	27
	236
	

	TOTAL JAPAN
	
	209
	27
	236
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