| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/97/19 18 November 2025 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-seventh Meeting

Montreal, 1-5 December 2025

Item 8(a) of the provisional agenda

UPDATE ON THE STATUS OF IMPLEMENTATION OF THE 2025–2027 CONSOLIDATED BUSINESS PLAN OF THE MULTILATERAL FUND 
AND FINANCIAL PLANNING FOR THE TRIENNIUM 2024–2026

- Introduction

# This document consists of:

## Part I:	An update on the status of the implementation of the 2025–2027 business plan

## Part II:	Financial planning: Resource allocation for the 2024–2026 triennium

Recommendation

## Update on the status of the implementation of the 2025–2027 business plan

# At its 95th meeting, the Executive Committee endorsed the 2025–2027 consolidated business plan of the Multilateral Fund. In response to decision 95/27, the Secretariat adjusted the consolidated 2025-2027 business plan, as shown in table 1.

Table 1. Resource allocation of the adjusted 2025–2027 consolidated business plan of the Multilateral Fund (US $)*

| Description | 2025 | 2026 | 2027 | Total (2025–2027) |
| --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 56,520,741 | 67,316,489 | 33,313,171 | 157,150,401 |
| HPMP stage II – preparation | 110,900 | 0 | 0 | 110,900 |
| HPMP stage II | 1,913,851 | 1,690,836 | 775,205 | 4,379,892 |
| HPMP stage III – preparation | 318,340 | 42,800 | 0 | 361,140 |
| HPMP stage III | 9,221,502 | 6,720,339 | 22,499,633 | 38,441,474 |
| HPMP stage IV | 0 | 3,691,000 | 5,537,000 | 9,228,000 |
| HCFC production phase-out management plan (HPPMP) stage III – preparation | 321,000 | 0 | 0 | 321,000 |
| HPPMP stage III | 0 | 0 | 23,540,000 | 23,540,000 |
| HPMP verification** | 588,600 | 588,600 | 588,600 | 1,765,800 |
| HPMP – energy efficiency (decision 89/6) | 3,328,995 | 558,112 | 76,000 | 3,963,107 |
| HCFC activities subtotal | 72,323,929 | 80,608,176 | 86,329,609 | 239,261,714 |
| HFC activities |  |  |  |  |
| Approved Kigali HFC implementation plans (KIPs) | 10,127,716 | 6,689,529 | 25,853,153 | 42,670,398 |
| Approved HFC-23 emission control | 519,900 | 584,100 | 552,371 | 1,656,371 |
| Enabling activities for HFC phase-down | 428,000 | 0 | 0 | 428,000 |
| Kigali HFC implementation plan for the production sector stage I – preparation | 321,000 | 0 | 0 | 321,000 |
| KIP stage I – preparation | 3,378,021 | 926,893 | 100,000 | 4,404,913 |
| KIP stage I | 24,739,456 | 16,818,239 | 39,876,189 | 81,433,885 |
| KIP stage I – investment | 0 | 339,000 | 0 | 339,000 |
| HFC investment preparation | 85,600 | 0 | 0 | 85,600 |
| HFC investment | 0 | 96,000 | 0 | 96,000 |
| HFC demonstration | 650,000 | 0 | 0 | 650,000 |
| HFC-23 investment | 0 | 8,000,000 | 0 | 8,000,000 |
| HFC – technical assistance | 678,000 | 0 | 0 | 678,000 |
| HFC activities subtotal | 40,927,693 | 33,453,761 | 66,381,713 | 140,763,167 |
| Other activities |  |  |  |  |
| Energy efficiency manufacturing (decision 94/60) | 2,354,000 | 4,280,000 | 0 | 6,634,000 |
| Pilot demonstration projects for energy efficiency (decision 91/65) | 5,370,000 | 0 | 0 | 5,370,000 |
| Pilot investment projects for energy efficiency (decision 91/65) | 1,880,000 | 0 | 0 | 1,880,000 |
| National inventories of banks of waste-controlled substances preparation (decision 91/66) | 3,346,247 | 0 | 0 | 3,346,247 |
| Other activities subtotal | 12,950,247 | 4,280,000 | 0 | 17,230,247 |
| Standard activities |  |  |  |  |
| Compliance Assistance Programme (CAP) | 12,113,777 | 12,310,330 | 12,679,640 | 37,103,747 |
| Core unit | 6,641,293 | 6,083,582 | 6,126,167 | 18,851,043 |
| Institutional strengthening (IS) | 5,898,152 | 22,008,918 | 17,095,016 | 45,002,085 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 8,280,544 | 7,949,674 | 8,018,727 | 24,248,945 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |
| Standard activities subtotal | 33,433,766 | 48,852,504 | 44,419,550 | 126,705,820 |
| Total | 159,635,634 | 167,194,441 | 197,130,873 | 523,960,948 |
| By agency |  |  |  |  |
| Australia | 463,113 | 0 | 105,090 | 568,203 |
| France | 671,075 | 0 | 0 | 671,075 |
| Germany | 1,191,480 | 5,769,916 | 1,675,197 | 8,636,593 |
| United Kingdom of Great Britain and Northern Ireland (the) | 533,900 | 0 | 0 | 533,900 |
| UNDP | 37,604,225 | 62,114,178 | 46,675,877 | 146,394,281 |
| UNEP | 38,121,523 | 35,574,374 | 30,739,664 | 104,435,561 |
| UNIDO | 48,279,677 | 41,880,004 | 58,533,404 | 148,693,084 |
| World Bank | 23,401,497 | 12,817,695 | 50,294,313 | 86,513,506 |
| HPMP verification** | 588,600 | 588,600 | 588,600 | 1,765,800 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 8,280,544 | 7,949,674 | 8,018,727 | 24,248,945 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |

* Including agency support costs where applicable.

** Funding for the preparation of HPMP verification reports for low-volume-consuming countries is approved by the Executive Committee on an annual basis.

Status of implementation of the 2025 business plan

# The total business plan value for 2025 amounts to US $159,635,634. Of this amount, US $38,076,531 has been approved at the 96th meeting. In addition, activities amounting to US $116,794,673 would be considered at the 97th meeting; if funding for all project proposals submitted as requested are approved, a balance of US $4,764,430 would be available from the 2025 business plan, as shown in table 2.

Table 2. 2025 consolidated business plan, approvals at the 96th meeting, projects recommended to the 97th meeting, and balance (US $)*

| Budget items | Total value in business plan | Approvals at the 96th meeting | Activities recommended to the 97th meeting | Balance (above)/below |
| --- | --- | --- | --- | --- |
| Bilateral agencies | 2,859,568 | 444,025 | 877,135 | 1,538,408 |
| UNDP | 37,604,225 | 8,967,086 | 17,637,857 | 10,999,282 |
| UNEP | 38,121,523 | 5,582,925 | 21,325,465 | 11,213,133 |
| UNIDO | 48,279,677 | 18,000,378 | 60,769,526 | -30,490,227 |
| World Bank | 23,401,497 | 4,680,117 | 7,404,145 | 11,317,235 |
| HPMP verification | 588,600 | 402,000 | 0 | 186,600 |
| Subtotal (agencies) | 150,855,090 | 38,076,531 | 108,014,129 | 4,764,430 |
| Secretariat/Executive Committee/Monitoring and Evaluation (excluding Canadian counterpart) | 8,280,544 | 0 | 8,280,544 | 0 |
| Treasurer | 500,000 | 0 | 500,000 | 0 |
| Subtotal (standard costs) | 8,780,544 | 0 | 8,780,544 | 0 |
| Total | 159,635,634 | 38,076,531 | 116,794,673 | 4,764,430 |

* Including core unit costs.

# The value of project proposals recommended to the 97th meeting of US $108,014,129 is US $14,136,621 above its value in the 2025 business plan and includes US $10,304,295 associated with project proposals not included in the 2025 business plan.

# The value of HFC-related activities recommended to the 97th meeting is US $12,667,813, of which US $1,557,729 is associated with project proposals not included in the 2025 business plan.

# The value of projects recommended to the 97th meeting under the funding window for pilot projects for energy efficiency pursuant to decision 91/65 is US $3,987,881. Taking into account approvals from the 92nd to the 96th meetings of US $10,349,589, and the values recommended to the 97th meeting, the remaining funding available under this funding window is US $5,662,530.

# The value of projects recommended to the 97th meeting under the funding window for energy efficiency pursuant to decision 94/60 is US $21,262,663. Taking into account approvals at the 95th and 96th meetings of US $771,137, and the values recommended to the 97th meeting, the remaining funding available under this funding window is US $77,966,200.

# The value of projects recommended to the 97th meeting under the funding window for the preparation of national inventories of banks of waste-controlled substances pursuant to decision 91/66 is US $2,674,620, including US $1,459,010 that is not included in the 2025 business plan.

# Forward commitments

# The total amount for existing forward commitments for multi-year agreements (MYAs) for the period 2025 to 2031 is US $329.95 million, assuming that the funding requests of MYAs submitted to the 97th meeting will be approved in principle, as shown in table 3.

Table 3. Forward commitments (2025–2031) (US $000)

| Description | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approved in principle | 90,377 | 74,593 | 67,051 | 25,286 | 16,806 | 20,108 | 685 | 294,905 |
| Submitted to 97th meeting | 15,408 | 0 | 13,888 | 2,210 | 1,261 | 2,275 | 0 | 35,041 |
| Total | 105,785 | 74,593 | 80,938 | 27,495 | 18,067 | 22,382 | 685 | 329,946 |

Tranche submission delays

# Thirty-three out of 69 activities (21 out of 41 countries) associated with tranches of HPMPs or KIPs due for submission to the 97th meeting were not submitted. Annex I lists the outstanding tranches that are expected to be submitted to the 98th meeting.

# II.	Financial planning: Resource allocation for the 2024–2026 triennium

# The Secretariat has prepared the financial planning for the 2024–2026 triennium taking into consideration decision XXXV/1 of the Thirty-Fifth Meeting of the Parties on the level of replenishment of the Fund, and the commitments and resource availability in the light of expected cash flow during the triennium.

# The resources approved by the Parties to the Montreal Protocol for the 2024–2026 triennium amount to US $965,000,000. Taking into account the approvals in 2024 and at the 96th meeting of US $222,222,826, the submissions to the 97th meeting including Secretariat/Executive Committee and Treasurer costs of US $116,794,673, the remaining resource allocation for 2026 is US $625,982,501.

Table 4. Resource allocation for the 2024–2026 triennium

| Description | Amount (US $) |
| --- | --- |
| Total budget for the 2024–2026 triennium | 965,000,000 |
| 2024 approvals (94th and 95th meetings) including Secretariat/Executive Committee/Monitoring and Evaluation/Treasurer | 184,146,295 |
| 96th meeting approvals | 38,076,531 |
| 97th meeting submissions | 108,014,129 |
| 2025 Secretariat/Executive Committee/Monitoring and Evaluation/Treasurer | 8,780,544 |
| Resources available for 2026 | 625,982,501 |

II.1	Possible factors impacting financial planning and cash flow during the 2024–2026 triennium

# The cash flow of the Multilateral Fund for the 2024–2026 triennium is influenced by several factors, inter alia: receipt of agreed 2024–2026 pledged contributions; payment of contributions in arrears included in the carry-over; interest to be accrued; the loss/gain due to the fixed-exchange rate mechanism (FERM); and the balances returned from cancelled or completed projects. The following paragraphs provide forecasted information for the 2024–2026 triennium based on actual data from 2024 and 2025.

Receipt of agreed pledged contributions

# Based on the rate of contributions received in the current triennium for 2024 and 2025 (i.e., 95.6 per cent), of the US $525.6 million of pledged contribution, US $502.5 million is estimated to be received during the 2024–2026 triennium, including US $168 million in 2026.

Payment of outstanding contributions in arrears included in the carry-over

# The estimated carry-over towards the 2024–2026 triennium from the 2021–2023 triennium is approximately US $428.7 million, including US $2 million of outstanding contributions expected to be collected.

Potential interest accrued during the 2024–2026 triennium

# Based on the cash balance in 2024 and 2025 and using the average interest collected for 2024 and up to 21 October 2025, it might be expected that the interest accrued during the 2024–2026 triennium would amount to US $110 million.

# Gains/losses due to the FERM

# In 2024, the US dollar has strengthened against most other currencies and the FERM loss was US $946,507; however, in 2025, the US dollar was weakened against most other currencies and the FERM gain was US $1,159,808, hence net gain of US $213,301 as at 10 November 2025. In 2026, the situation might change and a conservative estimate for 2026 will be a FERM loss of US $300,000, hence a net loss of US $100,000 for the triennium 2024–2026.

# Potential balances returned from cancelled or completed projects

# It is difficult to calculate the potential total funds associated with the return of balances from cancelled or completed projects during the 2024–2026 triennium. The funds and interests returned for 2024 were US $7,893,778 and US $926,271 for the 96th meeting. US $6.28 million is expected to be returned for funds and interests at the 97th meeting. Bilateral and implementing agencies are strongly encouraged to immediately return all the balances for those projects which have been operationally completed or cancelled.

# Recommendation

# The Executive Committee may wish to note:

## The update on the status of implementation of the 2025–2027 consolidated business plan of the Multilateral Fund and financial planning for the triennium 2024–2026 contained in document UNEP/OzL.Pro/ExCom/97/19; and

## That the total value of activities recommended to the 97th meeting amounts to US $108,014,129 (including US $12,667,813 for HFC-related activities; US $3,987,881 for pilot projects for energy efficiency pursuant to decision 91/65; US $21,262,663 for energy-efficiency projects pursuant to decision 94/60; and US $2,674,620 for the preparation of national inventories of banks of waste-controlled substances pursuant to decision 91/66), of which US $10,304,295 is associated with project proposals not included in the 2025 business plan.

Annex I

# OUTSTANDING TRANCHES EXPECTED TO BE SUBMITTED TO THE 98TH MEETING

| Country | Sector | Agency | Tranche | Amount including support costs (US$) |
| --- | --- | --- | --- | --- |
| Afghanistan | HCFC phase-out plan (stage II) | UNIDO | 2025 | 300,135 |
| Bahamas (the) | HCFC phase-out plan (stage II) | UNEP | 2025 | 85,315 |
|  |  | UNIDO | 2025 | 145,057 |
| Benin | HCFC phase-out plan (stage II) | UNEP | 2025 | 236,100 |
| Cabo Verde | HCFC phase-out plan (stage II) | UNEP | 2024 | 148,030 |
| Democratic Republic of the Congo (the) | HCFC phase-out plan (stage II) | UNEP | 2024 | 180,267 |
|  |  | UNDP | 2024 | 225,235 |
| Fiji | HCFC phase-out plan (stage II) | UNDP | 2025 | 148,730 |
|  |  | UNEP | 2025 | 106,107 |
| Grenada | HCFC phase-out plan (stage II) | UNEP | 2025 | 44,861 |
|  |  | UNIDO | 2025 | 13,161 |
| Guyana | HCFC phase-out plan (stage II) | UNDP | 2023 | 37,450 |
|  |  | UNEP | 2023 | 51,415 |
| Indonesia | HCFC phase-out plan (stage III) | Australia | 2025 | 463,113 |
|  |  | UNDP | 2025 | 5,794,084 |
| Iraq | HCFC phase-out plan (stage II) | UNEP | 2023 | 730,610 |
|  |  | UNIDO | 2022 and 2023 | 722,250 |
| Kenya | HCFC phase-out plan (stage II) | France | 2023 | 671,075 |
| Kuwait | HCFC phase-out plan (stage II) | UNEP | 2025 | 299,298 |
|  |  | UNIDO | 2025 | 64,200 |
| Malaysia | Kigali HFC implementation plan (stage I) | World Bank | 2025 | 3,473,530 |
| Mauritius | HCFC phase-out plan (stage I) | Germany | 2023 | 75,343 |
| Niger (the) | HCFC phase-out plan (stage II) | UNEP | 2025 | 95,485 |
|  |  | UNIDO | 2025 | 177,620 |
| Nigeria | HCFC phase-out plan (stage II) | UNDP | 2025 | 1,723,205 |
| Qatar* | HCFC phase-out plan (stage II) | UNEP | 2025 | 77,970 |
|  |  | UNIDO | 2025 | 64,200 |
| Syrian Arab Republic (the) | HCFC phase-out plan (stage I) | UNEP | 2024 and 2025 | 618,121 |
|  |  | UNIDO | 2024 | 924,965 |
| Thailand | HCFC phase-out plan (stage II) | World Bank | 2022 | 186,763 |
| Timor-Leste | HCFC phase-out plan (stage II) | UNDP | 2025 | 15,173 |
|  |  | UNEP | 2025 | 23,594 |
| Venezuela (Bolivarian Republic of)* | HCFC phase-out plan (stage II) | UNIDO | 2025 | 526,654 |

* Submitted but subsequently withdrawn.

UNEP/OzL.Pro/ExCom/97/1

One energy-efficiency project under decision 89/6 for Senegal (UNEP); stage III of the HPMPs for Bangladesh (UNDP), Cameroon (UNIDO) and Egypt (UNEP and UNIDO); one IS project for Bosnia and Herzegovina (UNIDO); stage I of KIPs for Oman (UNEP and UNIDO) and Turkmenistan (UNIDO); two project preparation activities for stage I of KIPs for Bahrain (UNDP) and Kuwait (UNDP); seven verification projects for stage I of KIPs for Albania (UNIDO), the Congo (UNIDO), Cuba (UNDP), Kyrgyzstan (UNDP), Malawi (UNEP), Mozambique (UNEP) and  North Macedonia (UNIDO); and 16 project preparation activities for national inventories of banks of waste-controlled substances under decision 91/66 for Algeria (UNIDO), Angola (UNDP), Argentina (UNIDO), Cabo Verde (UNIDO), the Central African Republic (UNIDO), the Comoros (UNIDO), the Democratic Republic of the Congo (UNIDO), Equatorial Guinea (UNIDO), Gabon (UNIDO), Guinea (UNIDO), Jordan (UNEP), Morocco (UNIDO), Papua New Guinea (Germany), the Philippines (UNIDO), Sao Tome and Principe (UNIDO), and Tunisia (UNIDO).

The document on tranche submission delays would be submitted at the first Executive Committee meeting of the year (decision 95/91(c)).